Performance and Finance Committee Action Log

| Open Action |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action No. | Minute Ref. | Date | Agreed Action | Lead | Timescale | Status |
|  | 162/23 | 24/10/23 | Pathology Deb Lewis to circulate an update outside of the committee on the dashboard for pathology now that this data was available through the data warehouse. | Chief Operating Officer | Ongoing | In progress. Update to be received at the August Committee, to liaise with the department to confirm when the dashboard would be available, and update be provided outside the committee. |
|  | 91/24 | 23/07/2024 | Targeted Intervention Report To include comparable figures across Wales within the next targeted intervention report. | Chief Operating Officer | November 2024 | To be included in the reporting to the November 2024 committee. |
|  | 110/24 | 27/08/2024 | Continuing healthcare performance report To update the committee on progress with centralisation of the CHC commissioning function. | Interim Director of Strategy | January 2025 | To be added to the work programme. |
|  | 125/24 | 24/09/2024 | Thematic Programme A further update and visibility to the committee of opportunities to come forward following the recovery and sustainability board. | Director of Performance and Finance | November 2024 | To be included on the November 2024 agenda. |
|  |  | July Board Action | Demand and capacity modelling An initial verbal update to be given at the October committee; a paper to follow early 2025. | Director of Performance and Finance/Chief Operating Officer | November 2024/March 2025 | D&C work being done as part of 2025-2028 planning process – update to be provided in early 2025 as part of the plan process as soon as available. |
|  |  | July Board Action | Financial risks to the work of tackling diabetes innovation and how to provide support Verbal update to be provided at the October 2024 committee. | Director of Performance and Finance | November 2024 | A verbal update will be provided to the January 2025 committee, following discussion on resource allocation for future years to be held at Exec Team time out December 2024 |
|  | 133/24 | 24/09/2024 | Planned Care To provide an update on the waiting list management limited assurance and follow-up review of outpatient’s services and the management response reports to ensure that all recommendations had been made. | Chief Operating Officer | January 2025 | To be included on the January 2025 agenda. |
|  | 147/24 | 29/10/2024 | Service Group Financial Position Report – Morriston Hospital To action an exercise that would use national benchmarking which is available to support a review of the Morriston Service Group base budget and understand where the variances are. | Director of Performance and Finance | December 2024 | CHKS data to be added to the Repository. Whilst the repository had been updated in the last two weeks, unfortunately the CHKS figure was not available at this point. It is anticipated the data will be updated in the December 2024 Committee. |
|  | 149/24 | 29/10/2024 | Following the establishment of the Recovery and Sustainability Board (RSB), a map showing Health Board financial governance would be drawn up and presented to the Committee. | Director of Performance and Finance | December 2024 | Paper will come to December 2024 committee and will also be referred to audit Committee for scrutiny |
|  | 153/24 | 29/10/2024 | Quarterly Operational Estates Report To provide the Waste Audit conducted in October 2024 and the findings from Natural Resources Wales (NRW) to be shared in the next report to the Committee. | Director of Performance and Finance | February 2025 | To be included on the February 2025 agenda. |
|  | 154/24 | 29/10/2024 | Quarterly Estates Strategy A report to be received at the next committee to include further detail of Cefn Coed Hospital location and decision. | Director of Performance and Finance | February 2025 | To be included on the February 2025 agenda. |
|  | 155/24 | 29/10/2024 | Risk Register To update the Risk Register and include UEC key actions as it did not cover the frailty strategy. | Assistant Head of Risk and Assurance | February 2025 | To be included on the February 2025 agenda. |
|  | 156/24 | 29/10/2024 | Cost Savings Arrangements Audit Wales report To arrange a session with independent members outside of the committee as it would require exploration and cover repository. | Director of Performance and Finance | December 2024 | A session on the Repository scheduled for the In-Committee session on the 17th of December 2024. |
| Closed Actions |  |  |  |  |  |  |
| 1. | 111/24 | 27/08/2024 | Theatre Performance To provide a report on how the theatre Board was progressing. | Associate Service Group Director | December 2024 | Complete – added to the work programme. |
| 2. | 112/24 | 27/08/2024 | Report on the Neurodevelopment Service An update report be provided to the committee in December 2024. | Interim Director of Strategy | December 2024 | Complete added to the work programme. |
| 3. | 115/24 | 27/08/2024 | Update on the Ophthalmology Target Figures To receive an update report in February 2025 with a focus on cataract services. | Associate Service Group Director | February 2025 | Complete added to the work programme. |
| 4. | 126/24 | 24/09/2024 | Month Five Performance To ensure the Quality and Safety Committee discuss the rise in numbers around healthcare acquired infections in more depth and feedback. | Vice Chair | October 2024 | Complete. This issue was discussed in depth at the QSC meeting on 24.9.24 and will be a regular item on QSC agendas in the future. The data will be communicated to the Board via the Committee 3A reports. |
| 5. | 73/24 | 25/06/2024 | Frailty Unit A report detailing the financial benefits of the Frailty Unit given the interest and significant impact it would have on unscheduled care performance. | Morriston Service Group Director | October 2024 | Complete and included on the October agenda. |
| 6. | 107/24 | 27/08/2024 | Month Six Financial Position To include the savings repository opportunities. | Assistant Director of Finance | October 2024 | Complete. Included in the October 2024 reporting. |
| 7. | 126/24 | 24/09/2024 | Radiotherapy Waiting Times To seek further assurance and confirmation around the radiotherapy waiting times as new resourcing had been provided. | Director of Performance and Finance | October 2024 | Complete. Information on radiotherapy waiting times was circulated to members on 22/10/2024 |
| 8. | 126/24 | 24/09/2024 | National Reportable Incidents To seek further assurance and confirmation related to the rise of national reportable incidents. | Director of Corporate Governance | October 2024 | National change in the criteria for reportable NRI’s in November 2023 which has resulted in an increase in cases reported which had not been specified for reporting. Change of criteria shared with the IM’s outside of the meeting. |

Financial Reporting and Monitoring Final Internal Audit Report Actions

| Ref No: | Recommendation | Lead | Timescales | Update |
| --- | --- | --- | --- | --- |
|  | The importance of signing and returning delegation letters is re-iterated to budget holders to formally recognise budget accountability | Deputy Director of Finance | Quarter 3 2022-23 | CLOSED - The 2023/24 Letters have been issued to all Service Group Directors and Executive Directors setting out the opening budgets, with clear timescales on returning the signed acceptance form. The document also included the Budgetary Management process agreed by PFC in April. Responses required in 2 weeks and follow up emails will be issued is no response received by this deadline from the DOF office. |
|  | Consideration is given to assess the need to issue delegation letters to a wider group of budget holders | Deputy Director of Finance | Quarter 3 2022-23 | CLOSED - Actions as per point 1 above |
|  | FCP 6 - Budgetary Control Procedures should be updated to reflect current working practices. | Assistant Director of Finance | Quarter 3 2022-23 | CLOSED - At the November Audit Committee the standard update on FCPs was presented. This along with the covering paper provided the committee with the assurance on what has been reviewed and updated. Below is the extract from the report on FCP 6. Summary this was reviewed in July ’23 and is scheduled for a further review to commence in Q3 23/24, which will need to build in any additional control linked to the 2024/25 Budget Management document approved as part of the Financial Plan process. |
|  | Further work is undertaken to establish what support budget holders require and consider regular engagement | Deputy Director of Finance | 2023/24 | CLOSED - There will be two elements to this. (1) Information provided to the Budget Holders; (2) Training of Budget Holders. On the first point a new NHS Wales Budget Holder Dashboard is due to be launched. We have received confirmation that this will be introduced in Q4 23/24 and go fully live across the HB in Q1 24/25, hence the delay in the some of the work being started. Therefore communication and support programme being developed linked to this change during Feb/March 2024. This will then need to be reflected in the formal training programme (point 2) and so is not scheduled for completion until later in 2024/25. Further information on the new Budget Holder Dashboard will be shared with PFC for information in Q4 23/24. |
|  | We recommend a wider review of this listing is undertaken, to assess the need for this number of authorisers given the NHS Wales ‘No PO, No Pay’ policy | Assistant Director of Finance | Annual Process | CLOSED - Work linked to 2 significant service changes in 2023/24 (1) AMSR and (2) transfer Services to NPTS (Theatres/T&O/Anaesthetics), this has ensured the approval hierarchy has been reviewed in 2023/24. There will be a formal requirement built into the Accountability Letter to Budget Holders to ensure that there is an annual review at Service Group level. |
|  | A virements listing is maintained that captures budgetary transfers between Service Groups. | Deputy Director of Finance | July 2022 | CLOSED – and part of standard processes at Month End. |