| Meeting Date | 26 November 2024 |  | Agenda Item |  |  | 5.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Annual Plan 24/25 Delivery: Quarter 2 Progress Report |  |  |  |  |  |
| Report Author | Andrea Folland, Strategic Planning Manager Ruth Tovey, Head of Strategic Planning Ffion Ansari, Head of IMTP Development & Implementation |  |  |  |  |  |
| Report Sponsor | Karen Stapleton, Deputy Director of Strategy Deb Lewis, Chief Operating Officer |  |  |  |  |  |
| Presented by | Karen Stapleton, Deputy Director of Strategy |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This paper provides the reported Quarter 2 status of the priorities for delivery, as set out in the Health Board Annual Plan 24/25 as Goals Methods Outcomes (GMOs). |  |  |  |  |  |
| Key Issues | - High-level summary provided of the position at the end of Q2 (1st July 2024 – 30th September 2024) in respect of delivery against Annual Plan priorities (Goals and Methods). Where Methods are reported as off-track, mitigating actions and revised delivery timescales are highlighted as approved by the Annual Plan Oversight Group on 01.10.2024. - Performance against Annual Plan System Indicators (aligned to KPIs set by WG) at the end of Q2 are reported for assurance. - The Minimum Data Set (MDS) is updated with actual Q2 data against the required metrics, as requested by Welsh Government as part of the NHS Wales planning process. Reporting to Board for approval to submit to WG. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☒ |  |
| Recommendations | Members are asked to: - NOTE the areas of achievement in delivering the Annual Plan in Q2. - NOTE mitigating actions against GMOs which are off-track. - APPROVE the changes to the plan where delivery is off track. - APPROVE the Minimum Data Set (MDS) updated in Q2, for submission to Welsh Government. |  |  |  |  |  |

ANNUAL PLAN 24/25 DELIVERY: QUARTER 2 PROGRESS REPORT

1. INTRODUCTION

This paper provides the reported status against the priorities for delivery in Quarter 2 24/25, as set out in the Annual Plan as Goals Methods Outcomes (GMOs). Any changes from the plan submitted to WG, including revisions to quarterly milestones, are presented for the approval of the Board.

2. BACKGROUND

The Health Board has a statutory duty to submit a financially balanced Integrated Medium Term Plan (IMTP) annually. The Health Board approved and submitted to WG its Annual Plan for 24/25 in March 2024. Subsequently, the Health Board resubmitted the Annual Plan for 2024-25 to WG on 31st May 2024. Whilst the Plan remained unchanged in terms of planning assumptions, the HB advised WG that further work at speciality/divisional level had been undertaken to refine the 24/25 demand and capacity profiles, leading to revised performance trajectories for several WG Key Performance Indicators (KPIs). As such, the respective Ministerial Templates and Minimum Data Set (MDS) were resubmitted as revised based on the updated trajectories set against new targets from WG.

The Annual Plan is structured in ‘systems’-based programmes of work that have key deliverables (GMOs) outlined. The responsibility for GMO operational delivery and performance sits with the Service Groups.  However, the accountability in providing direction and monitoring the delivery progress of System GMOs is via Programme Boards (or equivalent group). The Exec Lead/SROs for the system areas are set out in Table 1, below:

| System /Programme | SRO/ Exec Lead |
| --- | --- |
| Urgent & Emergency Care | Chief Operating Officer |
| Planned Care | Chief Operating Officer |
| Cancer | Executive Medical Director |
| Children and Young People | Executive Director of Nursing and Patient Experience |
| Maternity and Womens’ Health | Executive Director of Nursing and Patient Experience |
| Mental Health and Learning Disabilities | Group Service Director for Mental Health and Learning Disabilities (reporting to Chief Operating Officer) |
| Primary Care | Group Service Director for Primary, Community, and Therapies (reporting to Chief Operating Officer) |
| Workforce | Executive Director of Workforce and Organisational Development |
| Digital | Director of Digital |

The Annual Plan Oversight Group (APOG), chaired by the Executive Director of Strategy, received an update on Q2 position from all areas on 1st October, 2024.

3. ANNUAL PLAN 24/25 DELIVERY UPDATE

3.1 PROGRESS AGAINST PLAN – SUMMARY

SROs were asked to update on the Q2 status of the Method (Action) component of the GMOs, assessed against delivery of Q2 milestones, using the definitions outlined in Table 2:

| METHODS STATUS | Definitions |
| --- | --- |
| Green | ON TRACK - Progressing as planned /to agreed timelines |
| Amber | OFF TRACK – Not progressing as planned/ to original timelines, however this is manageable & mitigating actions are in place |
| Red | OFF TRACK – Not progressing as planned/ to original timelines, there are significant issues which require escalating |

Q2 Highlight Reports were also provided to inform discussions at the APOG meeting.

Service Group reporting on the GMOs that they own and lead (as agreed through the GMO Mapping and Governance exercise, undertaken by Strategy in May 2024) were extracted into the System Highlight Reports. The Service Group Directors provided their review and sign off on the resulting System Plan Highlight Reports related to their areas.

Table 3, below, summarises performance by reporting area, reflecting cross-cutting (Service Group and Programme Board reporting group) GMOs in the figures of each area to which they are relevant:

| Reporting Area: | Q2 status METHODS: |
| --- | --- |
| Primary Care, Community & Therapies |  |
| Neath Port Talbot Singleton |  |
| Morriston |  |
| Mental Health & Learning Disabilities |  |
| Outpatients |  |
| Urgent & Emergency Care |  |
| Digital |  |
| Workforce & Operational Development |  |
| Value Based Healthcare |  |
| Population Health |  |
| One Bay Way |  |
| Overall performance against Q2 milestones: |  |

Table 4, below, summarises performance of systems included in the figures reported by service, above:

| Reporting System: | Q2 status METHODS: |
| --- | --- |
| Cancer |  |
| Children & Young People |  |
| Maternity & Women’s Health |  |
| Planned Care |  |

3.2 Q2 ACHIEVEMENTS

Q2 achievements included in the full reporting of all GMOs, are outlined in Appendix 1.

3.3 Off-Track Methods

Table 5, below, details red, ‘significantly off-track,’ methods reported, including reasons for delay and the mitigating actions being undertaken. In addition, where it has been identified that GMOs which are off-track at Q2-end will have a knock-on effect on delivery by the end of the year, revisions to subsequent milestones were proposed and agreed by the Annual Plan Oversight Group (APOG), as detailed. Performance & Finance Committee is asked to approve these changes to the Plan. Performance & Finance Committee is also asked to note that in the next period, as part of the routine Annual Plan Reporting processes the Mid-Year review of delivery will be undertaken in December to establish the potential end of year position and approve necessary changes to the Plan, including the rationale for deviation from the original Plan.

| GMO (Reference number and Method) | Off-track Milestone for Q2 | Reason for delay and what is being done to bring activity back ‘on track’ (Mitigating actions) | Change to Plan & Proposed Next Steps |
| --- | --- | --- | --- |
| PRIMARY CARE, COMMUNITY & THERAPIES (PCCT) Service Group Lead: Craige Wilson |  |  |  |
| PCT_08: Ensure delivery of all actions/recommendations from HMP Swansea HIW inspection reports alongside delivery of Health, Care and Wellbeing Delivery Plan (HCWDP) 2023-25. | Establishment to be reviewed again once the new Deputy Head of Nursing is in post. Aim will be to identify any possible additional staffing from a forensic review of all nursing workforce plans in conjunction with a deep dive review of all the activities that require a RGN in HMP. | Deputy Head of Nursing not in post. Commenced employment at the end of August 2024 | Original Q3 milestone: Dependent on identification of funding, further progress against actions in the Health Delivery Plan. Later update: Work will continue with the GMO Lead to establish re-profiled milestones for Q3 and Q4, together with a possible revised outcome. Given the complex and fragile situation surrounding this GMO, changes may be required each quarter. Proposed revised Q3 Milestone: Develop a costed workforce plan for HMP Swansea. Original Q4 milestone: Dependent on identification of funding, full delivery of actions in the Health Delivery Plan. Later update: Work will continue with the GMO Lead to establish re-profiled milestones for Q3 and Q4, together with a possible revised outcome. Given the complex and fragile situation surrounding this GMO, changes may be required each quarter. Proposed revised Q4 Milestone: Formally present a revised and costed workforce plan for HMP Swansea. |
| NEATH PORT TALBOT SINGLETON (NPTS) Service Group Lead: Ceri Gimblett |  |  |  |
| Sitting within the NPTS Service Group, this method also relates to the Children & Young People System, led by Hazel Powell. NPTS_59: Work with RPB and colleagues within Mental Health services to undertake a review of services required for children with learning disabilities, to identify gaps in service provision, unmet need and priorities for development. Implementing the multi-agency CYP Emotional Wellbeing & Mental Health Delivery Plan | Identify lead within Health Board to work with WGRPB in undertaking analysis | Awaiting feedback/update from WGRPB to understand whether this piece of work falls under any WGRPB programmes/tasks to eliminate duplication of work, | Proposed original Q3 milestone: Identify lead within Health Board to work with WGRPB in undertaking analysis Original Q4 Milestone: Quarterly Strategic Board meetings to deliver key strategic actions Proposed revised Q4 milestone: Establish a Steering Group to take forward the actions identified from the CYP summit and to develop a CYP Strategy |
| Sitting within the NPTS Service Group, this method also relates to the Children & Young People System, led by Hazel Powell. NPTS_60: Revise business case in line with recommendations from Welsh Government ND Improvement Programme in readiness to bid for future recurrent funding (RPB funding) | Development of a workforce plan to retain current level of staffing and complete a workforce plan which will provide adequate capacity to meet demand and also start to address the backlog of children and young people awaiting assessments, including finalising a proposal for insourcing support to start to reduce the backlog of patients waiting for an assessment | Off track due to considerable staffing issues related to staff leavers and sickness. | Original Q3 Milestone: Clinical Director and Directorate Manager undertaking a deep dive service review with team to identify short term and long term actions required to improve service whilst undertaking further recruitment and retention of staff. Proposed revised Q3 milestone: Implement short and medium term actions identified from deep dive service review carried out Sept - Dec 2024. Proposed Q4 Milestone: Utilise the non-recurrent funding from WGH in best way to support families, children and service |
| MORRISTON Service Group Lead: Sue Moore |  |  |  |
| M_04: Create a Mental Health A and E in conjunction with mental health division. (Also reported via the UEC system.) | Undertake review of current provision | Focus on progressing Frailty and SDEC. MH will be addressed within the year to formalise a strategy. | This GMO is planning only for 24/25. Further work being undertaken to develop the future model of ED. Consideration given to Mental Health ED in the plans. |
| Sitting within the MGH Service Group, this method also relates to the Outpatients System, led by Ceri Gimblett. M_18: Increasing Surgical Capacity: Development of 3 new theatres at Singleton to increase capacity by 30 sessions | Await WG decision on capital and revenue funding | Currently not progressing due to financial pressures facing the HB | This will not progress until the financial position improves or an executive decision is made to progress. Propose to place on hold on GMO list. |
| Sitting within the MGH Service Group, this method also relates to the Outpatients System, led by Ceri Gimblett. M_24: Creation of a new 6-day service pathway for Acute Coronary Syndrome (ACS) within an ARCH project with HDdUHB to achieve the 72-hour treatment target which is best practice - Year 1 Planning | Update awaited from finance teams, with the GMO having been through the VBHC teams of both SBUHB and Hywel Dda. Further review on how to progress to be undertaken on receipt of update. Milestones will be revised when an update is available. | No engagement from HDda to financially support this. Progress stalled. | This will not progress without engagement from HDda. Propose to place on hold on GMO list. |
| Sitting within the MGH Service Group, this method also relates to the Outpatients System, led by Ceri Gimblett. M_34: Extend temporary contract as part of the DXA recovery, establish evening scanning shifts to meet demand. for DXA reporting, look at recruitment options. HDda: Revise SLA and agree recovery strategy Prevention of vertebral fractures; Recruitment and training of 2 x clinical nurse specialists Year 1 Planning | SBU: Extended evening scanning lists re-established to meet demand. DXA reporting backlog being discussed; risk open on the risk register. HDda: SLA revised and recovery strategy agreed. Scanning training in progress and reporting recruitment being finalised. Prevention of vertebral fractures: Recruitment and training of 2 x clinical nurse specialists - business case to be developed. | This is planning only for 24/25. Work will continue to assess capacity v demand, and given the new constraints of no further WLI, the impact that has on waiting times. |  |
| MENTAL HEALTH & LEARNING DISABILITIES Service Group Lead: Dermot Nolan |  |  |  |
| MHLD_16: Adult Mental Health (Inpatient) Centralised inpatient model of service within a purposed built environment meeting the needs of the patient population for the Health Board area. Development of Adult Mental Inpatient provision business case. | Approval from WG received. Restart Project Board and continue with recruitment to supply chain partner and other posts. | Awaiting decision from WG in relation to project bid submitted. | Discussions continue with Executive Management Board in relation to the project bid. Original Q3 milestone: Develop Outline Business Case for Approval Proposed revised Q3 Milestone: Await decision from WG Original Q4 milestone: Submission of OBC Proposed revised Q4 Milestone: If successful, develop outline business case for approval. |
| MHLD_17: Adult Mental Health (Inpatient) To provide safe and effective care in Ward F when Seclusion Facility is in use | Outcome from capital regarding prioritisation and funding availability | Capital funding and prioritisation is still required for refurbishment work. | The team has had a recent uplift and 2 posts are in recruitment, which will bring Ward closer to being fully established and will support safe and effective care, however, environment still remains an issue. |
| MHLD_26: Older People’s Mental Health (Inpatient) Continue with the redesign of the Older Peoples Mental Health Inpatient Services across the Service Group and input into the wider West Glamorgan regional work | Renovation of Suite 4, Tonna Hospital. Await confirmation of funding from Welsh Government | No further progress made. The scheme continues to require confirmation of funding. | Original Q3 milestone: Begin tender process to identify contractor to undertake the renovation. Proposed revised Q3 Milestone: Finalise capital plans already drawn up and approved. Original Q4 milestone: Tender agreed. Renovation to commence. Proposed revised Q4 Milestone: Begin tender process to identify contractor to undertake the renovation. |
| MHLD_028: Development of co-located Older Adult Team for Area 1 & 2 in Central Swansea for Swansea Residents (Westfa/Phillips Parade) | Engagement with Capital Planning to reinstate working group that was stepped down. Review previous design plans. | No further progress made. The scheme continues to require investment. | The capital team is supporting the Directorate in sourcing alternative accommodation with nothing suitable at present. Original Q3 milestone: Begin tender process to identify contractor to undertake the project. Proposed revised Q3 Milestone: Submit design plans and secure funding. Original Q4 milestone: Tendering completed and submitted for consideration. Proposed revised Q4 Milestone: Begin tender process to identify contractor to undertake the project. |
| MHLD_34: Service Wide (Digital) Digital Systems and Infrastructure Programme (WCCIS) Also reported by Digital. | DHCW to submit full business case to WG. Alternative solution to WCCIS agreed. To be taken forward by Connecting Care programme | Work still ongoing via Connecting Care programme on a National Level to find alternative solution. | Business Case submitted to WG. Awaiting Swansea LA procurement bid outcome. Briefing paper to be completed with concerns by Connecting Care Team who are also exploring options available. Original Q3 milestone: Development of implementation plan of viable alternative to WCCIS. Proposed revised Q3 Milestone: Awaiting outcome of National work to find alternative solution to WCCIS. Original Q4 milestone: Agreed timescales for data migration, training and implementation agreed. Proposed revised Q4 Milestone: Awaiting outcome of National work to find alternative solution to WCCIS and on approval await agreed timescales for data migration, training and implementation. |
| MHLD_41: Psychology (MH&LD) Meeting therapeutic demand in a timely manner | Psychological therapy demand is outstripping capacity, risk identified on risk register, paper developed to go to RPB | No further progress made. | Psychological Therapies lead will continue to highlight risks in this domain but no additional resource is available to deploy into the services. Reviewing digital options (WPAS) to assist reporting. Original Q3 milestone: Recruitment Deployment of longstanding vacancies into psychological therapy. Proposed revised Q3 Milestone: Paper being submitted to RPB for consideration in relation to potential pump priming. Original Q4 milestone: Matter also being discussed in MHLD division-with MHLD associate director. Proposed revised Q4 Milestone: NHS are aware of the pressures and SC RL continue to lobby for resources alongside colleagues in Wales. |
| OUTPATIENTS Lead: Ceri Gimblett |  |  |  |
| OP_02: Reduce the number of patients on a Follow Up waiting list by 30% (on the March 2019 baseline) (Also reported in One Bay Way GMOs) | Anyone waiting over two years to be transfer to PIFU pathway and informed of decision and rights of appeal Development of SOP. | Work not started due to issues with the stored procedure in WPAS. This has now been identified as a local issue and the digital team are working towards resolving this. Activity underway to validate which patients should be included in the Follow-Up waiting list | Workshop has been arranged for 19th Sept and will inform SOP development for the agreed SOS and PIFU pathways. Proposed revised milestones for Q3: Development of SOPs |
|  | Verification testing and roll out of new FUNBs vital dashboard across all specialities (in dashboard) |  | Development delayed due to issue identified with the stored procedure in WPAS. Digital have worked closely with DHCW to find a resolution for milestone to be delivered in Q3 Proposed revised Q3 Milestones: - Dashboard developed and tested. Monitor position using dashboard and refining in response to end user feedback |
| OP_03: Reduce the number of patients who are more than 100% delayed on their Follow Up appointment by 30% (March 2019 baseline) and address Targeted Intervention target: 15% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2023 baseline) | Digital validation with downtrend in number of patients more than 100% delayed | As above - due to the issue with the stored procedure in WPAS. Digital have been working with DHCW to resolve the issue | As above |
| OP_04: SOS and PIFU Activity to demonstrate an annual increase as agreed within the Outpatient Steering Group | Identify Clinical Leads Establish Task & Finish groups Identify pathways appropriate for SOS, PIFU & direct discharge by speciality Development of SOP and Staff training | Project Manager appointed and Clinical leads have been identified in all areas. Digital task and finish group established. TOR drafted for communication and clinical pathway groups. Workshop arranged for 19th Sept. | The workshop will be the first meeting of the clinical pathway group and will inform the direction of the clinical group. Workshop will also identify the SOS and PIFU pathways. GIRFT guidelines have been collected and circulated to the Clinical leads. Future milestones TBC |
| OP_05: Show an annual increase in the number of pathways where virtual appointments and reviews are carried out virtual | Digital colleagues scoping available replacements for Attend Anywhere | Digital colleagues have been scoping alternatives to Attend Anywhere. A SBAR has been circulated to senior digital colleagues outlining the options. | Awaiting feedback from the SBAR. Future milestones TBC |
| OP_09: Develop fit for purpose Referral Management System - Year 1 Planning | Planning | Planning Activity not started due to capacity | Milestones to be developed for Q3 & Q4. |
| OP_10: Deliver Integrated E-Referral and E-Advice | Reduce rejected and redirected referrals, time taken from referral to triage and manual referrals | - PID written including benefits map for recommended plans. There is no clinical lead allocated to the project. - Digital recommendations have been internally validated and shared with DHCW. - The submission routes are being identified. Delivery group being established end of Q2/start of Q3 to submit RFCs and track outcomes. - Effective Referral dashboard not yet developed which prevents us from accurately measuring the deliverables. | Q3 and Q4 Milestones to be updated once the groups have allocated timelines to the delivery plan. |
| Op_12: Provide Advice, guidance, and support to empower patients to better self-manage their condition and prepare for treatment and recovery (Goal 3: SBUHB to deliver on outcomes identified within Phase 2 of the 3Ps Policy delivery plan and service specification following receipt of deliverables from WG) | Q2 Milestone amended as follows: Recruit into SPOC Team, Inclusion of Referral Acknowledgement letters with QR codes to WW Webpages, Inclusion of Prep 4 Surgery Pages info at stage 5 letters, condition specific areas within 6 specialities added to promptly roll out for 3Ps | SPOC Team not recruited. | Escalated to WG by NHS Executive. Revision of Q3 Milestone: Recruit SPOC Team, Go Live with Non-Digital offering, Deliver MECC Level 2 Training for team, Complete creation of SPOC SOP and escalation process. Revision of Q4 Milestone: Implementation of WG 3Ps WW PROM across services on roadmap. |
| OP_13: Ensure Efficient Use of Resources | Performance team to continue to assist services to create plans to deliver zero breaches against 52-week target by 31 March 2025 Monitor through performance scrutiny meetings and measure against service demand | - Issues re: Allocate - Data Hub: inability to automatically extract relevant data required to the Data Warehouse prevents progress of dashboard development. - Project pause has been agreed at Medical Workforce Group and Outpatient Redesign and Recovery Group. - Work ongoing through meetings with RLDatix (supplier) to progress solution to the issue. | Propose to place on hold on GMO list. |
| OP_19: Modernised Outpatient Dataset | Verification testing and roll out of new FUNBs vital dashboard across all specialities (in dashboard) | Work not started due to issues with the stored procedure in WPAS. | This has now been identified as a local issue and the Digital Team are working towards resolving this. |
| UEC Lead: Deb Lewis |  |  |  |
| UEC_01: Predictive identification of future high users of UEC - Data analysis & interpretation | Planning – data collection and review | Lack of available resource to deliver in 24/ 25 | Proposed that GMO be deferred to 25/ 26 and resource reviewed at that that time to confirm what is deliverable. Original Q3 milestone: Delivery/ Development - Synthesis of data sources into a form for use by key decision makers. Proposed revised Q3 Milestone: Initial planning discussions taken place – recognised that due to current resource constraints unable to take forward meaningful project in year – request to defer project into 25/ 26. Original Q4 milestone: Initial model for data collection in place. Review work to date (build on moving into 25/ 26.) Proposed revised Q4 Milestone: Initial planning discussions taken place – recognised that due to current resource constraints unable to take forward meaningful project in year – request to defer project into 25/ 26. |
| UEC_07: Expansion of District Nursing OOH/ SPoA - Enhance the Community Nursing Service over 24hrs to support End of Life care | Confirm additional resource required – recruit additional unregistered workforce provision | Lack of resource/ funding to deliver | Proposed that GMO be closed for 24/ 25 – no funding available to deliver (non-delivery) |
| UEC_12: Evaluation of current Home First discharge support and subsequent agreement/ development of future intermediate bed provision | Planning | Flagged that Home First programme board has been discontinued by the RPB – work is continuing but has been incorporated into the older persons group – no plans noted to develop an evaluation or extend the programme (in current financial environment) | GMO has no support to be taken forward (due to changing structures and no resource to deliver) – proposal to close the GMO (non-delivery) |
| WORKFORCE Executive Lead: Sarah Jenkins |  |  |  |
| W_09: Develop a Swansea Bay ‘Widening Access to Careers in Healthcare’ (WATCH) Programme | Launch the programme | Still likely to launch this year but due to increased partners involved in the programme requiring additional time for collaboration, the launch is unlikely to be until Q3. Therefore, the original Q4 milestone (evaluation) is likely to be rolled over to the new planning year | Continuing to engage with key partners. Milestones revised as follows: |
| DIGITAL Executive Lead: Matt John |  |  |  |
| D_12: TOMS Re-development | Develop an options appraisal based on the requirements gathering. Identify resources requirements and timescales for each option | A theatre management solution will form part of the initial Digital Strategy implementation. The Theatres Board are looking at the wider theatre management processes, which will further inform the approach. | A theatre management solution will form part of the initial Digital Strategy implementation. The Theatres Board are looking at the wider theatre management processes, which will further inform the approach. Propose to remove from 24/25 GMOs. |
| D_18: Welsh Intensive Care Information System - Implementation | TBC, based upon the National Programme Board decision | An Independent Assessment has been undertaken by WG to assess WICIS as a solution for Intensive Care | Awaiting outcome of Independent Assessment |
| D_21: Align the local ePMA solution to the National ePMA Framework and the recently published National Standards relating to interoperability | Commence readiness activities, support national configuration and testing | The procurement activities for a new EPMA system were paused, due to contractual limitations with the current supplier and organisation pressures in unscheduled care. This will be aligned to the new digital strategy. | Propose to remove from 24/25 GMOs |
| D_22: WCCIS/Connecting Care | Connecting Care - Procurement readiness Understand resourcing requirements for implementing alternative solution and agree a plan | Delays to the National Programme | Although this programme is not funded, extensive work has continued locally to inform next steps including: - Engagement in the definition of the national set of requirements - Engagement with Swansea Council such that plans align on a regional basis - Engagement with Swansea Council to agree mitigations for Swansea Bay staff who currently use the Swansea LHB instance of WCCIS; ensuring integrated teams can continue to share information electronically - Market assessment and supplier engagement to establish how solutions can support integrated teams and mitigate against the issue that integrated teams may need to revert to paper once Swansea Council decommission WCCIS. |
| D_31: Replacement of NPT wireless equipment which will no longer be supported by Cisco | Secure funding | Funding has not been secured to support this work | Digital have shared this funding requirement with SBU Capital finance to inform the HB’s response to WG for requests to secure Capital from slippage in 24/25. However, there are higher capital priorities for the HB and digital which might mean this objective will slip to 25/26 depending on the level of funding secured. |

3.4 SYSTEM INDICATORS PERFORMANCE

Table 6 below details the key system indicators reported for Q2 which are aligned to the NHS Wales Key Performance Indicators and national targets, including those set by Targeted Intervention. Performance in Q2 is correct as at October 2024, encompassing the performance trajectories submitted by the Health Board to Welsh Government in June 2024, and are rated accordingly:

- Green, if the outcome measure has met or exceeded the original target/ trajectory,

- Amber, if the measure is moving away from the baseline position in the desired direction, has not yet reached the target / trajectory, but the trajectory indicated that it is likely to do so,

- Red, if the measure is not moving in the desired direction, or the trajectory indicates that it will not meet the target. Mitigating actions being undertaken for off track outcomes are routinely reported to P&F Committee and the Board and are therefore not duplicated in this report.

| System | System Indicator | Target | Baseline Position (March 2024) | July 24 FORECAST | July 24 ACTUAL | August 24 FORECAST | August 24 ACTUAL | September 24 FORECAST | September 24 ACTUAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| URGENT AND EMERGENCY CARE | Number of ambulance patient handovers >1 hr | National target: 30% reduction by December 2024 TI Target: A continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on quarter 2 and 3 2023 baseline) | 629 | 580 | 578 | 570 | 670 | 560 | 591 |
|  | Number of patients who spend 12 hrs or more in all major and minor emergency care facilities from arrival until admission | National target: 20% reduction by September 202, Further 20% reduction by March 2025 TI Target: Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across the health board | 1,132 | 975 | 1013 | 950 | 1167 | 900 | 1129 |
| PLANNED CARE | Number of patients waiting more than 52 weeks for a new outpatient appointment | National target: 40% reduction by end of September 2024 Zero by March 2025 TI Target: 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months | 0 | 0 | 0 | 0 | 0 | 0 | 2 |
|  | Number of patients waiting more than 104 weeks for referral to treatment | National target: Zero end of December 2024 TI Target: 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months | 1,832 | 1,379 | 1,284 | 1,223 | 1,278 | 965 | 1,241 |
|  | Number of patients waiting over 8 weeks for a specified diagnostic | National target: 95% to be zero by December 2024 TI Targets: - 80% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months. - 80% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 months. - 80% of patients waiting for a NOUS and non-cardiac MRI to be waiting less than 8 weeks and maintained for 3 months | 3,687 | 3,193 | 3,490 | 3,115 | 3,425 | 3,020 | 3,296 |
| CANCER | Percentage of patients starting their first definitive treatment within 62 days from point of suspicion (regardless of the referral route) | National target: 60% performance by December 2024 70% performance by March 2025 TI Target: 60% performance maintained for 3 months against the SCP target | 56% | 58% | 58.6% | 59% | 55.7% | 60% |  |
| MENTAL HEALTH | Percentage of therapeutic interventions started within (up to and including) 28 days following an assessment by LPMHSS for people age under 18 years | National target: 80% by December 2024 TI Target: 65% of therapeutic interventions started within 28 days following an assessment by LPMHSS | 100% | 90% | 100% | 90% | 100% | 90% | 100% |
|  | Percentage of therapeutic interventions started within (up to and including) 28 days following an assessment by LPMHSS for adults age 18 years and over | National target: 80% by December 2024 | 98% | 90% | 100% | 90% | 100% | 90% | 95% |

3.5 MDS UPDATE FOR QUARTER 2

Welsh Government has requested formal submission of the MDS, updated for Quarter 2 24/25. A copy of the Q2 actual data as provided, to date, is included as Appendix 2 and will be submitted to WG following approval by the Board.

3.6 WELLBEING OBJECTIVES: ALIGNMENT AND REPORTING

It is intended that updates in relation to the Health Board’s duty to deliver the Wellbeing of Future Generations Act (2015) be included in reporting in Q3 following agreement at the Board Briefing on the Indicators on October 15th. These will indicate position mapped against the strategic indicators.

4. FINANCIAL IMPLICATIONS

The Health Board submitted an Annual Plan on 28th March 2024 which reported a deficit of £50.1m. The expectation was that the in-month position would reflect a 12th of the £50.1m deficit, and so at Month 5 this would be £20.9m. At Month 5 the Health Board reported Year To Date deficit of £39.8m against the £20.9m plan value, and so is now £18.9m off target. The operational pressures which are driving the variance from plan have been apparent since Month 1 and as reported through the Monthly Monitoring Return submission, during Q1 and Q2 there has been significant work undertaken to re-assess the financial position for 2024/25, develop a significant number of opportunities to mitigate the operational pressures and establish a Recovery & Sustainability Team and associated Board. The output of this work was included in the Recovery & Sustainability Assessment presented at the Public Board in September and submitted to Welsh Government on   26th September 2024. The Health Board will now be focusing on the delivery of this document for the remaining 6 months of 2024/25.

5. WORKFORCE IMPLICATIONS

There have been some workforce achievements in Q2, with recruitment progressing and key roles now in post for some service areas.

However, the financial pressures facing the Health Board are clearly impacting on the ability of some services to deliver their GMOs, particularly where funding for additional resources are required. This, coupled with the ongoing recruitment pause for administrative and clerical roles has resulted in some services experiencing limited capacity and a lack of support to deliver their GMOs within the planned milestones. Services are being asked to consider how they might deliver their GMOs differently without additional resource and/or GMOs are being re-prioritised accordingly.

6. RISKS TO ONGOING DELIVERY OF THE 2024/2025 ANNUAL PLAN

At the end of Q1, it was reported that the need to address run-rate in order to de-risk the Health Board financial forecast poses a risk to the potential to realise the desired level of additionality in planned activity for 2024/2025. It was discussed at APOG on 1st October, that this is now playing out and is reflected, to a degree, in the delivery position outlined in section 3.3, above. It was agreed, therefore, that a different way of reporting on affected GMOs, outside of the RAG-based system, is required to accurately reflect the way in which they stand. To this end, it was also agreed that GMOs which were intended as ‘planning only’ for year 1, will be reported outside of the RAG system.

A scoping exercise will be conducted, as part of the mid-year performance review, to deduce which GMOs are required to be placed on hold, for the reasons described above, and a detailed reporting position will be provided a paper to Board in December covering the full Q2 end position, inclusive of KPI and MDS reporting, and analysis of mid-year position.

Members are asked to:

- NOTE the areas of achievement in delivering the Annual Plan in Q2.

- NOTE mitigating actions against GMOs which are off-track.

- APPROVE the changes to the plan where delivery is off track.

- APPROVE the Minimum Data Set (MDS) updated in Q2, for submission to Welsh Government

| Governance and Assurance |  |  |
| --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |
|  | Best Value Outcomes and High Quality Care |  | ☐ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |
| No direct implications of this report, however the Plan is predicated on improving quality, safety and patient experience. |  |  |
| Financial Implications |  |  |
| No direct financial implications of this report, see financial implication section for detail on the Finance Plan. |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |
| A Quality Impact Assessment and Equality Impact Assessment process will be part of the broader planning arrangements to ensure that service models detailed in the Plan are quality and equality/ diversity impact assessed. |  |  |
| Staffing Implications |  |  |
| No direct impact outlined in this report however there will be significant staffing implications as a result of new service models outlined in the Annual Plan – risks and implications to workforce form an integral part to planning arrangements. |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |
| The Annual Plan aims to deliver Strategic Objectives aligned to our Wellbeing Objectives through development of the Organisational Strategy. This paper sets out the alignment of the approved Health Board Wellbeing Objectives directly to the Annual Plan Deliverables. |  |  |
| Report History |  | Third version of this report, following presentation to Management Board on 16.10.2024 and Performance & Finance Committee on 29.10.2024. |
| Appendices |  | Appendix 1: Q2 Achievements and Milestones Appendix 2: SB Plan MDS 2024-25 Q2 |