| Meeting Date | 25 November 2025 |  | Agenda Item |  | 3.1 |
| --- | --- | --- | --- | --- | --- |
| Report Title | Welsh Government Oversight and Escalation Update |  |  |  |  |
| Report Author | Meghann Protheroe, Head of Health Board Performance |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention Darren Griffiths, Director of Finance and Performance |  |  |  |  |
| Presented by | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |
| Purpose of the Report | To provide the Committee with a summary of the performance and outcomes issues for the services escalated as part of Welsh Governments Oversight and Escalation Framework. |  |  |  |  |
| Key Issues | This report provides updates on all areas of delivery currently in escalation against WG’s Performance Framework, namely: Level 4 - Maternity and Neonates (escalated in July 2025). - Finance, strategy and planning. - Performance and outcomes relating to cancer, Urgent and Emergency Care and quality of care related to HCAIs. Level 3 - Performance and outcomes relating to planned care and CAMHS. Level 2 - Mental Health and Learning Disabilities This report provides an update against performance measures following the previous oversight and assurance of the programme. The report also includes a formal update against the MH&LD Transformation Programme to date. |  |  |  |  |
| Specific Action Required (Please choose one only) | Information | Discussion | Assurance | Approval |  |
|  | ☒ | ☐ | ☒ | ☐ |  |
| Recommendations | Committee Members are asked to: - CONSIDER the monthly update in respect of performance against escalation measures and de-escalation criteria. |  |  |  |  |
| Appendices | Appendix 1 –MH&LD Transformation programme update |  |  |  |  |

WELSH GOVERNMENT OVERSIGHT AND ESCALATION UPDATE

- INTRODUCTION

The previous reports have described the actions and longer-term proposals being developed and implemented in response to services who were escalated to targeted intervention status. The report provided an update on the operational programme to manage the delivery of improved performance and outcomes for services under targeted intervention.

The current report will provide an update against all levels of Oversight and Escalation of services within Swansea Bay University Health Board and will include;

Performance against Areas of concern (Level 2)

- Adult Mental Health and Learning Disabilities

Performance against Areas of Enhanced Monitoring (Level 3)

- Planned Care

- Child and Adolescent Mental Health

Performance against Areas of Targeted Intervention (Level 4)

- Cancer

- Urgent & Emergency Care

- Quality of Care related to Healthcare Acquired Infections

- Maternity and Neonatal Services

- Finance

- Strategy and Planning

- BACKGROUND

Following Welsh Government’s tripartite meeting in December 2023, the Health Board was notified of an escalation of performance monitoring for performance and outcomes from enhanced monitoring to Targeted Intervention.  The services listed in the introduction of this report were specifically included in the escalation.

On 12th April 2024, the Health Board had its inception meeting with Welsh Government colleagues and on 24th April 2024 the first quarterly meeting was held with the Chief Executive of NHS Wales.  Quarterly meetings subsequently alternate with formal Joint Executive Team (JET) meetings.  Monthly review meetings are with WG officers focussing on key updates against the escalated areas.  The Chief Operating Officer is the Senior Responsible Officer (SRO) for targeted invention and each work programme is supported by senior management and clinical leads. Summarised updates against the escalation levels will be provided throughout this report.

Following the Tripartite meeting in February 2025, the levels of escalation have been revised and updated as follows;

- Child and Adolescent Mental Health Services de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

- Planned care de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

Updated de-escalation criteria was provided by Welsh Government in April 2025 which provided updated targets for several areas within Level 3 Enhanced Monitoring. The updated de-escalation criteria can be seen throughout the paper.

Following the publication of the Independent Maternity and Neonatal Review published on 15th July 2025, the decision was made to escalate Maternity and Neonates to Level 4 (Targeted Intervention) from Level 3 Enhanced Monitoring.

- PERFORMANCE AGAINST THE AREAS OF CONCERN

Mental Health and Learning Disabilities

Welsh Government has identified Mental Health and Learning Disabilities (MH&LD) as an area of concern, with regards to the oversight and escalation. Assurance has been sought with regards to the key areas of concern within the Service Group and are outlined below.

- The work is now complete, and feedback report provided back to the Health Board Executive team and the Service Group. Meeting took place between the HB Executives and Welsh Government, and a formal response has been sent back to WG following those meeting setting out the details of how the findings of this review will be embed the MH Transformation Program being implement within the MH and LD Service Group.

- The Health Board had already commenced work in advance of the receipt of the report and had established a Transformation Program. This has been informed by a review of the service by an external advisor. The recommendations which were considered urgent by the Board have now been implemented and working is planned and ongoing in relation to some of those immediate environmental changes. A program of work for Tawe Clinic estates work commences on the 17th Nov for six month period and the work to the roof above the Mother and Baby unit commenced in Oct and will be completed at the end of Nove.

- The Transformation Programme is continuing to be led by a Programme Board with supporting all the workstream structures including Workforce, IT/digital, Service Redesign, Quality and Safety and Estates fully established.

- The Health Board will receive its next update in the November Board.

A more detailed update regarding the progress of the MH&LD transformation programme can be found in Appendix 1.

- PERFORMANCE AGAINST THE ENHANCED MONITORING SERVICES

4.1 Planned Care

| Criteria to Achieve | Current Performance (October 2025) |
| --- | --- |
| - 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months. | - 100% |
| - Continuous improvement towards 75% of all open outpatient pathways waiting less than 26 weeks. | - 76.99% |
| - 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months. | - 100% |
| - Continuous improvement towards 80% of all open pathways waiting less than 36 weeks. | - 74.82% |
| - 12% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2024 baseline). | - 15.15% increase against baseline |
| - 68% R1 ophthalmology patient pathways to be waiting within or no longer than 25% of their target date for an outpatient appointment and maintained for 3 months. | - 72.28% - meets de-escalation criteria |
| - 85% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months. | - 75.52% |
| - 85% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 months. | - 37.61% |
| - 85% of patients waiting for a NOUS and non-cardiac MRI to be waiting less than 8 weeks and maintained for 3 months. | - 85.98% |
| - 90% of patients waiting for therapies to be waiting less than 14 weeks and maintained for 3 months. | - 100% |

Actions being taken to improve include:

- Robust monitoring via live dashboards

- Weekly monitoring meetings chaired by Service Group Directors

- Bi-weekly oversight meeting chaired by the Chief Operating Officer

- Specific support commissioned for Gynaecology improvement plans

4.3 CAMHS

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral. | - July – 81% - August – 88% - September – 97% |
| - 70% of therapeutic interventions started within 28 days following an assessment by LPMHSS. | - July – 53% - August – 55% - September – 58% |
| - 85% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan. | - July - 93% - August – 92.8% - September – 95% |

Actions being taken to improve include:

- CAMHS Part 1B:

- Revise the current trajectories based on the current performance expectations following recent demand and capacity work undertaken within the service.

- The service are currently developing a position paper which will outline opportunities to clear the backlog position which will require approval.

- PERFORMANCE AGAINST THE TARGETED INTERVENTION SERVICES

5.1 Cancer

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 60% performance maintained for 3 months against the Single Cancer Pathway (SCP) target. | - July – 61% - August – 61% - September – 60% |

Actions being taken to improve include:

- Continued focus on front end of pathway for all specialties

- NHS Performance & Improvement visit 15th October 2025, specifically focussing on the Prostate pathway

- Commence demand and capacity work in relation to the cancer pathway supported by Transformation Team

- Outsourcing pathology backlog for Skin, Urology and LGI

- Detailed Dermatology demand and capacity exercise, supported by Healthcare Systems Engineering team currently in progress.

- Phase 2, business case development for the long-term provision of complex gynae-oncology surgery commences.

5.2 Urgent and Emergency Care

| Criteria to Achieve | Current Performance |
| --- | --- |
| - A continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on quarter 2 and 3 2023 baseline). | - August – 111 (22.9% reduction) - September – 145 (30.6% increase) - October – 173 (19% increase) |
| - Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across the health board. | - August – 8.71% - September – 9.39% - October – 9.17% |
| - Median time from arrival at an emergency department to assessment by a clinical decision maker should not exceed 60 minutes. | - August – 89.20% - September -89% - October – 90.28% |
| - A continuous reduction in delayed pathways of care of 5% for three consecutive months and then maintained for three months (based on Oct-Dec 23 baseline). | - August – 178 - September – 191 - October - 186 |
| - Assessment of declared BCIs, including reasons why, actions taken, and lessons learnt. | - BCI declared 10th – 13th February 2025 |

Actions being taken to improve include:

- Full implementation of D2RA model – Paper presented to community and older persons board, requesting support for joint commitment to OCP in respect of Health and Social care staff required to deliver the D2RA hub. Health Board and Swansea Local Authority have provided full commitment linked to the wider organisational changes process, ‘Organising for Success’ and a recruitment process in Swansea Local Authority. Neath Port Talbot Local Authority have committed to the current level of provision based on a “drop-in” arrangement at intervals throughout the day.

- Grip & control operational management – Full Capacity protocol and zero tolerance on chair and trolley waits in full operation with additional 3:30 huddle now in situ at Morriston Hospital. Recent meeting held with colleagues from NHS Performance and Improvement to review the All-Wales escalation framework with potential to align the operational response to the Six Goals Framework, awaiting confirmation of workshop. There is high reliance on the use of ‘Your Next Patient’ capacity owing to the high number of clinically optimised patients held on the Morriston site. There is agreement to reorganise the distribution of the clinically optimised patient group to reduce the number of patients on the Morriston site and also a programme of work is on progress supported by Deloitte colleagues to better understand the capacity and demand for each of the D2RA pathways.

- UEC Care co-ordination Hub – Formally referred to as single point of access, the service was launched on 2nd October 2025 with a focus on the National initiative “Clinical Conversation Before Conveyance”, CCBC is a national programme of work in partnership with WAST aimed at reducing patient conveyance from care homes where clinically appropriate. Focus on measurement and reporting metrics will allow good compliance with the national data set proposed. The D2RA hub is now co-located with the single point of access to pool the multi-disciplinary resource to deliver both admission avoidance and timely discharge/transfer of patients. The first reporting of metrics is due 21st November 25.

- Pathway of Care Delays (PoCD) – The Health Board have seen a recent increase in the POCD’s. Focussed attention on this position continues through weekly site based clinically optimised meetings, a weekly COO led meeting and weekly Health Board/LA Director meetings. Work has commenced 13th October in relation to increasing discharge of both clinically optimised and patients who are near to recovery. The “discharge sprint” demonstrated limited success with a 7% increase in medical discharges offset by the increased ED and ambulance demand. Deloitte are working with the Health Board to review capacity and demand for each of the D2RA streams and we are awaiting feedback from the recent D2RA and POCD review undertaken by the NHS Wales Performance and Improvement team. It is anticipated that feedback will demonstrate opportunity to improve ward based flow with the Optimal Hospital Flow programme having just commenced on three acute medical wards.

- Revised flow operating model: Initial UEC tests of change have proven successful in decompressing the Emergency department and improving ambulance handover. Phase 2 UEC test of change will commence September 2025 and will focus on the acute medical unit (AMU) downstream wards and the single point of access. There is a plan to deliver 6 PDSA’s across the AMU/SDEC service with clinical sponsorship and robust measurement in place.

- Falls Pathway – New opportunity exists to further improve management of patient falls in the community. Linking community-based teams and WAST with the single point of access provides potential benefits in terms of reduced conveyance to hospital. Further work is required to define these pathways which will enhance the Falls level 2 provision. Recent funding secured via the six goals national programme which will allow enhancement of the level 2 falls provision.

- UEC capital redesign – Building on the success of recent UEC tests of change and taking into consideration the learning, there is still ambition to co-locate the assessment function for acute medicine, frailty and same day emergency care (SDEC) services. Recent communication from Director of Finance to Welsh Government requesting funding to proceed to the next phase of design in relation to wards A&B at Morriston which could deliver an integrated assessment facility co-located with the emergency department.

Elements of the above are all linked to front door assessment in patient pathways, and complex discharge is being tested via the Quality Improvement process around the thematic review of Urgent and Emergency Care Services. Deloitte are leading on this work as part of the financial recovery and sustainability programme.

5.3 Maternity and Neonatal Services

On 12th December 2023, the maternity and neonatal services within Swansea Bay University Health Board were escalated to level 3 (enhanced monitoring) following an assessment of issues and concerns

related to staffing levels, quality and safety issues, the issues within the HIW unannounced inspection at Singleton as set out in the report published on the 15th December 2023. Subsequently, in July 2025 the decision was made to escalate Maternity and Neonatal Services to Level 4 – Targeted Intervention.

The updated de-escalation criteria aligned with the new escalation status is still in draft format awaiting Welsh Government final sign off. Following agreement of the updated de-escalation criteria, detailed progress against these areas will be provided as part of the Perinatal Committee, chaired by the Executive Director of Nursing.

5.4 HCAI Improvements

| Criteria to Achieve | Current Performance |
| --- | --- |
| - Stabilisation of the increased trajectory of cases of HCAI and evidence of continuous improvement accompanied by a strong QI approach and plan that has oversight and monitoring by board Quality Safety (Q&S) Committee and Board. | - Embedded Quality Improvement approach in this area, monitored closely via Q&S Committee and Board. |
| - The Health Board to have a clear improvement plan based on a root cause analysis to address the issue of hospital onset HCAIs. | - In place |
| - C.difficile: reduce the number of hospital onset infections by 40% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 10 cases to no more than 6 per month) | - August – 9 - September -19 - October -5 |
| - Staph aureus: reduce the number of hospital onset infections by 25% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 4 cases to no more than 3 per month) | - August – 4 - September – 5 - October - 3 |
| - E-coli: reduce the number of hospital onset infections by 20% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 5 cases to no more than 4 per month) | - August – 5 - September – 6 - October - 4 |
| - Klebsiella: reduce the number of hospital onset infections by 10% and maintain for 3 months based on 2017/18 figures (baseline – 54 cases in 2017/18, reduce to average of at most 4 per month) | - August – 5 - September – 2 - October - 4 |

During October 2025 there was an increase in patients presenting to hospital due to a variety of seasonal, acute respiratory viruses. There were 9 new infection related incident/outbreaks (non-C. difficile related) reported in Datix that involved a total of 55 patients. All but one of these has now concluded. Covid-19 was the most common virus affecting in-patient locations.

COVID-19 (overall: 0 bed days lost).

- Singleton Hospital - 2 wards affected by COVID-19 (0 bed days lost).

- Mental Health – 2 wards affected: Rhinovirus and Influenza. (0 bed days lost).

- Morriston - 5 wards affected by Covid-19. (0 bed days lost)

- Themes from HCAI C. difficile case reviews; patients with multiple co-morbidities and antibiotic requirements, high occupancy, insufficient single rooms to meet needs, inability to decant bays and deep clean (4D clean) the environments and equipment.

- There were 4 new wards identified to have and increased incidence of C difficile infections and two wards with possible transmission of C. difficile evidenced through additional analysis of samples using whole genome sequencing.

Actions being taken to improve include:

- Gold C. difficile High Incidence Management Group.

- Monitoring of C. difficile Standards: Risk Assessment & Governance Framework.

- Continuation of QI Project in Acute Medical Unit focusing on AMS and 72-hour review and improving switch to oral route for administration.

- Scoping exercise to explore the feasibility of extending role of ward based enhanced cleaner.

- Trial of new Microfibre cleaning systems

- Primary care QI projects to reduce urinary tract infections in care home residents

5.5 Finance

The Health Board’s assessment on performance against the £58.7m deficit has three components Operational Pressure, Savings Target, and Planned Deficit. Performance against these three elements at Month 7 is summarised in Table 1 below. At Month 7 there was an In-Month deficit of £4.1m, which is £0.8m below the £58.7m planned deficit, with the YTD position reporting a £47.2m deficit, which is £12.9m above £58.7m plan.

Table 1: Delivery YTD

It is clear from Table 1 that currently the Year-to-Date issue remains the non-delivery of savings. However, there are variances, risks and pressures within the Operational Pressures line which are detailed later in this section of the letter.

The submission made on 11 September 2025 set out the Plan to deliver the £55.4m savings in 2025/26. This was a combination of savings delivery supported by our external strategic partner, alongside an increased and sustained delivery of underspends in the operational budget specifically around the corporate directorates and N/R opportunities. Performance against the £55.4m plan submitted in September is provided in Table 2 below:

Table 2: Summary Performance against £55.4m

Whilst there remains a plan for the £55.4m, there is a forecast delivery gap of £14.8m. The two key areas of non-delivery identified to date relate to £6.8m of pipeline ideas presented by the Health Board’s External Strategic Partner and £9m in increased controls and associated spend reductions. Neither of these are identified on the trackers as delivering savings in year at the end of Month 7.

Of note is that since the trackers were assessed in the Month 7 closedown there have been several discussions on further opportunities to support the work underway on 2025/26 In Year and Recurrent Forecast. This has identified a potential additional £1.0-1.2m of savings, although non-recurrent, which will be added to the tracker in readiness for the next round of reporting to R&S Board at the end of November, thus could reduce the gap to £13.6m. The forecast work has also allowed a detailed challenge of the forecast at Service Group level and the requirement for all areas to identify further opportunities to support the position either recurrent or non-recurrent. At this point there are several areas where work is ongoing, and these along with the current position are included in the table below:

Whilst the 2025/26 In Year and Recurrent Forecast work confirms the ongoing pressures of non-delivery of savings, it has also provided insight into the operational pressures, risks and underspends, with key points summarised below:

- Service Groups

  - Both NPTS and PCT are underspending against their delegated budgets, excluding savings;

  - Morriston is £2m over against their delegated budgets, excluding savings with pressures in UEC and Specialist Surgical Services.

  - MH/LD presents greatest operational overspend against their delegated budgets, excluding savings, and the greatest risk to the delivery of the plan after savings. This is driven by CHC growth, temporary adult placements and variable pay. With regards to the temporary adult placements at the start of Month 7, this had reduced to 3 patients from a high in June of 26. However during the latter half of Month 7 this increased to a high of 29.

- Corporate Directorates

  - It is forecast that the Corporate Directorates will exceed the target set in 11 September 2025 submission of £4.0m underspend.

- Central (Z Codes)

  - Assumes performance benefits for both Provider and Commissioner LTA of £2.4m combined, N/R opportunities as per 11 September 2025 submission of £4.6m but with pressures in areas such as Losses and Bad Debt provision, which the Health Board will need to find further mitigating actions.

Work on the forecast will continue through November, with the initial output to be presented at an In-Committee session of the PFC at the end of November 2025. Further details will be provided in the Month 8 MMR, as whilst the delivery of the £55.4m is key to the delivery of the Health Board plan, there are operational pressures and risks which will also need to be mitigated to enable the Health Board is to achieve the £58.7m deficit.

5.5 Planning

Updates against the de-escalation criteria outlined by Welsh Government can be found below;

| De-escalation Criteria | Actions – Updated Oct 2025 |
| --- | --- |
| Submission of a balanced and credible three-year medium-term plan or acceptable annual plan in line with the current planning framework. | - Annual Plan workshop held 12th November focussing on key areas for delivery in 26/27. - Further workshops in place for 26th November 3rd December, 15th December and 23rd January. - Key work underway to establish parameters and targets for financial, workforce and performance delivery. |
| Evidence of a clear roadmap and implementation of the health board’s Clinical Services Plan. | - Stakeholder engagement undertaken throughout October testing the outline CSP framework - Clinical Reference Groups for Integrated Community Care and Networked Hospitals established with broad representation from across secondary and primary care. First meetings to be held 16th and 18th of December. - First draft of ‘State of the Nations’ Report and Overview Demand and Capacity report to be consider by the Executive Working Group 10th December. |
| Welsh Government’s confidence in delivery based on an assessment against an agreed planning maturity matrix | - Re-assessment of SBUHB position completed. Action Plan and supporting evidence being collated. - Chair received Brief on re-assessment and is included in Planning and Partnership Board Update to the Board meeting November 27th - Re-assessment to be submitted to Welsh Government 28th November |
| Progress made with regional planning | - Previous Regional Joint Committee 18th August. Subgroup updates were received for: Regional Health Economy, Clinical Services Planning, Workforce and OD, Data and Digital, Finance and Commissioning, Research and Innovation. - The Regional Drive and Delivery Group, Chaired jointly by Abi Harris and Phil Kloer, met on 16th October and provides oversight of subgroup work programmes - Full updates are scheduled to be reviewed at the next RJC meeting 22nd January. |

- RECOMMENDATION

Committee members are asked to:

- CONSIDER the monthly update in respect of performance against oversight and escalation measures and de-escalation criteria.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Outlined within the body of the paper but in summary considerable backlog of patients awaiting a diagnostic and treatment services across a range of services. Issues of harm in relation to high levels of HCAIs noted. |  |  |  |
| Financial Implications |  |  |  |
| Funding not yet agreed for 24/25 |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Delay to diagnosis and treatment potential.in service delivery |  |  |  |
| Staffing Implications |  |  |  |
| Additional support staffing required to deliver the programme |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Report History |  | Routine report |  |
| Appendices |  | Appendix 1 –MH&LD Transformation programme update |  |