| Meeting Date | 24 October 2023 |  | Agenda Item |  |  | 5.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Management Report – Performance & Finance Risks |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Interim Director of Corporate Governance Gareth Howells, Executive Director of Nursing |  |  |  |  |  |
| Presented by | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to highlight the risks from the Health Board Risk Register (HBRR) assigned to the Performance & Finance Committee (PFC) for scrutiny. |  |  |  |  |  |
| Key Issues | - The Health Board Risk Register was last received by the Board July 2023. - Since then, Health Board risk register entries have been circulated to lead Executive Directors monthly for review and update. This report presents an extract of risks from the September 2023 HBRR. - Ten risks are assigned to the Performance & Finance Committee for oversight. Six risks are assessed to meet or exceed the Board risk appetite threshold. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee. - CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any. |  |  |  |  |  |

RISK MANAGEMENT REPORT – Performance & Finance Risks

- INTRODUCTION

The purpose of this report is to highlight the risks from the Health Board Risk Register (HBRR) assigned to the Performance & Finance Committee for scrutiny.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular HBRR update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

Risk Register management is supported by a Risk Management Group (RMG) which meets quarterly and is responsible for overseeing the operational management of risk, ensuring local systems and processes are in place and are operating effectively to ensure appropriate reporting and escalation. The Group last met in July 2023.

Additionally, a Risk Scrutiny Panel is responsible for ensuring there is an appropriate and robust risk management system in place and working throughout the organisation. It is responsible for moderating new risks and risks escalated to the Health Board Risk Register (HBRR) and Board Assurance Framework (BAF) and recommending and advising the Management Board on the escalation and de-escalation of risks. The Panel last met in September 2023.

2.2 Risk Appetite

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating  lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

3.	MANAGEMENT OF PERFORMANCE & FINANCE RISKS

3.1 Action to Update the HBRR

Health Board risk register entries are circulated to lead Executive Directors monthly for review and updated where required. A consolidated, updated register is circulated to Executive Team for agreement and final version issued. The register was received by the full Board in July 2023. This report presents the risks allocated to this Committee as recorded in the September 2023 HBRR – the relevant risk extracts are attached at Appendix 1. Key changes made in the most recent monthly update are highlighted in red font.

3.2 HBRR Performance & Finance Risks

Ten risks are assigned to this Committee for oversight. The profile of risk scores is presented below:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 |
| --- | --- | --- | --- | --- | --- |
| Number of Risks | 3 | 0 | 1 | 4 | 2 |

There are no new risks to report and no movements in risk scores since the HBRR was presented to Board in July 2023.

There are six risks currently meeting or exceeding the Health Board’s risk appetite thresholds, for which action is required so that they may be reduced to acceptable levels. Table 1 below highlights recent changes / actions of note since the last meeting of the Committee for those risks that are currently meeting or exceeding the thresholds:

Table 1 – HBRR High Risks Assigned to the Performance & Finance Committee

| Risk Reference | Risk Description | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. | 25 | Lead: Chief Operating Officer The risk score currently remains unchanged. Update 31/07/2023 & 11/08/2023: The Health Board is working in partnership with the national Six Goals team and NHS Wales to pilot an alternative flow model call continuous flow. This is part of a pilot to develop a standardised toolkit for NHS Wales (1 of 3 pilot sites in Wales). Pilot to commence as a service improvement project in Aug 2023. Collaborating with WAST to identify further opportunities for partnership working around falls in the community. Actions completed: - Implementation of criteria led discharge (review to take place. - Care home pilot with pharmacist medicines review and rapid response to avoid hospital admission, monthly reporting in place. Further actions: - Increased hours in SDEC (01/03/2024). - OPAS exploring internal & external funding options (31/09/2023). - Work ongoing in ED/SDEC to pilot additional initiatives (30/09/2023). - Redesign GP referral flow so that all referrals are directed to SDEC in the first instance rather than attend AMU (11/09/2023) - Surgical SDEC opening (01/09/2024) - Continuous flow model (31/08/2023) |
| 16 (840) | Access and Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 20 | Lead: Chief Operating Officer The risk score currently remains unchanged. Update 18/08/2023: The Health Board has received an additional allocation of £14m for orthopaedic (NPTH development) which will support the delivery of the 104 week target. The first additional theatre at NPTH will be available from 28 August, providing additional capacity for 20 cases per week. Following the approval of the additional funding, the end of year trajectory based on the service plan will be finalised by the end of August. Further action: - Implement demand management initiatives (target 31/03/2024) - Work ongoing with Finance colleagues to establish the funding allocation for elective recovery for 2023/24 (31/10/2023) |
| 50 (1761) | Access to Cancer Services A backlog of patients now presenting with suspected cancer has accumulated during the pandemic, creating an increase in referrals into the health board which is greater than the current capacity for prompt diagnosis and treatment. Because of this there is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | 25 | Lead: Chief Operating Officer The risk score currently remains unchanged. Update 18/08/23: Issues identified with tracking of cancer patients and variability of approach taken by the Service Groups. Agreement to move management of trackers and MDM co-ordinators to the central cancer team with effect from September 2023. Additional financial support agreed for cellular pathology outsourcing to help reduce current backlog position which is contributing to delay in some pathways. Further Action: - Cancer Performance Group to monitor improvement trajectories for both cancer backlog and SCP performance on a monthly basis (31/03/2024). - Additional theatre capacity for gynaecological cancer agree to reduce current backlog (31/09/2023). |
| 88 (3110) | Non-delivery of AMSR programme benefits There is a risk that the Acute Medical Service Re-Design (AMSR) programme may not deliver the expected performance & financial benefits in a timely way. The principal potential causes of this risk are: workforce (OCP and recruitment requirements), capacity constraints linked to significant number of clinically optimised patients (COP), financial affordability linked to 90 beds in Singleton hospital that are due to close in Q3 2023. | 20 | Lead: Chief Operating Officer Update 11/08/23: AMSR was discussed at 1st August UEC Board. It was recommended for closure as a defined programme, for ongoing management as ‘business as usual’. Risks identified and open on HBRR in relation to benefits still to be fully realised to be transferred to Medicine Division for management. |
| 92 (3444) | Financial Deficit Achievement Forecast deficit is not met due to insufficient progress on COVID cost reduction, savings identification, run rate reduction and the potential for new in-year pressures. | 20 | Lead: Director of Finance & Performance The risk score currently remains unchanged. Ongoing Actions: - Continuation of weekly escalation meetings and escalation of other areas as necessary - Focus on efficiency of core resource to avoid spending premium cost resource - Develop robust cross system service change plans which improve quality of care and reduce system cost Update 16/08/2023: Letter from Welsh Government (WG) dated 3rd August 2023 outlined that the Health Board had failed to meet its statutory duty to submit an IMTP and to have an IMTP approved by the Welsh Ministers. Although the deficit financial plan is not agreed with Welsh Government, the Board is working to deliver the deficit number unless advised to the contrary. Since submission of the plan the Health Board has also been required to identify options to reduce the deficit below the £86.6m which was submitted to Welsh Government on 11th August along with an Accountability Officer Letter. A comprehensive mid-year review of trajectory to 31st March 2024 will be completed in October for discussion with WG and Board. |
| 93 (3448) | Capital Plan Reduced discretionary capital funds and reduced National NHS funds requiring a restricted Capital Plan for 2023/24 | 20 | Lead: Director of Finance & Performance The risk score currently remains unchanged. Board members will be aware that capital plans are dynamic through the year with mitigating actions taken and opportunities for slippage and further support from WG sought on a consistent basis. This process will continue in 2023/24 in efforts to de-risk the capital plan. Ongoing Action: Routine review and flexing of plan as spending is committed through the year. Routine monitoring processes will identify any potential slippage and will deploy this on risk based basis. |

Table 2 below lists additional risks assigned to the Quality & Safety Committee whose risk levels do not meet the threshold currently set within the Health Board’s risk appetite. However, when the current appetite was agreed in November 2022, it was the Board’s aspiration that thresholds could be reduced in the future. In view of this, these risks are presented for information:

Table 2: HBRR risks assigned to the Committee that do not currently meet the risk appetite threshold.

| Risk Reference | Risk Description | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| 48 (1563) | CAMHS Risk of failure to sustain Child & Adolescent Mental Health Services | 12 | Lead: Chief Operating Officer This risk is being reviewed and redrafted within the Mental Health & Learning Disabilities Service Group to reflect the transfer of services into the direct management of SBU. |
| 52 (1763) | Strategic Impact Assessments The Health Board does not have sufficient skills & resource in place to undertake impact assessments in line with strategic service change and policy development. | 12 | Lead: Director of Insight Communications & Engagement The risk score currently remains unchanged. Further Actions: - Appoint Head of EDI – Delayed due to need to confirm budget (30/09/2023) - Review of the current process for developing Equality Impact Assessments around service change, engagement and consultation (31/10/2023) - Robust policies and processes to be in place for Impact Assessment going forward (31/10/2023 – in progress) - Roll out Impact Assessment process across organisation (30/09/2023). |
| 75 (2522) | Whole-Service Closure Risk that services or facilities may not be able to function if there is a major incident or a rising tide that renders current service models unable to operate. | 10 | Lead: Chief Operating Officer Risks in relation to major incidents and business continuity are being reviewed with a view to refreshing/replacing this HBRR entry. |
| 82 (2554) | Risk of closure of Burns service if Burns Anaesthetic Consultant cover not sustained There is a risk that adequate Burns Consultant Anaesthetist cover will not be sustained, potentially resulting in closure to this regional service, harm to those patients would require access to it when closed and the associated reputational damage. | 16 | Lead: Acting Executive Medical Director The risk score currently remains unchanged. Further Action: Welsh Government (WG) have agreed funding in principle for capital works to progress. Scoping document submitted to WG and discussions ongoing about expediting a decision on an outline/full business case (target 30/11/2023) |

Some of the risks allocated to this Committee for scrutiny are reported to other Committees for information. These are summarised here for information:

Table 3: Risks Reported to other Committees for Information

| HBRR Ref | Risk Detail | Current Risk Score | Committee |
| --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. | 25 | Quality & Safety |
| 16 (840) | Access and Planned Care. There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 20 | Quality & Safety |
| 48 (1563) | CAMHS Failure to sustain Child and Adolescent Mental Health Services | 12 | Quality & Safety |
| 50 (1761) | Access to Cancer Services A backlog of patients now presenting with suspected cancer has accumulated during the pandemic, creating an increase in referrals into the health board which is greater than the current capacity for prompt diagnosis and treatment. Because of this there is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | 25 | Quality & Safety |
| 82 (2554) | Risk of closure of Burns service if Burns Anaesthetic Consultant cover not sustained There is a risk that adequate Burns Consultant Anaesthetist cover will not be sustained, potentially resulting in closure to this regional service, harm to those patients who would require access to it when closed and the associated reputational damage. | 16 | Quality & Safety Workforce & OD |
| 88 (3110) | Non-delivery of AMSR programme benefits There is a risk that the Acute Medical Service Re-Design (AMSR) programme may not deliver the expected performance & financial benefits in a timely way. The principal potential causes of this risk are: workforce (OCP and recruitment requirements), capacity constraints linked to significant number of clinically optimised patients (COP), financial affordability linked to 90 beds in Singleton hospital that are due to close in Q3 2023. | 20 | Quality & Safety |

- GOVERNANCE AND RISK

This report and appendix present information on each of the risks assigned to the Committee for oversight. Within the report, particular attention is drawn to those risks exceeding the Board’s appetite, together with updates on action being taken to treat them by lead Directors and management.

- FINANCIAL IMPLICATIONS

There are financial implications to minimising the risks entered on the HBRR in relation to significant revenue implication around strengthening resources in the Health Board, Service Groups and Departments.  Capital monies may also be required in relation to supporting the improvements required to improve and where this is the case further detail is provided in the individual entries on the HBRR.

- RECOMMENDATIONS

Members are asked to:

- NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee.

- CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements in place that ensure organisational risks are captured, assessed and mitigating actions are taken, is a key requisite to ensuring the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| The risks outlined within this report have resource implications which are being addressed by the respective Executive Director leads and taken into consideration as part of the Board’s IMTP processes. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Unit Directors are requested to review their existing operational risks on Datix Risk Module to ensure SBUHB has an accurate and up to date risk profile. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR and the Covid 19 risk register sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - This report provides an update on risks allocated to the PFC which were last reported to the Board in July 2023. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) Risks Assigned to the Performance & Finance Committee |  |