| Meeting Date | 29 October 2024 |  | Agenda Item |  |  | 6.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Management Report – Performance & Finance Risks |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Interim Director of Corporate Governance |  |  |  |  |  |
| Presented by | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to highlight the risks from the Health Board Risk Register (HBRR) assigned to the Performance & Finance Committee (PFC) for scrutiny. |  |  |  |  |  |
| Key Issues | - The Health Board Risk Register was last received by the Committee in May 2024. - Since then, Health Board risk register entries have been circulated to lead Executive Directors monthly for review and update. This report presents an extract of risks from the September 2024 HBRR. - Ten risks are assigned to the Performance & Finance Committee for oversight. This reflects the closure of one risk since the last meeting. Two risks have increased in risk score, one now reaching the Board’s appetite level. There are eight risks in total assessed to meet or exceed the Board risk appetite threshold. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - RECEIVE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee. - REVIEW & COMMENT on the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any. |  |  |  |  |  |

RISK MANAGEMENT REPORT – Performance & Finance Risks

- INTRODUCTION

The purpose of this report is to highlight the risks from the Health Board Risk Register (HBRR) assigned to the Performance & Finance Committee for scrutiny.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular HBRR update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

Risk Register management is supported by a Risk Management Group (RMG) which meets quarterly and is responsible for overseeing the operational management of risk, ensuring local systems and processes are in place and are operating effectively to ensure appropriate reporting and escalation. The Group last met in May 2024.

Additionally, a Risk Scrutiny Panel is responsible for ensuring there is an appropriate and robust risk management system in place and working throughout the organisation. It is responsible for moderating new risks and risks escalated to the Health Board Risk Register (HBRR) and Board Assurance Framework (BAF) and recommending and advising the Management Board on the escalation and de-escalation of risks. The Panel last met in September 2024.

2.2 Risk Appetite

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating  lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

3.	GOVERNANCE & RISK

3.1 Action to Update the HBRR

Health Board risk register entries are circulated to lead Executive Directors monthly for review and updated where required. A consolidated, updated register is circulated to Executive Team for agreement and final version issued. This report presents the risks allocated to this Committee as recorded in the September 2024 HBRR – the relevant risk extracts are attached at Appendix 1. Key changes made in the most recent monthly update are highlighted in red font.

3.2 HBRR Performance & Finance Risks

Ten risks are assigned to this Committee for oversight. The profile of risk scores is presented below:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 |
| --- | --- | --- | --- | --- | --- |
| Number of Risks | 2 | 0 | 1 | 4 | 3 |

Movements since last meeting:

- New risks

  - Nil

- Risks increased in score

  - HBR52 Strategic Impact Assessments (1216)

  - HBR92 Forecast Deficit (2025)

- Risks reduced in score

  - Nil

- Risks closed/de-escalated

  - HBR97 Disruption due to Industrial Action

There are eight risks currently meeting or exceeding the Health Board’s risk appetite thresholds, for which action is required so that they may be reduced to acceptable levels. Table 1 below highlights recent changes / actions of note since the last meeting of the Committee for those risks that are currently meeting or exceeding the thresholds:

Table 1 – HBRR High Risks Assigned to the Performance & Finance Committee

| Risk Ref | Risk Description | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. (This risk includes ED, AMU and impact in community from ability to release ambulances at both front doors.) | 25 | Lead: Chief Operating Officer The score remains unchanged currently. Ongoing actions (targets refreshed): - Review of senior decision making capacity within Same Day Emergency Care (SDEC) and Acute Medical Unit (AMU) (31/12/2024). - Implementation of 7-day community services such as virtual wards (31/12/2024). - Criteria led discharge roll out. (Rollout across specialties outside Medicine by 31/12/2024). Continuous Flow Model is now on hold pending improvement from other actions. Urgent & Emergency Care (UEC) summit held in October 2024 to consolidate system approach. This will be repeated in six weeks. |
| 16 (840) | Access and Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 20 | Lead: Chief Operating Officer The score remains unchanged currently. Progress against the Planned Care agenda continues with 52 weeks maintained and 156 weeks now removed. Actions: - Theatre Optimisation Programme now in place to maximise efficient use of theatre capacity (31/03/2025). - Revised demand and capacity planning underway to utilise additional funding from Welsh Government to clear 104 week waits by the end of March 2025 (31/10/2024) |
| 50 (1761) | Access to Cancer Services There is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | 25 | Lead: Chief Operating Officer The score remains unchanged currently. August performance reduced against the trajectory (56% v 59%). The target of 60% for end of September remains in place. Ongoing actions (targets refreshed): - Cancer Performance Group to monitor improvement trajectories for both cancer backlog and SCP performance on a monthly basis. (31/12/2024) - Full review of Gynaecology / Gynae-oncology pathway given service constraints to be done. Additional theatre capacity for gynaecological cancer to be agreed to reduce current backlog (31/12/2024). |
| 52 (1763) | Strategic Impact Assessments The Health Board does not have sufficient skills & resource in place to undertake integrated equality impact assessments in line with strategic service change and policy development. | 16 (was 12) | Lead: Director of Insight Communications & Engagement This risk has increased in score. Judicial Review has been applied for in relation to EMRTS / Air Ambulance Changes which implicates the Health Board. This may indicate a rising likelihood of such challenges being launched in relation to service change. Action targets refreshed: - Appoint Head of EDI. Delayed due to vacancy suspension (31/12/2024) - Review of the current process for developing Equality Impact Assessments around service change, engagement and consultation. Progress slowed as delay in recruitment of Head of EDI. (31/01/2025) - Robust policies and processes to be in place for Impact Assessment going forward. (30/03/2025) - Roll out Impact Assessment process across organisation. (30/06/2025) |
| 92 (3444) | Forecast Deficit Forecast deficit is not met due to insufficient progress on run rate reduction and £26.1m saving targets across all areas which is required to ensure the planned in month deficit is achieved. | 25 (was 20) | Lead: Executive Director of Finance & Performance Controls refreshed and actions taken previously include: - Establishment of the Recovery and Sustainability (R&S) Team from July 2024 to support both immediate actions and longer term sustainability. With a Recovery & Sustainability Board overseeing the delivery, from October 2024. - Review of all controllable expenditure and directions issued via the R&S Team, including Variable Pay targets. - Savings Programme Management Office (PMO) remit has been expanded to support the Recovery & Sustainability Programme. Actions continuing until targets achieved: - Continuation of financial performance meetings and escalation as necessary - Develop robust cross system service change plans which improve quality of care and reduce system cost Additional actions: - Recommendations following Star Chamber and Executive Team meetings to be presented as part of the revised Financial Plan at the Board meeting on 25th September. This will then set the trajectory to the 31st March 2025 (30/09/2024) - Building on the above, all service areas will be issued with control totals to deliver, recognising the areas of options and controllable expenditure. Oversight of this will be via the Recovery & Sustainability Board commencing in October. Director of Finance & Performance to issue targets (30/09/2024). Service and Corporate Directors to deliver targets (31/03/2025). |
| 93 (3448) | Capital Plan Reduced discretionary capital funds and reduced National NHS funds requiring a restricted Capital Plan for 2024/25. | 20 | Lead: Executive Director of Finance & Performance The score remains unchanged currently. Action ongoing through the year: - Routine review and flexing of plan as spending is committed through the year. Routine monitoring processes will identify any potential slippage and will deploy this on risk based basis. Additional action: - Submission of slippage bids to Welsh Government (30/09/2024). |
| 96 (3571) | Failure to Develop an Approvable IMTP (statutory compliance) Failure to have an approvable (Integrated Medium Term Plan) IMTP for 2024/5 and 2025/6 then we will lose public confidence and breach legislation. | 20 | Lead: Director of Strategy The score remains unchanged currently. It is unlikely that the Health Board will be able to submit a financially balanced IMTP in March 2025. Additional/Refreshed Actions: - Establish baseline assessment against the Planning Maturity Matrix with an associated action plan (30/09/2024). - Development of a draft Clinical Services Plan to be shared with WG in March 2025 (31/03/2025). - Development of a robust Annual Plan for 2025/6 in a three year context to be submitted to Welsh Government in March 2025 (31/03/2025). |
| 98 (3692) | Overall condition/compliance and suitability of Health Board Estate 6 FACET survey undertaken in 2022 confirmed the poor condition and suitability of premises where health care services are provided. The backlog maintenance costs are in excess of £200 million. | 20 | Lead: Executive Director of Finance & Performance The score remains unchanged currently. Some backlog maintenance issues are currently being addressed in accordance with the allocated Welsh Government funding. To date a total of 11 schemes are being BLM (Building Lifecycle Management) addressed by Capital Planning and Estates teams using EFAB (Estates & Facilities Advisory Board) capital allocation, with a number of other areas for action pending further funding allocation. The expenditure and progress of associated schemes is being closely monitored via a monthly steering group and reported back to Welsh Government on a bi-monthly basis. Ongoing Actions: - Maintain effective engagement with Welsh Government to provide funding to implement estates strategy and development control plans to address all areas outlined. (31/03/2025) - Work with Welsh Government to source alternative solutions to funding the Health Board estates strategy and development control plans. (31/03/2025) |

Table 2 below lists additional risks assigned to the Quality & Safety Committee whose risk levels do not meet the threshold currently set within the Health Board’s risk appetite. However, in line with the Board’s aspiration that thresholds could be reduced in the future, these risks are presented for information:

Table 2: HBRR risks assigned to the Committee that do not currently meet the risk appetite threshold.

| Risk Reference | Risk Description | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| 75 (2522) | Whole-Service Closure Risk that services or facilities may not be able to function if there is a major incident or a rising tide that renders current service models unable to operate. | 10 | Lead: Chief Operating Officer Risks in relation to major incidents and business continuity are being reviewed and will be reflected afresh as part of the resetting of Board-level risk reporting arrangements. This work is underway currently. |
| 94 (3516) | CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. This is further hindered by poor data quality which presents a risk to reporting until validation is complete. | 12 | Lead: Chief Operating Officer The risk score currently remains unchanged. |

Some of the risks allocated to this Committee for scrutiny are reported to other Committees for information. These are summarised here for information:

Table 3: Risks Reported to other Committees for Information

| HBRR Ref | Risk Detail | Current Risk Score | Committee |
| --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. | 25 | Quality & Safety |
| 16 (840) | Access and Planned Care. There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 20 | Quality & Safety |
| 50 (1761) | Access to Cancer Services A backlog of patients now presenting with suspected cancer has accumulated during the pandemic, creating an increase in referrals into the health board which is greater than the current capacity for prompt diagnosis and treatment. Because of this there is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | 25 | Quality & Safety |
| 94 (3516) | CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. This is further hindered by poor data quality which presents a risk to reporting until validation is complete. | 12 | Quality & Safety |

4. FINANCIAL IMPLICATIONS

There are financial implications to minimising the risks entered on the HBRR in relation to significant revenue implication around strengthening resources in the Health Board, Service Groups and Departments.  Capital monies may also be required in relation to supporting the improvements required to improve and where this is the case further detail is provided in the individual entries on the HBRR.

5. RECOMMENDATIONS

Members are asked to:

- RECEIVE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee.

- REVIEW & COMMENT on the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - This report provides an update on risks allocated to the PFC which were last reported to the Committee in May 2024. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) Risks Assigned to the Performance & Finance Committee |  |

This increase has resulted in the risk reaching the Board’s appetite threshold

This risk has been closed, however a further risk relating to potential industrial action within a different staff group has been added to the HBRR and is overseen by the Workforce & OD Committee.