HEALTH BOARD RISK REGISTER

September 2025

RISKS ALLOCATED TO THE

PERFORMANCE & FINANCE COMMITTEE

| Datix ID Number: 738 Health & Care Standard: |  |  | HBR Ref Number: 1 Risk Target Date: 31/12/2025 |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Urgent & Emergency Care (UEC) |  | BAF Ref: 2.4 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Performance & Finance Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Access to Unscheduled Care If we fail to provide timely access to Unscheduled Care, then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. (This risk includes ED, AMU and impact in community from ability to release ambulances at both front doors.) |  |  | Date last reviewed: September 2025 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 5 = 20 Current: 4 x 4 = 16 Target: 3 x 4 =12 |  |  | Rationale for current score: The UEC system continues to see high demand, with ambulance attendances higher than seen previously. However, this demand has been mitigated (beginning June 25) by improvement activity across the hospital resulting in improved flow away from ED. This improvement activity has been married with additional capacity at the front door (Ward) to decongest ED and resulted in the resultant reduced risk score (previously 25). |  |  |  |
| Level of Control = 50% |  |  | Rationale for target score: The HB is currently under escalating performance monitoring from WG (Targeted Intervention or TI) for delivery of UEC services. The improvement plan developed as a response to TI and that already included in the HB annual plan is to implement models of care that reflect best practice and focus on areas that will benefit patients, staff and the UEC system most. The implementation of this plan will improve patient flow, length of stay and reduce emergency demand. |  |  |  |
| Date added to the SBU HB risk register Apr 2019 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| Five main areas of work within the plan: - Frailty strategy (already achieved: Older Persons Assessment & Short Stay Unit stood up; Hub stood up to triage/stream/capture outcomes from incoming calls; standard operating procedures developed for Short Stay, Assessment Unit, Neck of Femur Pathways/beds, and Hub; Phase 1 capital works completed) - Grip & control operational management and centralisation of patient flow resources - Senior decision makers at front door services - Pathway of care delays (PoCD) Implementation of Discharge-To-Reassess (D2RA) - Home First - Acute Care Team (ACT) - Interface with local authority (LA) - Urgent & Emergency Care redesign programme linked to capital expansion scheme. - Development of a UEC Care Co-ordination Hub to promote pre-hospital triage redirection and streaming. In addition to (Business As Usual) BAU improvement actions: - Continued focussed roll-out of 6-Goals schemes of work - D2RA / Trusted assessor model - SAFER - Criteria-led discharge - Continuous Flow Model (CFM) - Robust SDEC model During June 25 improvement work (PDSA) was undertaken (and subsequently continued) at Morriston Hospital including: - Anglesey Ward to temporarily operate as a General Medical ward to help decompress the ED - Streamlining ED assessment and direct referrals to medicine Redesigning the medical assessment model in the AMU - Enhancing specialty assessment and patient allocation - Implementing a 7-day Same Day Emergency Care (SDEC) model - Reviewing and applying consistent criteria to reside - Roll-out of a new Patient Flow Model: ‘Your Next Patient |  |  | Action | Lead |  | Deadline |
|  |  |  | Implementation of revised senior decision-making capacity within SDEC (Same Day Emergency Care) and AMU (Acute Medical Unit) | Group Medical Director, Morriston |  | 31/10/2025 |
|  |  |  | Amended action: Review of community services being undertaken by Group Nurse Directors for PCT / Morriston to ensure return of investment ahead of expansion. (See below) | Group Nurse Directors (Morriston & PCT) |  | 31/10/2025 |
|  |  |  | Implementation of UEC (Urgent & Emergency Care) Navigation Hub to decrease demand and implement right patient right place process. | Chief Operating Officer |  | Complete (Initial launch – SPOA (Single Point Of Access) in place from Oct 2025. National Clinical Conversation Before Conveyance implemented in line with Six Goals framework. |
|  |  |  | Focus on reducing pathway of care delays (POCDs) as per the Care Action Committee 50-day Challenge. Update: Initial improvement made through ‘Test of Change’ and advanced D2RA work. Some deterioration in POCD position – working with LA partners to mitigate the risk. Formal agreement to progress to permanent D2RA Hub. | Associate Service Group Director, PCTS |  | 31/01/2026 (reduce to 100 Clinically Optimised Patients) |
|  |  |  | Further develop admission avoidance pathways with Welsh Ambulance Services Trust, focussing on Falls prevention and Respiratory conditions. Level 2 Falls service launch October 25. | Assistant Director Operations UEC |  | 31/10/2025 (linked to 6 Goals reporting & funding) |
|  |  |  | Discharge improvement sprint, focusing on clinically optimised patient (COP) wards, to free up bed capacity/ improve flow across Morriston site. This will be followed by refresh of the Optimal Hospital Flow Framework at Board Rounds via sustainable ward-level discharge coaching and support. | Assistant Director Operations UEC/ Group Director Morriston |  | Discharge sprint - 13/10/2025-23/10/2024 Flow activity – Oct 25-Mar 26 |
| Assurances (How do we know if the things we are doing are having an impact?) - Urgent & Emergency Care Board is meeting monthly chaired by the COO. - Six Goals programme reviews the plan on a monthly basis - UEC Redesign held 2-weekly to update on work streams - UEC Summit meetings held x 2 with Executive Management Board – 3rd summit planned March 25. - D2RA Executive meeting held Feb 25 – Memorandum of Understanding (MOU) re D2RA agreed. Operational workshop held Mar 25 with a plan to test D2RA principles pre-Easter weekend - Ongoing delivery of the Integrated Discharge Hub with both front and back door focus – programme of work in progress to design sustainable solution - Improved performance metrics (ambulance handover, patient time in ED department, flow & discharge) |  |  | Gaps in assurance (What additional assurances should we seek?) Affordability of the UEC Care Co-ordination Hub longer term post 25/26 F/Y when WG Six Goals funding ceases. Affordability of a sustainable D2RA model and right sizing of the community services and bedded facilities to support timely discharge. Commitment of Local Authorities to support the Integrated Discharge Hub (IDH) at the required level. Although the Test of Change initiatives have had a positive impact on ambulance handovers and flow through to down-stream wards, there remain unacceptably long delays for ED patients to be seen and treated. Therefore, the risk score remains as noted until improvement is made in this area. This is now a focus in Q2/Q3. Availability of project resource to roll out all improvement initiatives in a timely way. |  |  |  |
| Additional Comments / Progress Notes 08/08/2025: Reviewed & no change 16/10/2025: Risk entry reviewed & actions updated. Recent UEC diagnostic demonstrates increased ambulance and ED attendance profile. |  |  |  |  |  |  |

| Datix ID Number: 840 Health & Care Standard: |  |  | HBR Ref Number: 16 Risk Target Date: 31/03/2026 | Current Risk Rating 4 x 3 = 12 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Planned Care |  | BAF Ref: 2.5 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Performance & Finance Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Access and Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. NB: Whilst cancer care is an element of Planned Care this risk does not include the Cancer Waiting Times target, which is covered in HBR Ref 50. |  |  | Date last reviewed: September 2025 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 4 = 16 Current: 4 x 3 = 12 Target: 4 x 2 = 8 |  |  | Rationale for current score: The Health Board delivered the 104 week and 52 week waiting time targets at the end of March 2025. This has been sustained during Qtr 1 & 2 of 25/26. Current risk score reflects that improved position. |  |  |  |
| Level of Control = 90% |  |  |  |  |  |  |
|  |  |  | Rationale for target score: There is scope to reduce the likelihood score to reduce the overall risk to an acceptable level. The risk target date indicates when we expect to see some reduction in waiting lists – albeit the overall risk level may remain as work continues. |  |  |  |
| Date added to the SBU HB risk register Apr 2019 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - There is a bi-weekly Enhanced Monitoring meeting specifically for assurance on the recovery of our elective programme. - Specialty level capacity and demand models set out the baseline capacity and identify solutions to bridge the gap this financial year. - A focused intervention is in train to support to the 10 specialties with the longest waits. - Long waiting patients are being outsourced to the Independent Sector, where appropriate - Additional internal activity is being delivered on weekends (via insourcing), which is working towards reducing the wait for outpatient appointment to below 26 weeks. - Planned care trajectories were developed and submitted to Welsh Government. - Governance process put in place to monitor performance against trajectories internally, and with Welsh Government as part of Targeted Intervention. - External & internal validation continues. - All long waiting patients are receiving clinical reviews to ascertain continued need for surgery. - Monitoring of complaints and concerns in regards to waiting times are in place to identify issues and trends. |  |  | Action |  | Lead | Deadline |
| Assurances (How do we know if the things we are doing are having an impact?) - TI dashboard developed to monitor performance in a live state - Weekly monitoring meetings chaired by the Assistant Director of Performance - Bi-weekly planned care meetings chaired by the Chief Operating Officer - Monthly TI monitoring meetings with Welsh Government |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| Additional Comments / Progress Notes 16/05/2025: Action complete: Theatre Optimisation Programme now in place to maximise efficient use of theatre capacity. Risk assessment revised to reflect improved performance and de-escalation by Welsh Government to Enhanced Monitoring status. Monitoring of continued delivery is ongoing. 18/07/2025: Risk score reduced in line with continued delivery of RTT targets. 08/08/2025: Reviewed and no change – no patients waiting over 104 weeks. |  |  |  |  |  |  |

| Datix ID Number: 1761 Health & Care Standard: |  |  | HBR Ref Number: 50 Risk Target Date: TBC | Current Risk Rating 5 x 4 = 20 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Cancer Care |  | BAF Ref: 2.6 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Performance & Finance Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Access to Cancer Services There is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. The health Board remains unable to deliver on the target of 75% of patients being treated within 62 days and is currently under targeted intervention by Welsh Government to improve performance. |  |  | Date last reviewed: September 2025 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 5 = 20 Current: 5 x 4 = 20 Target: 4 x 3 = 12 |  |  | Rationale for current score: Risk score is based on being off trajectory for SCP but reduced (July 25) in line with improvements in delivery. |  |  |  |
| Level of Control = 70% |  |  | Rationale for target score: Target score reflects the challenge this area of work presents the Board and where small numbers of patients impact on the potential to breach target. |  |  |  |
| Date added to the SBU HB risk register: Apr 2019 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Tight management processes to manage each individual case on the Single Cancer Pathway (SCP). Enhanced monitoring & weekly monitoring of action plans for top 6 tumour sites. - Initiatives to protect surgical capacity to support SCPs have been put in place - Tumour sites have been given additional targets to achieve by the end of Qtr1: - Achieve the 10-day 1st Outpatient target - Deliver a decision to treat (DTT) by day 31 - A specific plan is being delivered to support Pathology services and ensure SCP tests are turned around within 5 days. |  |  | Action |  | Lead | Deadline |
|  |  |  | Following a review of governance processes for our Annual plan, Cancer monitoring will now be included in the Planned Care Board |  | Chief Operating Officer / Director of Planning Partnerships | Complete |
| Assurances (How do we know if the things we are doing are having an impact?) - TI dashboard developed to monitor performance in a live state - Weekly TI monitoring meetings chaired by the Chief Operating Officer - Bi-weekly Cancer meetings chaired by the Deputy Chief Operating Officer - Monthly TI monitoring meetings with Welsh Government |  |  | Gaps in assurance (What additional assurances should we seek?) Performance and activity data monitored, but delays to treatment continue while sustainable solutions found. |  |  |  |
| Additional Comments / Progress Notes 15/10/2025: Action completed – Cancer monitoring included in Planned Care Board |  |  |  |  |  |  |

| Datix ID Number: 1763 Health & Care Standard: |  |  | HBR Ref Number: 52 Risk Target Date: TBC |  | Current Risk Rating 4 x 3 = 12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: People of Swansea Bay live healthier, equitable and more equal and prosperous lives |  | BAF Ref: 1 | Director Lead: Richard Thomas, Director of Communications and Engagement Assuring Committee: Performance & Finance Committee |  |  |  |
| Risk: Impact Assessment Requirements The Health Board does not have sufficient skills & resource in place to undertake integrated equality impact assessments in line with strategic service change and policy development. |  |  | Date last reviewed: September 2025 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 4 = 16 Current: 4 x 3 = 12 Target: 4 x 2 = 8 |  |  | Rationale for current score: - Current lack of required skills / staff to deliver requirements. - Risk lowered to 12 because new Integrated Impact Assessment process developed and being tested across a range of issues. |  |  |  |
| Level of Control = 50% |  |  | Rationale for target score: - All of these areas need to have adequate resourcing and robust processes / policies in place for the organisation to make robust plans, engage public confidence and meet our statutory and public duties. |  |  |  |
| Date added to the SBU HB risk register Apr 2019 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Robust policies and processes to be in place for Impact Assessment going forward. - EIA responsibilities incorporated into wider Impact Assessments. - Development of Strategic Equality Group across organisation to support processes. |  |  | Action | Lead |  | Deadline |
|  |  |  | Action amended: Revised structure within Engagement team to ensure equity, diversity & belonging (EDB) issues coordinated across Health Board. | Assistant Director of Insight, Charity & Engagement & DICE |  | 30/09/2025 |
|  |  |  | Revised structure agreed and posts appointed to. | Assistant Director of Insight, Charity & Engagement & DICE |  | 01/10/2025 |
|  |  |  | Roll out Impact Assessment process across organisation. Training and integration with planning processes across the organisation will be required. | Assistant Director of Insight, Charity & Engagement & DICE |  | 30/09/2025 |
| Assurances (How do we know if the things we are doing are having an impact?) Advice on Equality Impact Assessment and then wider Impact Assessments available across organisation supported by robust policies and procedures, overseen by Strategic Equality Group. |  |  | Gaps in assurance (What additional assurances should we seek?) Participation from across organisation in Strategic Equality Group. |  |  |  |
| Additional Comments / Progress Notes 04/08/2025: Risk reviewed. Rationale comments & action target refreshed. Discussions underway regarding investment in Engagement / EDB capacity. Risk lowered because new Integrated Impact Assessment process developed and being tested across a range of issues. 20/08/2025: A revised structure has been produced and will be subject to review and sign off in September. |  |  |  |  |  |  |

| Datix ID Number: 2522 Health & Care Standard: |  |  | HBR Ref Number: 75 Risk Target Date: TBC |  | Current Risk Rating 5 x 2 = 10 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is high quality, safe, efficient, and delivers the best possible outcomes for people |  | BAF Ref: 2 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Performance & Finance Committee |  |  |  |
| Risk: Whole-Service Closure Risk that services or facilities may not be able to function if there is a major incident or a rising tide that renders current service models unable to operate |  |  | Date last reviewed: September 2025 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 4 = 20 Current: 5 x 2 = 10 Target: 5 x 1 = 5 |  |  | Rationale for current score: Risk reflects transition to business as usual as part of living with Covid strategy. BCP plans in place. There is still fluctuation in patient numbers and new variants continue to emerge so score maintained as watching brief. |  |  |  |
| Level of Control = 25% |  |  | Rationale for target score: The strategy of moving towards living with Covid will eventually lower the risk level to target. |  |  |  |
| Date added to the SBU HB risk register May 2021 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Sites have business continuity plans and the impact of one site being overwhelmed by COVID demand has been reviewed. - Monitoring of associated risks has been being transferred to appropriate forums such as UEC Board, Elective Care Board and Nosocomial Group with overall oversight by Management Board. - Ongoing surveillance of epidemiology data for early warning and further change to risk level via live Covid dashboard. |  |  | Action | Lead |  | Deadline |
|  |  |  | Periodic review of risk | COO |  | See Notes Below |
| Assurances (How do we know if the things we are doing are having an impact?) Monitored via Management Board for early warning signs. |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| Additional Comments / Progress Notes A risk entry on Emergency Preparedness, Resilience and Response, (EPRR) and Recovery has been written as part of the strategic risk register development to replace this entry and reflect business continuity risk. |  |  |  |  |  |  |

| Datix ID Number: 3444 Health & Care Standard: |  |  | HBR Ref Number: 92 Risk Target Date: 31/03/2026 | Current Risk Rating 5 x 5 = 25 |  |
| --- | --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, financially sustainable and responsible organisation |  | BAF Ref: 6 | Director Lead: Darren Griffiths, Director of Finance and Performance Assuring Committee: Performance & Finance Committee |  |  |
| Risk: Forecast Deficit Forecast deficit is not met due to (1) insufficient progress on run rate reduction, (2) the saving targets required across all areas are not achieved. |  |  | Date last reviewed: September 2025 |  |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 4 = 20 Current: 5 x 5 = 25 Target: 5 x 1 = 5 |  |  | Rationale for current score: - Delivery of the deficit plan is predicated on a combination of savings and run rate reductions - Consequence is significant as failure to deliver the plan could impact service delivery if cost reduction required later in the year - A deficit plan is a failure to meet a statutory duty |  |  |
| Level of Control = 25% |  |  |  |  |  |
| Date added to the SBU HB risk register June 2023 |  |  | Rationale for target score: - The consequence will not change given the important of financial delivery and its relationship with the delivery of the Health Board recovery and sustainability plan - Reducing likelihood to 1 supports a confidence that the deficit plan will be delivered. |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |
| The Health Board is doing the following: - Accountability Letters and Budgetary Management Framework were issued to all Directors in April 2025, which set the expectation and budget for 2025/26. - Introduced in Q3 of 2024/25 the Health Board has put in place further oversight via the Recovery & Sustainability Board, which reported directly to PFC and is chaired by the CEO. This Board is held bi-weekly. - Supporting the R&S Board is the R&S Team, which for 2025/26 has dedicated resource to lead the programmes of work agreed for 2025/26, of which the Board has agreed on 5 key areas. - Budgetary Management approach 2025/26 requires all Services Groups to produce a Financial Strategy by end May 2025. - Continued transparent exchange of position with NHS Executive & Welsh Government, with both weekly and monthly meetings with the NHS Executive. - Standard Day 5 Finance Reports on Variable Pay, Savings Performance and Flash report published via SharePoint site. - Variable Pay Cap agreed by the organisation to deliver £32m of savings as set out in the Financial Framework dated 30th June 2025. - Strengthening of the Recovery & Sustainability governance and controls aligned to the initial recommendations from work by Deloitte (external partner). |  |  | Action | Lead | Deadline |
|  |  |  | Extension to commissioning of external support (Deloitte), in collaboration with Welsh Government, which commenced on 14th July 2025. | Director of Finance & Performance | Started. Expected date of completion 31/10/2025 |
|  |  |  | As set out in the Mth 3 MMR WG reply letter a plan with clear deliverables and milestones must be submitted to WG to provide assurance on delivery of the 2025/26 Financial Target. | Director of Finance & Performance | Complete |
|  |  |  | Service Group Directors and Finance Business partners are required to provide robust forecast for 2025/26 and recurrent, including savings delivery for Check & Challenge meeting with Director of Finance & Performance. This will support wider assessment of the Health Board forecast to 31st March 2026. | Director of Finance & Performance | Submission Data from Service Groups 3rd November. Check & Challenge Meetings 4th November. Assessment wider Health Board position by mid November. |
| Assurances (How do we know if the things we are doing are having an impact?) The Health Board financial performance is reviewed and monitored through: - WG Monthly Monitoring Returns and letter signed by CEO and DOF - Monthly financial performance meetings - Monthly performance meetings (New 2025/26) - Performance & Finance Committee - Independent Member briefings - Recovery & Sustainability Board - Routine reporting to Board of most recent monthly position and financial forecasts - Weekly meetings with the NHS Executive - Monthly TI Meetings with NHS Executive - Face to Face meetings with Director Finance for NHS Wales |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |
| Additional Comments / Progress Notes 04/08/2025: Financial Framework submitted to WG on 30th June clearly outlines recovery actions required by HB to meet WG expectations 04/08/2025: Formal reply letter submitted to WG on 18th July 2025 as requested setting out the assurance regarding delivery of the financial plan and the £42.5m target as discussed with PFC and Board. 04/08/2025: Follow up letter to 18th July was submitted to WG on 31st July 2025 providing further details on the savings delivery for 2025/26. 11/09/25 As set out in the Mth 3 MMR WG reply letter, a plan with clear deliverables and milestones was to be submitted to WG to provide assurance on delivery of the 2025/26 Financial Target. This was completed and the document submitted to WG on 11th September. This was followed with a number of meetings with WG during September. Formal updates on progress will be reported via the monthly WG MMR submissions. |  |  |  |  |  |

| Datix ID Number: 3448 Health & Care Standard: |  |  | HBR Ref Number: 93 Risk Target Date: 31/03/2026 | Current Risk Rating 5 x 4 = 20 |
| --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, financially sustainable and responsible organisation |  | BAF Ref: 6 | Director Lead: Darren Griffiths, Director of Finance and Performance Assuring Committee: Performance & Finance Committee |  |
| Risk: Reduced Capital Funds Reduced National NHS funds available for major capital schemes requiring a restricted Capital Plan for 2025/26. |  |  | Date last reviewed: September 2025 |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 4 = 20 Current: 5 x 4 = 20 Target: 5 x 1 = 5 |  |  | Rationale for current score: - The Health Board has been advised that its discretionary capital allocation for 2025/26 is £13.875m. - The funding available within the Capital Resource Limit (CRL) will not meet the demands for capital investment. Discretionary capital is deployed to replace ageing medical devices & equipment; to address backlog maintenance of premises; and to support small scale, non-National service improvements with capital investments - The outcome of the national capital prioritisation exercise means some major capital scheme business cases are on hold. A number of high-risk priority schemes will require funding support from WG, including interim measures for ED and Acute Adult Mental Health In-patients services. - The approved plan assumes income of £1.499m from WG for expended business case fees. - There is potential for further capital requirements arising from service model changes which will need to be managed. - Potential consequences of this risk are the inability to achieve the ambitions set out within health board plans; the potential failure of ageing equipment leading to service disruption; the exposure to potential environmental health & safety risks. |  |
| Level of Control = 25% |  |  |  |  |
| Date added to the SBU HB risk register June 2023 (refreshed June 2024) |  |  | Rationale for target score: The target score expresses the aspiration of the health board for addressing this risk. The target date indicated above reflects the point which the current actions are anticipated to reduce the risk, though knowledge of the actual funding available is required to reduce it further and this is not available until some months into the financial year. |  |

| Controls (What are we currently doing about the risk?) | Mitigating actions (What more should we do?) |  |  |
| --- | --- | --- | --- |
| The Health Board is doing the following: - Regular dialogue with Welsh Government regarding capital requirements. - Clear communication and reporting of the capital position, the risks and limitations. - Close management of all schemes to ensure slippage is understood along with the impact on service. - Clear prioritisation of any new requirements recognising the current constraints | Action | Lead | Deadline |
|  | Routine review and flexing of plan as spending is committed through the year. Routine monitoring processes will identify any potential slippage and will deploy this on risk-based basis. | Director of Finance & Performance | Monthly through the financial year as plan is dynamic |
|  | Examine the specific prioritisation and phasing of capital investment to meet health board objectives through the Capital & Estates Taskforce. | Director of Finance & Performance | Bi-Monthly |
|  | Maintenance of risks through the Capitalisation Prioritisation Group should additional WG funding become available later in the year. | Assistant Director of Finance (Strategy & Planning) | On-going |
|  | Fix in-year CRL position with WG | Assistant Director of Finance (Strategy & Planning) | 31/10/25 |
| Assurances (How do we know if the things we are doing are having an impact?) The Health Board capital position is reviewed and monitored through: - Quarterly capital prioritisation group - Performance & Finance Committee quarterly finance report - Capital & Estates Taskforce - Capital & Estates Board - Capital Management Group - Monthly Monitoring Returns to Welsh Government. | Gaps in assurance (What additional assurances should we seek?) Reporting on impact of constraints to the capital programme on service delivery. |  |  |
| Additional Comments / Progress Notes 24/6/2025: Risk remains at 20 following Performance & Finance Committee meeting. 24/6/2025: Some uncertainty around the future approval of capital funding following WG letter of 6/6/25 on the unapproved revenue financial plan for the Health Board. 16/10/25: There are new constraints on the national funding position which is putting pressure on the local in-year capital plan. Decisions made on fixing the in-year CRL position on 31st October with WG will need to take account of the new unfunded local pressures. |  |  |  |

| Datix ID Number: 3516 Health Care Standards: |  |  | HBR Ref Number: 94 Risk Target Date: TBC |  | Current Risk Rating 4 x 3 = 12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Mental Health & Learning Disability Services |  | BAF Ref: 2.3 | Director Lead: Deb Lewis, Chief Operating Officer Assuring Committee: Performance & Finance Committee For information: Quality & Safety Committee |  |  |  |
| Risk: CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. Links to other CAMHS risk register entries: (Ref: 3410/3373/3351/3346/3349/3350) |  |  | Date last reviewed: September 2025 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 5 = 20 Current: 4 x 3 = 12 Target: 3 x 3 = 9 |  |  | Rationale for current score: Marked improvement in the performance against the Mental health Measure for CAMHS. Data validation for new patients complete. Current risk score 12 in view of improved performance however this reflects the fragility in the workforce to deliver sustained performance. Work is still ongoing within CAMHs to maintain and improves the situation. |  |  |  |
| Level of Control = % |  |  | Rationale for target score: The rationale for the target score is linked to successful recruitment and more timely access to services for children and young persons which will reduce risk. |  |  |  |
| Date added to the SBU HB risk register October 2023 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| -Ongoing recruitment into all staff groups -Temporary agency workforce in nursing at premium pay rates to sustain current levels of performance -Recent appointment into psychological therapies lead posts. -Recent appointments to substantive consultants psychiatrist posts. -Moved vacancy nursing establishments into part 1 of the services to recruit and increase capacity. |  |  | Action | Lead |  | Deadline |
|  |  |  | Continued efforts at recruitment | Acting Associate Service Director |  | 31/10/2025 |
| Assurances (How do we know if the things we are doing are having an impact?) -Monthly CAMHS Directorate meeting in place where performance and workforce are scrutinised -Reporting into Weekly Business Team and MH & LD management board. -Reporting into SBU Performance & Finance Committee and IQPD (Integrated Quality & Performance Delivery) meeting with Welsh Government -Ongoing validation of the waiting list to ensure robust reporting going forward |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| Additional Comments / Progress Notes 01.09.25: Performance against Part 1B will remain a challenge until the backlog of >28-day waiters is cleared. However, there is a recovery plan to support this, and demand & capacity review will help to identify the gap. Agency usage has been reduced since October 2024 in line with the need to support the Health Board financial position from 8.4wte to 3.5wte. However, the continuation of 3.5wte agency use is essential to maintain current capacity/performance levels whilst vacancies are recruited, and new staff are inducted. Current vacancies (2.65wte) are live on TRAC recruitment system.. |  |  |  |  |  |  |

| Datix ID Number: 3571 Health & Care Standard: |  |  | HBR Ref Number: 96 Target Date: 31/03/2026 |  | Current Risk Rating 4 x 5 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, financially sustainable and responsible organisation |  | BAF Ref: 6 | Director Lead: Marie Davies, Executive Director of Planning & Partnerships Assuring Committee: Performance & Finance Committee |  |  |  |
| Risk: Failure to Develop an Approvable IMTP (statutory compliance) If we fail to have an approvable Integrated Medium-Term Plan (IMTP) for 2026/27 then we will not meet our statutory duty to break even and may lose public confidence. |  |  | Date last reviewed: September 2025 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 4 x 5 = 20 Current: 4 x 5 = 20 Target: 4 x 2 = 8 |  |  | Rationale for current score: The Health Board does not have a WG approved IMTP and has been placed in enhanced monitoring for Finance, Strategy and Planning following the inability of the Health Board to submit a balanced IMTP since March 2023. Given the All-Wales financial context the Health Board was not able to submit an IMTP in March 2025. It has instead developed an Annual Plan 25/26 set in a three-year context. |  |  |  |
| Level of Control = 70% |  |  |  |  |  |  |
| Date added to the SBU HB risk register October 2023 |  |  |  |  |  |  |
|  |  |  | Rationale for target score: The target remains to develop a financially balanced IMTP so that we meet our statutory duties. |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - As per the Welsh Government de-escalation criteria for Strategy and Planning, work has commenced to update and realign the Health Board’s strategy and clinical services strategic plan. - As per the Welsh Government de-escalation criteria for Strategy and Planning, work has been undertaken to assess the Health Board against the planning maturity matrix and develop an action plan in response. This will be reported via the Board Planning & Partnerships formal report. - The Recovery and Sustainability Board monitors delivery of agreed actions in relation to the financial position. - The Annual Plan Oversight Group has been superseded by the Integrated Planning and Performance Review Meeting which takes on a quarterly basis and is chaired by the CEO with the purpose of providing formal management oversight to the delivery of the Annual Plan, and to act as a forum for future planning discussions. - Plan development will continue to be subject to robust challenge and scrutiny through regular briefings to Independent Members, Performance and Finance Committee (now meeting twice a month, once informally and once formally) and with detailed oversight from the Board itself. |  |  | Action | Lead |  | Deadline |
|  |  |  | Refresh Clinical Services Plan | Executive Director of Planning & Partnerships/ Medical Director |  | 31/03/2026 |
|  |  |  | Recovery and Sustainability Board to continue to focus on savings delivery and now shift to a more sustainable approaches in the longer term. A new monthly performance review regime and Executive Team members to oversee thematic savings workstreams and support Service Groups to meet targets. | Executive Director of Finance and Performance |  | 31/03/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) Progress against the delivery of the plan will be scrutinised through strengthened governance supported by a new performance management and accountability framework. |  |  | Gaps in assurance (What additional assurances should we seek?) |  |  |  |
| Additional Comments / Progress Notes 13/10/2025: Register entry reviewed & updated. |  |  |  |  |  |  |

| Datix ID Number: 3692 Health & Care Standard: |  |  | HBR Ref Number: 98 Target Date: TBC | Current Risk Rating 5 x 4 = 20 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in safe and appropriate settings |  | BAF Ref: 3 | Director Lead: Darren Griffiths, Executive Director of Finance & Performance Assuring Committee: Performance & Finance Committee |  |  |  |
| Risk: Overall condition/compliance and suitability of Health Board Estate 6 FACET survey undertaken in 2022 confirmed the poor condition and suitability of premises where health care services are provided. The backlog maintenance costs are in excess of £200 million. The overall level of controllable risk is affected – compounded – by the resilience of the HB’s H&S infrastructure (Datix 2159) and the level of resourcing of Operational Estates, which influences the adequacy of capacity and capability for responding to priority risk mitigation (Datix 3444) |  |  | Date last reviewed: September 2025 |  |  |  |
| Risk Rating (consequence x likelihood): Initial: 5 x 4 = 20 Current: 5 x 4 = 20 Target: 3 x 3 = 9 |  |  | Rationale for current score: 6 FACET survey Estates Strategy and Development control plans General compliance with fire regulations and WHTM/WHBN requirements. Backlog maintenance Health Board estates strategy and DCP task and finish group Audit and Assurance limited assurance report Access to funding Ability to respond effectively to key HB initiatives and the need to support mental health services and primary and community care services with limited budgets and resources |  |  |  |
| Level of Control = 40% |  |  | Rationale for target score: Through the 6 FACET survey a number of key items have been identified covering the Physical condition, Functional suitability, Space utilisation, Quality audit, Statutory compliance and Environmental management. All of which identified significant issues with the current estate, with very few areas achieving condition ‘B’. The overall backlog maintenance is in excess of £200m. The development of a plan to improve the capabilities of Operational Estates will allow a more proactive approach to risk mitigation. |  |  |  |
| Date added to the SBU HB risk register 07/02/2024 |  |  |  |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Planned preventative maintenance, prioritising highest risk depending on funding available (EFAB Year 2, Targeted Estate Fund 25/27 (TEF), Discretionary) – linked to creation of decant space through service changes - Planned preventative maintenance. Update Asset Register and review of all PPMs to ensure that these remain relevant and a good use of available resource - Reactive maintenance on-going but on the increase due to more frequent break downs and age of estates infrastructure. - Address issues where practicable through EFAB/Discretionary capital - Estates Strategy and development control plans task and finish group - Regular reviews of the estate with reference to benchmarked best practice from NHS Wales/NHS England. Further Developing Arrangements: - Review 6 Facet conclusions with Oakleaf Consulting Ltd with reference to Operational Estates site knowledge and updated Asset Register, with a focus on the patient journey and patient safety. - Develop partnership approach to working with Capital Planning to ensure that capital schemes are better informed of risks from an Operational Estates perspective. - Develop Workforce Plan with HR/OD to address disproportionately high numbers of ‘retire and returns’ and loss of considerable experience, which is increasing in frequency. - Review and make recommendations on structure of Operational Estates and investment plans, which will need to be cost neutral as far as reasonably possible. - Continual review of the overall backlog maintenance and the risk to business continuity and where new risks are identified (e.g., recent Black start test at Morriston Hospital), re-prioritise to minimise impact on business continuity. |  |  | Action |  | Lead | Deadline |
|  |  |  | Maintain effective engagement with Welsh Government to provide funding to implement estates strategy and development control plans to address all areas outlined. |  | Assistant Director of Capital Planning | Achieved (TEF as below). Engagement will remain ongoing with bids being submitted to the WG for funding including end of Oct 25 bids to be completed 25/26. |
|  |  |  | Work with Welsh Government (WG) to source alternative solutions to funding the HB estates strategy and development control plans i.e. Private Financial Investment (PFI) - Mutual Investment Model (MIM) or other investment sources. |  | Assistant Director of Capital Planning | Working with WG will remain ongoing and raised at every WG Capital Resource meeting with understanding the problems on MIM and way forward and roll out to health boards. |
|  |  |  | Review capacity and capability of Operational Estates and make recommendations on cost neutral investment in a longer-term plan to improve effectiveness. Update: Review on estates budget is on-going with paper submitted to PFC in May 2025 and revised in the context of the health board savings plan. We are currently implementing some key positions to support the business continuity and savings plan, appointment internal through the TRAC system. Estates remain reactive to all unplanned works and break downs within limited budgets. |  | Assistant Director of Estates | March 2026 Plans are on track with the estates review completed by end of financial year and some key resources in place dependent on TRAC approvals process. |
|  |  |  | Update Asset Register, review PPMs, and implement SFG20 (industry standard compliance management) to enhance approach to ensuring viability of core infrastructure and provide assurance on business continuity. Deadline dates to be reviewed as progress varies by objective: SFG20 purchased; Asset register update currently cost prohibitive. Soft market testing complete and working on a value engineering exercise relating to affordability within limited budget / constraints. Estates and Capital centralised location end of Oct 25 to support this way of working ensuring a more proactive approach with hand over details feeding into the asset register being a live document data base linked to the Estates risk register linked to impact on business continuity. |  | Assistant Director of Estates | January 2026 required for update following deferred implementation of Software package upgrade for SFG20 with the asset register providing a base line on plant condition for replacement / end of life. |
| Assurances (How do we know if the things we are doing are having an impact?) - Monitoring through quality & Safety, Audit & Assurance and Performance and Finance committee to receive assurance and or identify gaps for key compliance and adherence to applicable legislation. - NWSSP internal audits - Site visits/tours to identify compliance and gaps in compliances with NWSSP Shared Services - Completion of FRA’s within targeted schedule - Estates strategy and development control plans being implemented - Half yearly Board oversight of strategy implementation. Consider appointment of Independent Member to support review of Operational Estates to provide advice to Officers and assurance to the Board on the range of proposed improvements. Further Developing Arrangements: - Complete review of capacity and capability of Operational Estates, which commenced in December 2024, and make recommendations on a way forward for improved effectiveness of resource utilisation and enhanced resilience. - Complete review of Approve Persons and how duties are quality assured. This to also include action to address current gaps, i.e. AE Lifts and AE Pressure Vessels - Continual review of the overall backlog maintenance and the risk to business continuity and where new risks are identified (e.g. recent Black start test at Morriston Hospital), re-prioritise to minimise impact on business continuity. |  |  | Gaps in assurance (What additional assurances should we seek?) - Suitable funding to implement the estates strategy and development control plans and sufficient resource to ensure that Operational Estates is capable and competent with regard to critical risk mitigation. This will need to be planned and implemented iteratively over the longer term, say 5 to 10 years, etc. - Allocate funds where available to address issues outlined - Detailed work and level of resourcing available for supporting same to be commissioned to consider primary and community estates strategy along with mental health services and awaiting the Primary care service model. |  |  |  |
| Additional Comments / Progress Notes Through the 6 FACET survey a number of key items have been identified covering the Physical condition, Functional suitability, Space utilisation, Quality audit, Statutory compliance and Environmental management. The benefits of the 6 FACET survey will be enhanced through more detailed review of assets through updating the HB’s critical infrastructure asset register. All of which identified significant issues with the current estate, with very few areas achieving condition ‘B’. The overall backlog maintenance is in excess of £200m. Key areas include ventilation and cooling with major infection control and other implications. Theatres/Wards/ED and general acute settings including mental health and learning disabilities being old and not compliant with the latest WHBN’s and WHTM’s. The heating, power and medical gas systems have also been identified as issues for concern in the 6 FACET surveys and from independent audits. The health board’s latest NWSSP estates audit received a limited assurance due to limited Welsh Government funding available to undertake backlog maintenance and implementation of estates strategy. 27/08/2025: Continuation of works through TEF and estates discretionary capital in addition to major capital schemes to address compliance. 16/10/2025: Continuation of works as above. |  |  |  |  |  |  |

Risk Score Calculation

For each risk identified, the LIKELIHOOD & CONSEQUENCE mechanism will be utilised.  Essentially this examines each of the risks and attempts to assess the likelihood of the event occurring (PROBABILITY) and the effect it could have on the Health Board (IMPACT).  This process ensures that the Health Board will be focusing on those risks which require immediate attention rather than spending time on areas which are, relatively, a lower priority.