## Slide 1
Swansea Bay University Health Board
Integrated Performance Report
August 2026

## Slide 2
Report Overview
Section 1: Summary of performance against the SBUHB Breakthrough Objectives and the Welsh Government Oversight & Escalation criteria
Section 2: Detailed updates against the SBUHB Breakthrough Objectives and the Welsh Government Oversight & Escalation criteria
Section 3: NHS Performance Framework 2026-27 metrics & Local Measures
The Health Board Integrated Performance Report will provide updates against all areas under escalation with Welsh Government, all performance metrics outlined within SBUHB Breakthrough Objectives, updates against the NHS Wales Performance Framework 2026-27, along with Service specific or Annual plan updates as requested.

## Slide 3
Section 1:
Summary of performance against the SBUHB Breakthrough Objectives and the Welsh Government Oversight & Escalation criteria

## Slide 4
SBUHB 2026-27 Breakthrough Objectives
Strategic Objective | Long Term Success | Breakthrough Objective 2026/27 | Baseline Data (March 2026) | July-26 | Executive Lead
Better Health for all | People of Swansea Bay live healthier, fairer and more prosperous lives | Flu vaccine uptake improved in most deprived areas by 1% to reach 69.9% (Flu programme runs during the winter months) | 68.90% | N/A | Director of Public Health
 |  |  | (65 years +) |  | 
 |  | Bowel screening rates up by 1% to reach 63.3% by March 2027 | 62.30% | 61.1% | 
Improved patient safety | Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | No patients waiting more than 104 weeks for referral to treatment. | 0 | 0 | COO
 |  | Single Cancer Pathway performance to reach 76% | 55% | 49.5% (June 2026) | COO
 |  | Reduce the number of adults placed out of area for mental health inpatient treatment by 50% to 11 patients in March 2027 | 22 | 16 | COO
 |  | 30% reduction in avoidable pressure ulcers to reach < 87 PU's reported in March 2027 | 124 | 114 (Total No.) (May 2026) | Executive Director of Nursing
 |  | Reduce the number of patients waiting 12 hours or more in ED by 10% to < 1,212 by March 2027 | 1,356 | 1,364 | COO
Care is delivered in partnership | Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation | Delayed Packages of Care patients reduced to <100 at any one time | 223 | 159 | COO
 |  | Increase in the take up of the NHS App by 25% (from a March 2026 baseline) to 111,854 users by March 2026 | 88,842 | 101,322 | Director of Digital
A great place to work | The health board is a great place to work where all staff feel valued and work together towards a common goal | Improvement in staff engagement score by 5% to reach 75.3% (Annual data collection) | 70.30% | N/A | Director of Workforce & OD
 |  | Improvement in staff health & wellbeing by 1% to reduce sickness rates to < 6.09% | 7.09% workforce sickness absence | 8.22% | Director of Workforce & OD
Use every NHS £ wisely | The health board is a resilient, sustainable and responsible organisation | Deliver savings plan of £65m of which £50m is recurrent | £55.4m delivered in year with £22.9m recurring | £3.7m Savings | Director of Finance

## Slide 5
Delivery against Welsh Government Targeted Intervention Criteria
TI Area (Level 4) | Criteria to achieve | Performance (July-26)
Cancer | 60% performance maintained for 3 months against the SCP target. | 49.5% (June-26)
UEC | Continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on Q2/Q3 2023 baseline) | 391 (8.2% increase)
 | Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across HB | 10.85%
 | Median time from arrival at emergency department to assessment by a clinical decision maker should not exceed 60 minutes | 85
 | Continuous reduction in delayed pathways of care of 5% for three consecutive months and then maintained for three months (based on Oct-Dec 23 baseline) | 159 (8.8% reduction)
HCAIs | A clear improvement plan based on a root cause analysis to address the issue of hospital onset HCAIs. | In place
 | C-Diff: reduce the number of hospital onset infections by 40% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 10 cases to no more than 6 per month) | 12 cases
 | Staph aureus: reduce the number of hospital onset infections by 25% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 4 cases to no more than 3 per month) | 6 cases
 | E-coli: reduce the number of hospital onset infections by 20% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 5 cases to no more than 4 per month) | 4 cases
 | Klebsiella: reduce the number of hospital onset infections by 10% and maintain for 3 months based on 2017/18 figures (baseline –54 cases in 2017/18, reduce to average of at most 4 per month) | 4 cases
Finance | Detailed updates included within the report | 
Strategy & Planning | Detailed updates included within the report | 
Maternity & Neonates | Detailed updates included within the report | 
Dashboard

## Slide 6
Delivery against Welsh Government Enhanced Monitoring Criteria
Dashboard
Escalation Area (Level 3) | Criteria to achieve | Performance (July-26)
CAMHS | 80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral | 85%
 | 70% of therapeutic interventions started within 28 days following an assessment by LPMHS | 85%
 | 85% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan | 95%
Planned Care | 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 month | 100%
 | Continuous improvement towards 75% of all open outpatient pathways waiting less than 26 weeks | 89.41%
 | 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months | 100%
 | Continuous improvement towards 80% of all open pathways waiting less than 36 weeks | 77.30%
 | 12% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2024 baseline.) | 37.36%
 | 68% R1 ophthalmology patient pathways to be waiting within or no longer than 25% of their target date for an outpatient appointment and maintained for 3 months | 65.81%
 | 85% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months | 70.55%
 | 85% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 month | 52%
 | 85% of patients waiting for a NOUS and non cardiac MRI to be waiting less than 8 weeks and maintained for 3 months. | 70.77%
 | 90% of patients waiting for therapies to be waiting less than 14 weeks and maintained for 3 months | 100%

## Slide 7
Section 2:
Detailed updates against the SBUHB Breakthrough Objectives and the Welsh Government Oversight & Escalation criteria

## Slide 8
Targeted Intervention (Level 4) - Strategy & Planning
De-escalation Criteria | Actions – Updated June 2026 | RAG Status
Submission of a balanced and credible three-year medium-term plan or acceptable annual plan in line with the current planning framework. | Throughout Quarter 1, a significant programme of work was undertaken to respond to Welsh Government feedback and strengthen both the Plan and the supporting delivery arrangements Improvements focused on: Strengthened delivery plans, trajectories and accountability arrangements. A clearer and more robust financial position, including articulation of the underlying deficit, savings programme and opportunities pipeline. Improved governance, oversight and organisational grip through the establishment of the Delivery Unit. Stronger alignment between priorities, milestones, ownership and measurable outcomes. The updated Annual Plan was considered by the Board on 25 June 2026 and formally resubmitted to Welsh Government. While the Plan remains unable to achieve statutory financial balance in-year, the Board concluded that it now represents a more credible and deliverable plan, supported by strengthened governance, financial control and evidence of early Quarter 1 delivery improvements. The Health Board remains focused on sustaining delivery, strengthening organisational grip and progressing towards financial recovery and improved performance throughout 2026/27. | 
Evidence of a clear roadmap and implementation of the health board’s Clinical Services Plan. | Engagement has been ongoing internally and with trusted stakeholders focusing on the case for change and the principles for transformation including Top 100 Leadership Event, CEO ‘Ask Abi’ Session, Stakeholder Reference Group Health Professionals Forum and operational leadership groups. Large Clinical Leadership Event held 1st July with 135 colleagues from across the Health Board Llais, CVS and neighbouring Health Boards confirming our principles for transformation and to begin the work of developing our future model of care The summer months will see pre-engagement with public and stakeholders and additional work being undertaken by the clinical reference group to further develop the model of care. ‘Transforming for the Future’ report to go to Board in November 2026 | 
Welsh Government’s confidence in delivery based on an assessment against an agreed planning maturity matrix | Letter received from WG setting expectations for assessment on Planning Maturity Matrix to be undertaken and approved through Boards in November 2026. Process initiated and underway | 
Progress made with regional planning | The Regional Drive and Delivery Group (RDDG) (Chaired by CEOs Abi Harris and Phil Kloer) did not meet in August as planned due to time constraints. However, RDDG members met within a productive Regional Exec-to-Exec Board and much of the planned RDDG agenda was covered within the session. Regional plans and progress updates were received from all RJC subgroups – Regional Health Economy; Clinical Service Planning; Finance and Contracting; Workforce and Organisational Development; Data and Digital, and Research, Innovation, and Excellence. | 
Updates against the de-escalation criteria outlined by Welsh Government can be found below;

## Slide 9
Breakthrough Objective: Increase Bowel screening rates in Swansea Bay UHB by 1% | July 2026 Performance | 61.1%
 | How are we doing? The SBUHB public health team continue to support Public Health Wales on efforts to enhance the uptake of bowel screening. What actions are we taking to improve? Bowel Cancer UK’s Early Diagnosis Programme is running for 12 months in Neath Port Talbot and upper Valley Towns from 1st June 2026. The programme combines: Community awareness events and volunteer activity; Education and engagement with GPs, pharmacies and other healthcare professionals; Local advertising and the “Tell Your GP Instead” campaign; Work with community groups and local partners; Encouraging eligible people to complete bowel-screening kits; and Encouraging people with possible symptoms to contact their GP promptly. The programme is intended to address areas where bowel cancer tends to be diagnosed later or bowel-screening participation is lower Submitted a plan to the Planned Care Recovery Programme to address the backlog of patients waiting for Bowel screening and are seeking a sustainable solution for the South-West Wales Region. We are continuing to provide local insight to Public Health Wales in relation to further targeted programmes. What are the risks to delivery? The focus of Public Health Wales may be affected by the development of other areas of responsibility through this year, and changes to staffing. | 
People of Swansea Bay live healthier, fairer and more prosperous lives

## Slide 10
Enhanced Monitoring Target: 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months | July 2026 Performance | 100%
Breakthrough Objective: No patients waiting more than 104 weeks for treatment | July 2026 Performance | 0
 | How are we doing? In July 2026, the Health Board reported 100% of open pathways waiting less than 104 weeks for treatment, maintaining performance against the enhanced monitoring target. What actions are we taking to improve? Grip & Control Six-week forward operational review maintained. Weekly specialty delivery reviews focussed on highest-risk pathways. Enhanced validation programme and establishment of central validation capability. Productivity Theatre productivity programme progressing including utilisation, late starts, turnaround times and job planning. Outpatient transformation programme progressing including validation, PIFU, direct listing and pathway redesign. Recovery Delivery Welsh Government recovery submission completed. Costed specialty recovery plans developed across elective pathways. Regional recovery proposals developed with Hywel Dda for orthopaedics, and cataracts Immediate delivery actions commencing within available resources whilst national funding decisions are awaited What are the risks to delivery? Clinical engagement is a critical dependency for delivery of productivity and theatre transformation Delivery of recovery trajectory remains dependent on non-recurrent WG investment Diagnostic constraints continue to limit elective throughput in selected specialties Workforce availability and sustained productivity improvements remain essential to maintaining 104 week waits. | 
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships

## Slide 11
TI Target: 60% performance maintained for 3 months against the SCP target | June 2026 Performance | 49.5%
Breakthrough Objective: Single Cancer Pathway performance to reach 76% by March 2026 |  | 
 | How are we doing? The organisation reported a deterioration in performance against the SCP target in June 2026, reporting 49.5% compared with the previous 54% in May. Backlog figures are seeing a steady decline in recent months An opportunity for resubmission to reflect a corrected performance for January – March 2026 will be available in August 2026. What actions are we taking to improve? Tumour-site recovery plans completed across priority specialties Outpatient and Inpatient component waiting list backlog reduction to 2 & 4 weeks, by re-prioritising use of existing elective capacity (by end of September 26) Reduce Pathology reporting waits. (Outsourcing delayed start – aim to commence end of August) Reduce Urgent Suspected Cancer (USC) demand by addressing inconsistencies in application of USC criteria amongst surgical and gastroenterology consultants & potential use of canSense(in conjunction with FIT testing, 63% of USC/STT colonoscopies could be avoided and it would be a useful alternative to support triage where a FIT test is not returned. (by end of August) Improve theatre productivity at the Morriston site. High acuity of patients often leads to extended surgical waits due to limited access and on-call commitments further hampers flexibility and ability to schedule patients in a timely manner. (Work commenced under Planned Care Board) Appraising opportunity to create short term increase in capacity for hysteroscopies Reduce BSW waits to index colonoscopy. Waiting times have reduced but remain long. One of our consultants has recently become an accredited screening colonoscopist, a positive development that supports our ability to reduce waiting times. Skin: Re-aligning outpatient resource towards cancer patients, away from non urgent activity has commenced, appointment of 17 additional sessions of hybrid skin and plastic surgeons to enhance capacity (going to PFAG in August) & appointment of clinical skin cancer lead from July. | 
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships

## Slide 12
TI Target: 60% performance maintained for 3 months against the SCP target |  | June 2026 Performance | 49.5%
Breakthrough Objective: Single Cancer Pathway performance to reach 76% by March 2026 |  |  | 
 | What are the risks to delivery? Cancer services are subject to underlying growth in demand from both increased prevalence and availability and cost of drugs. Reliance on outsourcing to reduce backlog in diagnostics within 3 months Resource for elements of the diagnostic programme are yet to be identified UHB’s core capacity has limited resilience as we seek to balance finance and performance Pathology backlog is prohibiting our ability to accurately report accurately | What are the risks to delivery? Looking across the whole PTL, there is evidence of increasing volumes at the start of the pathway and diagnostic stage, this is more noticeable in the following tumour sites: Gynaecological, Head & Neck, Skin, Upper GI & Urological. Pathology delays are the primary driver for the increased volumes in diagnostic backlog, accounting for 50% of the backlog. Seasonal increase in overall skin volumes are beginning to be seen. Healthcare System Engineering Demand & Capacity report findings to be discussed with the COO, date to be agreed. PMB waits are currently more than 6 weeks. The plans to decouple the one stop service and increase Outpatient hysteroscopy capacity has taken place from 1st June 2026, which has coincided with increased scan capacity. The service are now working through a plan to increase capacity by 10-20 patients per day for the scan only clinics to specifically address backlog, | 
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships

## Slide 13
Breakthrough Objective: Reduce the number of adults placed out of area for mental health inpatient treatment by 50% | July 2026 Performance | 16
 | How are we doing? The end of month figure for the number of adults placed out of area for mental health inpatient treatment was 16. There is currently a high demand for both Adult Acute and PICU beds. How do we compare across Wales? The use of private beds varies across Health Boards and is based on individual population need and is influenced by local clinical models. We now report daily to NHS Wales Performance Improvement on bed occupancy, discharges and planned discharges and POCDs. The All- Wales data is shared daily with Health Boards Executives from NHS Wales PI. Swansea was in a steady decline in terms of usage, but a busy weekend 31st-2nd August resulted in a significant spike in usage which the Service group is working at pace to mitigate. What actions are we taking to improve? Private Patient MDT Coordinator in role to ensure oversight of private placements, safe discharge, and accurate financial tracking.​ Weekly scrutiny meetings are in place within the Adult Directorate, alongside discharge planning meetings.​ Daily MDT Board Rounds initiated on all three adult mental health wards to improve LOS and flow through our own beds. A safe holding space in NPTH is being utilised and staffed to provide overnight capacity.​ Options to increase Home Treatment Team capacity and input for those in private placements under development. Bid approved by PFAG and now out to advert for posts. MDT approach to revising discharge pathways for male patients, and in future female patients, where there is no local low secure or rehabilitation provision and delays due to patients no longer meeting the criteria to reside have been extended.​ Input into All Wales meetings with NHS Wales PO on the out of area beds workstream What are the risks to delivery? Volatility in demand Ongoing increases in the cost of private provision. Challenges related to patient flow and repatriation. | 
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships

## Slide 14
Breakthrough Objective: 30% reduction in avoidable pressure ulcers | May 2026 Performance | 114 (Unvalidated) (Total number of Pressure Ulcers) c.f. 124 in March 2026
 | In May, 114 Pressure Ulcer incidents were reported, 23 less than April. Figures remain changeable due to Datix amendments. Inpatient rate: R 2.48 per 1,000 bed days, a rate of 15% There is no national benchmark, with the highest inpatient rate recorded in Q3 (R 3.0). Primary Care Services rates remain unreliable due to caseload dashboard inaccuracies. We have seen an increase in reporting numbers in Q 4 2026, 34% Hotspots continue to be highest in Unscheduled Care | 
What actions are we taking to improve? Governance & Assurance - Pressure Ulcer Strategic Improvement Group established, Standardised scrutiny panels aligned to national frameworks, Improved incident closure rates and data quality validation and Service Group-level bespoke Quality Improvement Plans have been developed Clinical Practise and Systems - Implementation of standardised prevention pathways and policies (All Wales alignment), centralised Tissue Viability Service model, Rollout of digital wound imaging (Improvement Cymru), progression of equipment provision (including bed contract) and development of specialist neonatal prevention pathways Workforce & Education - Multi-modal education programme (face-to-face, virtual, video), targeted hotspot training in high-risk areas, Band 6/7 leadership development, Pre-registration Tissue Viability skills training, Tissue Viability Champions network and MDT complex wound forums Audit & Improvement Culture - Health Board-wide tissue viability audits, documentation and care quality reviews, peer review and shared learning processes and Staff engagement campaign: “Pressure Ulcer Superhero League 2026” |  | 
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships
What we expect to see (Outcomes by 2027):
↓ 20% PU rates in acute sites; ≤1.6/1000 bed days.
↓ 20 % avoidable PU in HB.
↓ Reduce the total number of HBA incidents by 10%
↓ Reduce HB acquired Deep damage by 10%
What are the risks to delivery?
Improvement in the number of incidents closed (64% in Quarter 4),
Focus on increasing the accuracy of data
Pressure Ulcer Strategic Group, Scrutiny alignment and peer reviews.
Audit of documentation and care provided
Multi-layered education (face-to-face, Teams, videos
Development of PU pathways, policies, and improvement plans supported by All Wales Tissue Viability Forum.
Centralised Tissue Viability service, digital wound imaging
(Improvement Cymru), and bed contract finalisation. Shared education, champions and skills programme
Quality Improvement awareness campaign 2026

## Slide 15
TI Target: Continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on Q2/Q3 2023 baseline | July 2026 Performance | 391 (8.2% increase)
Annual Plan ambition: 0 ambulance handovers > 45 minutes from September 2026 |  | 
 | How are we doing? In July 2026, the organisation reported an increase in the number of ambulance handovers over one hour, reporting an 8.2% increase in ambulance handovers. What actions are we taking to improve? Call before conveyance (CCBC) Care Home PDSA is having a small but positive impact - recent empirical data suggests a reduction of 5-6 ambulance attends per day Contact First GP mobilised into SPOA (full CCBC enabler) to enable call before conveyance (CCBC) for all ambulances (exc red and purple). Heightened WAST focus on the decision to convey, patient by patient SPOA direct referral pathways into all specialties – implemented end June 26. Aim 2-3 diverted away from ED/day (weekdays). Falls pathway - use of St Johns vehicle to respond > CCBC - pilot with WAST - mid June 26. Aim improve outcomes/reduce interventions Continue CCBC Care Home PDSA 24/7 after 1 week test of change - in place. AMU Assessment & OPAU are operating more effectively as a result of various clinically led operational changes – thus creating improved pull from ED / turnaround What are the risks to delivery? Reliance on major system change: success depends on full adoption of SPOA + push-flow model + Frailty Model Workforce reallocation risk: shifting staff/funding (primary care → UEC) may not be achieved or sustained Delivery timing risk: multiple enablers unlikely to be fully in place before July to start trajectory | 
Level 4 - Unscheduled Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships

## Slide 16
TI Target: Median time from arrival at emergency department to assessment by a clinical decision maker should not exceed 60 minutes | July 2026 Performance | 85 minutes 38.39% seen < 60 mins
Daily median time to first review in the Emergency department since the 1st May, the date we changed our method for measuring this objective is shown below, along with a heat map of the median time by hour and day. Performance is strongest at the start of the working day (08:00) and then gradually deteriorates. | How are we doing? In July 2026, the organisation reported a slight increase in the percentage of patients assessed by a clinical decision maker within 60 minutes, reporting 38.39%. What actions are we taking to improve? We are currently testing the rapid decision-making process in the department and overall we are trying to reduce demand into the emergency department through the single point of access work. Actions described on improving UEC and flow, are likely to also improve assessment time. Weekly performance & improvement meeting with ED senior team (management & clinical) commenced 23rd June 2026 What are the risks to delivery? Workforce & Roster constraints: balancing out of hours demand with clinician capacity vs working time and rota rules. Competing priorities: focus on high-acuity patients limits capacity to progress lower-acuity queue Clinical risk appetite: concern about safely accelerating decisions out of hours with reduced support services Demand unpredictability: 3-4 fold variance in individual hourly arrivals can overwhelm with delayed recovery. Queue management discipline: requires consistent real-time oversight and escalation, underpinned by robust digital system as a key enabler System-wide alignment risk: lack of available alternatives to ED at times of peak demand | 
Level 4 - Unscheduled Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships

## Slide 17
TI Target: Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across HB | July 2026 Performance | 10.85%
Breakthrough Objective: Reduce the number of patients waiting in ED for over 12 hours by 10% | July 2026 Reduction against March 2026 Baseline | 1.25% increase against baseline
 | How are we doing? In July 2026, 1,364 patients, which is 10.84% of all attendances were waiting more than 12 hours in the Emergency Department. A range of between 22–63 patients/day What actions are we taking to improve? Resident Doctor rota redesign (from 5 Aug): Expected to improve weekday afternoon/evening cover, but reduced weekend resident doctor availability presents a risk to weekend performance. Ambulatory pathway trial: Progressing as planned, with a new Category 3/4 assessment process due to be tested from 17th August. Assessment process review / HCSE refresh: Improved understanding of demand versus capacity, but analysis suggests current staffing productivity alone is unlikely to meet demand. Clinician zoning allocation (PDSA 1): Improved ambulance triage flow and pace, but no measurable improvement in overall departmental performance. Redesign planned. Consultant-led referral model: No demonstrable benefit from routing all referrals through the consultant in charge. Continuing with a more targeted approach. Rapid Access Physician (RAP) trials: No improvement seen across four separate tests. Trial discontinued. What are the risks to delivery? Flow dependency risk: reduction depends on improving discharge and bed capacity (same constraint as ambulance handovers) including a reduction in the number of clinically optimised patients in acute/non-acute beds. Exit block risk: high numbers of patients awaiting admission → ED cannot handover, sustaining 12h waits Demand pressure risk: continued high attendances or admissions will offset gains | 
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships
Measure/ Trajectory Line | Ambition | Extraction Status | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Patients waiting in ED > 12 hours | 10% reduction in patients waiting >12 hours by end of March 2027 | Expected | 1350 | 1300 | 1190 | 1100 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997
 |  | Observed | 1319 | 1347 | 1366 | 1364 |  |  |  |  |  |  |  | 

## Slide 18
Enhanced Monitoring Target: 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months | July 2026 Performance | 100%
 | How are we doing? In July 2026, the Health Board reported 100% of open outpatient pathways were waiting less than 52 weeks. How do we compare across Wales? We are currently the only organisation that has maintained the 100% target for 52 weeks over the last year as seen in the comparative table below. What actions are we taking to improve? Reviewing clinic utilisation, slot allocation and template variation across specialties. Using learning from recent targeted improvement work to develop a more standardised approach to clinic template design across services. Strengthening validation and demand/capacity monitoring processes to support sustainable performance. Continuing regular operational oversight to identify risks to pathway waits at the earliest opportunity. What are the risks to delivery? The principal operational concerns are now focused on Gastroenterology, Endoscopy funding, Plastics administrative capacity, Orthodontic August capacity and emerging ENT/Vascular pressures for late summer. Workforce availability and unplanned reductions in clinical capacity. Increasing referral demand | 
Level 4 – Planned Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships

## Slide 19
Enhanced Monitoring Target: Continuous improvement towards 75% of all open outpatient pathways waiting less than 26 weeks | July 2026 Performance | 89.41%
 | How are we doing? In July 2026, the Health Board reported 89.41% of open outpatient pathways were waiting less than 26 weeks. What actions are we taking to improve? Continuing focused work to reduce longer waits through demand and capacity oversight. Reviewing outpatient clinic utilisation and template variation across specialties to support improved access and consistency. Using learning from recent improvement initiatives to support a standardised approach to clinic template configuration across services. Strengthening validation and pathway monitoring processes to support sustainable recovery performance. What are the risks to delivery? Outpatient demand exceeds activity volumes; sustainability is dependent upon successful delivery of the outpatient transformation programme. There will be a re-alignment of capacity towards urgent cancer referrals Workforce availability and unplanned reductions in clinical capacity. Increasing referral demand | 
Level 4 - Planned Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships

## Slide 20
Enhanced Monitoring Target: Continuous improvement towards 80% of all open pathways waiting less than 36 weeks | July 2026 Performance | 77.30%
 | How are we doing? In July2026, the Health Board reported 77.30% of open pathways were waiting less than 36 weeks. How do we compare across Wales? The Health Board continues to demonstrate sustained improvement in the percentage of patients waiting less than 36 weeks for treatment and is performing close to the enhanced monitoring target trajectory when compared with the all-Wales position What actions are we taking to improve? Continuing targeted work with specialties to reduce longer waits and improve pathway flow. Reviewing clinic utilisation, scheduling practices and capacity variation across services. Maintaining demand and capacity oversight arrangements to support sustainable trajectory improvement. What are the risks to delivery? In order to deliver the 104-week access standard and reduce costs uniformly across the board, resources may need to be re-allocated from specialties with shorter waiting times to those with longer waits. This includes re-alignment of capacity towards patients requiring urgent cancer treatment Increasing referral demand and pressure on treatment capacity. Workforce availability and reduced resilience due to vacancies, sickness or annual leave. | 
Level 4 - Planned Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships

## Slide 21
Enhanced Monitoring Target: 68% R1 ophthalmology patient pathways to be waiting within or no longer than 25% of their target date for an outpatient appointment and maintained for 3 months | July 2026 Performance | 65.81%
 | How are we doing? In July the Health Board reported 65.81% of Ophthalmology patients were waiting within or no longer than 25% of their target date, this is a deterioration on the previous months performance. What actions are we taking to improve? The Health Board has dropped below the Welsh Government de-escalation criteria for the first time in almost two years. What are the risks to delivery? Workforce pressures, including consultant and non-medical workforce vacancies, sickness and reduced clinic availability. Competing operational pressures impacting the ability to release additional outpatient capacity. | 
Level 4 - Planned Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships
​ | May | June | July | Risks ​ | Solutions & Mitigations
Vitreoretinal​ | 61% | 76% | 84% | Limited regional VR workforce limiting clinic capacity. ​ | Optimising workforce utilisation​ Regional Consultant started working across SBU & HD – vital skill mix across teams, ensuring activity is delivered at the most appropriate level​
Cataract​ | 46% | 58% | 61% | Core Pre-Assessment capacity does not meet current demand. | Maintaining operational grip​ Weekly review of performance, clinic utilisation, and recovery trajectories at specialty level​ Clear ownership of delivery against improvement actions​
Cornea​ | 47% | 48% | 47% | Backlogs with both news and follow-ups. Only 1 Cornea Consultant within the department. ​ | Targeting backlog reduction​ Systematic validation of long waits and risk stratification to prioritise patients appropriately​ Use focused additional capacity (e.g. super clinics) for paediatric areas​
Orthoptics​ | 86% | 94% | 94% | Workforce gaps in clinical and admin staff ​ | Fully established Clinical staff ​ Full training underway for new Orthoptists – significant improvement already established ​
Paediatrics ​ | 53% | 50% | 42% | R1 backlog mainly consists of new referrals.​ 1 Consultant vacancy ​ | Targeting backlog reduction​ Systematic validation of long waits and risk stratification to prioritise patients appropriately​ Use focused additional capacity (e.g. super clinics) for paediatric areas​
Diabetic Retinopathy ​ | 67% | 64% | 63% | R1 backlog consists mainly of follow up patients. ​ 1 Consultant vacancy | Improving clinic productivity to ensure follow ups are managed​ Optimise clinic templates, reduce unused slots and introduce overbooking where appropriate​ Increase use of technician-led and diagnostic clinics to release consultant capacity​ Utilising 'either or' slots to book to demand of news or FUPs ​
Glaucoma ​ | 70% | 72% | 75% | 2 Consultant vacancies since June 2025. ​ Considerable risk – on service Risk Register since June 2025. ​ | Maintaining operational grip​ Weekly review of performance, clinic utilisation, and recovery trajectories at specialty level​ Clear ownership of delivery against improvement actions​ Two consultants appointed to due to start across the summer. Improvement in performance is anticipated from August onwards once clinics are fully established. ​

## Slide 22
Enhanced Monitoring Target: 12% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2024 baseline.) | July 2026 Performance | 37.36% (above the baseline)
 | How are we doing? In July 2026, the Health Board reported 37.36% performance against the enhanced monitoring trajectory for follow-up waits. Although some improvement work has been undertaken, performance remains below the required target and follow-up pressures continue across a number of specialties. What actions are we taking to improve? Targeted validation work has taken place in both Gynae and Neurology throughout June which has seen noticeable reductions in those waiting for a follow-up Continuing targeted validation and review of follow-up waiting lists to ensure clinical prioritisation and pathway accuracy. A clinical review of the HSBUK outcomes has been undertaken, which identified some inappropriate listing to follow-up which has since been addressed. Implementing recommendations arising from GIRFT/CIN improvement work to reduce unwarranted variation in follow-up management practices. Reviewing clinic utilisation, follow-up scheduling and capacity variation across specialties. What are the risks to delivery? Workforce pressures, including vacancies, sickness and reduced clinic availability. Competing operational pressures impacting the ability to release additional outpatient capacity. | 
Level 4 - Planned Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships

## Slide 23
Enhanced Monitoring Target: 85% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months | July 2026 Performance | 70.55%
Level 4 - Planned Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships
Enhanced Monitoring Target: 85% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 month | July 2026 Performance | 52%
Enhanced Monitoring Target: 85% of patients waiting for a NOUS and non cardiac MRI to be waiting less than 8 weeks and maintained for 3 months. | July 2026 Performance | 70.77%
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships
How are we doing?
In July 2026, the organisation reported:
4,620 patients were waiting greater than 8 weeks for a reportable diagnostic test, a reduction of 624 from the June position
An improvement in performance against the percentage of patients waiting less than 8 weeks for a diagnostic test, with the percentage increasing to 70.55% compared to 68.02% in June 2026.
878 patients waiting over 8 weeks for a diagnostic endoscopy, which is a minor reduction on the number of patients waiting over 8 weeks which was recorded in June 2026.
2,203 patients waiting over 8 weeks for NOUS and non-cardiac MRI, which is a reduction of 67 patients from the figures reported in June 2026.

## Slide 24
Enhanced Monitoring Target: 85% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months | June 2026 Performance | 70.55%
Level 4 - Planned Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships
Enhanced Monitoring Target: 85% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 month | June 2026 Performance | 52%
Enhanced Monitoring Target: 85% of patients waiting for a NOUS and non cardiac MRI to be waiting less than 8 weeks and maintained for 3 months. | June 2026 Performance | 70.77%
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships
How do we compare the rest of Wales
What actions are we taking to improve?
Interim diagnostics plan submitted to Welsh Government with trajectories. Trajectories to be updated as timing and quantum of resources are known.
Regional solutions being developed – sustainability approach
MRI, Endoscopy and Dexa remain priority recovery areas
Costed recovery actions developed pending funding decisions
Reallocating funding to highest need modalities.
NOUS overtime + insourcing; Performance & Improvement referral guidelines being followed and targeting a 15% increase in productivity
Mobile MRI will be running 7 days/week, plus Saturday reporting and extended gantry hours.
CT scanners will be running 7 days/week for at up to 12 hours/day.
Endoscopy insourcing, Waiting List Initiatives, new appointment and additional Bowel Screening Wales accreditation. P&I Validation Guidelines
Neurophysiology: Increasingly moving to Physiology provided service, with minimal medical resource available
Established Diagnostics Board
What are the risks to delivery?
Resource for elements of the diagnostic programme (MRI, Endoscopy, Neurophsiology, Dexa) are yet to confirmed but are referenced in plan.
Workforce market very tight, with number of staff potentially joining agencies in near future and 2 year training window
Sonography dependent upon returns from mat leave
NP – shortage of skilled workforce, unstructured programme for developing HSSTs in Wales (Physiologists at doctorate level who can manage own casemix)

## Slide 25
Enhanced Monitoring Target: 90% of patients waiting for therapies to be waiting less than 14 weeks and maintained for 3 months | July 2026 Performance | 100%
 | How are we doing? Therapies services remain fully compliant with the escalation target, with sustained 100% delivery since July 2025. Performance is closely monitored, and assurance processes are firmly embedded to maintain this position. How do we compare across Wales? All adult and children/young people therapy services in SBUHB have consistently met the escalation standard and demonstrate a stable position relative to peers. What actions are we taking to improve? We continue to maintain robust capacity and demand management alongside effective job planning, refining these arrangements to ensure alignment with activity. Currently have bid for planned care additional funding for the physiotherapy service, due to the increased risk of breaching as a result of increased outpatient and diagnostic activity. In parallel, we are improving access routes and pathways to better empower patients, support self-management where appropriate, provide advice to stakeholders (e.g. schools), and optimise use of available capacity What are the risks to delivery? The principal risk to sustained delivery is any reduction in available capacity against a backdrop of sustained or increasing demand. There is also a need to manage clinical risk across the pathway, for example follow-up appointments. These risks are being actively managed through workforce planning, easy and early access and advice, prioritisation, and continued validation and oversight of demand trends. | 
Level 4 - Planned Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships

## Slide 26
Enhanced Monitoring Target: 80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral | July 2026 Performance | 85%
Enhanced Monitoring Target: 70% of therapeutic interventions started within 28 days following an assessment by LPMHS | July 2026 Performance | 85%
Enhanced Monitoring Target: 85% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan | July 2026 Performance | 95%
 | How are we doing? CAMHS has met de-escalation criteria for several months this year, which reflects positively on our current performance. Our team’s efforts have been instrumental in achieving and maintaining these standards. However, Part 1A returned to compliance for July (85%), having fallen in June due to administrative capacity including high levels of sickness. The 1B target for CAMHS remains in national target for delivery of 80% (85% for July) as well as the Enhanced Monitoring target of 70%. What actions are we taking to improve? To sustain this level of performance, the service are focusing on several actions: Actively monitoring key indicators, regularly reviewing processes, and providing ongoing training and support for our staff. Reinforcement of Managing attendance at work policy when staff are hitting the relevant concern points. Staffing levels are being reviewed and additional clinical capacity has been sought and secured to make delivery of targets sustainable for the future. Engaging with stakeholders to identify further opportunities for improvement and ensuring early intervention where needed What are the risks to delivery? There are some risks to delivery that we need to be mindful of. These include staffing challenges, increasing demand for services, and potential changes in funding long term. The service is working proactively to mitigate these risks. | 
Level 3 – CAMHS
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships

## Slide 27
Enhanced Monitoring Target: 80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral | July 2026 Performance | 85%
Enhanced Monitoring Target: 70% of therapeutic interventions started within 28 days following an assessment by LPMHS | July 2026 Performance | 85%
Enhanced Monitoring Target: 85% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan | July 2026 Performance | 95%
Level 3 – CAMHS
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships
How do we compare across Wales?
Our performance is broadly comparable with other health boards in Wales across all areas. Nonetheless, there remains scope for further enhancement, particularly in domains where national targets are only just being achieved. Ongoing internal scrutiny is maintained to ensure that performance standards continue to be raised wherever possible.

## Slide 28
Targeted Intervention (Level 3) – Mental Health
De-escalation Criteria | Actions – Updated July 2026 | RAG Status
Immediate Concerns – Three out of six immediate concern actions have been achieved by the service. The service consider there to be sufficient risk mitigations in place for two out of the three unachieved actions. | In July, Capital Planning procured a new personal attack alarm system for roll out across Caswell Clinic (120k). An installation contractor has also been secured, and costs are being finalised prior to commencing installation, which will take approximately 10 months. Security Framework Document, designed to ensure that all internal security procedures are conducted in a manner that supports maintenance of security whilst supporting therapeutic care, is listed for ratification at Policy Review Group on 27th July. Capital work to clear the secure garden area of environmental risks, completed on the 18th June. Internal courtyards will also be subject to the same work by an external contractor. Risk assessments (including mitigations) are in place for all patients who continue to access courtyards. Estates (SBUHB) continue to lead on the procurement and installation of wall mounted boilers (with controllable water temperature) across wards in Caswell Clinic. Awaiting costs from a contractor to install the products. Priority Actions for August 2026 Estates (CTUHB) to complete tiling of staff changing rooms in Caswell Clinic (tiling). Completion of this work is required prior to procurement and installation of new staff lockers to strengthen the services governance of prohibited items entering clinical areas. This is the only action without sufficient risk mitigation at present. | 
Wider De-escalation Measures – Fourteen actions in total with nine complete. | All actions across the following domains have been achieved during July: 1. Medication Management 2. Section 17 Leave documentation 3. Restrictive Interventions 4. Environment 5. Staffing Priority Actions for August 2026 Complete audits of CTPs and Care Plans to ensure all plans address mental and physical health needs of the patients. Any deficits to be resolved in-month to close this action. Increase risk assessment compliance for WARRN (100%) and HCR-20 (80%). Improvement plan developed by Directorate Manager and Consultant Psychologist. | 
Updates against the de-escalation criteria outlined by Welsh Government can be found below;

## Slide 29
Enhanced Monitoring Target: C-Diff: reduce the number of hospital onset infections by 40% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 10 cases to no more than 6 per month | July 2026 Performance | 12 cases
 | How are we doing? There were 12 cases of C.difficile reported as hospital onset in July 2026 SBUHB continues to have the highest incidence in Wales. What actions are we taking to improve? Increased executive oversight of service group HCAI performance and improvement plans. Autumn Health Board C. difficile Summit – review principal risks, existing strategies, refocus priorities and accountabilities for Q3 & 4. What are the risks to delivery? Increased infection risk to service users: over crowding, bed spacing, single room availability, ratio of toilets: service users, lack of ventilation, patient acuity, co-morbidities, older inpatient populations, increasing number of clinically optimised service users. Risks impacting of cleaning provision: over occupancy, reduced bed spacing, cleaning staff retention and recruitment, funding, lack of decant facility, ageing estate. Lack of mechanical ventilation in majority of inpatient areas increases risk of transmission of infections transmitted through the air. | 
Level 4 - Planned Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships
Notes: Update chart

## Slide 30
Enhanced Monitoring Target: Staph aureus: reduce the number of hospital onset infections by 25% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 4 cases to no more than 3 per month | July 2026 Performance | 6 cases
 | How are we doing? July 2026, 6 cases. Previous month – 3 cases What actions are we taking to improve? Focus on asepsis, audits on invasive device presence and Chlorhexidine impregnated wash cloth use. Executive team oversight with the Medical Director meeting regularly with the Service Group Directors. Gold High incidence meetings continue to take place. What are the risks to delivery? Adherence with ANTT, invasive device presence and monitoring, service user acceptance of skin decolonisation wipes - Refresh ANTT training package and drive with assessors to increase competency assessment Inability to sustain the current cleaning hours (2009 minimum standards) due to ongoing recruitment and retention of staff. This would be further compounded when considering the additional hours required to meet the 2025 NHS Wales Standards of Healthcare Cleanliness, which have been introduced without additional national funding. | 
Level 4 - Planned Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships
Notes: Update chart

## Slide 31
Enhanced Monitoring Target: E-coli: reduce the number of hospital onset infections by 20% and maintain for 3 months (from a baseline of the average number of · cases in quarter 3 of 5 cases to no more than 4 per month) | July 2026 Performance | 4 cases
 | How are we doing? July 2026 – 4 Hospital Onset cases June 2026 – 8 Hospital Onset cases What actions are we taking to improve? Actions to improve quality of urine sampling, appropriate diagnosis and focus on reducing unnecessary invasive device presence. Care home work to reduce urinary tracts infections. MDT case reviews for each toxin positive cases reviews are taking place within in each SG to identify themes, share learning and identify potential QI projects. There is a review and gap analysis of the NHS Wales Standards for cleanliness 2025 taking place. Trial of new cleaning systems (microfibre). Additional UV_C cleaning equipment purchased. What are the risks to delivery? Increased acuity, comorbidities and age of inpatient population. Increasing numbers of clinically optimised patients. Inadequate ratio of toilets to inpatient population. Inadequate numbers of available single rooms to meet demands for isolation, thereby increasing risks of infection exposure to higher numbers of patients. | 
Level 4 - Planned Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships
Notes: Update chart

## Slide 32
Enhanced Monitoring Target: Klebsiella: reduce the number of hospital onset infections by 10% and maintain for 3 months based on 2017/18 figures (baseline –54 cases in 2017/18, reduce to average of at most 4 per month) | July 2026 Performance | 4 cases
 | How are we doing? July 2026 – 4 Hospital Onset Cases June 2026 – 6 Hospital Onset Cases What actions are we taking to improve? Actions to improve quality of urine sampling, appropriate diagnosis and focus on reducing unnecessary invasive device presence. Undertaking risk-based impact assessment of new NHS Wales Standards for Healthcare Cleanliness, to identify quality and financial impact of moving towards implementation. Invasive device audits are being undertaken in the Audit Management and tracking system (AMaT). What are the risks to delivery? The increasing incidence of hepatobiliary disease in the population of Wales, Klebsiella spp. bacteraemia are often associated with hepatobiliary source. Target time for ambulance release impact’s ability to undertake effective cleaning, not only in admission areas, but on the wards that patients are subsequently transferred to. Cleaning provision risks: over-occupancy, recruitment/retention, funding, no decant facility and ageing estate. | 
Level 4 - Planned Care Performance
Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships
Notes: Update chart

## Slide 33
Targeted Intervention (Level 4) – Maternity & Neonates
Criteria to Achieve | Current Performance
Ensure that the recommendations and actions in the Independent Review are progressed in line with agreed timescales and report progress to Welsh Government monthly, highlighting risks to delivery. | Perinatal improvement programme has been established Dec 2025 Exec led workstreams are underway Dec 2025 Quarterly Perinatal updates to Board ongoing Final Perinatal Improvement Programme agreed by Independent Oversight Panel and Health Board July 2026; 70% of recommendations delivered to date.
Ensure that the agreed actions in the family-led review into Swansea Bay maternity services are progressed in line with agreed timescales and report progress to Welsh Government monthly, highlighting risks to delivery. | The agreed actions of the family led review have been integrated to the Independent Review improvement plan – Jan 2026. 70% of recommendations delivered. Reporting to Welsh Government on quarterly basis, additional independent assessment reported by Independent Observer to Cabinet Secretary on quarterly basis.
Receive a positive assessment from the Welsh Government independent observer on progress against the agreed maternity and neonatal action plan. | Complete Positive assessment received on 31 March 2026, full response to be brought to Health Board meeting in May 2026.
Agree a set of sustainability conditions with Welsh Government that can be used to track improvements. | "Scorecard" in development mapping ten thematic recommendations with key metrics to track improvements – will be presented to Board in September 2026 Have developed Perinatal reporting to Board through Quality & Safety committee Jul 2025 Routinely reviewing staff retention and well-being plan – revised plan signed off Jan 2026 Pulse surveys underway – quarterly Robust Governance processes in place – Dec 2025
Evidence effective Board scrutiny and oversight of maternity and neonatal services. | Complete Governance structure in place – July 2025; updated Dec 2025 Although complete, we will continue to review and benchmark against other HBs on cyclical basis to seek out best practice
Embed the maternity and neo-natal dashboard across the service to demonstrate that data is driving real decision making. | Complete
Regularly review the risk register, appropriate risk management, and mitigations. | Complete Embedded as business-as-usual The risk register is reviewed at monthly Perinatal committee and flagged at Quality & Safety Committee and through to the Board Development of an organisation-wide Learning and Improvement Group (due to launch Q3 26/27 will further embed thematic learning from LRI/NRIs, complaints and concerns processes, Listening to People, and other feedback channels.
Regularly review against agreed outcomes to demonstrate that there is continued embedding of the LRI/NRIs, complaints and concerns process within quality governance, ensuring responses in a timely manner. | Ongoing Monthly reporting through Perinatal Committee and Board Ward to Board reporting Development of an organisation-wide Learning and Improvement Group (due to launch Q3 26/27 will further embed thematic learning from LRI/NRIs, complaints and concerns processes, Listening to People, and other feedback channels.
Evidence a joint and effective PMRT meetings across the service with engagement of affected families. | Ongoing Part of the improvement plan and reported through Perinatal committee Evidence of ongoing family engagement throughout investigations, including contact, communication, and feedback; 100% of families are engaged in investigations which trigger duty of candour.

## Slide 34
Criteria to Achieve | Current Performance
Maintain the required staffing establishment at appropriate numbers and grades. | Ongoing Reported monthly through Perinatal committee, into Quality & Safety committee and into Board. Key element of performance report
Achieve and maintain training compliance rates for all staff in maternity and neonatal services. | Complete Reviewed at monthly performance and perinatal committee – key element of the report
Demonstrate required corrective action against Patient Reported Outcome Measures and Patient Reported Experience Measures data for maternity and neonatal services. | Ongoing All reported monthly through Perinatal committee, into Quality & Safety committee and into Board. Additional requirements included in perinatal improvement plan
Evidence how women and family feedback shapes service design within the health board. | Ongoing – Perinatal Improvement Plan outlines Engagement strategy as follows: Service specific engagement undertaken by the service itself, mostly using its own contact with service users; ongoing rolling programme with reporting through Perinatal Committee. Service specific engagement undertaken by corporate teams, particularly DICE “Always on” engagement at a pan-Health Board level which sees generic engagement activity offering up insights and feedback relevant to the maternity and neonatal services. Ongoing Mapping of groups across the Swansea and Neath Port Talbot areas – completed April 2026 Development of a Network of Sounding Boards, including a Women's sounding board that can focus on maternal experiences, as part of the Women’s Health Plan – completed April 2026
Provide assurance that clinical leadership is consistent, visible, effective, and that leadership development support is in place. | Complete Senior clinical staff present as required by BAPM guidance; underpinned by audit cycle and key indicators which include care planning in decision making. Reported to Perinatal Committee on monthly basis, as follows: Neonatal senior clinician presence in complicated deliveries inc presence at deliveries < 28 weeks gestation compliance against British Association of Perinatal Medicine (BAPM) guidelines Senior obstetrics presence at complicated Caesarean Section or rotational forceps deliveries as per Royal College of Obstetrician and Gynaecologists guidelines. All Wales Midwifery Care Guidelines in Midwifery-led Birth settings. Multidisciplinary Team Development Programme rooted in compassionate leadership, culture and behaviours to be delivered between Feb and April 2026 - Focus on embedding the learning from the leadership development programme and consideration of next phases of cascade following the evaluation.
Provide assurance and evidence of an improving culture through appropriate surveys, and/or qualitative assessment for maternity and neo-natal services. | Ongoing Reported through monthly Perinatal committee and includes: Workforce heat maps that cover staff feedback Patient feedback Guardian service Patient voices forum Pulse surveys Feedback from all visitors reporting positive change Implementation of Rate My Shift for a six-month pilot in collaboration with HEIW - pilot approved 06/26 with plan of Implementation in 09/26
Targeted Intervention (Level 4) – Maternity & Neonates

## Slide 35
TI Target: Continuous reduction in delayed pathways of care of 5% for three consecutive months and then maintained for three months (based on Oct-Dec 23 baseline) | July 2026 Performance | 159
Breakthrough Objective: The number of Clinically Optimised patients should be <100 at any one time |  | 
 | How are we doing? In July 2026, the organisation reported that there were 159 patients classified as being clinically optimised which is an improvement on the 173 reported in June 2026. What actions are we taking to improve? Continue to Strengthen D2RA in line with outcomes requested by the Older Peoples Programme Board, this includes delivering the implementation plan for Pathway 1 over the next 8 weeks which has been endorsed by ROAG. In addition, the finalisation of the P2 Workshop and starting the workshop to map and agree the processes and escalations for Pathway 3. Optimal hospital flow is being rolled out. All pilot wards delivering 2 early morning discharges Alignment work with UEC 3 Pillar Programme and Older Peoples Programme is underway. Assessment capacity is being ringfenced to create space for assessment Improved alignment via Regional Partnership Board on delivery of our COP reduction programme What are the risks to delivery? Understanding of Pathway 1 capacity and demand – Regional Partnership Board/Health Board work stream in progress Workforce reallocation risk: shifting staff/funding (primary care → UEC) may not be achieved or sustained Flow dependency risk: plan requires sustained improvements in discharge and bed turnover, including flow of the high numbers of clinically optimised patients | 
Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation

## Slide 36
Breakthrough Objective: Increase in the take up of the NHS App by 25% (from a March 2026 baseline) | July 2026 Performance | 101,322 registered users
 | How are we doing? As of the end of July 2026, there were 101,322 registered users of the NHS Wales App within Swansea Bay. Registrations are currently increasing at approximately 3,000 users per month. How do we compare across Wales? Swansea Bay’s uptake is around the national average across NHS Wales organisations, currently at 25% adoption rate, an increase of 1.5% from May Comparative adoption rates: BCU, AB, CAV: ~24% SBU: ~23.5% CTM: ~23% HDD and Powys: ~21% What actions are we taking to improve? DHCW has been asked to provide clarification on whether individual Health Boards can undertake local promotion of the NHS Wales App, given the absence of a national awareness campaign. A response is awaited and expected by mid July. We have continued to promote access to the Swansea Bay Patient Portal (SBPP) via the NHS Wales App through existing communications channels. We are exploring opportunities to work with Primary Care colleagues and GP practices to increase awareness of the NHS Wales App and encourage patient registration, subject to national guidance and approval. Communications continue to highlight the benefits of accessing SBPP through the NHS Wales App to increase awareness and uptake across Swansea Bay. What are the risks to delivery? Staff engagement across primary, secondary, and community care remains a key dependency. Increasing uptake will require consistent reinforcement at all patient touchpoints. The absence of a coordinated national awareness campaign and the lack of clarity regarding local promotional activity may limit public awareness and delay opportunities to increase uptake. | 
Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation

## Slide 37
Breakthrough Objective: Improvement in staff health and wellbeing by 1% to reach a target of 6.04% in March 2027 | July 2026 Performance | 8.22%
 | How are we doing? The In-month sickness absence was 8.22% July. Which is an increase on 7.37% reported in June 2026. The rolling sickness absence figure for July is 7.47% which is an increase compared to June, where 7.41% was reported. What actions are we taking to improve? Strengthen data, governance, and early intervention to improve sickness absence management Maintain sickness reporting through the monthly Workforce Steering Group, feeding into R&S Board Embed timely sickness reviews, return-to-work discussions, and access to wellbeing support Adopt a holistic approach to understand cultural and environmental factors influencing absence Target interventions in high-risk areas and promote a proactive, preventative approach to workforce wellbeing What are the risks to delivery? Some of the risks include the cultural challenges, organisational change and capacity. Currently, reporting is retrospective and limited to a monthly view, which restricts the ability to intervene early and effectively manage sickness absence. | 
The health board is a great place to work where all staff feel valued and work together towards a common goal

## Slide 38
Breakthrough Objective: Improvement in staff health and wellbeing by 1% to reach a target of 6.04% in March 2027 | July 2026 Performance | 8.22%
The health board is a great place to work where all staff feel valued and work together towards a common goal

## Slide 39
Breakthrough Objective: The health board is a resilient, sustainable and responsible organisation | July 2026 Performance | £3.7m Savings delivered (against the month 3 target of £5.42m)
Month 4 Performance: | Overall Position The Health Board’s actual performance against the planned deficit shows that at the end of Month 4 the reported deficit is £6.0m, which is £0.4m below the planned deficit. | 
Use every NHS £ wisely
Reported Month 4 deficit
£0.4m worse than the planned monthly deficit.
£6.0m
2026/27 planned deficit
£76.6m
Plan not approved/accepted by Welsh Government; revised submission made 29 May 2026.
PSPP performance
97.01%
Above the reported >95% target for public sector payment policy.

## Slide 40
Breakthrough Objective: The health board is a resilient, sustainable and responsible organisation | July 2026 Performance | £3.7m Savings delivered (against the month 3 target of £5.42m)
Main drivers in Month 4: The in-month delivery in Month 4, was £3.8m against a target of £5.4m and remains the key driver of the Health Board overspend. Income remains high for Month 04, Higher level of recharging between other Health Boards for blood products along with other one-off benefits in month including within nuclear medicine and radiology. The actual variable pay spend at Month 04 was £4.7m, Bank and Agency continue to be the key driver for this continued high spend | Other Spend Indicators The in-month increase in non-pay relates to clinical consumable costs driven by activity in specialist services and Theatres totalling £1.6m. It should be noted that £0.6m of this is offset by JCC income. In Month 4 CHC was overspent by £0.6m, this is a slight increase on the Month 3 position despite a reduction in case numbers within PCT. | 
Use every NHS £ wisely

## Slide 41
Section 3:
Summary of the performance against the NHS Wales Performance Framework Measures 2026-27

## Slide 42
Quadruple Aim 1: People in Wales have improved health and well-being with better prevention and self-management |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Percentage of adult smokers who make a quit attempt via smoking cessation services | 5% Target (2025-26) |  | 4.75% | Q4 2025/26 | Quarterly
Percentage of adult smokers who make a quit attempt via smoking cessation services & co-validated at 4 weeks | 40% |  | 45.12% | Q4 2025/26 | Quarterly
Percentage of children who are up to date with the scheduled vaccinations by age 5 (‘4 in 1’ preschool booster, the Hib/MenC booster and the second MMR dose) | 95% |  | 90.7% | March 2026 | Quarterly
Percentage of children receiving the Human Papillomavirus (HPV) vaccination by the age of 15 | 95% |  | 86.5% | March 2026 | Quarterly
NHS Wales Performance Framework Measures 2026-27

## Slide 43
Quadruple Aim 1: People in Wales have improved health and well-being with better prevention and self-management |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Percentage uptake of the influenza vaccination amongst adults aged 65 years and over | 75% |  | 68.9% | 2025/26 | Monthly
Percentage uptake of the Respiratory Syncytial Virus (RSV) for those turning 75 years old | 70% |  | 48.0% | June 2026 | Monthly
Percentage of Adult population receiving NHS Dental Care over a 24-month period | Improvement compared to the same period in the previous year |  | 42.4% | Q3 2025/26 | Quarterly
Percentage of Children population receiving NHS Dental Care over a 12-month period | Improvement compared to the same period in the previous year |  | 50.8% | Q3 2025/26 | Quarterly
NHS Wales Performance Framework Measures 2026-27

## Slide 44
Quadruple Aim 2: People in Wales have better quality and more accessible health and social care services, enabled by digital and supported by engagement. |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Percentage of Local Primary Mental Health Support Service (LPMHSS) assessments undertaken within (up to and including) 28 days from the date of receipt of referral for adults aged 18 years and over | 80% |  | 94% | July 2026 | Monthly
Percentage of therapeutic interventions started within (up to and including) 28 days following an assessment by Local Primary Mental Health Support Service (LPMHSS) for adults aged 18 years and over | 80% |  | 80% | July 2026 | Monthly
Percentage of children and young people waiting less than 26 weeks to start an ADHD or ASD neurodevelopment assessment | 80% |  | 41.91% | July 2026 | Monthly
Percentage of patients waiting less than 26 weeks to start a psychological therapy in Specialist Adult Mental Health | 80% |  | 37.45% | July 2026 | Monthly
NHS Wales Performance Framework Measures 2026-27

## Slide 45
Quadruple Aim 2: People in Wales have better quality and more accessible health and social care services, enabled by digital and supported by engagement. |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Percentage of people to have a heartbeat restored after a period of cardiac arrest which is subsequently retained until arrival at hospital (Return Of Spontaneous Circulation) | End of quarter on end quarter improvement |  | 22.2% | June 2026 | Monthly
Median emergency ambulance response time to purple: arrest category calls | 6-8 Minutes |  | 6.49 | June 2026 | Monthly
Median emergency ambulance response time to red: emergency category calls | 6-8 Minutes |  | 9.16 | June 2026 | Monthly
Number of ambulance patient handovers over 45 minutes | 0 |  | 438 | July 2026 | Monthly
NHS Wales Performance Framework Measures 2026-27

## Slide 46
Quadruple Aim 2: People in Wales have better quality and more accessible health and social care services, enabled by digital and supported by engagement. |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Percentage of ambulance patient handovers within 15 minutes | 80% |  | 32.90% | July 2026 | Monthly
Percentage of patients who spend less than 4 hours in all major and minor emergency care (i.e. A&E) facilities from arrival until admission, transfer or discharge | 95% |  | 66.70% | July 2026 | Monthly
Number of adults waiting more than 14 weeks for all audiology pathways (to include new and existing pathways for hearing aids, tinnitus and balance) | 0 |  | 27 | July 2026 | Monthly
Number of children waiting more than 6 weeks for all audiology pathways (to include new assessment and intervention pathways) | 0 |  | 182 | July 2026 | Monthly
NHS Wales Performance Framework Measures 2026-27

## Slide 47
Quadruple Aim 3: The health and social care workforce in Wales is motivated and sustainable |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Turnover rate of nurse, midwifery, medical and dental registered staff leaving NHS Wales | Rolling 12- month reduction |  | 5.8% | April 2026 | Monthly
Agency spend (£000s) | 30% reduction from 2025-26 outturn |  | £982 | July 2026 | Monthly
NHS Wales Performance Framework Measures 2026-27

## Slide 48
Quadruple Aim 4: Wales has a higher value health and social care system that has demonstrated rapid improvement and innovation, enabled by data and focused on outcomes. |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Percentage of episodes clinically coded within one reporting month post episode discharge end date | 95% |  | 74% | June 2026 | Monthly
Nationally reportable incidents open over 12 months | 0 |  | 0 | July 2026 | Monthly
Gabapentin and pregabalin DDDs per 1,000 patients | 10% reduction compared to same period in the previous year |  | 1397.8 | Q4 2025/26 | Quarterly
Average quantity per item prescribed from start period for the reference basket of medicines | 35 |  | 30.91 | May 2026 | Monthly
NHS Wales Performance Framework Measures 2026-27

## Slide 49
Quadruple Aim 4: Wales has a higher value health and social care system that has demonstrated rapid improvement and innovation, enabled by data and focused on outcomes. |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Number of low Global Warming Potential (GWP) inhalers as a percentage of all inhalers prescribed | 60.6% |  | 45.6% | Q4 2025/26 | Quarterly
Number of never events | 0 |  | 0 | July 2026 | Monthly
Overall HB patient experience score | 85% |  | 91% | July 2026 | Monthly
NHS Wales Performance Framework Measures 2026-27

## Slide 50
Stroke |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
% of patients Thrombolysed | 20% |  | 10.5% | April 2026 | Monthly
% door to needle within 30 minutes | 95% |  | 0% | April 2026 | Monthly
% received mechanical thrombectomy | 10% |  | 0% | April 2026 | Monthly
% received CT scan within 20 minutes | 40% |  | 5.3% | April 2026 | Monthly
SBUHB Local Watch Metrics

## Slide 51
Stroke |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
% admission within 4 hours | 95% |  | 35.1% | April 2026 | Monthly
% received swallow screening within 4 hours | 95% |  | 62.5% | April 2026 | Monthly
% assessed by a Stroke Consultant within 14 hours | 95% |  | 47.4% | April 2026 | Monthly
% received occupational therapy within 24 hours | 95% |  | 76.5% | April 2026 | Monthly
SBUHB Local Watch Metrics

## Slide 52
Stroke |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
% received physiotherapy within 24 hours | 95% |  | 76.5% | April 2026 | Monthly
% received SALT within 72 hours | 95% |  | 95.5% | April 2026 | Monthly
SBUHB Local Watch Metrics

## Slide 53
Theatres |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Theatre Utilisation | >85% |  | 80% | July 2026 | Monthly
Late Starts > 15 mins | <20% |  | 26% | July 2026 | Monthly
Early Finishes > 60 mins | <10% |  | 28% | July 2026 | Monthly
% cancelled Operations on the day | 0% |  | 6% | July 2026 | Monthly
SBUHB Local Watch Metrics

## Slide 54
Fractured Neck of Femur (NOF) |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Prompt orthogeriatric assessment - by a senior geriatrician (ST3+) within 72 hours of presentation | 70.9% |  | 97.4% | June 2026 | Monthly
Prompt surgery - by the day following presentation with hip fracture | 52.0% |  | 35.45% | June 2026 | Monthly
NICE compliant surgery - consistent with the recommendations of NICE CG124 | 66.1% |  | 60.2% | June 2026 | Monthly
Prompt mobilisation after surgery - out of bed (standing or hoisted) by the day after operation | 74.2% |  | 84.9% | June 2026 | Monthly
SBUHB Local Watch Metrics

## Slide 55
Performance Measure | Target | Data | Latest Position |  | Frequency
Not delirious when tested - (<4 on 4AT test) when tested in the week after operation) | 58.6% |  | 73.0% | June 2026 | Monthly
Return to original residence - discharged back to original residence, or in that residence at 120-day follow-up | 72.2% |  | 76.0% | March 2026 | Monthly
30-day mortality - Case mix Adjusted | 5% |  | 4.4% | Q4 25-26 | Quarterly
Number of children (< 18 years) waiting more than 52 weeks for referral to treatment | 0 |  | 747 | July 2026 | Monthly
SBUHB Local Watch Metrics

## Slide 56
Primary Care |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Number of practices reporting escalation level 3 or above |  |  | 12 | July 2026 | Monthly
Sustainability Risk Score > 55 or > 80 |  |  | 10 | July 2026 | Monthly
Number of sustainability applications received |  |  | 0 | July 2026 | Monthly
GDS Number of courses of treatment |  |  | 15,893 | July 2026 | Monthly
SBUHB Local Watch Metrics

## Slide 57
Primary Care |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
GDS Number of unique patients seen |  |  | 16,896 | July 2026 | Monthly
Number of new patients treated at GDS practice |  |  | 1,504 | July 2026 | Monthly
Percentage of ACORNs completed |  |  | 77.20% | July 2026 | Monthly
Percentage of Fluoride varnish application in children |  |  | 81.40% | July 2026 | Monthly
SBUHB Local Watch Metrics

## Slide 58
Primary Care |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Number of patients receiving care from EHEW |  |  | 2,693 | July 2026 | Monthly
Number of NHS eye tests carried out |  |  | 8,247 | July 2026 | Monthly
Number of patients receiving Low Vision Care |  |  | 18 | July 2026 | Monthly
Number of practices (Pharmacy) reporting escalation Level 3 or above |  |  | 7 | July 2026 | Monthly
SBUHB Local Watch Metrics

## Slide 59
Primary Care |  |  |  |  | 
Performance Measure | Target | Data | Latest Position |  | Frequency
Number of Common Ailment Scheme consultations provided |  |  | 7,971 | July 2026 | Monthly
Number of Independent Prescriber Consultations |  |  | 2,474 | July 2026 | Monthly
Percentage of patients re-attending NHS primary dental care between 6-9 months |  |  | 13.56% | July 2026 | Monthly
SBUHB Local Watch Metrics