## Slide 1: Integrated Planning and Performance Review
Annual Plan 26/27 Quarter 1 Reporting
Meeting 23rd July 2026
Version updated post meeting and aligned with IPR

## Slide 2: RECAP ON PURPOSE Health Board Performance & Accountability Governance
    As set out in the Performance Accountability Framework (PAF), approved by Board May 2026, delivery of the Annual Plan 26/27 will be reported and monitored through:
    1. Quarterly Integrated Planning & Performance Reviews
    Half a day sessions with Execs reviewing System (i.e. Programme Board level) progress in UEC, Planned Care & Cancer, Primary Care & Community, Mental Health & Learning Disabilities, CHC and Complex Care, Babies/ CYP/ Womens, Population Health & Prevention. Additionally, Digital and Workforce Priorities will be reported as Enabling / Cross Cutting Systems.
    System Leads expected to provide:
          Strategic overview and delivery of System Programme Plans
          Risks to delivery and issues for escalation onward to Board.
    Summary of discussions & updates to be included in the IPR shared quarterly with PFC and Board.
The quarterly review meetings will provide the forum for identifying opportunities, and challenges, and consider how learning should shape our ongoing delivery.
These meetings will also help ensure a shared understanding of priorities, risks and expectations and a collective understanding of delivery across the R&S, Performance and BAU, and System Transformation priorities as set out in the Plan.
This meeting serves as the first quarter reporting on Annual Plan 26/27 Delivery
2. Service Group Monthly Performance Reviews
The monthly performance meetings will focus on operational delivery and delivery against national performance measures at individual Service Group level.
A subset of key performance and financial metrics will be reviewed and discussed in line with Service Group Operational Plans, with appropriate actions developed as a result.
This is not within the scope of this meeting.

## Slide 3: THE ASK
These slides will form the Q1 Data Pack which will be issued with IPPR papers for meeting on 23rd July.
Information has been extracted from the latest versions of System Programme Plans as shared with Planning, showing the agreed Plan Priorities (Schemes/ Projects), the Delivery Actions (Deliverables for 26/27) and their associated Outcomes and Milestones. Leads are asked to fully populate any missing information, as part of this request.
For their respective areas, System Leads are asked to complete the RAG status (see definitions below) at Q1 for all listed Priorities and Delivery Actions. These should be as reported through the relevant Programme Boards in the period:
  Outcomes (the measures / metrics demonstrating if the expected performance associated with the Delivery Action is On Track / Off Track)
  Milestones (what will be achieved by each quarter, demonstrating if delivery action is On Track / Off Track)
  RAG Status definitions:
ON TRACK – Action progressing as planned / to agreed timelines/ in line with expected performance
OFF TRACK – Action not progressing as planned / to agreed timelines/ in line with expected performance; however management of issues/ mitigating actions are in place
OFF TRACK – Action not progressing as planned / to agreed timelines/ in line with expected performance; there is significant issue(s) which require escalating
If reporting Off Track (Amber or Red), System Leads need to list the reasons why, the mitigating action being progress, and/or issues for escalating to Exec Board.
Performance Team will compile the summary Q1 reporting on Key System Performance Measures against the agreed trajectories, e.g. the Ministerial Delivery Expectations, TI/Escalation measures

## Slide 4: Q1 REPORTING TIMELINES
ACTION | DATE | WHO
Issue requests for Q1 updates on System Programme Plans (Q1 Progress updates on Delivery Actions Outcomes and Milestones) UEC – Ali Gallagher Planned Care and Cancer – Hannah Parsons Primary Care and Community System – Craige Wilson Mental Health and Learning Disabilities System – Dermot Nolan CHC and Complex Care – Hannah Roan Babies, Children and Womens – Ceri Gimblett Population Health and Prevention – Hugo Van Worden / Raj Krishnan Digital – Matt John Workforce – Tina Ricketts | 15th June 2026 | Planning
Deadline for Q1 System Programme Plan reporting to Planning | Deadline 3rd July 2026 | System Leads
Planning collate returns and share back with Leads to develop their Summary Slides on Q1 Look Back and Q2 Look Forward (Template will be shared) | 6th – 10th July 2026 | System Leads
Leads develop their Summary Slides on Q1 Look Back and Q2 Look Forward | Deadline 14th July 2026 | System Leads
Input Q1 performance data reporting including Ministerial Delivery Expectations, MAG Recommendations, Enabling Actions aligned to each System | By 14th July 2026 (note, data is not available until 10th working day of the month) | Performance
Circulate papers for Integrated Planning and Performance Reporting Meeting | 16th July 2026 | Planning
Q1 Integrated Planning and Performance Review Meeting | 23rd July 2026 | Planning to service meeting; System Leads to present updates from their areas
Draft Integrated Performance Report and cover paper for Board using information from IPPR meeting | 25th August – PFC (11th Aug. deadline) 25th September - Board | Performance supported by Planning

## Slide 5: URGENT AND EMERGENCY CARE OVERVIEW
Performance Outcomes | Confidence assessment
Ensure no ambulance patient handover waits over 45 minutes | 95% compliance from Sept
Ensure no patient spend spends 12 hours or more in all major and minor emergency care facilities from arrival until admission, transfer or discharge. | 10% reduction
Deliver a 12-month reduction trend in both the number of people who are delayed in hospital and the total days delayed for these patients, as measured by the Delayed Pathways of Care dashboard. | Trajectory to achieve 100 DPoC by end March 2027
Increase in capacity at the weekend of community nursing and specialist palliative care nursing to at least the required levels previously set for 2024/25 and greater where possible | Aligned to Community Services Review
Finance Impact | FYE £ savings | £9.613M
Key Schemes | 
CIP_05 | Bed Base Reconfiguration (also including Planned Care Elective Beds) Reduce cost through reduction of the core bed base and supported by enabling work: •Avoid admission for frail older people where safe •Pathway 1 - get patients home with support in 72 hrs • Pathway 3 - Cohort Care Home pathway patients for more streamlined assessment process. •IDH and optimal flow - Create discharge grip and reduce internal waits •SPOA - Reduce avoidable conveyancing and admission •Lower cost wards- Reduce cost of clinically optimised bed days.
UEC_B_01 | Community Redesign: Integrated models of Health and Social care aligned to Community by Design Community Nursing Review
UEC_B_02 | Community Based Falls Service Continue commissioned resource (St John providing first aider in vehicle for faller pick-up in the community) H45 Enabler: WAST Falls Service linked to SPOA
UEC_B_03 | Single Point of Access H45 Enabler: Implement SPOA model
UEC_B_04 | SDEC and Acute Front Door Frailty Service H45 Enabler: Protect frailty assessment
UEC_B_05 | Acute and Community Hospital ‘Back Door’ flow H45 Enabler: Discharge Support.
UEC_B_06 | Communities and Older People Strategy
UEC_C_01 | Improving Ambulance handover times – Implementation of Handover 45 (H45) and associated enablers H45 Enabler: Acute Medical Patient Flow improvements H45 Enabler: Criteria to Admit H45 Enabler: ED assessment and flow H45 Enabler: Flow
UEC_C_02 | Reducing Clinically Optimised Patients
UEC_C_032 | Maintaining Stroke/ SNAP targets
Risks | Mitigations
Reliance on major system change: success depends on full adoption of SPOA + push-flow model + Frailty Model Financial: no budget for SPOA: redesign of existing workforce Workforce reallocation risk: shifting staff/funding (primary care → UEC) may not be achieved or sustained Flow dependency risk: plan requires sustained improvements in discharge and bed turnover, including flow of the high numbers of clinically optimised patients | Plan prioritised to deliver the performance commitments we have set out: 0 ambulance handover waits over 45 minutes by September 2026; 12-hour ED waits to reduce by 10% in-year, whilst reducing COP patients by 112 and realising the associated financial benefit
Our programme aligns with National Six Goals policy to deliver a unified system that helps patients understand where and when to access the right support. We will do this through consistent and integrated delivery of the Six Goals (Three Pillars) for UEC, and strengthened joint planning and accountability with partners, to ensure the best possible outcomes, value and experience for patients and staff. See Annex 2a for full programme plan
43

## Slide 6: UEC System Summary
RAG | Green | Outcomes | Milestones | Amber | Outcomes | Milestones | Red | Outcomes | Milestones | Total | Outcomes | Milestones
 |  | 3 | 6 |  | 15 | 16 |  | 0 | 0 |  | 18 | 22
Achievements |  |  |  |  |  | Challenges |  |  |  |  |  | 
Handover 45 action plan developed and in process of implementation – this in conjunction with WAST Transfer of Contact First GP to SPOA to provide additional resource for anticipated increased call volumes Clinical Conversation before Conveyance (CCBC) trialled for care homes CCBC implemented for all ‘non-urgent’ calls to increase admission avoidance opportunities (requires outward referral pathways from SPOA) – to support H45 PDSA improvement activity at front door(s) – ED, AMU, OPAU Optimal Hospital Flow framework rolled out/ trialled with 3 wards – positive performance to date namely: (1) Weekend discharge rates increased from 12% to 27% on pilot wards. (2) Reduction in medically delayed patients. (3) Better use of Red-to-Green processes. (4) Improvements appearing sustained. |  |  |  |  |  | No confirmation of any improvement budget for UEC activity (any improvements reliant on no cost ‘sweating of existing assets’) Challenges re; capacity of outward referral pathways from SPOA back to the community No confirmation post-July 26 of existing improvement resource being in post to drive sustainable change (QI matron & Optimal Hospital Flow roles) Commissioned falls vehicle to end moving into Q2 (cessation of funding) Cessation of Frequent Attenders Service moving into 26/ 27 F/Y – no available resource to continue Reliance on major system change: success depends on full adoption of SPOA + push-flow model + Frailty Model Workforce reallocation risk: shifting staff/funding (primary care → UEC) may not be achieved or sustained Flow dependency risk: plan requires sustained improvements in discharge and bed turnover, including flow of the high numbers of clinically optimised patients Capacity mismatch: non-acute sites must absorb additional demand (accept overcapacity) Delivery timing risk: multiple enablers unlikely to be fully in place before July to start H45 trajectory Operational discipline risk: relies on consistent execution (quotas, ringfencing, SOP adherence) Interdependency risk: failure of any one element (SPOA, discharge, transfers) undermines whole plan Bottom line: delivery risk is high due to complexity, scale of change, and tight timeline |  |  |  |  |  | 

## Slide 7: UEC System Summary
Learnings from Q1 | Risks/ Issues | Mitigations
Successful delivery of UEC pathway/ system improvements dependent on whole system solutions i.e. sufficient back door discharges & flow, protecting of bedding of assessment spaces, alternatives to admission at an acute site in the community required Plan is to continue activity in line with agreed portfolio/ programme/ pillar structure under headings of: Pillar 1: Pre-hospital & community Pillar 2: Front door & first 72hrs Pillar 3: Ward based flow & discharge All areas within the portfolio could be amplified with sufficient resource | Reliance on major system change: success depends on full adoption of SPOA + push-flow model + Frailty Model Workforce reallocation risk: shifting staff/funding (primary care → UEC) may not be achieved or sustained Flow dependency risk: plan requires sustained improvements in discharge and bed turnover, including flow of the high numbers of clinically optimised patients Capacity mismatch: non-acute sites must absorb additional demand (accept overcapacity) Delivery timing risk: multiple enablers unlikely to be fully in place before July to start H45 trajectory Operational discipline risk: relies on consistent execution (quotas, ringfencing, SOP adherence) Interdependency risk: failure of any one element (SPOA, discharge, transfers) undermines whole plan Bottom line: delivery risk is high due to complexity, scale of change, and tight timelines | Whole system, multi organisation (health & social care) working with full and appropriate resource support to deliver
Q2 Priorities |  | 
Confirm available resource to deliver improvements with Executive colleagues Continue to deliver whole system actions as agreed in line with portfolio/ programme/ pillar structure under headings of: Pillar 1: Pre-hospital & community Pillar 2: Front door & first 72hrs Pillar 3: Ward based flow & discharge |  | 

## Slide 8: Urgent and Emergency Care System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
RECOVERY AND SUSTAINABILITY | Bed Base Reconfiguration – Also includes Planned Care Elective Beds | Reduce cost through reduction of the core bed base •Avoid admission for frail older people where safe •Pathway 1 - get patients home with support in 72 hrs • Pathway 3 - Cohort Care Home pathway patients for more streamlined assessment process. •IDH and optimal flow - Create discharge grip and reduce internal waits •SPOA - Reduce avoidable conveyancing and admission •Lower cost wards- Reduce cost of clinically optimised bed days. | Mar-27 | See R&S PID |  | Deliver 20 assessment / day , 50% community discharge ambition Demand baseline , 72 Hour standard Centralised hub , professional standards, breach escalation Pre conveyancing clinical conversation , alternative directory Cohort lower acuity delayed patients , revise skill mix |  | 4 hour community response, protected front door frailty capacity . Bridging care team capacity workforce and mobilisation plan Dedicated cohort ward, two week assessment standard , aligned nursing , therapy , lower acuity skill mix Red 2 Green, Board Round and EDD compliance Strengthened MDT telephony hub , 111 redication Governance , escalation and quality dashboard. | In development | In development

## Slide 9: Urgent and Emergency Care System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Community Redesign: •Regional Partnership | Develop new model of integrated community based care across Health and Social Care that is financially sustainable and focussed on the principles of Community By Design. | Integrated Model March 2027 | Identify opportunities to strengthen community based intermediate care capacity, including highlighting any shortfalls, gaps, duplication in current provision. Improve pace and consistency of flow for all D2RA pathways. |  | Gap analysis report Pathway 1, 2 and 3 workshops and action plans |  | Continuation of pathway workshops and action plans | Review of finance/ workforce and recommendations and action plans | Develop revised pathways and model.
 | •Internal Community Nursing Review | To include review of District Nursing, Community Resource Teams, Specialist Palliative Care and wider Virtual Wards/ Acute Clinical Teams. Delivery focus cluster based model for one community pathway aligning core services and enhanced care services to provide seamless step up/ step down. | Mar-27 | TBC being developed. |  | Planned transformation of CPTC and SPC IP unit. DN service transformation (caseload, digital, workforce) Implementation of Enhanced Care community pathway and re-design of core community services. |  | 1. Implementation of Enhanced Community Care model to support UEC pillar 3 and prevention programme 2. Transformation plan roll out into IP unit SPC. | 1. Workforce transformation - Community pathways aligned to clusters 2. ECC delivery - UEC and prevention programmes 3. Core services alignment - CRT and DN | 1. SPC transformation plan evaluation against productivity 2. Digital programme - Single EPR roll out (pending funding) 3. Service and systems evaluation of productivity against core and enhanced community services.

## Slide 10: Urgent and Emergency Care System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Community Based Falls Response Services PILLAR 1: Pre-hospital & community | Aspirational Delivery To implement (subject to sufficient resource) a regional broader falls programme of works aimed at: •Prevention •Early pick up/ intervention post-fall •Getting the faller to the right place first time if additional support is needed (which may be at home with support) •Avoiding readmission where possible Which would address WG expectation to: •Reduce ambulance conveyance of Level 1 and Level 2 fallers to emergency departments by 10-15% on the 2025/26 baseline |  |  |  | Model approved in principle via OPB however currently no resource available to progress |  | TBC | TBC | TBC

## Slide 11: Urgent and Emergency Care System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Community Based Falls Response Services PILLAR 1: Pre-hospital & community | Continue commissioned resource (St John providing first aider in vehicle for faller pick-up in the community) until August 26 |  |  |  | •Working with WAST to maximise use of SJAC vehicle (until contract end in Aug) |  | Working with WAST to maximise use of SJAC vehicle (until contract end in Aug) |  | 
 |  | H45 Enabler: WAST Falls Service linked to SPOA |  | 10% reduction in ambulance conveyance Measures: •Process - ambulance arrivals at ED who have contacted SPOA •Outcome - ambulance conveyance numbers daily/Care Home conveyance numbers daily •Balancing - ambulance conveyance AMU, SDEC, SAU, OPAU and ambulance handover time |  | WAST pilot Falls Vehicle linked to SPOA commences 22nd June 26. |  |  |  | 

## Slide 12: Urgent and Emergency Care System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | SDEC and Acute Front Door Frailty Service PILLAR 2: Front door & first 72 hrs | Aspirational Delivery Implement/ improve (subject to sufficient resource) SDEC and acute front door frailty services that delivers the recommendations set out in the NHS P&I local health board SDEC reports (November 2025) by end of Q2. and addresses UEC Ministerial priorities to: •Increase community and ED referrals to medical SDEC services, discharging at least 80% on the same day of referral •Reduce emergency admissions of >75s from emergency departments to hospital by 10- 15% on the 2025/2026 baseline by the end of December, sustained until the end of March 2027 |  |  |  | Confirm level of resource available so as to develop services. Carry out PDSA activity so as to test system - level of available resource and PDSA results to drive future activity |  | TBC | TBC | TBC
 |  | H45 Enabler: Protect frailty assessment to deliver 20 assessments/day with community service resource to support admission avoidance | Delivery as per Implementation to support H45 from July 1st (Phased) | 20 pts per day-40% discharge rate |  | •Agree priority area for allocation of rapid access to community resource to be implemented |  |  |  | 

## Slide 13: Urgent and Emergency Care System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Acute and Community Hospital ‘Back Door’ flow PILLAR 3: Ward based flow and discharge | Aspirational Delivery Implement (subject to sufficient resource) the Optimal Hospital Flow Framework and realise outcomes of: •Consistently realise 33% of discharges by midday •Achieve a minimum of 20% of total weekly discharges on weekends (Saturday and Sunday) by the end of December 2026, and exceed 25% by the end of March 2027, while maintaining mid-week discharge volumes at current levels. •POCD targets |  |  |  | Trial Flow Team (1x B8b and 1x B6) for confirmed 3 months initially - after that confirm way forward to carry out activity that will positively work to national targets |  | TBC - resource dependent. Hoped that Flow Team can be continued post Q1 and continue improvement activity | TBC | TBC
 |  | H45 Enabler: Discharge Support. Key actions include: •Improve NEPTS usage (process & timeliness). •Increase discharge lounge capacity across all sites supported by a clear understanding of discharges and transfers required across all wards (health board wide) and LA to ensure flow form ED possible. •Improve the IDH function | Delivery as per Implementation to support H45 from July 1st (Phased) | NEPTS - Aim to book 6 patient journeys before midday D/C Lounge - All transfers prebooked and conveyed before midday IDH - Admission avoidance with support at home from community services |  | •Discharge lounge relocated to AMU Yellow zone – 15th June •IDH development underway (resource neutral) |  | •Confirmed NEPTS support following workshop and implemented as agreed | TBC | TBC

## Slide 14: Urgent and Emergency Care System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Communities and Older Peoples Strategy | Strategy – approved 2025/26 | Mar-27 | Year 1 - planning. Outcomes will be around governance and having workstreams in place. |  | Programme Board approval/ RPB presentation |  | Cluster engagement / RPB approval. | Establish workstreams and agree membership | Develop action plans and milestones
 |  | Establish workstreams for agreed areas of work |  |  |  |  |  |  |  | 
 |  | Develop Action and Delivery plan/ timescales for 2026/27 (It has been agreed at C&OP that immediate priority is the delivery of the Community Services Review, therefore this work will be picked up later in the financial year.) |  |  |  |  |  |  |  | 

## Slide 15: Urgent and Emergency Care System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
BAU/ PERFORMANCE | Acute Hospital ‘Front Door’ flow PILLAR 2: Front door & first 72 hrs | Fully Implement approved Ambulance Handover 45 (H45) Action Plan | Implement H45 from July 1st (Phased) | H45 is the immediate focus – phased roll-out: 80% of handovers in 45 mins (7am-7pm) – 1st July 26 95% handovers in 45 mins from 1st Sept 26 Linked metric 10% reduction in patients waiting in ED >12 hrs by end of March 2027 |  | Develop robust action plan to deliver, working with WAST and P&I colleagues |  |  |  | 
 |  | H45 Enabler: Acute Medical Patient Flow improvements Key actions include: • Re-introduce ED based medical patient MDT to manage the pathway of this patient group • Relaunch speciality retrieval from ED to ensure earlier decision making and flow | Delivery as per Implementation to support H45 from July 1st (Phased) |  |  | •Medical patient ED MDT ‘Top 10’ patient reviews reinstated •Specialty identification and retrieval in ED plans implemented W/C 22nd June |  | •Complete prospective audit - as per agreed mechanisms from retrospective audit |  | 

## Slide 16: Urgent and Emergency Care System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
BAU/ PERFORMANCE | Acute Hospital ‘Front Door’ flow PILLAR 2: Front door & first 72 hrs | H45 Enabler: Criteria to Admit • Audit to confirm that correct patients are being admitted or whether potential for alternative treatment pathway | Delivery as per Implementation to support H45 from July 1st (Phased) | To scope % avoidance opportunity against current admissions to acute medicine |  | •Retrospective Audit complete – no significant admission avoidance opportunity noted |  | •Undertake Various PDSA cycles |  | 
 |  | H45 Enabler: ED assessment and flow –Key actions include: • Trial various models to improvement queue management Key actions include: • re-trial consult review of referrals in and supporting internal operational standards (& escalation) | Delivery as per Implementation to support H45 from July 1st (Phased) |  |  | •Undertake Various PDSA cycles •Consultant review of referrals and internal operational standards from 15th June |  | •Roll out Revised versions of SOPs as agreed with clinical leaders in Q1 |  | 

## Slide 17: Urgent and Emergency Care System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
BAU/ PERFORMANCE | Acute Hospital ‘Front Door’ flow PILLAR 2: Front door & first 72 hrs | H45 Enabler: Flow - Key actions include - •Focus on improved ambulance flow by alleviating any additional duties form ambulance flow coordinators. •Develop health board wide ‘push’ flow SOP. •Enhanced compliance with internal operational standards to reduce LOS | Delivery as per Implementation to support H45 from July 1st (Phased) | Ambulance Flow - Maintain ringfence beds in resus / AMU / SDEC and OPAU Process - number ambulances <120 mins, number ambulances <45 mins Outcome - % ambulance handover <45 mins, % breaches over 45 mins Balancing - number ambulances / day, number patients awaiting beds at 9am |  | •Flow support 1 WTE in place from 29th June •Quota modelling being picked up as part of bed modelling programme - first workshop 17th June |  |  |  | 

## Slide 18: Urgent and Emergency Care System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
RECOVERY AND SUSTAINABILITY | Reducing Clinically Optimised Patients PILLAR 3: Ward based flow and discharge | Undertake baseline capacity and demand in respect of the Pathway 2 bed pool. |  |  |  | Undertake baseline capacity and demand in respect of the Pathway 2 bed pool. |  | N/A | N/A | N/A
 |  | Analyse the findings of the Pathway 2 snapshot audit of all patients in Pathway 2 beds in hospital and community settings. |  |  |  | Analyse the findings of the Pathway 2 snapshot audit of all patients in Pathway 2 beds in hospital and community settings. |  | N/A | N/A | N/A
 |  | Remodel the bed pool based on the learning from the audit, benchmark LoS opportunities and scenario planning (what does an increased P1 offer do the number of P2 beds required). |  |  |  | N/A |  | Implement actions in line with available resource linked to remodelling bed pool | Implement actions in line with available resource linked to remodelling bed pool | Implement actions in line with available resource linked to remodelling bed pool
 |  | Implement a COP reduction programme (cross system – health & social care) |  |  |  | N/A |  | Implement actions in line with available resource linked to remodelling bed pool | Implement actions in line with available resource linked to remodelling bed pool | Implement actions in line with available resource linked to remodelling bed pool

## Slide 19: Urgent and Emergency Care System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
BAU/ PERFORMANCE | Maintaining Stroke / Snap targets | Delivering on Therapies action plan to work towards achieving the Sentinel Stroke National Audit Programme (SSNAP) targets |  | Improvement in 24 hrs assessment target for OT and PT Improvement in 72 assessment hrs target for SLT Improvement in median daily therapy minutes for each patient Improvement in number of days patients receive therapy Increase % of mood, cognition and visual assessments by discharge Increase % of applicable patients seen by dietitian by discharge Increase % of patients who receive on-going stroke specific input in the community through ESD or Outreach Explore joint office space for ESD and outreach to enhance community provision Design ICSS model for SBHUHB, including workforce design |  | Increase % of mood, cognitive and visual assessments to > 85 % prior to d/c Increase & of dietitian assessment for those applicable to > 80% by D/C |  | Increase % of those receiving 24 hour OT and PT assessment to > 80% Increase SLT assessment within 72 hrs to >90% | Increase % of patients receiving stroke specific community based intervention through ESD and Outreach to >65% | Increase median therapy minutes for all patient to >45mins Increase median days therapy received for all patients (days to be specified after further data review - will update after Q1)
 |  | Evaluate service delivery models to ascertain re-design opportunities to enhance integrated community stroke services |  |  |  | Work with site management to identify suitable office space to collocate ESD and outreach. |  | ESD and outreach data to analyse current demand on discharge | Use PROMs data along with demand data to design ICSS model for SBUHB, including workforce | Service delivery evaluation, including workforce to identify re-design opportunities

## Slide 20: Urgent and Emergency Care System Reporting – Off Track Delivery in Q1
Scheme/ Project | Delivery Action | Q1 Milestone Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate, Revised milestones to agree
Bed Base Reconfiguration – Also includes Planned Care Elective Beds | Reduce cost through reduction of the core bed base Avoid admission for frail older people where safe Pathway 1 - get patients home with support in 72 hrs Pathway 3 - Cohort Care Home pathway patients for more streamlined assessment process. IDH and optimal flow - Create discharge grip and reduce internal waits SPOA - Reduce avoidable conveyancing and admission Lower cost wards- Reduce cost of clinically optimised bed days |  | Activity dependent on resource to deliver and/ or require confirmation whether appropriate: Analysis shows a negative bed base – any improvements to close gap rather than reduce core bed base Work underway with OPAU re; improving processes to avoid frailty admissions. Improvement resource in place till end of July (no confirmation past this date) – to increase to 7-day provision will require investment P1 – requires sufficient capacity in line with demand to ensure 72hr target IDH = currently in informal consultation with IDH temporary resource (pulled from other services) to see if willing to work in certain model. If not agreed will either require formal OCP and associated budget SPOA = no confirmed budget | Escalation to Executive Team to flag delivery is dependent on resource availability | TBC – with no budget/ resource aligned this will not get back on track and will become ‘red’ or requires amendment as a realistic delivery action within 26/ 27 | N/A
Community Based Falls Response Services | See all falls activity |  | No budget/ resource allocated. Current L1 falls vehicle to cease August 26 | Working regionally to identify opportunities | TBC – with no budget/ resource aligned this will not get back on track and will become ‘red’ or requires amendment as a realistic delivery action within 26/ 27 | N/A
Milestones

## Slide 21: Urgent and Emergency Care System Reporting – Off Track Delivery in Q1
Scheme/ Project | Delivery Action | Q1 Milestone Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate, Revised milestones to agree
SDEC and Acute Front Door Frailty Service | SDEC/ frailty |  | Working group in place to drive improvements. Additional project management support required to fully drive Initial group set up – process improvements underway but limited by level of available support To fully embed any improvement, require service to avoid overcapacity/ bedding etc System-flow an enabler Sufficient QI/ project management support alongside clinical capacity for change activity | Escalation to Executive Team to flag delivery is dependent on resource availability (QI improvement resource ending July 26) | TBC – requires confirmation as to whether QI improvement resource will be continued. Also dependent on patient flow to avoid bedding/ overcapacity | 
SDEC and Acute Front Door Frailty Service | H45 Enabler: Protect frailty assessment |  | Dependent on system flow and sufficient staffing – key enabler for unit to function is avoiding bedding and pulling the appropriate patients | Whole system improvements re; flow. Escalation to Executive Team to flag delivery is dependent on resource availability (QI improvement resource ending July 26) | TBC – requires confirmation as to whether QI improvement resource will be continued. Also dependent on patient flow to avoid bedding/ overcapacity | 
Milestones

## Slide 22: Urgent and Emergency Care System Reporting – Off Track Delivery in Q1
Scheme/ Project | Delivery Action | Q1 Milestone Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate, Revised milestones to agree
Acute Hospital ‘Front Door’ flow | H45 (several action still to be completed) |  | H45 (several action still to be completed in developed action plan) Achieving desired outcome dependent on sufficient discharge capacity at back door Periods of BCI due to system escalation | Complete all actions in H45 action plan Carry out system wide support activity (flow, discharge, admission avoidance) | Action plan completed in Q2 (immediate delivery of mitigating actions). To sustainably deliver H45 will require improvement across the whole system (Admission avoidance, timely triage, pull / push throughout the acute site plus overall system flow and discharge) | N/A
Acute and Community Hospital ‘Back Door’ flow | Optimal Hospital Flow Framework |  | 1 FTE (split across two colleagues) recruited to drive forward activity and working with flow colleagues already in post. Currently working with 3 wards. Increased focus on Anglesey, Ward L, Gowers - aim to roll-out improvement activity to all wards. Will be required to adapt to non-acute sites as appropriate Enabling activity to include baseline assessment and forward planning re; bed utilisation Risk that current B8B resource timetabled to end at end of July 26 | Escalation to Executive Team to flag delivery is dependent on sufficient improvement resource (current role(s) end July 26) | TBC – requires confirmation as to whether board round/ flow improvement resource will be continued. Also dependent on patient flow to avoid overcapacity | N/A
Milestones

## Slide 23: Urgent and Emergency Care System Reporting – Off Track Delivery in Q1
Scheme/ Project | Delivery Action | Q1 Milestone Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate, Revised milestones to agree
Reducing Clinically Optimised Patients | Undertake baseline capacity and demand in respect of the Pathway 2 bed pool. Remodel the bed pool based on the learning from the audit, benchmark LoS opportunities and scenario planning (what does an increased P1 offer do the number of P2 beds required). Implement a COP reduction programme (cross system – health & social care) |  | Ongoing scrutiny of reporting system underway Remodelling the bed-pool will require resource to stand up a bridging team care team of carers that would enable patients to return home while longer term care arrangements are confirmed COP reduction programme dependent on whole system changes for improved system flow and more timely discharges (outside of annual variation) | - Joint working across organisations to align resources | - TBC – sustainable reduction of COP (outside of annual variation) reliant on whole system changes for improved system flow and more timely discharges | N/A
Milestones

## Slide 24: Urgent and Emergency Care System Performance
WG Delivery Expectation | SBU Commitment 26/27 | Baseline position 25/26 | Performance Trajectories 26/27 |  |  |  |  |  |  |  |  |  |  |  | Actual Data |  | 
 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | 
 |  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Ensure no ambulance patient handover waits over 45 minutes | We will commit to 0>45 mins ambulance handovers by Sept 2026 | Q4= Jan 26 = 703, Feb 26 = 733, Mar 26= 932 | 540 | 500 | 460 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 501 | 432
Ensure no patient spend spends 12 hours or more in all major and minor emergency care facilities from arrival until admission, transfer or discharge | We will deliver 10% reduction in patients waiting in ED >12 hrs by end of March 2027 | Q4 Jan 26= 1272, Feb 26= 1203, Mar 26= 1356 | 1350 | 1300 | 1190 | 1100 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 997 | 1,319 | 1,347 | 1,366
Deliver a 12-month reduction trend in both the number of people who are delayed in hospital and the total days delayed for these patients, as measured by the Delayed Pathways of Care dashboard | We will deliver a 12-month reduction trend in the Number of people who are delayed in hospital as measured by the Delayed Pathways of Care Dashboard, reducing this to 100 patients delayed in hospital by March 2027 | Q4=175 | 210 | 200 | 190 | 180 | 170 | 160 | 150 | 140 | 130 | 120 | 110 | 100 | 200 | 192 | 173
Increase in capacity at the weekend of community nursing and specialist palliative care nursing to at least the required levels previously set for 2024/25 and greater where possible. | TBC as per Community Services Review in progress- unable to provide until this concludes. Discussion with Execs in June 2026. | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC |  |  | 

## Slide 25: PLANNED CARE AND CANCER OVERVIEW
Performance Outcomes | Confidence assessment
No patients waiting more than 104 weeks for referral to treatment. | Ambition to maintain 0 however recognising current gaps and risks
Number of patients waiting more than 8 weeks for a specified diagnostic | Achieve reduction
Follow up outpatients Backlog (TI) | 
Achieve the suspected cancer pathway target of 75% through implementing the nationally agreed pathways, while reducing the backlog of patients waiting more than 62 days by end of March 2027. | 76% in Q4
%SCP >60% 3 months consecutive (TI) | Confident to exceed TI Target
Financial Impact | FYE savings | £2.27m
Key Schemes |  |  | 
CIP_06 and 07 | Infrastructure Consolidation via Productivity (Theatres and Outpatients) |  | 
CIP_27 | Review Vascular Interventional Radiology Service Development |  | 
TBC | Pipeline opportunities: Cap Diagnostic Services to reduce Variable Pay Review of non statutory and waiting list pathway work Low Value Interventions and INNUs |  | 
PC_B_01 | Community By Design Programme |  | 
PC_B_02 | Theatre Transformation Programme |  | 
PC_B_03 | Diagnostics Transformation Programme and Delivery of 8 weeks Diagnostics Waits |  | 
PC_B_04 | Outpatients Redesign Programme |  | 
PC_B_05 | Cancer Improvement Programme |  | 
PC_B_06 | Planned Care Digital Transformation: |  | 
 | LIMS and RISP Digital Health Assessments Patient Portal and Hybrid Mail | Ambient Voice Technology Internal Referrals Digital Cellular Pathology | 
PC_B_07 | Capital Planned Care/Cancer Priorities |  | 
 | Radiotherapy expansion 5th Linac/6th Bunker and Replacement Linacs at SWWCC PET CT | Regional Cellular Pathology relocation Urology OR1 Theatres Hybrid Theatre Morriston | Regional Cellular Pathology relocation Urology OR1 Theatres Hybrid Theatre Morriston
PC_C_01 -02 | RTT Delivery Plans and SCP Delivery Plans A key assumption underpinning the revised trajectory for SCP is successful implementation of the Cellular Pathology recovery scheme, including outsourcing arrangements to support backlog reduction and stabilisation of ongoing reporting capacity. |  | 
Our Planned Care and Cancer programme focuses on rightsizing services, efficiency and productivity to maximise value for money, ensuring quality and improving waiting times
Risks | Mitigations
Productivity not achieved in line with plan | Executive oversight and benchmarking
Delays in workforce plan progress and workforce resistance | Early engagement and vacancy control
Activity/performance delivery risk | Phased consolidation, close monitoring

## Slide 26: Planned Care & Cancer System Summary
RAG | Green | 5 | Amber | 5 |  | Red | 0 | Total | 10
Achievements |  |  |  |  | Challenges |  |  |  | 
Planned Care Infrastructure via Productivity: Completed demand and capacity assessment and developed implementation approach for productivity programme. Theatre implementation planning commenced, supported by Deloitte benchmarking. Pre-Surgical Pathway: Programme initiated with governance, SRO, programme management and Healthcare Systems Engineering mapping established. Digital Pre-Assessment (PRO-MAPP): Contract signed, implementation governance established, questionnaire finalised and phased implementation commenced. Pathway Redesign: Current-state mapping completed across booking, administration and pre-assessment functions with future-state design progressing. Waiting Well: Continued delivery of Stage 1 model with further service onboarding underway. Regional Recovery: Interim Welsh Government recovery plan submitted incorporating regional elective solutions. Cancer Refreshed Cancer Improvement Programme established with agreed programme workstreams and strengthened governance. Tumour-site improvement plans completed, reviewed and incorporated into a unified Cancer Delivery Plan. Revised recovery trajectories submitted to Welsh Government. Monthly tumour-site assurance arrangements established. Priority workstreams commenced across diagnostics, treatment capacity, pathology and early diagnosis |  |  |  |  | Planned Care Theatre redesign implementation progressing more slowly than planned due to scale of clinical and workforce change. Anaesthetic pathway mapping extends into Q2 before future-state model can be finalised Diagnostics Transformation governance continues to mature alongside development of detailed delivery plans. Outpatient redesign remains in implementation phase, with validation and pathway redesign continuing through Q2. Currently no DU support allocated to planned care R&S schemes. Cancer Performance remains below WG target despite improvement. Variation in quality and maturity of tumour-site delivery plans. Capacity constraints across diagnostics and oncology pathways. Workforce pressures continue across several services. Requirement to deliver significant improvement whilst responding to evolving national expectations. |  |  |  | 

## Slide 27: Planned Care & Cancer System Summary
Learnings from Q1 | Risks/ Issues | Mitigations
Planned Care Sustainable recovery depends as much on clinical ownership and organisational change as additional investment. Regional collaboration offers greater opportunity than organisation-specific solutions in several specialties. Robust demand and capacity modelling provides greater confidence in investment decisions. Productivity improvement requires dedicated programme management alongside operational delivery. Cancer Improvement requires whole-pathway ownership rather than individual service improvement. Tumour-site plans require measurable actions linked directly to performance outcomes. Stronger programme management and consistent governance improves delivery assurance. Earlier intervention on pathway delays provides greater opportunity for sustained improvement. | Planned Care Delay to theatre redesign impacting delivery of productivity assumptions. Workforce availability across key specialties. Ability to deliver planned recurrent savings within required timescales. Continued growth in outpatient demand offsetting productivity gains. Delivery of diagnostics recovery without enabling investment. No PMO support Cancer Failure to achieve SCP trajectory. Diagnostic delays impacting treatment pathways. Workforce recruitment and retention. Variable clinical engagement across tumour sites. Dependence on regional and national support. | Planned Care Phased implementation of theatre design Increased clinical engagement Continued operational validation and pathway transformation Regional working to maximise available elective capacity Development of detailed implementation plans lined to governance and programme assurance DU to establish adequate programme support. Cancer Refresh Cancer Improvement Programme workstreams. Monthly tumour-site assurance meetings. Strengthened performance monitoring and escalation. Focused support for priority tumour sites. Alignment with emerging Clinical Services Plan and Cancer Strategy.
Q2 Priorities |  | 
Planned Care Begin implementation of agreed theatre redesign. Deliver approved 104-week and diagnostics recovery plans. Accelerate outpatient transformation including PIFU and follow-up redesign. Progress diagnostics transformation programme. Translate productivity opportunities into measurable recurrent benefit. Strengthen regional elective delivery arrangements. |  | 
Cancer
Implement refreshed Cancer Improvement Programme.
Deliver measurable improvements in priority tumour sites.
Reduce >62-day backlog.
Improve diagnostic turnaround and pathway flow.
Strengthen programme governance and benefits reporting.
Continue trajectory towards 70% SCP performance.

## Slide 28: Planned Care and Cancer System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
RECOVERY AND SUSTAINABILITY | Infrastructure Consolidation Via Productivity | Benchmark theatres and outpatient productivity against upper-quartile standards. |  | Minimise zero 104 week waits for treatment ensuring increased productivity and optimisation in theatres |  | Infrastructure via Productivity: Completed demand and capacity assessment and developed implementation approach for productivity programme. Theatre implementation planning commenced, supported by Deloitte benchmarking |  | Begin implementation of agreed theatre redesign. Translate productivity opportunities into measurable recurrent benefit |  | 
 |  | Define target infrastructure footprint required at benchmark productivity. |  |  |  |  |  |  |  | 
 |  | Consolidate theatre sessions and outpatient clinics accordingly. |  |  |  |  |  |  |  | 
 |  | Align workforce establishment to reduced infrastructure. |  |  |  |  |  |  |  | 
 |  | Deliver recurrent cash-releasing savings. |  |  |  |  |  |  |  | 
 | Review Vascular Interventional Radiology Service Development | Review planned recruitment and options to develop the VIR service. |  |  |  |  |  |  |  | 
 | Cap Diagnostic Services to reduce Variable Pay |  |  |  |  |  |  |  |  | 
 | Review of non statutory and waiting list pathway work |  |  |  |  |  |  |  |  | 
 | Low Value Interventions and INNUs |  |  |  |  |  |  |  |  | 
SERVICE TRANFORMATION | Community by Design | Participate in a pilot of a bespoke, community-based breathlessness pathway in one cluster which will inform and shape the rollout of a national service under a Once for Wales approach as part of 'Delivering Integrated Services' |  | Assess and manage patients experiencing chronic breathlessness, with no formal diagnosis, and identify an appropriate treatment pathway. |  |  |  |  |  | 

## Slide 29: Planned Care and Cancer System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANFORMATION | Theatres Transformation Programme: •Pre Surgical Pathway and Implementation of PROMAPP | Programme Setup: •Agreed programme scope & governance •Confirmed clinical & operational leads •Baseline Health Care Engineering current-state mapping | Programme initiation complete Q1 |  |  | Programme initiation complete |  |  |  | 
 |  | Electronic Health Screening Questionnaire Implementation: •Procurement / approval of digital solution •Co‑designed digital questionnaire (clinical sign‑off) •Technical integration with WPAS/EPOA (where required) •Testing, training and comms plan •Go‑live | By Q4 |  |  | Digital solution confirmed March 2026 Clinical content signed off March 2026 |  | Soft launch / pilot |  | Full roll-out
 |  | Pathway and Workforce Redesign •Current-state mapping (all specialties within the generic pre-assessment) •Future-state pathway with risk stratification •Standardised triage and optimisation criteria •Standard operating procedures (SOPs) •Workforce model for nurse-led / specialist-led clinics / Anaesthetics | By Q4 |  |  | Process model designed March 2026 Pilot with 1–2 specialties March 2026 |  | Scale to full elective programme |  | Future-state design approved SOPs signed off

## Slide 30: Planned Care and Cancer System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANFORMATION | Diagnostics Transformation Programme |  |  |  |  | Establish Diagnostics Board and confirm scope/ delivery plans for 26/27 |  | Progress diagnostics transformation programme |  | 
 | Outpatients Redesign: Outpatient Safety, Validation and Risk | Complete clinical validation of all follow-up waiting lists, prioritised by risk |  | ·≥95% of follow-up waiting lists clinically validated ·Reduction in high-risk follow-up backlog ·Clear assurance reporting on follow-up safety |  |  |  | Accelerate outpatient transformation including PIFU and follow-up redesign. |  | 
 |  | Implement standard risk stratification approach for follow-up backlog |  |  |  |  |  |  |  | 
 |  | Establish regular (e.g. monthly) specialty-level follow-up safety reviews |  |  |  |  |  |  |  | 
 | Outpatients Redesign: Effective Referral Management & Front Door Control | Mandate referral triage for all priority outpatient specialties |  | ·≥95% of new referrals clinically triaged ·Increased proportion of referrals resolved without face-to-face OPD ·Reduced referral-to-triage times |  |  |  |  |  | 
 |  | Expand Advice & Guidance usage with agreed response standards |  |  |  |  |  |  |  | 
 |  | Increase use of straight-to-test and direct listing pathways |  |  |  |  |  |  |  | 
 |  | Align referral thresholds with Health Pathways and primary care engagement |  |  |  |  |  |  |  | 

## Slide 31: Planned Care and Cancer System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANFORMATION | Embed Waiting Well Phase 2 Pre-optimisation service | Embed Waiting Well Phase 2 Pre-optimisation service |  |  |  | Continuing Support of all Stage 1 on boarded priority Services using digital Waiting Well |  | Health Assessment - 5th Service T&O Support rollout of Surgical Opt In Digital identification, optimisation & tracking of complex patients Support establishing of Digital/Virtual Prehabilitation model in Swansea Bay Patient Portal (SBPP) |  | 
 | Outpatients Redesign: Prudent Follow-up & PIFU at Scale: | Identify and agree PIFU / SOS eligible cohorts by specialty |  |  |  |  |  | Accelerate outpatient transformation including PIFU and follow-up redesign. |  | 
 |  | Implement standard PIFU operating models (including re-access routes) |  |  |  |  |  |  |  | 
 |  | Increase discharge-as-default where clinically appropriate |  |  |  |  |  |  |  | 
 |  | Monitor re-access and outcomes to ensure safety and equity |  |  |  |  |  |  |  | 
 | Cancer Improvement Programme |  |  |  |  | Confirm focused set of system priorities and programme workstreams to inform a refreshed, Board-owned Cancer Improvement Programme and unified Cancer Delivery Plan |  | Implement refreshed Cancer Improvement Programme. Strengthen programme governance and benefits reporting. Continue trajectory towards 70% SCP performance. |  | 

## Slide 32: Planned Care and Cancer System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
BAU/ PERFORMANCE | RTT Delivery Plans | Deliver 104 week wait RTT plan |  | Minimise zero 104 week waits for treatment ensuring increased productivity and optimisation in theatres |  | Submitted Recovery Plans and Sustainable Planned Care Plan for additional monies |  |  |  | 
 |  | Deliver 26 week wait RTT Stage 1 Outpatients plan |  |  |  |  |  |  |  | 
 |  | Deliver 8 week wait Diagnostics plan |  | Work towards reducing the number of patients waiting over 8 weeks for a diagnostic endoscopy, and continue to maintain our current position of patients waiting over 8 weeks for all other diagnostics (aim of achieving 80% TI target) |  | Revised recovery trajectories submitted to Welsh Government. |  |  |  | 
 |  | Deliver 14 week wait Therapies Plan |  |  |  |  |  |  |  | 
 |  | Deliver 14 week wait Audiology (Adults) Plan |  |  |  |  |  |  |  | 
 |  | Deliver 6 week wait Audiology (Paediatrics) Plan |  |  |  |  |  |  |  | 
 | Suspected Cancer Pathway (SCP) Delivery Plan | Deliver tumour site plans to deliver SCP % improvements in line with trajectories |  | • Deliver a 12-month improvement trend in patients starting first definitive cancer treatment within 62 days from point of suspicion (regardless of the referral route), achieving 70% by January 2027 and maintaining this until end of March 2027. • Reduce the backlog over 62 days to 100 by end of March 2027 |  | Tumour-site improvement plans completed, reviewed and incorporated into a unified Cancer Delivery Plan. Revised recovery trajectories submitted to Welsh Government. Monthly tumour-site assurance arrangements established. |  | Continue trajectory towards 70% SCP performance. |  | 

## Slide 33: Planned Care and Cancer System Performance
WG Delivery Expectation | SBU Commitment 26/27 | Baseline position 25/26 | Performance Trajectories 26/27 |  |  |  |  |  |  |  |  |  |  |  | Actual Data |  | 
 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | 
 |  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
No patients waiting more than 104 weeks for referral to treatment | Maintain ambition of 0 over 104 weeks, acknowledging current gap and risk of 850 people waiting and continue to work with colleagues in NHSP&I to address these | Q4=0 | 0 | 0 | 0 | 101 | 155 | 172 | 207 | 378 | 416 | 579 | 689 | 850 | 0 | 0 | 0
Health boards to achieve the suspected cancer pathway target of 75% through implementing the nationally agreed pathways, while reducing the backlog of patients waiting more than 62 days by end of March 2027 | Ambition to deliver 70% waiting for first definitive treatment from point of suspicion of cancer,62 Days by end of Q2 and 76% by end of Q4 Reduce the backlog over 62 days to 50 by October 2026 | Q4 = 55% SCP | 48% | 48% | 48% | 57% | 59% | 61% | 68% | 73% | 75% | 76% | 76% | 76% | 48% | 54% | 
 |  | 359 Backlog | 326 | 489 | 626 | 640 | 545 | 317 | 220 | 125 | 116 | 107 | 104 | 104 | 326 | 489 | 625
Number of patients waiting more than 8 weeks for a specified diagnostic – target zero | We will work towards reducing the number of patients waiting over 8 weeks for a diagnostic endoscopy and continue to maintain our current position of patients waiting over 8 weeks for all other diagnostics (80% TI target). |  |  | 6411 | 8781 | 8111 | 6830 | 5649 | 5846 | 6022 | 6267 | 5867 | 5464 | 5238 | 3,031 | 5,065 | 5,244

## Slide 34: MENTAL HEALTH AND LEARNING DISABILITIES OVERVIEW
Performance Outcomes | Confidence assessment
Open Access Mental Health Support | Metrics nationally developed in Q1 26/27
Improve safety in Secondary Care Mental Health services (measured through agreed mental health safety matrix and PROM ReQol) | Metrics nationally developed in Q1 26/27
Improve Physical Health of People with long term MH problems by carrying out mortality reviews and implementing improvement plans | Metrics nationally developed in Q1 26/27
Key Schemes | 
MH_A_01 | Repatriation of Privatised Beds
MH_B_01 | Mental Health Transformation Programme
MH_B_02 | Alliance Clinical Model for Substance Use Clinical Services
MH_B_03 | Mental Health Capital Priorities: Seclusion Suites, Caswell Clinic Adult Acute Mental Health Unit Service Diversions, Cefn Coed & Other Mental Health In-Patient Estate Improvements Taith Newydd Anti ligature works across remaining MH estate
MH_B_04 | Mental Health Digital Transformation: ReQol Rio Electronic Patient Record
LD_B_01 | Learning Disabilities Transformation: Strategic Outline Case for the replacement of all remaining LD facilities. Consolidation of existing Complex Care Units
Our aim is to deliver mental health service transformation by ensuring people have easy access to tools and support to maintain their wellbeing. We will also strengthen the digital infrastructure and streamline complex MHLD pathways, while continuing the shift from inpatient to community focused care. We also need to centralise acute mental health inpatient services into modern facilities that better enable care, effective staffing and digital connectivity.
Risks | Mitigations
Rio: Timescales for implementation project is reliant on Swansea LA as needs to align and launch at same time. | Rio Assurance Group in place to monitor and review progress of project and includes both HB & LA members.
LD: Bed availability to close units is limited which impacts acute capacity, flow & could increase spend on placements | Management and escalation of POCDs working with stakeholders to prepare for changes
Financial Impact | FYE savings | ~ £0.43M-£1.1M
Low impact – RR Reduction of £431,672 over 3 months Medium Impact – RR Reduction of £797,044 over 3 months High Impact – RR Reduction of £1162415 over 3 months |  | 

## Slide 35: Mental Health & Learning Disabilities System Summary
RAG | Green | Outcomes | Milestones | Amber | Outcomes | Milestones | Red | Outcomes | Milestones | Total | Outcomes | Milestones
 |  | 19 | 17 |  | 4 | 6 |  | 0 | 0 |  | 23 | 23
Achievements |  |  |  |  |  | Challenges |  |  |  |  |  | 
SERVICE REDESIGN/TRANSFORMATION Reduction in out of area placement's in Q1 in line with ask to reduce use of OOA beds by 50% Establishment of a dedicated Home Treatment Team to support repatriation of OOA patients. Business case approved in Q1 and recruitment is planned for Q2 and progressing. Proposed service model - flexible, open access & reduced reliance on inpatient capacity. Alignment with national strategy, RPB structures & Community by Design. 2 Demonstrator pilot sites submitted All 3 wards now assessment and treatment aligned to local authorities Centralised out of hours crisis assessment services 48% reduction of private bed provision since Oct 25 against national target of 50%. Reduction of OPMHS beds from 78 to 58 WORKFORCE Baseline assessments completed for Nursing, AHP, Psychology and Medical staffing. Identified nursing deficit - require +113.85WTE, (includes MH,LD & Secure Services) or +62.55WTE for MH only, to meet minimum NSA expectations. Reduction in temporary staffing in line with WG targets for agency usage DIGITAL INFRASTRUCTURE EPR Phase 1 rolled out to 21 teams: >500 logins, >6400 referrals & >2080 appointments created in first month. Integrated working with local authorities. First interoperable system in Wales. Core performance and quality metrics developed with clinicians and in line with new WG requirements Power BI dashboard developed for daily core metrics to NHS Wales P&I and Q&S indicators SUBSTANCE USE Kaleidoscope contract awarded for 12 months from 1st April 2026. Planned introduction of alliance by June 1st 2026 |  |  |  |  |  | USC Unscheduled care demand is not linear. Therefore, there may be ongoing rises in OOA useage but overall the aim remains to reduce usage. Caswell Clinic Business Justification case for HDU facilities in Caswell Clinic delayed following queries from Welsh Government (relating to cost benefit and building specifications). These queries are now being worked through by Capital Planning SBUHB. |  |  |  |  |  | 

## Slide 36
Learnings from Q1 | Risks/ Issues | Mitigations
DIGITAL NFRASTRUCTURE Use of ReQol is inconsistent across services and more support is needed to continue implementation WORKFORCE Business Case to increase nurse establishment by 35 x Band 5s approved. Progress recruitment via Streamlining Scheme. Workforce proposals for Psychology, Psychological Therapies, AHP and Medical staffing progressing through scrutiny and governance processes. | Digital Data collection is sporadic across service due to training USC USC demand is not linear therefore Quarter on Quarter reductions may not be guaranteed. Substantial financial implications to address highest risk areas across all professions and meet minimum standards | Continue to collect the data until digitally operational. Continue to support staff to access training USC delivery plan and actions compiled to mitigate OOA use of beds.
Q2 Priorities |  | 
DIGITAL INFRASTRUCTURE Implementation of ReQol (Recovery Quality of Life), outcome measure tool. Currently a paper collection, continue to work with external bodies to complete integration to support digital collection. TRANSFORMATION •Business case to improve nurse staffing establishment and reduce remaining reliance on temporary staffing. •Finalise workforce proposals for Psychology, AHP and Medical staffing and progress through scrutiny and governance processes. Mental Health Transformation – Develop and agree on the model through the service redesign work stream. Continue to review OOA bed usage through Q2 to ensure numbers are reduced by 50% year end. SUBSTANCE USE SERVICE Develop detailed operational plan for full Alliance mobilisation. Monitor Implementation of alliance model having come into effect by end of Q2 CASWELL CLINIC Expedite building works of the first HDU on Cardigan Ward immediately, subject to approval by WG. LEARNING DISABILITIES Establish steering group for development of case for change Information and evidence gathering with stakeholder Dan y Deri Redevelopment: Commence enabling works, including the demolition of Dan y Deri. CCU Reduction Programme: Continue engagement, develop and submit proposals, and secure Board sign-off. |  | 
Mental Health & Learning Disabilities System Summary

## Slide 37: Mental Health & Learning Disabilities System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
RECOVERY AND SUSTAINABILITY | Private Placements | Review of admission criteria and processes |  |  |  |  |  |  |  | 
 |  | Workforce review and evaluation completed and case submitted for consideration. | Q2 | Recruitment to dedicated team to aid repatriation of those in private and to bolster HTT services. |  | Business case outcome awaited and implementation plan drafted in anticipation. |  | Recruitment to posts hopefully agreed in Q1. |  | 
 | Review Inpatient Unavailability | Reduction in variable pay for nursing. | Q1 | Reduced spend on variable nurse pay. |  |  |  |  |  | 
SERVICE TRANSFORMATION | Mental Health Transformation | Establish a robust governance arrangement that provides strengthened executive oversight, clear decision-making routes and consistent, transparent reporting. | Q1 | Address deficits in service against best practice to ensure that service users have access to best in class care. Improved outcomes and experience for people and carers. Better reporting and monitoring of key quality, safety and performance indicators, incidents and risks Strengthened partnership working with regional teams, local authorities, third sector, service users and carers. Alignment with regional and national programmes. |  | MH Transformation Programme Board in place Workstreams full embedded Governance Structure in place |  | N/A | N/A | N/A
 |  | Delivery of a robust Transformation Plan, with key deliverables for each workstream. This will include the capital business case development for the programme and the service model design. | Q1 Q3 |  |  | ToR agreed for all Workstreams |  | Development of Transformation plan for each workstream | Implementation of Transformation Plan for each workstream | Implementation of Transformation Plan for each workstream
 |  | Implementation of a modern service model with an integrated care pathway across Mental Health Services for the population of Swansea and Neath Port Talbot, following the Stepped Care 2.0 model and in alignment with evidence-based best practice | Q4 |  |  | Develop and agree model |  | Action plan development | Action plan implementation | Continued implementation and test of change.

## Slide 38: Mental Health & Learning Disabilities System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Mental Health Transformation | Development of a sustainable and skilled Mental Health workforce. | Q4 | Address deficits in service against best practice to ensure that service users have access to best in class care. Improved outcomes and experience for people and carers. Better reporting and monitoring of key quality, safety and performance indicators, incidents and risks Strengthened partnership working with regional teams, local authorities, third sector, service users and carers. Alignment with regional and national programmes. |  | Development of business case for nurse staffing |  | Development of business case for multi-professional priority staffing | Workforce planning | Workforce planning
 |  |  |  |  |  | Development of stabilisation plan |  | Next step agreed with WG for the Estates Stabilisation plans is the production of a technical PBC (Programme Business Case) for capital investment which will come to the Sept Health Board meeting for endorsement. | Procurement/implementation of stabilisation plan and continued development of SOC for long term solution | Implementation of stabilisation plan and continued development of SOC for long term solution
 |  | Modernisation and improvement of the quality and safety of Mental Health estates and facilities for inpatient care within SBU Health Board. | Q4 |  |  | Development of stabilisation plan |  | Procurement for stabilisation plan and development of SOC for long term solution | Procurement/implementation of stabilisation plan and continued development of SOC for long term solution | Implementation of stabilisation plan and continued development of SOC for long term solution
 |  | Digitalisation of Mental Health services within SBU Health Board | Q4 |  |  | Continue work to develop and expand Dashboard and undertaken evaluation of reporting mechanisms |  | Continue work to develop and expand Dashboard and undertaken evaluation of reporting mechanisms | Continue work to develop and expand Dashboard and undertaken evaluation of reporting mechanisms | Continue work to develop and expand Dashboard and undertaken evaluation of reporting mechanisms
 |  |  |  |  |  | Dates for workstream in diaries Agreed ToR |  | Launch Transforming for the future engagement in line with timelines for MHTP | Incorporate MHTP into transforming for the future engagement | 
 |  | Development and delivery of an effective engagement and consultation plan with stakeholders, public and staff. | Q4 |  |  | Dates for workstream in diaries Agreed ToR |  | Launch Transforming for the future engagement in line with timelines for MHTP | Incorporate MHTP into transforming for the future engagement | 

## Slide 39: Mental Health & Learning Disabilities System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Improvements to digital infrastructure | Implementation of ReQol (Recovery Quality of Life), part of the outcome measures framework for Wales to use across Adult and Older Adult MH services | Q3 | Reduced duplication in entering information. Improved user access to patient experience Reduction in paper processes and storing of paper records |  | Embed and Roll Out of ReQol across inpatient wards and ensure consistent data reporting. Training still been rolled out across service group. Some services have implemented |  | Implementation of ReQol into Community Services | Embed ReQol across community services and ensure consistent data reporting | Review data reporting of ReQol and digital options for reporting
 |  | Implementation of Rio to replace WCCIS. | Q4 |  |  | Continuation of Data Mapping, Migration and Reporting requirements |  | Continuation of Data Mapping, Migration and Reporting requirements | Continuation of Data Mapping, Migration and Reporting requirements | Confirmation of implementation plan in alignment with LA timescales
 |  | Electronic patient record for mental health & learning disabilities | Q4 |  |  | Working Group established to review requirements and resources required for rollout of Rio to remainder of MHLD Services |  | Development of proposal for additional funding for final rollout to Rio | Submission of Funding proposal | Development of Implementation plan for full out (funding required)

## Slide 40: Mental Health & Learning Disabilities System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Alliance Clinical Model for Substance Use Clinical Services | Assist with the implementation of the interim subcontracting arrangement, ensuring continuity of prescribing and clinical oversight for service users under Criminal Justice pathways | Q1 | Reduction in waiting times, through rapid assessment or near day prescribing, Reduced duplication across HB and Criminal Justice pathways with consistent clinical governance and standards |  | Kaleidoscope contract awarded for 12 months from 1st April 2026 |  | Continue to assess | Continue to assess | Continue to assess
 |  | Contributing to the development of an integrated clinical assessment and prescribing pathway that will support service users who require substance‑use‑related prescribing across all Health Board services. | Q4 |  |  | Review of waiting times and clinical prescribing pathways for HB services |  | Attendance at alliance meetings to review clinical pathways | Attendance at alliance meetings to review clinical pathways | Implement integrated clinical assessment and prescribing pathways.
 |  | Participating in embedding Health Board clinical governance, medicines management, and prescribing accountability across Alliance services. | Q1 |  |  | Already in place in Q1. CDAT services as well as Alliance members are aware of process and clinical governance arrangements |  | Continue to monitor | Continue to monitor | Continue to monitor
 |  | Develop detailed operational plan for full Alliance mobilisation | Q2 |  |  | Plan development underway Planned introduction of alliance by June 1st 2026 |  | Monitor Implementation of alliance model having come into effect by Q2 | Continue to monitor | Continue to monitor

## Slide 41: Mental Health & Learning Disabilities System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Caswell Clinic | BJC scrutiny and capital funding approval required from Welsh Government. | TBC | Improving access to care closer to home, with patient benefits Reduced costs to JCC and all HB's regarding use of the private sector for medium secure setting |  | Further technical detail requested by Capital Leads in WG.Capital Planning are compiling responses to WG to their queries around the BJC |  | TBC Pending approval of the BJC | TBC Pending approval of the BJC | TBC Pending approval of the BJC
 |  | Commence operational planning with capital planning and contractors to undertake the work in a live ward environment | TBC |  |  |  |  |  |  | 
 |  | Commence operational planning with capital planning and contractors to undertake the work in a live ward environment | TBC |  |  | This action is subject to approval of the BJC by WG |  | TBC Pending approval of the BJC | TBC Pending approval of the BJC | TBC Pending approval of the BJC
 |  | Commence building of the HDU facility on Cardigan Ward. | TBC |  |  | This action is subject to approval of the BJC by WG |  | TBC Pending approval of the BJC | TBC Pending approval of the BJC | TBC Pending approval of the BJC
 |  | Full commissioning of the HDU facility for patient use | TBC |  |  | This action is subject to approval of the BJC by WG |  | TBC Pending approval of the BJC | TBC Pending approval of the BJC | TBC Pending approval of the BJC

## Slide 42: Mental Health & Learning Disabilities System Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | LD Transformation | Development of case for change & commencement of Strategic Outline Case for the replacement of all remaining LD facilities. | Q4 | Progress in replacing out of date and not fit for purpose inpatient environments. |  | Confirmation of service model through 3 HB Strategic group. Scoping and set up - Meeting with SBUHB Capital for agreement of support for case for change development. |  | Establish steering group for development of case for change Information and evidence gathering with stakeholders | Case for Change report presented to Service group and if agreed to progress through HB governance. Scope engagement activities with stakeholders. | Develop long list of options for Strategic Outline case.
 |  | Consolidation of existing Complex Care Units for overall bed reduction and provision of effective flow and quality of care, ensuring maintained environments & appropriate levels of staffing. | Q4 | Implementation of the Dan y Deri development to provide new behaviour that challenges unit Progress in implementation of new inpatient service model for Complex Care Units measured by fewer beds. |  | Contract negotiations for commencement of on site work for development of Dan Y Deri CCU reduction - engagement with staff and staff side. |  | Enabling works including demolition of Dan Y Deri commences. CCU reduction - Engagement continued. Submit proposals and obtain Board sign off. | Review of timescales and progress for Dan Y Deri Development (estimated completion Sept 2027) CCU reduction - Engagement with Llais and hold public consultation. Respond to consultation. | CCU reduction - start process for closure of units.

## Slide 43: Mental Health & Learning Disabilities System Reporting – Off Track Delivery in Q1
Milestones
Scheme/ Project | Delivery Action | Q1 Milestone Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate, Revised milestones to agree
Mental Health Transformation | Implementation of a modern service model with an integrated care pathway across Mental Health Services for the population of Swansea and Neath Port Talbot, following the Stepped Care 2.0 model and in alignment with evidence-based best practice | Develop and agree model | Model is still being worked through via the service redesign workstream. Further discussion taking place with RPB about regional involvement in the service redesign aspect | Neighbourhood model has been presented to Transformation Project Board initially but will need further consideration with RPB structures | Q2 | None
Improvements to digital infrastructure | Implementation of ReQol (Recovery Quality of Life), part of the outcome measures framework for Wales to use across Adult and Older Adult MH services | Embed and Roll Out of ReQol across inpatient wards and ensure consistent data reporting. Training still been rolled out across service group. Some services have implemented | Q1 milestone is essentially an interim measure (paper collection) | Await external bodies to complete the necessary integrations prior to digital collections | Q2 | n/a
Caswell Clinic | BJC scrutiny and capital funding approval required from Welsh Government. | Submitted in Qtr1 but not accepted | Queries received from Welsh Government in relation to the BJC. Further delay caused by absence of independent cost advisor. | Capital Planning working through these queries. Alternative cost advisor being sought. | Q2 | none
Caswell Clinic | Commence operational planning with capital planning and contractors to undertake the work in a live ward environment | Operational planning of service delivery whilst building work is in progress. | Require approved BJC before commencing this detailed preparatory work. | n/a | Q2 | 
Caswell Clinic | Commence building of the HDU facility on Cardigan Ward. | Building work of the first HDU facility on Cardigan Ward | Require approved BJC before commencing this detailed preparatory work. | n/a | Q2 | 
Caswell Clinic | Full commissioning of the HDU facility for patient use | All building work complete | As above | n/a | 2027/28 | 

## Slide 44: Mental Health & Learning Disabilities System Performance
WG Delivery Expectation or Performance Metric | SBU Commitment 26/27 | Baseline position 25/26 | Performance Trajectories 26/27 |  |  |  |  |  |  |  |  |  |  |  | Actual Data |  | 
 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | 
 |  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Implement and evaluate Open Access Mental Health Support by March 2027 | Awaiting metrics to be developed on national basis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Improve safety in Secondary Care Mental Health services (measured through agreed mental health safety matrix and PROM ReQuol) by March 2027 | Awaiting metrics to be developed on national basis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Improve Physical Health of People with long term MH problems by carrying out mortality reviews and implementing improvement plans from the learning by March 2027 | Awaiting metrics to be developed on national basis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 45: CHC AND COMPLEX CARE OVERVIEW
Key Schemes | 
CIP_01-04 | Review, right sizing and repatriation of CHC and Complex Care patients Implement a comprehensive review and rightsizing programme to ensure timely, accurate, and economically sustainable care planning across all CHC and Complex Care
TBC | Pipeline opportunities: Hold cases presented to MH and LD Complex Case panel Out of area Repats
CHC_B_01 | Market Management Deliver recurrent CHC savings by actively managing the market to control inflation, negotiation of high-cost packages, and reduce reliance on spot purchasing
CHC_B_02 | Joint working arrangements Standardise joint funding processes and funding splits in collaboration with Local Authority partners
CHC_B_03 | CHC Operating Model Design and implement a future-ready CHC operating model through a structured transformation programme underpinned by a robust digital case management system
CHC_B_04 | CHC Direct Payments implementation plan
Risks | Mitigations
Lack of centralised digital CHC case management system results in inconsistent data management, increased risk of data loss, payment errors, and missed reviews. | Implement RIO and ADAM - digital case management systems
No agreement between SBUHB and Local Authorities to resolve outstanding | Commission an external review to clear the DST backlog and confirm case responsibility; share proposals early with Directors of Social Services to secure agreement.
Local Authorities refuse to accept the outcome of the external reviews | Share plans regularly with Directors of Social Services; take proposal through the Regional Commissioning Group for endorsement; include cases pending LA input to ensure balanced review
Financial Impact | FYE savings | £0.973M
This will also be addressing growth in demand estimated at £7M |  | 
Our CHC/Complex Care Transformation Programme is a strategic overhaul designed to address rising demand for Continuing Healthcare/ complex care, tackle fragmented commissioning across departments in the Health Board, enhance partnership working with our Local Authority colleagues and strengthen operational and financial sustainability. Our aim is to commission quality services and ensuring out residents are getting the right care in the right place.

## Slide 46: CHC and Complex Care Plan Summary
RAG | Green | Outcomes | Milestones | Amber | Outcomes | Milestones | Red | Outcomes | Milestones | Total | Outcomes | Milestones
 |  | 7 | 2 |  | 1 | 0 |  | 0 | 0 |  | 8 | 8
Achievements |  |  |  |  |  | Challenges |  |  |  |  |  | 
Completed procurement of costing benchmarking tool CareCubed. Training and roll-out for the system will take place during July/ August 2026. Successfully procured digital case management tool for CHC/ Complex Care called Access Adam. Joint Funding Matrix for Learning Disabilities has been jointly designed by the Health Board and Local Authority partners. Testing of the matrix is scheduled for Q2. Effectively engaged with external company to deliver pro-bono desktop review of high cost cases for the Health Board and Local Authorities. Proposal to be endorsed by Transforming Complex Care Programme Board on 21st July 2026 and joint meeting of all partners arranged for 29th July 2026. Local SOP developed for Direct Payments and staff have received training. Funding received from Welsh Government to support implementation of Direct Payments. |  |  |  |  |  | Progress in securing engagement with Local Authorities regarding outstanding reviews has been slower than anticipated. The West Glamorgan Regional Partnership Team is providing support by coordinating a meeting with all relevant stakeholders to facilitate discussion and agreement on next steps. Limited dedicated programme management resource is constraining the pace of delivery and coordination across the work programme. Capacity constraints within both the Corporate Commissioning Team and operational service groups are impacting the ability to progress actions alongside existing business-as-usual responsibilities. Uncertainty regarding future demand for Direct Payments may create additional financial pressure for the Health Board |  |  |  |  |  | 

## Slide 47
Learnings from Q1 | Risks/ Issues | Mitigations
Achieving effective partnership outcomes requires time to co-produce solutions with partners and ensure robust governance processes are appropriately followed | Delay in Local Authorities allocating resource to clear backlog of reviews. Lack of dedicated programme management support The financial benefits achieved to date could be adversely impacted by the emergence of new high-cost cases, potentially eroding existing savings | West Glamorgan Regional Partnership arranging meeting and work t be included in programme for Older Adults Board. Request made to Delivery Unit for support- awaiting outcome. Enhanced scrutiny at Service Group level and via Executive Oversight Panel
Q2 Priorities |  | 
Roll out of CareCubed and integration in process for commissioning new high cost cases and review process for existing high cost cases. Commence implementation of digital case management system Completion of high-cost case desktop review form external company Completion of testing for Joint Funding Matrix Commence work to develop regional fee setting methodology and regional CHC contract in conjunction with Local Authority partners Engage with CAVUHB regarding reciprocal peer review process Commission an external company to provider Support, Advice and Finance Service for the Health Board for Direct Payments |  | 
CHC and Complex Care Plan Summary

## Slide 48: CHC and Complex Care Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
RECOVERY AND SUSTAINABILITY | Review, right sizing and repatriation of CHC and Complex Care patients | Quantify the number of patients awaiting Social Worker allocation (DST) Engage with Swansea LA regarding agreeing a trajectory to clear backlog Agree trajectory for completion of DSTs | Mar-27 | Backlog of disputes cleared and agreed joint process implemented | OFF TRACK |  | Not due for Q1 |  |  | Implementation of jointly trajectory and process to eliminate outstanding DSTs
 |  | Quantify the number of packages currently in dispute over Primary Health Need or HB's contribution to joint package Develop proposal to establish Multi-Agency Peer Review Process with neighbouring HB area Gain agreement from neighbouring HB to support with Multi-Agency Peer Review Process Agree trajectory for completion of peer reviews | Mar-27 | Backlog of disputes cleared | ON TRACK |  | Not due for Q1 | Implementation of reciprocal multi-agency peer review process |  | Clearance of backlog of disputes where there is disagreement over Primary Health Need
 |  | 3 and 12 month reviews to be completed on time. | Mar-27 | Reduction in number of overdue 3 and 12 month reviews | ON TRACK | Continually align capacity to ensure that 3 and 12 month reviews are completed on time | ON TRACK | Continually align capacity to ensure that 3 and 12 month reviews are completed on time | Continually align capacity to ensure that 3 and 12 month reviews are completed on time | Continually align capacity to ensure that 3 and 12 month reviews are completed on time
 | Hold cases presented to MH and LD Complex Case panel REMOVED |  |  |  |  |  |  |  |  | 
 | Out of area repatriations | MH & LD Teams to review CHC cases and identify opportunities to repatriate from out of area placements and to step down from current placement. MH & LD Teams to work with Local Authorities to identify patients to repatriate from out of area placements and to step down from current placement. Identity opportunities to repatriate into vacant capacity Work with Local Authorities to create new opportunities to repatriate and step down (via Regional Accommodation Strategy Group) | Mar-27 | Reduction in the number of out of area MH and LD placements/ packages of care Reduction in spend resulting from repatriation of individuals. | ON TRACK |  | Not due for Q1 |  |  | All identified opportunities to repatriate high cost out of area packages actioned and costs of packages reduced

## Slide 49: CHC and Complex Care Plan Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Market Management |  Procure Care Cubed  Completion of staff training programme  Development of SOP to integrate Care Cubed into review process | Mar-27 | Care Cube integrated into review process for high cost cases (i.e. above CHC baseline) | ON TRACK | Care Cubed licence for 12 months procured | ON TRACK | All staff trained and SOP developed |  | 
 | Joint working arrangements |  Design and test Joint Funding Matrix for LD cases  Develop SOP for Joint Funding Matrix including streamlined DST process  Agree and implement trajectory to clear backlog of disputes based on disagreement with % funding split | Mar-27 | Backlog of disputes cleared | ON TRACK |  | Not due for Q1 | Joint funding matrix designed and SOP developed for implementation |  | Clearance of backlog of disputes where there is disagreement over % funding split
 | CHC Operating Model | Develop invest to save business case for procurement of digital case management system for CHC/ Complex Care With the support of Deloitte identify an optimum operating model for CHC within PCTSG (i.e. District Nursing, Fast Track) Develop case for change including cost of implementation and workforce implications Gain organisational approval on case. Develop implementation plan for new operating model | Jan-27 Mar-27 | Digital case management system (Rio- Adam) procured and implemented. Optimal operating model for Long Term Care designed, agreed and implementation plan in place | ON TRACK |  | Not due for Q1 | Roll out of implementation plan for new digital case management system | Case approved for optimal operating model for CHC within PCTSG | Implementation plan developed for optimal operating model for CHC within PCTSG
 | CHC Direct Payments implementation plan | Develop SOP for Direct Payments Completion of staff training Completion of procurement process to commission external company to provide Support, Advice and Financial transaction for Direct Payments | Sep-26 | Individuals are in receipt of Direct Payments for CHC | ON TRACK |  | Not due for Q1 | Process and structures embedded into HB for the consideration and management of Direct Payments |  | 

## Slide 50: CHC and Complex Care Plan Reporting – Off Track Delivery in Q1
Scheme/ Project | Delivery Action | Q1 Milestone Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate, Revised milestones to agree
Milestones NONE OFF TRACK
Outcomes
Scheme/ Project | Delivery Action | Q1 Outcome Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate,
CHC | Quantify the number of patients awaiting Social Worker allocation (DST) Engage with Swansea LA regarding agreeing a trajectory to clear backlog Agree trajectory for completion of DSTs | Backlog of disputes cleared and agreed joint process implemented | The year-end backlog clearance target is currently rated as off track. An agreed trajectory has not yet been established, and a number of cases remain outstanding, increasing the risk that the year-end position will not be achieved. | Joint meeting facilitated by West Glamorgan Regional Partnership is being arranged asap. Escalation through Transforming Complex Care Programme Board. The Health Board has agreed to prioritise Local Authority cases that require a nursing assessment, with the aim of facilitating progress on Health Board cases in return. | Q2 | No escalation required at present.

## Slide 51: BABIES, CHILDREN YOUNG PEOPLE AND WOMEN OVERVIEW
Performance Outcomes | Confidence assessment
CAMHS TI metrics | Confident to meet the de-escalation criteria
Maternity and Neonates TI criteria | Confident to meet the de-escalation criteria
Further expansion of the Women’s Health Hub model in each health board area by March 2027 (aligned to the Women’s Health Plan | Expansion only if external funding available Mitigation: Should anticipated in‑year funding not materialise services are being consolidated and improved through pathway standardisation, SPOA and self-referral where appropriate, workforce upskilling, digital pathway site, analysis of PNA, primary‑care‑led models that make better use of existing capacity, prioritise prevention, reduce variation and phased implementation
Improving quality of maternity services by reducing peri-natal mortality rates | Unable to predict
Key Schemes | 
PCYPWH_B_01 | Perinatal Improvement Plan Expansion of current paediatric radiology offer Establish elective obstetrics theatre to reduce delays to induction of labour Trauma informed and psychology-led perinatal care All-Wales Perinatal single point of access maternity triage service Perinatal staff experience, wellbeing and retention plan (SEWR) and education and training framework
PCYPWH_B_02 | Maternity Digital Transformation Integration of systems into Maternity Digital Record
PCYPWH_B_03 | Women’s Health Plan Embed national women’s health pathways and reporting against agreed national indicators
PCYPWH_B_04 | Regional Gynae Oncology
PCYPWH_B_05 | CYP and Womens Capital Priorities: Morriston Paediatric footprint redesign and relocation Creation of new Obstetric Suite and Theatres, Singleton
PCYPWH_B_06 | CYP Strategic Programme - Defining vision and objectives for Children & Young People’s Care
PCYPWH_B_07 | CYP Regional Programmes with partners WG: ND Service Improvement Programme and HCW2 RPB: No Wrong Door, NPT PSB: NPT Early Years CYP Strategy Swansea PSB: Ealy Years Programme NPT and Swansea LA Education: ALN
PCYPWH_C_01 | NDD waiting times
Risks | Mitigations
All Wales model for maternity triage detailed workings of model not confirmed. Women’s Health –Guidance on 26/27 Women’s Health Priorities from Women’s Health Network not yet received. CYP - Reduction in ASD or ADHD assessment dependant on Welsh Government funding – currently non recurrent funding received. | Local model in place to ensure single point of access for maternity triage (implemented Feb 26) Anticipated timeline requested from WHN and building flexible planning assumptions
This plan will improve the quality and safety of care for babies, women and families by strengthening maternity and neonatal services, reducing delays, and delivering more consistent, outcomes‑focused pathways

## Slide 52: Babies, CYP and Women's System Summary
RAG | Green | Outcomes | Milestones | Amber | Outcomes | Milestones | Red | Outcomes | Milestones | Total | Outcomes | Milestones
 |  | 18 | 20 |  | 5 | 7 |  | 0 | 0 |  | 23 | 28
Achievements |  |  |  |  |  | Challenges |  |  |  |  |  | 
Perinatal Improvement Programme established with clear governance, 4 workstreams and executive oversight Positive feedback received from Oversight Committee on maternity and neonatal improvements Continued development of Women’s Health Hub model with primary care training delivered Progress towards Gynaecology Oncology Network with C&V and approved service specification CYP Neurodevelopmental waiting times maintained below 156 weeks threshold despite workforce pressures |  |  |  |  |  | Neonatal transport -Interim model maintained - Significant workforce issues and uncertainty of service model moving forward continues Whilst women requiring care outside of maternity SOP is in place and proven to be effective, two site working for Perinatal Services will continue to be a risk for our Tertiary status and our increasing high risk population – options appraisal being compiled Developing sustainable Fertility Services - Continuous workforce issues and risk related to delivery of realigned contract. Workforce significant risk – recruitment plan in progress recruitment restrictions inhibited service in delivering increased activity. Paediatric ward footprint - Interim arrangement of ward environment continues to be an issue |  |  |  |  |  | 

## Slide 53: Babies, CYP and Womens System Summary
Learnings from Q1 | Risks/ Issues | Mitigations
Neurodevelopment service improvements - Learning from utilisation of outsourcing provision from 2024/25 was used to successfully deliver a further funding of outsourced capacity. Workforce continues to be a significant risk into 2026/27 with SBUHB having the smallest and least resources team in Wales together with staffing gaps. Service sustainability remains on risk register Continue to consider how we ensure we capture key strategic actions/achievements which occur through the year – examples around CYP – SARC opening, appointment to key roles Badger successfully launched 31/3/26, Phase 2 will launched on 19th May 2026. Take learning from this project work to improve support for future projects | 1. Fit for Purpose Paediatric accommodation. 2. Women’s Health Hub dependent on Welsh Government funding decision 3. Neonatal Transport governance and funding uncertainty 4. ND workforce capacity constraints | 1. Paediatric accommodation currently on risk-register and maintain escalation to Executive Board. Interim options to be worked through. 2. Await final outcome of Women’s Health funding decision. Meeting now in diaries 3. Continue monitoring and engagement with JCC 4. Currently on risk register; Develop recruitment proposal; Progress with procurement specification to increase capacity
Q2 Priorities |  | 
Revise and re-submit Care Board ToR for approval Progress Women’s Health Hub whilst awaiting Welsh Government funding decision Continue regional gynaecology oncology model development and MDT arrangements Progress CYP Steering Group and workshop programme Develop structured patient voice and engagement approach for development of CYP plan |  | 

## Slide 54: Babies, CYP and Womens System Reporting
Scheme/ Project |  | Delivery Actions 26/27 |  | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  |  | 
 |  |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) |  | Q2 | Q3 | Q4
Perinatal |  |  |  |  |  |  |  |  |  |  |  | 
SERVICE TRANSFORMATION | Perinatal Improvement Plan | Deliver agreed actions from Perinatal Improvement Plan (PIP) Actions include expansion of current paediatric radiology offer, establishment of elective obstetrics theatre to reduce delays to induction of labour, trauma informed and psychology-led perinatal care.) | Deliver agreed actions from Perinatal Improvement Plan (PIP) Actions include expansion of current paediatric radiology offer, establishment of elective obstetrics theatre to reduce delays to induction of labour, trauma informed and psychology-led perinatal care.) | Completed by end of 26/27 | Improved safety, quality, and consistency of maternity care by strengthening clinical practice, governance, and culture thus improving outcomes for women, babies, and families. |  | Continue to deliver agreed recommendations within the 4 programmes of work which include specific milestones and performance metrics. This has been supported by oversight panel for progress and reported to Board. Workshop with Oversight panel held on 18/6/26. |  | Provides updates on key milestones of the Perinatal improvement plan by summarising quarterly achievements reported through to Perinatal Improvement Programme Board chaired by CEO |  | <<< | <<<

## Slide 55: Babies, CYP and Womens System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
BAU/ PERFORMANCE | Perinatal Assessment Recommendations All Wales | Actions will be incorporated into Perinatal Improvement Plan Recommendations include provision of All-Wales Perinatal single point of access maternity triage service) | Mar-27 | Early identification, consistency, and quality of perinatal mental health assessments, ensuring timely, equitable support for parents and better outcomes for families across SBU HB. |  | The All Wales report has been systematically reviewed and benchmarked against current practice. The Perinatal Improvement programme has been refreshed where appropriate. Health Board specific recommendations and delivery plan awaited, expect receipt in July 2026 |  | Provides updates on key milestones of the Perinatal improvement plan by summarising quarterly achievements reported through to Perinatal Improvement Programme Board chaired by CEO | <<< | <<<
 | Maternity Digital Record | Continuing to integrate wider Health Systems into the Maternity Digital Record ultimately improves: Safety Quality Experience, efficiency equity and planning | May-26 | Integration of wider health systems into the maternity digital record improving safety, quality experience. Phase 2 deliverables include integrations of wider clinical safety programmes including WPAS bi-directional feed, LIMS, Viewpoint, and EDT. |  | Implementation went live as well on 19th May 2026 |  | Update against DPIF application for Phase 2 integrations | <<< | <<<

## Slide 56: Babies, CYP and Womens System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
BAU/ PERFORMANCE | Perinatal Workforce Plan to align with HEIW/ HIW | Implement a perinatal staff experience, wellbeing and retention plan (SEWR) | May-26 | A sustainable, skilled, and well‑governed workforce that meets national quality standards, supports service improvement, and delivers safe, effective, and consistent perinatal care across SBU HB. |  | SBU Health Board comments/feedback provided, aim to Benchmark against service specification when published Launch SEWR plan 9th June 2026 |  | Engagement with stakeholders and embed in governance structure | Evaluate Plan with staff feedback | Evaluation completed & BAU embedded
 |  | Develop an education and training framework across SEWR that ensures a competent, confident, and sustainable workforce structured around four pillars—Mandatory & Statutory Training, Essential to Role Training, Continuing Professional Development (CPD), and a Personal Development Offer | Sept-26 |  |  |  |  |  |  | 

## Slide 57: Babies, CYP and Womens System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
BAU/ PERFORMANCE | Sustainability of Jigso Programme | Embed Jigso into Early Years and midwifery service strategic objective | Mar-27 | Sustaining the JIGSO - programme long term would have major, measurable, and system‑wide benefits for the most vulnerable families. These benefits span early childhood development, maternal health, safeguarding, community resilience, and long‑term population health outcomes. Improve outcomes for the most vulnerable children Strengthen parents’ mental, emotional, and social wellbeing Reduce demand on acute and crisis services Tackle entrenched health inequalities Build resilience across families and communities Deliver long-term financial savings to the system Improve population health for future generations JIGSO’s sustainability is not only beneficial—it is foundational to improving long-term outcomes for vulnerable families and reducing inequalities across Wales. |  | Evaluation of JISO undertaken. NPTH LTA Discussions to be held in Q2. Review current and evaluate the differences in local authorities |  | Funding & delivery review completed | Options appraisal to be undertaken | Business case review on Sustainable model that all SBUHB residents received the same level of service
 |  | Maintain co-located, multi-disciplinary team working |  |  |  |  |  |  |  | 
 |  | Develop workforce plan to stabilise and retain specialist roles |  |  |  |  |  |  |  | 

## Slide 58: Babies, CYP and Womens System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) |  | Q2 | Q3 | Q4
WOMENS HEALTH |  |  |  |  |  |  |  |  |  |  | 
SERVICE TRANSFORMATION | Women's Health Plan | Evaluate outcomes from 2025/26 projects | Mar 27 | Improved patient outcomes and equity through earlier diagnosis, reduced waiting times and more efficient use of the workforce through clear, community‑based pathways and person‑centred, evidence‑based care. | Bid submitted to WG for the additional monies – Awaiting update from WG on the allocation of funding Mapping completed against NICE guidelines as normal | Complete formal evaluation of all 2025/26 Women’s Health Hub projects, including access, outcomes, equity, workforce and cost impacts notification from WG received meeting to be arranged to discuss bid ASAP in July. |  | Produce a lessons‑learned and benefits realisation summary and identify projects requiring continuation or sustainability funding beyond March 2026. |  | To be determined following evaluation and funding availability from central | 
 |  | Evaluate whether a business case needs to be developed for any 25/26 projects that require continuation/sustainability in 26/27 |  |  |  |  |  |  |  |  | 
 |  | Align SBU HB services with national contraception and abortion care pathways and NICE guidance |  |  |  |  |  |  |  |  | 
 |  | Align SBU HB services with national contraception and abortion care pathways and NICE guidance |  |  |  | Mapping completed against national pathways and NICE guidance; gaps and inequities identified |  | Priority actions agreed; clinical guidance, referral routes and SOPs updated |  | Revised pathways implemented; staff briefings and education delivered | Impact evaluated; compliance confirmed with audit arrangements in place
 |  | Embed national women’s health pathways and reporting against agreed national indicators/Participate in National System Level impact measure |  |  |  | Baseline assessment completed against national pathways and indicators; data gaps identified |  | Local reporting framework established; data capture improvements progressed |  | Routine reporting commenced; early data used for service improvement | Measured improvement demonstrated; sustainability priorities agreed
 |  | Strengthen local access and outcomes per Women's Health Plan |  |  |  | Local priorities agreed; access inequalities identified |  | Local priorities agreed; access inequalities identified |  | Targeted service improvements reviewed | Measured improvement demonstrated; sustainability priorities agreed

## Slide 59: Babies, CYP and Womens System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) |  | Q2 | Q3 | Q4
WOMENS HEALTH |  |  |  |  |  |  |  |  |  |  | 
BAU/ PERFORMANCE | Sustainable Fertility Services | Maintain robust governance and reporting processes | Mar-27 | Evidenced sustainable, safe and effective services | Robust governance processes maintained | Sustain governance process put in place and reporting through Divisional and HB processes. Deliver agreed recruitment and recovery plan |  | Develop and agree Staff engagement retention and wellbeing plan |  | Launch staff engagement retention and wellbeing plan | 
 |  | Recruit workforce that meets the demand of the service | Sep-26 |  | Workforce review is currently underway in line with funded contract levels |  |  |  |  |  | 
SERVICE TRANSFORMATION | Regional Gynae Oncology | Establish a South Wales Gynae‑Oncology Operational Delivery Network | Q3 2026 | Deliver an agreed South Wales Gynae-oncology service by progressing a sustainable model for Gynae Oncology across Wales in partnership with Cardiff & Vale UHB | Operational meeting held with colleagues from SBUHB and C&VUHB on 15th June 2026 with aim to discuss operational plans and risks. Wider MDT meeting planned. | Establish Workforce workstream and deliver co-designed recommendations Operational Meeting planned for Monday 15th of June with key colleagues in SBUHB & C&V. The aim of this meeting is to discuss operational plans/risks Wider MDT Meeting planned at the end of June |  | Clinical workshop being planned to agree specialist MDT arrangements and processes | Clinical workshop being planned to agree specialist MDT arrangements and processes | Options paper to be developed for shared HIPEC pathway to ensure consistency of access between both surgical centres | Network Launch Plan

## Slide 60: Babies, CYP and Womens System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  |  | 
 |  |  |  |  |  | Q1 |  | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
CYP |  |  |  |  |  |  |  |  |  |  | 
SERVICE TRANSFORMATION | Develop a Children & Young Peoples and Babies Plan | Develop a CYP Plan, setting out the strategic vision and objectives for Children & Young People’s Care | Mar-27 | More integrated, efficient, and equitable care that improves outcomes and experiences for children, young people, and their families. | Inaugural and second Board meetings held during qtr 1. CYP Steering Group first meeting also held on 24/6/26 | Implement inaugural Babies, Women's and Children's Care Board 27/4/26 | Implement inaugural Babies, Women's and Children's Care Board 27/4/26 |  | Establishment of a CYP Steering Group | Workshops to be held to inform development of CYP Plan | Workshop to be held to inform development of CYP plan
 | Regional CYP Programmes | WG: ND Service Improvement Programme including accommodation improvements |  | More coordinated use of resources and delivering better, more sustainable outcomes for children and their families across the region. | Maintained no patients waiting over 156 weeks as per agreed target | Commencement of procurement process to invest NDIP funding allocation | Commencement of procurement process to invest NDIP funding allocation |  | Continue with procurement process | Commence outsourcing | Conclude outsourcing
 |  | WG: HCW2 |  |  | Await WG sign-off of CYP Transfer of Care from Health Visiting to School Nursing pathway |  |  | Welsh Government workshop for sign-off of transfer of care framework delayed until 29th June | Implement a seamless transition pathway for children aged 5-7 from Health Visiting to School Nursing | Implement a seamless transition pathway for children aged 5-7 from Health Visiting to School Nursing | Continue implementation of transition pathway for children aged 5-7 from Health Visiting to School nursing
 |  | RPB: No Wrong Door, |  |  |  | Per RPB NWD Project co-ordinator workplan | Per RPB NWD Project co-ordinator workplan |  | Per RPB NWD Project co-ordinator workplan | <<<< | <<<<
 |  | NPT PSB: NPT Early Years CYP Strategy |  |  |  | Continue to contribute to the of the NPT Early Years, CYP Plan | Continue to contribute to the of the NPT Early Years, CYP Plan |  | Continue to contribute to the of the NPT Early Years, CYP Plan | Continue to contribute to the of the NPT Early Years, CYP Plan | 
 |  | Swansea PSB: Early Years Programme |  |  |  | Agree 2026/27 Priorities and develop milestone plans | Agree 2026/27 Priorities and develop milestone plans |  | Continue to contribute to the of the NPT Early Years, CYP Plan | <<<< | <<<<
 |  | NPT and Swansea LA Education: ALN |  |  |  |  |  |  |  |  | 

## Slide 61: Babies, CYP and Womens System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
CYP |  |  |  |  |  |  |  |  |  | 
BAU/ PERFORMANCE | NDD Service development | Ensure workforce meets population needs in line with NICE guidance | Mar-27 | Continue to reduce waiting times for children and young people awaiting ASD or ADHD Assessment |  | Tendering exercise completion |  | Commence outsourcing cohort 2026.27 | Embed All Wales ND Standards into practice and undertake workforce planning to align | Strengthen delivery of ND Standards through the continued implementation of workforce plans that support a resilient and sustainable service
 |  | Scope opportunities to provide a more appropriate environment to undertake ADHD and ASD assessments my minimising distraction and over-simulation | Mar-27 |  |  | Meeting with RPB to explore options |  | Continued engagement with RPB / Local Authority colleagues regarding options to deliver ND assessments within the Community/wellness hubs | Continued engagement/scoping to deliver ND services within Community/wellness hubs ensuring alignment to All Wales ND standards | Continued engagement/scoping to deliver ND services within Community/wellness hubs ensuring alignment to All Wales ND standards

## Slide 62: Babies, CYP and Womens System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
 | Transition | Gap analysis of transition process across CYP. |  | Implementation of the transition guidance within children services. Monitoring of compliance and patients' outcomes with governance reporting to corporate transition lead. | Gap analysis completed | Gap Analysis completed |  | Development of Task & Finish Groups Undertake a detailed review of existing transition pathways to highlight service variation , gaps , risks and opportunities for improvement across all specialities. | Benchmark against specialities such as diabetes and cystic fibrosis service to identify transferable learning and embed excellence across service. | Transition Group meeting undertaken to identify leads in specialties. Therapies, CAHMS ND and community . Review of all Toolkits are in current use. LA leads and parent carers to be invited to future meetings. Governance structure to be approved when corporate lead is identified.
 |  | Transition lead for services nominated | Mar-27 |  |  | Transition Lead corporate assigned. Vicki Burridge leads in CYP services and transition lead in services to be aligned as per policy |  | Outcome of subgroups to be agreed by the next quarter. | Senior operational Lead in each service within CYP. | Designated at serviced level take a key role in co-ordinating and promoting continuity and integration of the CYP health care. To lead throughout the transition , handover process and for six months post transition.

## Slide 63: Babies, CYP and Womens System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
CYP |  |  |  |  |  |  |  |  |  | 
BAU/ PERFORMANCE | Transition | Transition and hand over tools to be implemented. | Mar-27 | Implementation of the transition guidance within children services. Monitoring of compliance and patients' outcomes with governance reporting to corporate transition lead |  | Create practical tools to support transition planning including young person led information and communication resource. |  | Rising 16 THP review To be implemented and monitored at service level | To be implemented across all services utilising principles of transition toolkit | Provide education on national guidance roles and accountability documentation expectations and best practice models for transition and handover.
 |  | Governance structure to report compliance of guidance , patient experience to Service Group and CYP steering Group | Mar-27 |  |  | Governance structure in draft and will require approval through the SLT for CYP and the service group | Initial CYP Steering Group meeting scheduled for 24th June with the aim of review ToR and agreeing the scope of the CYP Plan Workshop dates have also been circulated for the development of a CYP Plan | Monitoring through Complaints / concerns Putting things Right and Early resolution process through existing service group governance structures and reporting PROMs / PREMs to evaluate experience of transition reporting through to service group quality safety and risk Group quarterly Training compliance Annual Audit Programme Digital Tracking of Transition Cohort | Compliance reporting to Welsh Government Through Quality Safety and Risk Group ( end of 2-year implementation period) | 

## Slide 64: Babies, CYP and Womens System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
CYP |  |  |  |  |  |  |  |  |  | 
 | Transition | Regional partnership transition board Bayouth co-produce patient engagement Document | Mar-27 |  |  | Working on a policy for transition |  | Co production at service level to be coordinated with regional partnership boards. | Create a digital dashboard to track transition readiness, pathway compliance , training completion , outcomes and patient experience measures. | Create a digital dashboard to track transition readiness, pathway compliance , training completion , outcomes and patient experience measures.
 | CYP and Women's Capital Priorities | Deliver a revised robust plan for the future relocation of Paediatric in-patient services at Morriston Hospital | Mar-27 | Safer, streamlined paediatric pathways, and a better environment for children and their families | Discussions are ongoing | Ensure this is a priority on capital schemes of Health Board and discussed at newly formed Capital Group meeting |  | Continue to ensure this is a priority on capital schemes of Health Board and discussed at newly formed Capital Group meeting | Actions to be determined following discussion as Capital Group meeting | Actions to be determined following discussion as Capital Group meeting
 |  | Provide a new Midwifery Lead Unit and specialist Obstetrics Theatres in Ward 18 Singleton Hospital | Mar-27 | Provision of modern efficient and user friendly midwifery led unit and specialist obstetrics theatres which meets up to date guidelines. | Discussions on-going in view of Independent Report - 2 Site Working | Discussions on-going in view of Independent Report with Two Site Working |  | Completion of optional appraisal | Actions to be determined following outcome of options appraisal | Actions to be determined following outcome of options appraisal

## Slide 65: Babies, CYP and Womens System Reporting– Off Track Delivery in Q1
Scheme/ Project | Delivery Action | Q1 Milestone Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate, Revised milestones to agree
Sustainability of Jigso Programme | Review current and evaluate the differences in local authorities | Evaluation of JISO undertaken. NPTH LTA Discussions to be held in Q2 | Delay in meeting with NPTH LTA | Service has redirected some resource to sustain current provision. Review of whole safeguarding provision to be undertaken and direct resources where appropriate | Q2 | None
Women's Health Plan | Evaluate whether a business case needs to be developed for any 25/26 projects that require continuation/sustainability in 26/27 Evaluate whether a business case needs to be developed for any 25/26 projects that require continuation/sustainability in 26/27 | Formal evaluation of all 2025/26 Women’s Health Hub projects completed. WH Bid submitted for 26-27 | Awaiting approval of WH Bid (£200k) which was submitted to WG on 26.5.26 Once approved we can appoint Clinical Leads and pick up formal evaluation and phase 2 of certain projects | WG have been approached and assure that a formal response will be made early Q2 | Q2 if bid is approved | None
 | Embed national women’s health pathways and reporting against agreed national indicators/Participate in National System Level impact measure | Baseline assessment completed against national pathways and indicators; data gaps identified | The Data Task and Finish Group are still working through data gaps | A workshop is being set up to identification and collection of women’s health data across the whole system pathway | Q2 | None
Regional Gynae Oncology | Establish a South Wales Gynae‑Oncology Operational Delivery Network | Regular operational meetings held on progress, risks etc. established. MDT Meeting cancelled – to be rearranged in July/August | MDT Meeting to be rearranged with wider stakeholders | Operational meetings continue to be success | Q2 | Cardiff and Vale UHB have experienced the loss of two Gynaecological Oncologists, creating a workforce risk and impacting the sustainability and resilience of the regional Gynaecological Oncology service model. Recruitment is underway, with consultant posts currently out to advertisement.

## Slide 66: Babies, CYP and Womens System Reporting– Off Track Delivery in Q1
Scheme/ Project | Delivery Action | Q1 Milestone Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate, Revised milestones to agree
Sustainable Fertility Services | Recruit workforce that meets the demand of the service | Nursing workforce review has been completed, supported by a comprehensive demand and capacity assessment aligned to service tasks and activity requirements. Reviews of all other staff groups are now underway using the same robust methodology to ensure a consistent and evidence-based approach across the service. | Staffing deficits have necessitated the prioritisation of clinical service delivery, resulting in delays. Workforce shortages continue to present challenges in delivering contracted activity and maintaining service capacity. | The Head of Service and Service Manager continue to undertake preparatory work to support the review process, ensuring that the requirement for expert clinical input is kept to a minimum. SEWR plan in development following x2 staff engagement initiatives. | Q3 | none
CYP and Women's Capital Priorities | Deliver a revised robust plan for the future relocation of Paediatric in-patient services at Morriston Hospital | Ensure this is a priority on capital schemes of Health Board and discussed at newly formed Capital Group meeting | Discussions still ongoing | Actions to be determined following discussion as Capital Group meeting | Actions to be determined following discussion as Capital Group meeting | Actions to be determined following discussion as Capital Group meeting
Milestones

## Slide 67: CAMHS System Performance
WG Delivery Expectation | SBU Commitment 26/27 | Baseline position 25/26 | Performance Trajectories 26/27 |  |  |  |  |  |  |  |  |  |  |  | Actual Data |  | 
 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | 
 |  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral | Maintain TI Target |  | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 87% | 61%
70% of therapeutic interventions started within 28 days following an assessment by LPMHS | Maintain TI Target |  | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 89% | 82% | 84%
85% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan | Maintain TI Target |  | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 88% | 95% | 94%

## Slide 68: PRIMARY CARE AND COMMUNITY OVERVIEW
Performance Outcomes | Confidence assessment
% population receiving NHS dental care | Maintain
% Community Pharmacies providing Pharmacist Independent Prescribing Services | Maintain
Financial Impact | FYE £ Savings | £0.7M
Key Schemes | 
CIP_29 | Review National Exercise Referral Scheme (Physio and COPD services)
CIP_30 | Review Primary Care Audiology Services
TBC | Pipeline opportunities: Review Integrated Sexual Health
PCC_B_01 | Digital Transformation in Primary Care
PCC_B_02 | HMP Swansea Improvement Plan
PCC_B_03 | Dental Services Implement Community Dental Service changes to safeguard access, capacity and sustainability by optimising pathways, reconfiguring clinics, reducing waiting times, improving workforce retention and strengthening workforce planning Maintain access and waiting times for Specialist Dentistry services
PCC_B_04 | Primary Care Estates Refresh of Primary and Community Estates strategy and Progress Primary Care Estates proposals: Croserw Ty'r Felin Participate in development of Swansea Wellness Hub
PCC_B_04 | General Medical Services
PCC_B_05 | Community Optometry Services Continued implementation of Optometry Contract Reform and increase capacity and coverage for WGOS Levels 4 & 5
We aim to provide equitable, safe and timely access to high‑quality, data‑driven care that supports people to stay well and receive the right help at the right time. We seek to deliver coordinated, person‑centred services that improve outcomes, reduce inequalities, and empower individuals to manage their health effectively.
Risks | Mitigations
Significant programmes of work requiring capacity building in the community including the transfer of resources/ staff into the community | SBUHB Clusters considered mature in providing excellent footprints for the delivery of services that it would not be prudent to operate in all community. Developing Primary Care and Community at the heart of the CSSP. Key forums i.e. Pan Cluster Planning Group and Community by Design Group identifying opportunities and unlocking barriers to drive forward further service change.
Limitations in Primary Care Estates | Development of strategy is key priority, as well as capital development projects in train to invest in primary care estates.
Access to diagnostics and digital capability in Primary Care | Close alignment with Planned Care/Diagnostics/ Digital programme to take forward opportunities to improve access, communication and digital capability - including systems and intelligence sharing.
Significant contract reform being undertaken simultaneously | Involvement in national working groups/ Close communication with primary care practices and their representative bodies.

## Slide 69: Primary Care and Community System Summary
RAG | Green | Outcomes | Milestones | Amber | Outcomes | Milestones | Red | Outcomes | Milestones | Total | Outcomes | Milestones
 |  | 12 | 12 |  | 1 | 1 |  | 0 | 0 |  | 16 | 16
Achievements |  |  |  |  |  | Challenges |  |  |  |  |  | 
Continued engagement with DHCW around a plan for the implementation of the Ophthalmic e-Referral system Ongoing work in HMP Swansea to work towards achievement of actions / recommendations from HIW Governance review Continued implementation of the new Dental contract Progress against Oral Surgery and Oral Medicine review Progress the refresh of Primary and Community Estates strategy Continued implementation of Contract Reform for GMS Continued roll-out of Optometry Contract Reform Re-integration of Virtual Wards and Acute Clinical Team Progress the Community By Design initiatives |  |  |  |  |  | Support the Health Board Programme to , procure and implement Electronic Patient Record (EPR) system across Community Services and Allied Health Professionals in order to improve quality and safety of communities through a 'one system' approach – Discovery workshop delayed to Q2 Reporting ‘green’ in terms of Annual Plan actions ie - Supporting national work around securing a Sexual Health replacement digital system. The National programme does not appear to be progressing and the Service Group and Digital team are reassessing the current plan of mitigation re managing via an ‘unsupported’ IT system. Reporting ‘green’ in terms of Annual Plan actions to progress to maintain Dental waiting lists and review of Oral Surgery and Oral Medicine, however, performance data for Restorative Dentistry (no longer maintaining at 26 weeks), Community Dental Service (new and recall) and Special Care Dentistry (Paeds and Adults) remain challenging. Limitations that cost savings targets are putting on development plans e.g Not offering frailty DSS to new practices and considering changes to Ophthalmology pathway to Optometry due to forecast overspend on Optometry contract |  |  |  |  |  | 

## Slide 70
Learnings from Q1 | Risks/ Issues | Mitigations
Monthly monitoring of progress against the annual plan supports early identification of concerns and opportunities to recover Health Board reporting timelines do not always align with Service Group governance and sign off. Reliance on external bodies to support progress can result in delay in delivery Reporting process for PCT Group other System Plans need developing | N/A – identified in challenges | N/A – identified in challenges
Q2 Priorities |  | 
Maintain progress against Q2 milestones and key deliverables Continued monitoring of service performance and development and implementation of recovery plans to support the achievement of year-end Delivery Actions. Consider options for Dental recovery with support of the Planned Care Recovery fund. Continued focus on improving Service Group Finance position Engagement on Cluster configuration Continued progress against Community By Design initiatives (Breathlessness, Dermatology, 0.5% Frail, Dental) Review options to deliver optometry activity within the contract regulations into Q2 and beyond whilst also maintaining balanced budget. |  | 
Primary Care and Community System Summary

## Slide 71: Primary Care and Community System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
RECOVERY AND SUSTAINABILITY | Review National Exercise Referral Scheme (Physio and COPD services) | Awaiting the outcome of the review of the Quality Impact Assessment before any actions can be agreed |  |  |  |  |  |  |  | 
 | Review Primary Care Audiology | Awaiting the outcome of the review of the Quality Impact Assessment before any actions can be agreed |  |  |  |  |  |  |  | 
 | Review Integrated Sexual Health | Awaiting the outcome of the review of the Quality Impact Assessment before any actions can be agreed |  |  |  |  |  |  |  | 
SERVICE TRANSFORMATION | Digital Transformation in Primary Care | Support the development of a business case to enable SBUHB to Procure Electronic Patient Record for Community Health Teams | Mar-27 | Business Case developed and approved to proceed to procurement phase. |  | Discovery workshop agree scope and identify requirements |  | Develop a business case in line with the funding decision expected from Welsh Government | Continued stakeholder engagement to inform business case development | Approval of business case.
 |  | Support the Implementation of Ophthalmic e-Referral System | Mar-27 | Implement the Ophthalmology e-referral solution; reducing time to patient triage and consultation. |  | Continued support and engagement with DHCW to agree a plan for deployment |  | Deployment dependent on DHCW progress and decision |  | 
 |  | Support the national discovery work as part of national programme to secure a Sexual Health Replacement System | Mar-27 | Full engagement with the national roll-out |  | TBC based on Public Health Wales 3rd party provider project plan |  | TBC based on Public Health Wales 3rd party provider project plan | TBC based on Public Health Wales 3rd party provider project plan | TBC based on Public Health Wales 3rd party provider project plan
 | HMP Swansea Improvement Plan | Continued progress within HMP Swansea against actions/recommendations from HIW Governance Review (2022), HIW Death in Custody / Death after Custody recommendations, alongside progress of the Health Needs Assessment (PHW 2024) and Mental Health and Substance Misuse (QNPMHS 2024) | Mar-27 | Reduction in red-rated actions within Health Board control Priority statutory actions (HIW, Death in Custody etc) delivered and on track Demonstrable reduction in workforce-related HIW actions from Q3 following implementation of 2 WTE posts. |  | Consolidated action plan confirmed and baselined Governance and reporting framework embedded Key risks (including workforce) escalated |  | First formal quarterly assurance report via PHSG Workforce uplift in place (2 WTE streamliner posts by end of Q2 Progress on priority statutory and health protection actions | Expected risk reduction in workforce-related HIW actions Reduction in red-rated actions Evidence of improved governance and incident learning | ≥90% of actions on track/complete Annual assurance report to Prison Partnership Board Clear position on residual risks and system constraints

## Slide 72: Primary Care and Community System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Dental Services | Implementation of new dental contract regulations to maintain access | Mar 27 | Continued access to general dental services/ improved access for new patients registering on the Health Board dental access portal |  | Issue allocation of new dental patients to dental practices in accordance with the new regulations. Commence retendering of West Coast dental activity |  | Monitor dental activity against the new regulatory metrics and consider whether contract metrics need adjusting / commence mid year review visits. Review budgetary position on patient charge revenue. | Monitor dental activity against the new regulatory metrics and consider whether contract metrics need adjusting / undertake mid- year review visits. Complete commissioning of West Coast activity. | Monitor dental activity against the new regulatory metrics and consider whether contract metrics need adjusting / undertake mid- year review visits. New dental practice scheduled to open in NPT.
 |  | Maintain access and waiting times for Specialist Dentistry services, including SCD - POHW GA lists, Oral Surgery and Oral Medicine. |  | Waiting times for SCD, Oral Surgery and Oral Medicine, are maintained |  | Complete Job Plan for New Paediatric Specialist. Complete capacity and theatre modelling for Paeds GA. Produce recovery plan for SCD 104 week wait. Progress service review of Oral Surgery (OS) and Oral Medicine (OM). |  | Waiting times and activity monitored. Complete service review of OM and OS. | Waiting times and activity monitored. Subject to outcome of service review, seek approval for final OM and OS model | Waiting times and activity monitored. Subject to outcome of service review and approval, progress planning for procurement for OS and OM service.
 |  | Implement Community Dental Service changes to safeguard access, capacity and sustainability by optimising pathways, reconfiguring clinics, reducing waiting times, improving workforce retention and strengthening workforce planning |  | Waiting times for CDS pathways are maintained or reduced |  | Commencement of new workforce, including Paeds Specialist. Present to staff outcome of staff engagement and scope and objectives for CDS changes. |  | Establish relevant TFGs to implement agreed changes | TFG operational with agreed plans and priorities in place | Implementation in progress or completed as part of business as usual.

## Slide 73: Primary Care and Community System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Primary Care Estates | Croeserw development | Mar 27 | Fully tendered scheme to develop BJC |  | Confirm SRO arrangements with NPT Council |  | Hold project board and agree final design | Go out to tender | Begin approval process
 |  | Ty’r Felin development | Mar 27 | Agreed and costed scheme in place to extend building in 27/28 |  | Agree revised site layout |  | Agree GMS rental levels | Scheme agreement/approval | Subject to scheme agreement, building works commence
 |  | Refresh of Primary and Community Estates strategy | Mar 27 | An agreed refreshed prioritised strategy in place |  | Senior management workshop to agree principles |  | Task and finish group established to review required service changes to support service delivery | Draft prioritisation produced for engagement | Finalise prioritisation for refreshed strategy
 |  | Participate in development of Swansea Wellness Hub | Mar 27 | Contribution to a clear short term and medium-term strategy for central clinic |  | Engage in wellness hub planning with corporate and estates colleagues. |  | Review space and utilisation rates in central clinic | Engage in wellness hub planning with corporate and estates colleagues. | Engage in wellness hub planning with corporate and estates colleagues.
 | General Medical Services | Implementation of Contract Reform for GMS | Mar 27 | Contract reform changes successfully implemented in accordance with directions. |  | Implement workforce fund. Obtain decision on the commissioning of the 0.5 most at risk DSS |  | Prepare for implementation of the Change fund | Prepare for implementation of the Directed Supplementary Service for Collaboration | Commence implementation of the DCSS.
 | Community Optometry Services | Continued implementation of Optometry Contract Reform and increase capacity and coverage for WGOS Levels 4 & 5 | Mar 27 | Increase the number of opticians providing WGOS 4 and 5 especially in the clusters of low provision as set out in the eye care report |  | Review of community optometry budget for capacity to extend services further |  | Rollout of HCQ pathway / Encourage uptake of WGOS 4 and 5 | Rollout of HCQ pathway / Encourage uptake of WGOS 4 and 5 | Rollout of HCQ pathway / Encourage uptake of WGOS 4 and 5

## Slide 74: Primary Care and Community System Reporting– Off Track Delivery in Q1
Scheme/ Project | Delivery Action | Q1 Milestone Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate, Revised milestones to agree
Digital Transformation in Primary Care | Support the development of a business case to enable SBUHB to Procure Electronic Patient Record for Community Health Teams | Discovery workshop agree scope and identify requirements | Workshop delayed | Workshop arranged for Q2 | Q2 | Agree revised milestone (noting this is Digital, MHLH and PCT delivery action)
Milestones
Outcomes
Scheme/ Project | Delivery Action | Q1 Outcome Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate,
See above |  |  |  |  |  | 

## Slide 75
POPULATION HEALTH AND PREVENTION OVERVIEW
Key Schemes | 
PH_B_01 | Healthy Weight/ Obesity Services Building sustainable weight management services to meet present and future need. Building opportunities for healthy weight and wellbeing in pregnancy to improve maternal and neonatal outcomes Prioritisation of GLP-1 provision and Level 3 service wrap around support System‑Wide Collaboration to support healthier behaviours
PH_B_02 | Tobacco Control Building sustainable services to meet present and future need.
PH_B_03 | Diabetes Programme Tackling Diabetes Together programme – reducing inequity in most deprived communities Review resource allocation within the diabetes pathway (primary to secondary care) by adopting the STAR (socio-technical allocation of resource) methodology Prevention of Type 2 diabetes onset and remission - Structured education programmes to enable improved self-management of diabetes Community diabetes model redesign Expand hybrid closed loop approach for Type 1 diabetics
PH_C_01 | Vaccinations and Screening Increase uptake and decrease inequity in Vaccinations and Screening
PH_C_02 | Healthy Child Wales Programme
Financial Impact
Prevention and Early Years funding allocation for WG priorities tobacco control and healthy weight services Diabetes: Expected to deliver within existing resources or re-allocation of resources
Performance Outcomes | Confidence assessment
Increase the proportion of children in Wales who are a healthy weight by halting the rise and contributing to a year-on-year decrease in the levels of overweight and of obesity as measured and reported through the National Child Measurement Programme, focusing on those most disadvantaged. | Annually reporting metric
Reduce inequity in the uptake in the most and least deprived areas in preventing ill-health especially in relation to vaccination, screening and diabetes prevention and care. | Annually reporting metric
Increase in % of patients (aged 12 years and over) with diabetes who received all eight NICE recommended care processes | TBC data for T1 diabetes under review
Risks | Mitigations
Diabetes: Demand for services is expected to increase – additional investment not available PEY funding - confirmed for 26/27 but uncertain from 27/28 | Reviewing allocation of resources across the pathway
Our goal is to expand prevention, early intervention and evidence‑based pathways reducing inequities, improving management of long‑term conditions like diabetes, and ensuring more consistent, proactive support across the life course

## Slide 76: Population Health and Prevention System Summary
RAG | Green | Outcomes | Milestones | Amber | Outcomes | Milestones | Red | Outcomes | Milestones | Total | Outcomes | Milestones
 |  | 10 | 13 |  | 5 | 1 |  | 0 | 1 |  | 19 | 19
Achievements |  |  |  |  |  | Challenges |  |  |  |  |  | 
Population health and prevention system Collaborative working between Public Health Team and Service Delivery Groups Healthy Weight/Obesity services Progress on development and strengthening the adult weight management pathways, including increased onboarding of patients to the digital Level 3 commercial service (Roczen) with early outcomes suggesting positive results in self-reported indicators Maternal Healthy Weight group established to explore how to meet unmet need Continued implementation of a Whole Systems Approach to healthy weight through strong stakeholder engagement on the public sector food procurement regional focus. Tobacco Control Continued to deliver Help Me Quit services (although with a reduced capacity for in hospital and maternity) Diabetes Programme (including prevention) Delivery of evidence-based diabetes prevention programme to high-risk population Establishment of group to support strategic direction of diabetes in health board Vaccinations and Immunisations Continue to support the immunisation system in collaboration with key stakeholders. Targeted interventions in areas of low vaccine uptake across the life course to reduce gap between least and most deprived areas Screening Development work completed to commence a collaborative feasibility pilot between primary care and health board immunisations team, to proactively contact non-responders for symptomatic bowel screening FIT testing Healthy Child Wales Programme Part 1: Reviewed compliance of contacts and compliance monthly, improvement plan and focus developed for areas with reduced contacts for 3.5 year olds (current compliance 88.5%). Healthy Child Wales Programme Part 2: Attended WG workshop 29 June 2026, programme plan being developed by WG and will be shared with HB. Implementation of HCWP2 to continue, areas of high risk to be identified, RAG to be updated. RAG with WG clarity by 31 July |  |  |  |  |  | Healthy Weight/Obesity services Delays in reaching consensus on key decisions which impact the adult weight management pathway onward development, including final agreement on the GLP-1 prioritisation provision for weight management, and the funding allocation for Prevention and Early Years (PEY) Funding to enable procurement of further adult weight management services for Level 2 and Level 3 Awaiting national announcement and directive for Obesity Innovation funding to inform local work Tobacco Control Recruitment restrictions for PEY funded posts have had impact on service capacity, reducing the opportunities for patient contacts and likelihood of meeting Welsh Government targets, as well as risking underspend of grant funding for 26/27 General capacity across HMQ and public health limited opportunity to further develop prevention and evaluation activity Diabetes Programme (including Prevention) Challenges in onward delivery of the Diabetes Prevention Programme model due to co-occurring reductions in funding from multiple funding streams Vaccinations and Immunisations Expansion of existing vaccination programmes and addition of new vaccination programmes Reduction in funding may impact on which initiatives the immunisation team can fully support. Screening There is insufficient capacity in the public health team to be resilient to staff sickness Healthy Child Wales Programme Part 2: Concerns around full implementation for future quarters. The highest risks are for special schools and those Educated Other Than At School (EOTAS). General – Prevention and Early Years Funding Establishing oversight and governance where the funding decisions, delivery, and monitoring is across different directorates/service groups |  |  |  |  |  | 

## Slide 77
Learnings from Q1 | Risks/ Issues | Mitigations
Importance of establishment of clear oversight and governance arrangements Important to set out clear responsibilities and ownership for cross-directorate working Short-term funding challenges compounded by delays in recruitment Improvements could be identified in management of the recruitment into externally funded fixed-term roles to minimise risk of disruption to externally funded services and risk of underspend Complexity of national and local accountabilities in screening system (across screening programme delivery, pathways, data, research and improvement programmes ) are a key dependency Delivery of increasing uptake and reducing inequality need to take a whole systems approach in order to identify opportunities for impact. There is a need to ensure that we identify and mitigate any unintended consequences of options for improvement. | Delays in final executive approval to release on Trac vacant posts (PEY funded) to support delivery of maternal and hospital smoking cessation services in SBUHB. | 1. Existing staff have been trained in both Help Me Quit in Hospital and Maternity, so can provide some cross-cover, but service offer decreased.
Q2 Priorities |  | 
Achieve consensus on the Prevention and Early Years Funding with a paper to Executives by the end of July 2026 to allow progression of funded activity to strengthen meeting the needs of the population for Healthy Weight and Tobacco Control Achieve consensus on the GLP-1 paper for weight management services in Q2, to enable prioritisation of resources and implementing evidence-based highest-value activity for the population Collate qualitative feedback and action plan through community engagement/co-production exercise by end Q2 (September 2026), through the Maternal Healthy Weight Group, to establish priority actions for maternal healthy weight, for delivery in Q3/Q4. Recruitment to the vacant Help Me Quit PEY funded roles, to enhance delivery of smoking cessation towards Welsh Government targets, and where capacity allows exploring the wider Tobacco Control prevention agenda. Continued delivery of the Diabetes Prevention Programme through the PCTSDG, minimising impact from reduced funding; to review using referral in model rather than practice based patient searches with engagement from primary care. Continued delivery of Vaccination and Immunisations and Healthy Child Wales work programmes Action plan in development on delivery of the Breakthrough Objective on Bowel Screening Initiation of the feasibility pilot for symptomatic non-responder Bowel Screening FIT test follow up in collaboration with primary care Collective cross-system action to support prevention including referrals into Help Me Quit services, healthy weight signposting, promoting vaccination/immunisations and screening, and other preventative initiatives such as Making Every Contact Count. |  | 
Population Health and Prevention System Summary

## Slide 78: Population Health and Prevention System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
RECOVERY AND SUSTAIN-ABILITY | Review Nutrition & Dietetics services and Diabetic Pump Growth |  |  |  |  |  |  |  |  | 
SERVICE TRANSFORMATION | Healthy Weight/ Obesity Services | Develop an accountable governed pathway approach to the management of GLP/GIP-1RAS prescriptions for obesity within SBUHB, in line with Welsh Health Circular WHC/2025/043. |  | The GLP1 business case is going to PFAG on May 20th and a decision will be made on outcome at that point. To align access to obesity intervention as outlined in the WHC/2025/043; Meet the requirements for access to obesity intervention as outlined in the NICE NG28 guidance-Diabetes |  | Decision on options paper submitted; Agreement on model of delivery, waiting list management; and funding due July 2026 |  | Delayed -Dependent on Exec decision on GLP1 Options Paper |  | 
 |  | Implement Blueteq for prescription monitoring of GLP1RAs prescribed for purposes of weight loss |  | Implementation of Blueteq will also be agreed June 2026 |  |  |  |  |  | 
 |  | Implement continuous monitoring of Level 2 and anti-obesity medication clinic Level 3 waiting lists and explore the benefits of a controlled temporary referral pause when demand exceeds safe service capacity |  | Decision on whether to close Level 2 ongoing following a validation of waiting list process. Anti-obesity medication provision waiting list closure to be decided in management panel, estimated June 2026 |  |  |  |  |  | 
 |  | Develop an enhanced healthy pregnancy offer for healthy weight and wellbeing |  | Setting up a task and finish group to plan a pilot project for 26/27 for maternal weight management delivery (PEY 26/27 funding only). In-house service funding to be determined June 2026 |  | Task and finish Maternal WM Working group to be established to outline Pilot Project |  | Begin coproduction and community engagement Agree PEY funding Agree, risk stratify and begin pilot projects |  | Evaluate pilot projects for best value and explore long term sustainability
 |  | Based on output of GLP-1 OA: •Repeat of 25-26 tender exercise to recommission Level 3 wrap around service with added psychology input as per findings of current service provision •Explore funding for in-house service - Commission L2 service to meet current waiting list demand following validation process |  | Decision to be made July 2026 |  | Decision to be made July 2026 |  | Dependent on Exec board panel decision |  | 
 |  | Delivery of wider system activity working with partners around the Whole System Approach to Healthy Weight |  | Regular reporting on progress to Public Health Wales and Welsh Government as per standardised reporting templates |  | Delivery against the Whole Systems approach workplan |  | Delivery against the Whole Systems approach workplan | Delivery against the Whole Systems approach workplan | Delivery against the Whole Systems approach workplan
 |  | Engagement and support to nationally led Obesity programmes to support local delivery of the All-Wales Weight Management Pathway and other relevant programmes |  | To be determined |  | Await announcement for nationally led programme work |  | Establish work plan as relevant following national announcement to develop local implementation plan | TBC | TBC

## Slide 79: Population Health and Prevention System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Tobacco Control | Continue delivery of Help Me Quit services through Health Board and Primary Care (community pharmacy). | Ongoing | Proportion of smokers accessing Help Me Quit services annually (Target 7.5% - Updated Welsh Government target for 2026/27) Quarterly reporting to Welsh Government: Number of smokers treated by the smoking cessation service during the quarter; Number of treated smokers followed up at their 4 week post quit date and who were CO validated as successfully quitting during the quarter |  | Continued delivery of Help Me Quit Services |  | Continued delivery of HMQ services | Continued delivery of HMQ services | Continued delivery of HMQ services
 |  | Ongoing development and embedding of Maternal and Hospital Smoking Cessation Services in SBUHB |  | Number (%) of vacancies in services. |  | Recruitment to vacant (PEY funded) posts to support delivery of maternal and hospital smoking cessation services in SBUHB |  | Continued delivery of HMQ services and onward recruitment of any remaining vacancies | Continued delivery of HMQ services | Continued delivery of HMQ services
 |  | Delivering health promotion/ tobacco control prevention activity across the health board including in hospital, community, and schools. |  | Report on tobacco control prevention activity in the Health Board (see Public Health workplan) |  | Scoping of Tobacco Control prevention public health work programme. |  | Delivery of Tobacco Control prevention public health work programme | Delivery of Tobacco Control prevention public health work programme | Delivery of Tobacco Control prevention public health work programme
 |  | Develop options plan for the sustainability of HMQ services and tobacco control activity, and action as relevant. |  | Report on wider activity undertaken by Help Me Quit services e.g. number of interactions Explore options for tobacco control metrics across all service/care groups e.g. smoking cessation referral rates, MECC training. |  | Scope evaluation of wider activity undertaken by Help Me Quit services |  | Conduct evaluation and develop options for future sustainability of HMQ services (contingent on evaluation findings). | Activity based on options for future sustainability of services. | Activity based on options for future sustainability of services.

## Slide 80: Population Health and Prevention System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
SERVICE TRANSFORMATION | Diabetes Programme | Tackling Diabetes Together programme – reducing inequity in most deprived communities |  |  |  | Establish a strategic approach to delivering a health board-wide direction for diabetes services, supported by the operational Diabetes Planning & Development Group |  |  |  | 
 |  | Review resource allocation within the diabetes pathway (primary to secondary care) by establishing a strategic health board-wide programme approach plus adopt the STAR (socio-technical allocation of resource) methodology |  |  |  |  |  | Develop plan to review resource allocation within the diabetes pathway (primary to secondary care) by adopting the STAR (socio-technical allocation of resource) methodology |  | 
 |  | Prevention of Type 2 diabetes onset and remission - Structured education programmes to enable improved self-management of diabetes, and review of onward delivery model reflecting evolving funding landscape |  | Coverage and Uptake to Diabetes Prevention Programme; Uptake and engagement to structured education programmes |  | Continued delivery of diabetes prevention programme and self-management programmes, and development of proposed future models as per the strategic approach workstream and reflecting future funding |  | Continued delivery of diabetes prevention programme and self-management programmes, and development/agreement of proposed future models as per the strategic approach workstream and reflecting future funding. | Continued delivery of diabetes prevention programme and self-management programmes, and development/agreement of proposed future models as per the strategic approach workstream and reflecting future funding | Continued delivery of diabetes prevention programme and self-management programmes, and agreement/implementation plan of proposed future models as per the strategic approach workstream reflecting future funding
 |  | Community diabetes model redesign |  | Reduce hospital admissions for patients with diabetes and reduce length of stay for patients with diabetes Continued focus on improving compliance with the NICE 8 Care Processes, bringing compliance for all eight elements in line with All Wales position. |  |  |  | Consider plan to redesign services to focus on establishment of community diabetes model |  | 
 |  | Expand hybrid closed loop approach for Type 1 diabetics |  |  |  |  |  | Consider plan to expand hybrid closed loop approach for Type 1 diabetics |  | 

## Slide 81: Population Health and Prevention System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 |  | Q3 |  | Q4
BAU/ PERFORMANCE | Vaccinations and Immunisations | Increase uptake and decrease inequity in Vaccinations/Immunisations |  | Improved uptake of vaccines in all clusters as measure by PHW produced reports and local dashboards. Reduce variance between practices, with reduced gap between most and least deprived areas. Oversight will be via Strategic Immunisation Group. |  | Review uptake across all immunisation programmes with alignment to the Strategic Immunisation Plan, and Vaccine Equity Strategic Plan. Focus on reducing variation between GP practices / clusters Initiate appropriate supportive targeted action in lower performing areas Measure impact and embed long-term improvements. |  | Review uptake across all immunisation programmes with alignment to the Strategic Immunisation Plan, and Vaccine Equity Strategic Plan. Focus on reducing variation between GP practices / clusters Initiate appropriate supportive targeted action in lower performing areas Measure impact and embed long-term improvements. |  |  |  | 
 | Screening programmes | Increase uptake and decrease inequity in screening programmes |  | Improved uptake of cancer screening in areas with low uptake. Reliable, up-to-date quarterly data on cluster uptake of cancer screening programmes is received from PHW that can be used to monitor progress and the success of initiatives. There is robust evaluation of local initiatives to reduce inequity in uptake and shared learning across clusters. |  | There is collation and shared knowledge of all current cancer screening uptake initiatives by partners taking place on the SBUHB footprint. |  | There is an ongoing commitment to share knowledge of planned and new cancer screening uptake initiatives taking place on the SBUHB footprint across partners, including primary care; SBUHB; PHW and third sector. | Reliable, up-to-date data on bowel and cervical cancer screening uptake in SBUHB clusters routinely being issued by PHW. There is Public Health Analyst capacity in place in SBUHB to analyse and interpret it. The information is used to inform planning of further screening uptake initiatives on the SBUHB footprint. | Reliable, up-to-date data on bowel and cervical cancer screening uptake in SBUHB clusters routinely being issued by PHW. There is Public Health Analyst capacity in place in SBUHB to analyse and interpret it. The information is used to inform planning of further screening uptake iniatives on the SBUHB footprint. | Reliable, up-to-date data on breast cancer screening uptake in SBUHB clusters routinely being issued by PHW. There is Public Health Analyst capacity in place in SBUHB to analyse and interpret it. The information is used to inform planning of screening uptake initiatives on the SBUHB footprint. | Reliable, up-to-date data on breast cancer screening uptake in SBUHB clusters routinely being issued by PHW. There is Public Health Analyst capacity in place in SBUHB to analyse and interpret it. The information is used to inform planning of screening uptake iniatives on the SBUHB footprint.

## Slide 82: Population Health and Prevention System Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
 | Healthy Child Wales Programme | Review findings and recommendations from Welsh Government following review of HCWP(1) due for launch July 2026, Review monthly all compliance levels inline with core contacts, develop a action plan to address any areas that are falling below national expectations |  | Ensure all core contacts inline with HCWP (1) are being delivered, continue monthly scrutiny and assurance reporting into PCT safety and compliance meetings |  | Initiate appropriate supportive targeted action in lower performing areas | Reviewed compliance of contacts and compliance monthly, improvement plan and focus developed for areas with reduced contacts 3.5 year old. | Review monthly, all compliance levels inline with core contacts action / improvement plan developed for contacts areas of concerns | Review monthly, all compliance levels inline with core contacts action / improvement plan developed for contacts areas of concerns | Initiate appropriate supportive targeted action in lower performing areas
 |  | HCWP(2) - Attend WG workshop June 2026 to understand clear scope and continued expectations of HB delivery. Current implementation date Sept 2026. |  | Implementation being monitored through PCT patient safety and compliance on a quarterly basis and monthly service assurance meetings being held |  | Attend WG workshop June 2026 to understand clear scope and continued expectations of HB delivery. | Attended WG workshop 29th June 2026, programme plan being developed by WG and will be shared with HB. Implementation of HCWP2 to continue, areas of high risk to be identified, RAG to be updated. | Dependent on Q1 workshop outcomes | Dependent on Q1 workshop outcomes | Dependent on Q1 workshop outcomes

## Slide 83: Population Health and Prevention System Reporting– Off Track Delivery in Q1
Milestones |  |  |  |  |  | 
Scheme/ Project | Delivery Action | Q1 Milestone Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate, Revised milestones to agree
Screening programmes | Increase uptake and decrease inequity in screening programmes | There is collation and shared knowledge of all current cancer screening uptake initiatives by partners taking place on the SBUHB footprint. | Staff sickness has prevented this from progressing. There is insufficient capacity in the team to be resilient to staff sickness. | The scope has been revised to focus on bowel screening uptake initiatives for the time being. | When staff return from sickness leave | Recommend revising milestones to account for this
Tobacco Control | Ongoing development and embedding of Maternal and Hospital Smoking Cessation Services in SBUHB | Recruitment to vacant (PEY funded) posts to support delivery of maternal and hospital smoking cessation services in SBUHB | SBUHB recruitment restrictions mean the vacant posts have been held on Trac at exec approval stage for a prolonged period. Update: On 2nd July, the posts have been released for recruitment to internal secondment fixed term roles to March 2027. | Existing staff have been trained in both Help Me Quit in Hospital and Maternal, so can provide some cross-cover, but service offer decreased. | Vacancies approved and recruited – risk of delay in recruitment meaning insufficient time to recruit and train for role, given fixed term to March 27 | Milestones may need to be revised pending the outcome of internal recruitment to the roles.
Healthy Weight/ Obesity Services | Decision on GLP-1 paper with associated actions | Decision on options paper submitted; Agreement on model of delivery, waiting list management; and funding due July 2026 | Requested revisions to GLP-1 paper means decision is still awaited. | Plan for decision to be made July 2025. | Following decision on GLP-1 paper. | Milestones will be revised once decision has been reached.
Outcomes |  |  |  |  |  | 
Scheme/ Project | Delivery Action | Q1 Outcome Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate,
Screening programmes | Increase uptake and decrease inequity in screening programmes | Reliable, up-to-date quarterly data on cluster uptake of cancer screening programmes is received from PHW that can be used to monitor progress and the success of initiatives. | PHW has not yet released the quarterly data for Q4 2025/26 and is unable to give a timeframe for this. | The importance of this data to SBUHB has been raised at the national Screening and Inequalities meeting and will continue to be. | When Public Health Wales provides the latest quarterly data | Recommend revising milestones to account for this
Tobacco Control | Continue delivery of Help Me Quit services through Health Board and Primary Care (community pharmacy). | Proportion of smokers accessing Help Me Quit services annually (Target 7.5% - Updated Welsh Government target for 2026/27); Quarterly reporting to Welsh Government: Number of smokers treated by the smoking cessation service during the quarter; Number of treated smokers followed up at their 4 week post quit date and who were CO validated as successfully quitting during the quarter | SBUHB has historically not met the smoking cessation target for Welsh Government (5%) though were close for 25/26 (estimated 4.75%), and the target has now increased to 7.5%. Vacancies in the HMQ service related to recruitment restrictions mean team is not operating at full capacity. | Cross-cover of HMQ service has been provided were possible across different sites. Mitigation will include where the existing vacancies have been filled to increase capacity. | Where the service have capacity to support sufficient quit attempts, including filling of vacancies and review of service delivery model. | To escalate that Welsh Government Smoking cessation targets are unlikely to be met without further support to the service to fill vacancies.
Tobacco Control | Delivering health promotion/ tobacco control prevention activity across the health board including in hospital, community, and schools. Develop options plan for the sustainability of HMQ services and tobacco control activity, and action as relevant. | Report on tobacco control prevention activity in the Health Board (see Public Health workplan) Report on wider activity undertaken by Help Me Quit services e.g. number of interactions Explore options for tobacco control metrics across all service/care groups e.g. smoking cessation referral rates, MECC training. | No standardised process of collating wider smoking cessation and tobacco control activity beyond basic indicators (service numbers, quit data). Delays related to organisational change process, and identification of appropriate position for visibility and reporting tobacco control metrics across the health board. Limited capacity in public health team, and Help Me Quit service, to optimise wider tobacco control prevention activity and evaluation. | Scoping exercise identified examples of prevention activity qualitatively, to be brought together into report. To work with new care group/organisational structures to confirm onward reporting measures. | Vacancies approved and recruited for Help Me Quit service. | Recommend escalating support for approval of the externally funded vacancies.

## Slide 84: Digital System Summary
RAG | Green | Outcomes | Milestones | Amber | Outcomes | Milestones | Red | Outcomes | Milestones | Total | Outcomes | Milestones
 |  | 30 |  |  | 5 | 5 |  | 2 | 2 |  | 37 | 37
Achievements |  |  |  |  |  | Challenges |  |  |  |  |  | 
The BadgerNet Maternity Module was successful implemented across Maternity Services at SBUHB during Q1 2026/27. A single pregnancy record will improve clinical safety and decision making, enabling safer and continued cross-border care through the provision of seamless access to information. Patients have access to their information via the Badgernet App. During Q1 2026/27 the OPERAi Electronic Referral Solution was implemented across Ophthalmology for primary, secondary and community care settings. Work continues to embed and refine clinical workflows. Rio was successfully implemented towards the end of Q4. During Q1 there has been a focus on embedding the system within operational practice, ensuring it supports efficient workflows, including strengthening data quality and data capture processes. Work has continued with the migration of WCCIS into Rio to support the second phase of implementation. The Radiology Information Systems Programme (RISP), which has replaced the legacy radiology and PACS solutions, successful completed its period of stable running at the end of May following go-live in March. Focus has now shifted to implementation of the Advanced Visualisation Workspace, supporting MDT working and enabling further benefits from the platform. 20% of all outpatients are using the Swansea Bay patient portal to access their medical record including appointment letters, clinical correspondence and blood results. Clinic letters generated from Cellma are now sent from secondary to primary care electronically; go live April 2026. Data from Rio and Badgernet has been successfully loaded into the data warehouse to develop operational dashboards, including measures and reports for submission of Welsh Government. Mental Health Q&S dashboard developed to be quality assured by the service in Q2. Development of a business case to support transformation of unscheduled care services in readiness for Q2 approval. |  |  |  |  |  | LIMS – The LIMS 2.0 programme continues to face significant delivery challenges; however, progress has been made in several key areas during Q1. Welsh Government have confirmed funding of the national costs overrun into Q1 & Q2. There has been increased focus on the essential functionality required for go live (aliquoting), although resolution of remaining high-priority issues remains critical to maintaining momentum. WCCIS Migration - Although good progress has been made with the referral migration phase, this is still not complete due to the complexities involved with splitting the data. The overall timeline has also extended due to national delays impacting the Swansea Council implementation date. Confirmation has yet to be received on a go live date but is estimated as Feb/March 2027. National Connecting Care funding for 2026/27 is yet to be confirmed. Lack of integration between the OPERAi referrals system and OpenEyes EPR, requires duplicate data entry across systems. This has been escalated to the national programme. Data Warehouse, dashboards and submissions WECDS – WPAS ED and Symphony do not currently contain the data items required to report on the WECDS. MIU will be reverting to WPAS ED in September due to the Symphony contract end date, this data will not be available until an alternative system in UEC is sourced. Digital Health Assessments – delayed delivery of outcome data back into the data warehouse. Implementation of WPAS ED in MIU - an archive solution has been developed in readiness to support operational service; however, it has been flagged that information relating to the number of attendances and safeguarding alerts should be migrated from WEDS into WPAS ED. This has been requested of DHCW, however there are ongoing challenges to the is request which are currently being worked through. |  |  |  |  |  | 

## Slide 85
Learnings from Q1 | Risks/ Issues | Mitigations
A key learning from Q1 has been the value of early and ongoing collaboration between Digital and operational service in the development of business cases. Collaborative working enables the business cases to better reflect frontline priorities and support achievable service and digital transformation. Maximise operational efficiencies through continued digitisation by increasing adoption of Hybrid Mail, Swansea Bay Patient Portal and the use of the digital dictation tools. This needs to continue as joint effort between digital, clinical and operational colleagues. | Digital Maternity – Key integrations to National solutions were not delivered during FY 2025/26, introducing manual tasks to digital processes and resulting in new clinical risks such as transcription errors and incorrect patient selection. Despite good progress with the migration of data from WCCIS to Rio, the timeline remains challenging to align with Swansea Council’s implementation date. If data migration delayed, there is a risk that Swansea Council will not meet the deadlines imposed by the WCCIS de-commissioning. LIMS 2.0 - Delivery continues to be constrained by supplier performance and the availability of critical defects fixes required to support a safe go-live. There is a risk that funding may not be secured to support the procurement and implementation of a system that spans UEC services. | Digital Maternity – A Technical Advisory Group has been established. All health boards are working with DHCW to progress their integration requirements to the National Architecture. Funding has been secured to take forward the national integrations. Continue to work closely with Swansea Council and The Access Group to ensure good progress is maintained and seek opportunities to secure additional resources, should funding become available via national Connecting Care business case and DPIF. Continued escalation through national programme governance arrangements, targeted focus on delivery of key aliquoting functionality and resolution of remaining critical defects, ongoing operational planning for Blood Sciences and Blood Transfusion deployment to maintain implementation readiness. Continue to explore funding opportunities.
Q2 Priorities |  | 
Rio implementation to replace legacy systems - Complete the migration of referral and progress note data, support user adoption and embedding of the solution, and successfully deliver the Virtual Wards go-live to enable operational use and benefits realisation. Revert to WPAS ED in MIU in line with the Symphony contract end date. UEC business case submitted to PFAG in July to support the procurement and implementation of a system to span the Health Board UEC footprint. LIMS 2.0. go-live with Blood Sciences in Morriston, Singleton and Princess of Wales laboratories. Provide support to Public Health Wales for go-live of LIMS 2.0 for their Microbiology lab in Singleton. Go live with Admission, Discharge and Transfer functionality in Signal which will enable patient movements to be automatically updated in Signal, freeing up staff time from duplicate entry and improving the accuracy and timeliness of patient flow information. Progress the integration requirements from Badgernet to the national architecture. Implementation of DMS and digital dictation tools in Mental Health. Hybrid Mail/SBPP – Increase adoption of SBPP to 30% and implement Hybrid Mail for remaining specialities. Implementation of Hospital Initiated Referrals (HIR) with a go-live planned for September 2026, preparation activities are underway, including system configuration, workflow validation, user testing, staff engagement and communications. Continue to collaboratively develop a business case with PCT and MH&LD services to support wider roll out of an EPR across Community and Mental Health. Data warehouse – continued development of Rio and Badgernet dashboards and reporting availability to support operational use. Identify scope for a pilot of Ambient Voice Technology. |  | 
DIGITAL System Summary

## Slide 86: Digital Reporting – CROSS CUTTING SYSTEM
Scheme/ Project | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
UEC Digital Priorities | Implement a system to span the Health Board UEC footprint; supporting flow and safety whilst enabling broader service transformation. ​ | 31/03/27 | Procure and implement a system to span the Health Board UEC footprint | Off track (Amber) | Prepare a business case with detailed benefits analysis in readiness for procurement and secure funding via DPIF | Off track (Amber) | Approval of business case by PFAG and commence procurement activities. Revert to WPAS ED in MIU to mitigate Symphony contract end date | Procurement activities | Award Contract
 | Continue to enhance Signal to support Optimal Hospital Flow ​ | 31/12/26 | Ability to perform admission, discharge and transfer in one system, removing duplication of effort | On track | Development of ADTs ready for testing | On track | Go-live of ADTs with Signal v4 | Complete transition to service | 
 | Implement Welsh Intensive Care Information System in line with national delivery | 30/03/27 | Organisational readiness and digital assessment of the WICIS system | On track | Awaiting outcome from Welsh Government (WG) on decision to implement WICIS. | On track | Commence implementation readiness for WICIS, in line with national delivery plan, depending on WG decision |  | 
Planned Care and Cancer Digital Priorities | Implement LIMS blood sciences and blood transfusion | 31/10/26 | Transition to new LIMS 2.0 | Off track (Red) | Receive all critical defect fixes from supplier | Off track (Red) | Blood Sciences go-live. | Blood Transfusion go-live. | 
 | Implement Diagnostic requesting | 31/12/26 | Digitisation of referrals to Radiology | On track | Establish project group | On track |  | Mandate referrals via ETR for key service areas | 
 | Embed use of RISP including business change | 31/12/26 | Completion of National RISP Implementation | On track | Achieve Stable Operations. | On track | Implement Advanced Visualisation Workspace (MDT Working) | Implement remaining interfaces. | 
 | Use of Digital Health Assessments (DHA’s / PROMS & PREMS) | 31/03/27 | Scaling up collection and use of digital health assessments for variety of uses, e.g. triage, screening, condition monitoring, direct patient care, to better understand outcomes of our patients. | On track | Outcome data from Promptly back into the HB data warehouse/GCP | Off track (Amber) | NHS App for DHAs & promptly patient portal and WPAS Integrations for National PROMs | NDR for National PROM pathways | 

## Slide 87: Digital Reporting – CROSS CUTTING SYSTEM
Scheme/ Project | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
Planned Care and Cancer Digital Priorities | Maximise DMS and digital dictation tools to support communication with primary care | 31/03/27 | The use of DMS and digital dictation tools successfully embedded within the service, resulting in more timely communication with primary care and a complete patient record | On track | Undertake a baselining exercise to establish current usage and requirements | On track | Commence implementation based on the outcome of the baselining exercise and the priorities provided by Mental Health | Continued implementation in line with the priorities agreed by Mental Health | 
 | Implementation of Swansea Bay Patient Portal including full roll out of Hybrid Mail | 31/03/27 | Efficiency savings via digital delivery of letters, including improved communication with patients | On track | 20% adoption - Raise purchase orders with remaining specialities in order to continue with the implementation plan | On track | 30% adoption - Implement Hybrid Mail with remaining specialties | 40% adoption - Implement Hybrid Mail with remaining specialties | 50% adoption
 | Ambient voice technology (AVT) pilot | 31/03/27 | Completed pilot of Ambient Voice Technology providing learning for AI technology adoption | On track | Early engagement with potential suppliers | On track | Identify scope for pilot | Confirm governance wrap for safe pilot use | Establish pilot and evaluation
 | Implement Internal referrals | 31/03/27 | More timely and coordinated care through an electronic referral process that improves referral quality, reduces delays and provides full visibility and tracking of referrals across secondary care pathways | On track | Evaluate the implementation of the extended pilot to inform ongoing implementation | On track | Implement internal referrals based on the approach agreed following evaluation | Implement internal referrals based on the approach agreed following evaluation | 
 | Roll out Validation of Waiting lists using AI | 31/03/27 | List of patients to validate generated | On track | Awaiting feedback on accuracy outpatient list. | On track | Automate data pipeline for agreed specialties and generate list of patients | Automate data pipeline for agreed specialties and generate list of patients | Automate data pipeline for agreed specialties and generate list of patients
 | Implement paper lite ways of working across outpatients | 31/03/27 | No requirement for the paper record. | On track | Digital capability available. | On track | Priority areas to be agreed as part of the clinical admin efficiency programme. Go live of priority areas. | Priority areas live. | Priority areas live.

## Slide 88: Digital Reporting – CROSS CUTTING SYSTEM
Scheme/ Project | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
Planned Care and Cancer Digital Priorities | Procure Digital Cellular Pathology | 01/02/27 | Procure the Digital Cellular Pathology solution | On track | Procurement tender live | On track | Close tender and begin evaluation period | Finalise evaluation and select supplier | Contract award
 | Digital Medicines Management | 31/03/27 | Implementation of Shared Medicines Record for admissions. Rolling out the Shared Medicines Record within HEPMA to support medicines reconciliation on admission, improving accuracy of medication histories, reducing errors, and supporting safer, more efficient patient care. | On track | SMR onboarding completed and submitted to DHCW with support from System C | On track | Continue engagement with DHCW and System C, and complete scoping for paediatrics, ICU, and a pilot in outpatients for HEPMA. | Continue engagement with DHCW and System C, and complete scoping for paediatrics, ICU, and a pilot in outpatients for HEPMA. | SMR development complete. Continue engagement with DHCW and System C, and complete scoping for paediatrics, ICU, and a pilot in outpatients for HEPMA.
Mental Health Digital Priorities | Implement ReQol (Recovery Quality of Life), part of the outcome measures framework for Wales | 31/03/27 | Collect ReQol from MH in-patient (Phase 1) & MH Community services (Phase 2) along with identified metrics to send quarterly to WG for benchmarking | Off track (Amber) | Paper collection embedded in services (Phase 1 and 2) | On track | National integration between WPAS and Promptly completed | Go-live with Promptly collection of ReQol Phase 1. Go live with Rio collection Phase 2 date tbc | Review digital collection
 | Rio implementation to replace WCCIS | 31/03/27 | Successful migration of WCCIS users into the Rio Live environment | Off track (Amber) | Complete the referral migration phase and commence the activities migration | Off track (Amber) | Complete migration of activities and progress notes and commence assessments. DPIF funding confirmed to expedite delivery. | Robust end user testing of the migration data and complete configuration activities | Go live with Rio for integrated teams (WCCIS users)
 | Develop a business case and complete procurement for an EPR across MHLD | 31/03/27 | Develop a business case and complete procurement for an EPR across MHLD | On track | Undertake scoping and readiness activities to inform development of a business case | On track | Confirmation of DPIF funding and commence business case | Agree procurement route | Procurement activities/Contract Award
 | Use of AI Voice to Text to address backlog of dictated MH clinic letters | 31/03/27 | Support admin staff with a pre-typed letter to validate, to address the backlog of clinic letters in Mental health | On track | Explore the use of Open AI solutions to support voice to text | On track | Seek approval for AI tool |  | 

## Slide 89: Digital Reporting – CROSS CUTTING SYSTEM
Scheme/ Project | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
Babies, CYP and Womens Digital Priorities | Continued implementation of Maternity Digital Record and Badgernet | 31/03/27 | Increased quality and safety through seamless sharing of a national maternity record | On track | Complete Phase 2 rollout of the BadgerNet implementation (across all maternity services) and support embedding of new digital solution. | On track | Support requirements gathering to progress integrations development to national solutions. | Continue to support integrations development to national solutions. | Continue to support integrations development to national solutions.
Primary Care & Community Digital Priorities | Develop a Business Case to support the procurement of an Procure Electronic Patient Record for Community | 31/03/27 | Business Case complete and Funding secured | On track | Undertake scoping and readiness activities to inform development of a business case | On track | Confirmation of funding and commence business case | Agree procurement route | Procurement activities/Contract Award
 | Rio implementation to replace legacy systems | 31/03/27 | Successful migration of WCCIS users into the Rio Live environment | Off track (Amber) | Complete the referral migration phase and commence the activities migration | Off track (Amber) | Complete migration of activities and progress notes and commence assessments. DPIF funding confirmed to expedite delivery. Go live with Virtual Wards. | Robust end user testing of the migration data and complete configuration activities | Go live with Rio for integrated teams (WCCIS users)
 | Implement Ophthalmic e-Referral System | 31/03/27 | More timely referrals from primary to secondary care and greater oversight of the patient pathway | On Track | Implementation of OPERA AI Electronic Referral Solution. | On track | Scoping and requirements gathering for integration to enable digitisation of Cataract pre-assessments. | Continue to support workflow enhancements. | Continue to support workflow enhancements.
 | Sexual Health Replacement System | 31/03/27 | Support national procurement | On track (Amber) | Await direction from Public Health Wales | On track (Amber) |  |  | 
 | Implement replacement Continuing Healthcare (CHC) system | 31/03/27 | Digital System to accurately case manage CHC | On track | Procurement activity and documentation completed | On track | System readiness activity with supplier |  | 

## Slide 90: Digital Reporting – CROSS CUTTING SYSTEM
Scheme/ Project | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
Digital Infrastructure | Laptop, PC, iPad and Printer Replacement | 31/03/27 | Replace legacy client hardware | On track | Continued equipment replacement | On track | Continued equipment replacement | Continued equipment replacement | Continued equipment replacement
 | Replacement of Singleton LAN | 31/12/27 | Replace legacy network and improve security | On track | Plan implementation activities | On track | Begin installation | Complete installation | 
 | Cyber Vault | 31/03/27 | Critical data is secured in an air gapped back up retention environment, increasing our cyber resilience | On track | Secure budget | On track | Implementation planning | Implement Cyber Vault | 
 | Replacement of Morriston LAN | 31/03/27 | Replace legacy network and improve security | On track |  | On track |  | Plan implementation activities | Complete installation
 | Install of Telephone System Hardware | 31/03/27 | Change networks to telecom equipment | On track | Secure Budget | On track | Implementation planning | Implement Cyber Vault | 
Digital Intelligence | Data warehouse and dashboards for LIMS 2.0 | 31/03/27 | Cell Path Validation | On track | Cellular Pathology Validation in progress | On track | Cell Path Validated | Cell path/Infection Control completed | Blood Science Dashboard Completed
 | Data warehouse, dashboards and submissions for Badgernet | 31/03/27 | Badgernet Data in Warehouse | On track | Badgernet Data in Warehouse and data validation started | On track | Submission Data and weekly reports validated - maternity Dashboard updated with Badgernet Data. | New Maternity DSCN development started | First phase of new Maternity DSCN completed
 | Data warehouse, dashboards and submissions for Rio | 31/03/27 | RIO Data in Warehouse | On track | RIO Data in Warehouse, Validation started and waiting list data submitted. | On track | RIO measures and reports created and pulled into Mental Health App as appropriate | RIO measures and reports created and pulled into Mental Health App as appropriate | RIO measures and reports created and pulled into Mental Health App as appropriate
 | Data warehouse, dashboards and submissions for WECDS | 31/03/27 | Successful reporting of the new WECDS | Off track (Red) |  | Off track (Red) |  | WPAS WECDS data for MIU pulled into Warehouse | Available WECDS data submitted

## Slide 91: Digital Reporting – CROSS CUTTING SYSTEM
Scheme/ Project | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
 | National Data Resource (NDR) | 31/03/27 | Options for approach to local care data repository discussed | On track | Options and Principles paper for approach to local Care Data Repository paper started | On track | Approach agreed for Health Board approach to local CDR and priority areas | Development started on initial CDR priority areas | Development continues on CDR priority areas
 | Re-banding of coding staff and development of auto-coding software | 31/03/27 | Approach to adding additional auto-coding specialties to model agreed. | On track | Generic Auto-coding model has been tested | On track | Additional specialties agreed and dataset curated for sending to model. | Auto-coding model live in four specialties | Auto-coding model live in four specialties
 | Data Literacy and Value | 31/03/27 | Data Literacy module training delivered | On track | Scheduled training sessions take place | On track | Scheduled training sessions take place | Scheduled training sessions take place | Scheduled training sessions take place

## Slide 92: Digital System Reporting– Off Track Delivery in
Scheme/ Project | Delivery Action | Q1 Milestone Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate, Revised milestones to agree
Planned Care and Cancer Digital Priorities | Implement LIMS blood sciences and blood transfusion | Receive all critical defect fixes from supplier | Supplier has not delivered required fixes to agreed timescales | Continue to escalate national supplier delays through national Programme Board. Maintain readiness to test fixes once available from supplier. Continue local readiness activities. | Q2 | N/A
Planned Care and Cancer Digital Priorities | Use of Digital Health Assessments (DHA’s / PROMS & PREMS). | Outcome data from Promptly back into the Health Board data warehouse/Google Cloud Platform | Awaiting on the structure of the data structures from Promptly. | Promptly supplier looking at this w/c 22/6/26. | Q2 | N/A
Mental Health Digital Priorities/Primary Care and Community Digital Priorities | Rio implementation to replace WCCIS for integrated teams | Complete the referral migration phase and commence the activities migration | Although good progress has been made with the referral migration phase, this is still not complete due to the complexities involved with splitting the data. The overall timeline has also extended due to national delays impacting the Swansea Council implementation date. Confirmation has yet to be received on a go live date but is estimated as Feb/March 2027. Confirmation of DPIF funding to expedite delivery expected in Q2 | Robust testing and validation processes to ensure data is migrated correctly. Close working with Swansea Council to ensure close alignment with their planned implementation date | Q2 | N/A
Digital Intelligence | Submission of new WECDS | Commence collection and reporting of the data required to report on the WECDS | Symphony contract end date has resulted in MIU going back to WPAS ED. WPAS ED does not contain the data items required to report on the dataset | Business case developed to procure a third-party solution that is able to capture the new data items. | Q2 | N/A
UEC | Implement a system to span the Health Board UEC footprint; supporting flow and safety whilst enabling broader service transformation. | Prepare a business case with detailed benefits analysis in readiness for procurement and secure funding via DPIF | Confirmation of DPIF outstanding | Working closely with PFAG and Welsh Government to secure funding | Q2 | N/A
Milestones

## Slide 93: Digital System Reporting– Off Track Delivery in
Scheme/ Project | Delivery Action | Q1 Outcome Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate,
Mental Health Digital Priorities | Implement ReQol (Recovery Quality of Life), part of the outcome measures framework for Wales | Collect ReQol from MH in-patient (Phase 1) & MH Community services (Phase 2) along with identified metrics to send quarterly to WG for benchmarking | Q1 milestone is an interim measure (paper collection) | Awaiting DHCW and Promptly to complete the necessary integrations prior to digital collections | Q2 | N/A
Outcomes

## Slide 94: WORKFORCE OVERVIEW
Performance Outcomes | Confidence assessment
% sickness absence rate | 
Turnover rate | 
Agency spend | 
Key Schemes | 
CIP_26 | Turnover Management Controls
CIP_25 | A&C Fixed Term Contracts
CIP_24 | A&C Reduction In Variable Pay
CIP_21 | Medical Workforce Job Planning Principles (Reducing SPAs)
CIP_19 | Maximise Substantive Medical Capacity (DCC) and Rostering
CIP_20 | Medical Cease Above Vacancy 26-27
CIP_18 | Medical Targeted Recruitment
CIP_22 | Reducing unavailability of Medical workforce
CIP_16 | HCSW reduction in variable pay
CIP_14 | HCSW Vacancy Substantiation
CIP_15 | Nursing & Midwifery Workforce Programme
CIP_17 | Home First – Review Bonymaen Beds/ Nursing workforce
TBC | Pipeline opportunities: AHP Workforce Estates and Facilities Workforce Maximisation of digital ways of working e.g. Microsoft 365, co-pilot
Risks | Mitigations
Workforce resistance to establishment and model of care changes | Exception process in place. Vacancies and variable pay reviewed by professional workforce boards
Insufficient operational capacity to deliver programme | Delivery unit established to provide targeted support for priority areas
Unforeseen surges in demand | Build flexible workforce models for temporary scaling; broaden skill mix and cross‑cover; prioritise stabilisation in high‑demand areas; implement contingency plans to limit premium‑rate staffing
Persistent national workforce shortages | Run targeted recruitment for hard‑to‑fill roles; strengthen links with training bodies; use alternative workforce models (e.g., SAS doctors, ANPs); develop local talent pipelines and grow‑your‑own schemes.
Finance Impact | FYE savings | £28.87M
Significant WTE reduction (550 wte substantive and 250wte variable staff) equating to 5% |  | 
Our workforce plan will build a stable, skilled and efficient workforce by strengthening recruitment, improving productivity, and developing flexible, sustainable staffing models that support safe, high‑quality care.

## Slide 95: Workforce System Summary
RAG | Green | Outcomes | Milestones | Amber | Outcomes | Milestones | Red | Outcomes | Milestones | Total | Outcomes | Milestones
 |  | 6 | 6 |  | 3 | 2 |  | 1 | 2 |  | 11 | 11
Achievements |  |  |  |  |  | Challenges |  |  |  |  |  | 
Delivery grip strengthened: 11 of the 16 admin and clerical turnover PIDs received, workforce-finance tracker agreed and FTC analysis submitted for validation. Staff reduction is ahead of May target/trajectory (1.0% vs 0.6% target); 6 of the 8 staff groups met or exceeded current target. Admin & Clerical, Allied Health Professions, Healthcare Scientists and Estates show the strongest early WTE reductions Variable pay reductions are emerging in several groups. Nursing transformation has live pilots with training progressing and staff engagement despite operational pressures. |  |  |  |  |  | Workforce CIP RAG is fragile: 0 green, 2 amber and 5 red across the seven workforce schemes. Financial validation/cashability remains incomplete. Some staff groups remain off trajectory or need strengthened plans, particularly Medical & Dental Reliance on natural wastage will become harder; Q2 needs stronger vacancy management |  |  |  |  |  | 

## Slide 96: Workforce Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
RECOVERY AND SUSTAINABILITY | Turnover Management Controls – Amended to A&C 5% Turnover management | Exec Leads identified for each Service Group and Corporate area . PIDs in place to describe how they will meet their 5% savings target​ ​Financial assumptions through further analysis of turnover by staff group / band​ Workforce to support implementation and transaction of agreed headcount reductions (from Q2 onwards)​ | 31/05/26 (Q1) 01/07/26(Q1) ​ 01/04/27(Q4) | All PIDs are submitted in full Financial assumptions are refined Agreed headcount reductions supported |  |  |  | ​ |  | 
 | A&C Fixed Term Contracts | Track FTCs and associated savings, and provide monthly updates​ Complete risk assessments for all A&C FTC due to end within the next six months.​ Terminate FTCs during the April–September period where risk assessments have been completed and early termination has been approved. ​ | 31/03/27​ (Q1) 1/06/26​ (Q1) 14/07/26 (Q2) | Tracking completed Risk assessments completed FTCs terminated |  |  |  |  |  | 
 | A&C Reduction In Variable Pay | POAP to reduce Variable Pay for high users: ED, Radiology, Cellular Path and Digital to be submitted by leads ​ Finance team to test assumptions within POAP​ Formal approval process for area plans at Workforce Steering Group ​ | 12/06/26​ (Q1) 13/07/26​ (Q2) 14/07/26 (Q2) | POAPs developed to reduce variable pay Assumptions tested Formal approval process |  |  |  |  |  | 

## Slide 97: Workforce Reporting
Scheme/ Project |  | Delivery Actions 26/27 | Delivery Date | Outcomes | Outcomes Q1 Reporting (RAG) | Delivery Milestones |  |  |  | 
 |  |  |  |  |  | Q1 | Milestones Q1 Reporting (RAG) | Q2 | Q3 | Q4
 | Medical Workforce Programme (amended to one overarching programme) | Job Planning Principles | 31.03.2027 |  |  |  |  |  |  | 
 |  | Targeted Recruitment | 31.03.2027 |  |  |  |  |  |  | 
 |  | Maximise Substantive Medical Capacity | 31.03.2027 |  |  |  |  |  |  | 
 |  | Limit vacancy-coded variable pay to actual gaps in medical staffing rotas | 31.03.2027 |  |  |  |  |  |  | 
 |  | Reduction in Variable Pay Associated with Unavailability - (Wellbeing Programme) | 31.03.2027 |  |  |  |  |  |  | 
 | HCSW Workforce Programme (amended to one overarching programme) | No updates available for Q1 |  |  |  |  |  |  |  | 
 | Nursing & Midwifery Workforce Programme | Alternative benchmarking tool to be identified at an all-Wales level to support project evaluation​ Model of Care NPTS: Go live in Ward C and Ward 12​ Model of Care Morr: Go live in Ward J and L​ Source BI analytical resource to support implementation as part of handover to BAU​ Ensure efficient handover from Deloitte to SBUHB​ | 25.06.26​ (Q1) 06.07.26​ (Q2) 20.07.26​ (Q2) 31.07.26​ (Q2) 31.07.26 (Q2) | Benchmarking tool identified Go live Go live BI analytical resource sourced Handover complete |  |  |  |  |  | 
 | Home First – Review Bonymaen Beds/ Nursing workforce AHP Workforce Programme (amended to one overarching programme) | Complete PID validation exercise. Review all 9 PIDs – previously submitted Nov 25’​ Confirm which services are actual variable pay drivers and establish clear financial baseline​ Align responsibility to correct services​ | 30.06.26 (Q1) ​ 30.07.26 (Q2) ​ 30.07.26 (Q2) | PIDS validated Baselines established Responsibility aligned |  |  |  |  |  | 

## Slide 98: Workforce – Off Track Delivery in Q1
Scheme/ Project | Delivery Action | Q1 Milestone Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate, Revised milestones to agree
A&C 5% Turnover management | Exec Leads for each SG to submit PIDs describing how they will meet their 5% savings target |  | 11 out of 16 received and require some refinement | Schedule an R&S Board deep dive for the Service Executive PIDs to review project and financial plans | R&S board will be held on 22/07/26 | Reported to R&S board
A&C Reduction In Variable Pay | POAP to reduce Variable Pay for high users: ED, Radiology, Cellular Path and Digital to be submitted by leads by 12/06 |  | Some POAPs remain outstanding | Leads have been emailed and finance BP requested to support | For discussion at workforce steering group on 14/07/26 | Reported to R&S board
Medical Workforce | Maximise Substantive Medical Capacity |  | Initial System for piece of work had capability issues | Switch of proof of concept to HCSE team. Review of variable pay by service group in progress | Reported to R&S board | Reported to R&S board
Nursing & Midwifery Workforce Programme | Alternative benchmarking tool to be identified at an all-Wales level to support project evaluation |  | Not identified | Escalation through appropriate channels (Exec and R&S Board) | Reported to R&S board | Reported to R&S board
Milestones
Outcomes – not completed as would be duplicating the above
Scheme/ Project | Delivery Action | Q1 Outcome Off track | Reason for off track | Management/ Mitigating Actions | When back on track | Decision for IPPR meeting, e.g. Issues to escalate,
A&C Reduction In Variable Pay | POAP to reduce Variable Pay for high users: ED, Radiology, Cellular Path and Digital to be submitted by leads by 12/06 |  | at £200k per month at the start of the year and are now down to £66k in June | Leads have been emailed and finance BP requested to support | For discussion at workforce steering group on 14/07/26 | Reported to R&S board

## Slide 99: Workforce Related CIP Schemes for 2026/27
The table provides a breakdown of the Workforce Cost Improvement Plans (CIPs)
The RAG status indicates which schemes are currently on or off track as of 10/07/26:
R&S Category Data Source Trackers | Planned Delivery In Year Total (£'000) | Planned Delivery Assumptions Workforce Element (£'000) | RAG Status
CHC | 973 | - | 
Medicines Management | 3250 | - | 
Planned Care Programmes |  | - | 
Planned Care | 11,364 | 8,607 | 
UEC (Bed Base) | 9,613 | 7,280 | 
Procurement / Non-Pay | 4,587 | - | 
General Efficiency & Productivity | 6,350 | - | 
Workforce A&C | - | - | 
A&C Turnover* | 4,997 | 4,997 | 
A&C Fixed Term Contracts | 200 | 200 | 
A&C Variable Pay | 900 | 900 | 
Workforce Medical | - | - | 
Job Planning | 4,382 | 4,382 | 
Maximising Capacity | 11,393 | 11,393 | 
Workforce Nursing | - | - | 
Nursing RNs | 2,273 | 2,273 | 
Nursing HCSW | 4,718 | 4,718 | 
Grand Total | 65,000 | 44,751 | 

## Slide 100: Workforce Reduction Progress
For 2026/27, the Health Board is required to save £44.7m in recurrent workforce costs, through CIPs, which financial modelling has indicated is equivalent to 550 WTE substantive roles and 250 WTE in variable staff usage. The graph below illustrates the HB’s progress against this target as of May 2026:
Chart: Health Board Total % Reduction
| Baseline | M1 Apr | M2 May | M3 Jun | M4 Jul | M5 Aug | M6 Sep | M7 Oct | M8 Nov | M9 Dec | M10 Jan | M11 Feb | M12 Mar
Actual % Reduction | 0 | -0.016456 | -0.010367 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Target % Reduction | 0 | -0.0027672 | -0.0055344 | -0.0083016 | -0.013555 | -0.018808 | -0.024061 | -0.028819 | -0.033577 | -0.038336 | -0.042804 | -0.047273 | -0.051742
Average Actual | #N/A | -0.013412 | -0.013412 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
The graph illustrates that the number of staff in post i has reduced by 1.0% in May 2026, ahead of its target reduction of 0.6%.
By M12, the target reduction is 5.2%, equivalent to 800 WTEs.
The largest actual reduction so far is in the Administrative & Clerical staff group at 2.2%.
6 out of 8 staff groups have met or exceeded their current targets
Q1 actual data will be available after 11/07/26
Note that targets will be refreshed as further detail becomes available

## Slide 101: Progress by Staff Group – Admin, Clerical and BMs (May 2026)
Chart: Administrative, Clerical & Board Members % Reduction
| Baseline | M1 Apr | M2 May | M3 Jun | M4 Jul | M5 Aug | M6 Sep | M7 Oct | M8 Nov | M9 Dec | M10 Jan | M11 Feb | M12 Mar
Actual % Reduction | 0 | -0.017542 | -0.022273 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Target % Reduction | 0 | -0.013341 | -0.026683 | -0.040024 | -0.041538 | -0.043052 | -0.044566 | -0.04608 | -0.047594 | -0.049108 | -0.050623 | -0.052137 | -0.053651
Average Actual | #N/A | -0.019908 | -0.019908 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Priorities for Q2:
Further work on reviewing fixed term contracts.
Review current vacancies and consider removing.
Consider alternatives to natural wastage.
Cross cutting reviews of services – (e.g. medical secretaries, admin support teams).
Review of corporate service areas.
Understand redeployment opportunities.
This staff group has the largest reduction so far at 2.2% but is under its current target of 2.7%. Achievements in Q1: Group pay spend within budget adjusted for CIPs.
Net reduction in WTEs in line with target.
Reduction in variable pay – Month 1 £177k, Month 2 £108k and Month 3 £67k.
Fixed term contracts reviewed and plans to remove.
Challenges in Q1:
Some PIDs not complete and others need further work.
Difficult not to recruit to some vacancies due to nature of posts (e.g. front line staff).
Emerging risks and mitigation:
Reliance on 'natural wastage' will become increasingly difficult. Further levers need to be considered particularly for future years.

## Slide 102: Progress by Staff Group – Medical and Dental (May 2026)
This staff group is off track at a 0.1% reduction compared to their current target of 1.6%.
Achievements in Q1: Some progress reducing variable pay.
Sickness remains low.
Challenges in Q1: Capacity to review job plans and rosters. Operational pressures. Emerging risks and mitigation: Target based on a 10% reduction in expenditure.
Priorities for Q2:
Reassess the opportunities to achieve £16m overall savings target.
Ongoing review of job plans, rosters and variable pay. .
Review current vacancies and consider removing.
Chart: Medical & Dental % Reduction
| Baseline | M1 Apr | M2 May | M3 Jun | M4 Jul | M5 Aug | M6 Sep | M7 Oct | M8 Nov | M9 Dec | M10 Jan | M11 Feb | M12 Mar
Actual % Reduction | 0 | -0.0062076 | -0.00069997 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Target % Reduction | 0 | -0.0079691 | -0.015938 | -0.023907 | -0.031876 | -0.039845 | -0.047814 | -0.055784 | -0.063753 | -0.071722 | -0.079691 | -0.08766 | -0.095629
Average Actual | #N/A | -0.0034538 | -0.0034538 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Slide 103: Progress by Staff Group – Nursing & Midwifery (May 2026)
This staff group is on track at a 0.4% reduction compared to their current target of 0.4%.
Achievements in Q1: Gowers ward pilot complete.
Some variable pay reductions.
Financial analysis undertaken on CIP plans.
Challenges in Q1:
Unfunded beds remain open.
Sickness remains high.
Overstaffing and redeployment alongside decision to recruit Student streamliners.
Emerging risks and mitigation:
Plans not developing savings at required rate. Plans being reviewed.
Priorities for Q2:
Understand unfunded wards.
Development of a Nursing Workforce Plan incl. plans for redeployment. Roll out of Transformation Project.
Chart: Nursing & Midwifery Registered % Reduction
| Baseline | M1 Apr | M2 May | M3 Jun | M4 Jul | M5 Aug | M6 Sep | M7 Oct | M8 Nov | M9 Dec | M10 Jan | M11 Feb | M12 Mar
Actual % Reduction | 0 | -0.010196 | -0.0041376 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Target % Reduction | 0 | -0.0022281 | -0.0044562 | -0.0066843 | -0.011941 | -0.017198 | -0.022454 | -0.026892 | -0.03133 | -0.035768 | -0.040206 | -0.044644 | -0.049082
Average Actual | #N/A | -0.0071666 | -0.0071666 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Slide 104: Progress by Staff Group – Additional Clinical Services (May 2026)
This staff group is on track at a 1% reduction compared their current target of 1%.
Achievements in Q1: Gowers ward pilot complete.
Financial analysis undertaken on CIP plans.
Some variable pay reduction.
Challenges in Q1:
Unfunded beds remain open.
Sickness remains high along with vacancies.
Redeployment opportunities
Emerging risks and mitigation:
Plans not developing savings at required rate. Plans being reviewed.
Priorities for Q2:
Development of a Nursing Workforce Plan.
Roll out of Transformation Project.
Chart: Additional Clinical Services % Reduction
| Baseline | M1 Apr | M2 May | M3 Jun | M4 Jul | M5 Aug | M6 Sep | M7 Oct | M8 Nov | M9 Dec | M10 Jan | M11 Feb | M12 Mar
Actual % Reduction | 0 | -0.027562 | -0.0099276 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Target % Reduction | 0 | -0.0047593 | -0.0095186 | -0.014278 | -0.022294 | -0.03031 | -0.038326 | -0.045257 | -0.052187 | -0.059118 | -0.065506 | -0.071895 | -0.078283
Average Actual | #N/A | -0.018745 | -0.018745 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Slide 105: Progress by Staff Group – Allied Health Professionals (May 2026)
This staff group achieved a 2% reduction, exceeding their current target of 0.2%
Achievements in Q1: Pay spend within budget.
Progress reducing variable pay use
Set rates with MEDACS.
Sickness remains low.
Challenges in Q1:
Service plans not complete, and limited capacity to review
Emerging risks and mitigation: Funding for some services will be required.
Priorities for Q2:
Finalisation of benchmarking data. Development of Service Workforce Plans.
Further work on reviewing fixed term contracts. Review current vacancies and consider removing.
Consider alternatives to natural wastage. Understand redeployment opportunities.
Chart: Allied Health Professionals % Reduction
| Baseline | M1 Apr | M2 May | M3 Jun | M4 Jul | M5 Aug | M6 Sep | M7 Oct | M8 Nov | M9 Dec | M10 Jan | M11 Feb | M12 Mar
Actual % Reduction | 0 | -0.01995 | -0.019274 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Target % Reduction | 0 | -0.0021565 | -0.0043129 | -0.0064694 | -0.0086258 | -0.010782 | -0.012939 | -0.015095 | -0.017252 | -0.019408 | -0.021565 | -0.023721 | -0.025877
Average Actual | #N/A | -0.019612 | -0.019612 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Slide 106: Progress by Staff Group – Healthcare Scientists and Prof Sc & Tech (May 2026)
This staff group achieved a 0.9% reduction, exceeding their current target of 0.2%.
See AHP slide for narrative
Chart: Healthcare Scientists % Reduction
| Baseline | M1 Apr | M2 May | M3 Jun | M4 Jul | M5 Aug | M6 Sep | M7 Oct | M8 Nov | M9 Dec | M10 Jan | M11 Feb | M12 Mar
Actual % Reduction | 0 | -0.01359 | -0.0091686 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Target % Reduction | 0 | -0.001122 | -0.002244 | -0.003366 | -0.003366 | -0.003366 | -0.003366 | -0.003366 | -0.003366 | -0.003366 | -0.003366 | -0.003366 | -0.003366
Average Actual | #N/A | -0.011379 | -0.011379 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Chart: Prof Scientific & Technical % Reduction
| Baseline | M1 Apr | M2 May | M3 Jun | M4 Jul | M5 Aug | M6 Sep | M7 Oct | M8 Nov | M9 Dec | M10 Jan | M11 Feb | M12 Mar
Actual % Reduction | 0 | 0.0053474 | -0.0014245 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Target % Reduction | 0 | -0.00054058 | -0.0010812 | -0.0016217 | -0.0016217 | -0.0016217 | -0.0016217 | -0.0016217 | -0.0016217 | -0.0016217 | -0.0016217 | -0.0016217 | -0.0016217
Average Actual | #N/A | 0.0019614 | 0.0019614 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
This staff group is on track at a 0.1% reduction compared to their current target of 0.1%.
See AHP slide for narrative

## Slide 107: Progress by Staff Group – Estates and Ancillary (May 2026)
This staff group is on track at a 1.6% reduction compared to their current target of 0.2%.
Achievements in Q1: Overall group spend is under budget.
Some progress in reducing variable pay
Sickness in some areas such as NPT Housekeeping and Porters Morriston has reduced.
Challenges in Q1:
Sickness absence levels in key areas continue to be high
Operational pressures
Recruitment delays
Emerging risks and mitigation: Recruitment delays are having an impact on sickness absence and the use of variable pay.
Priorities for Q2: Finalisation of workforce plans
Review of vacancies and recruit to essential ones
Focus on hot spot sickness absence areas with aim of reducing by 1%
Chart: Estates & Ancillary % Reduction
| Baseline | M1 Apr | M2 May | M3 Jun | M4 Jul | M5 Aug | M6 Sep | M7 Oct | M8 Nov | M9 Dec | M10 Jan | M11 Feb | M12 Mar
Actual % Reduction | 0 | -0.027869 | -0.016438 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Target % Reduction | 0 | -0.00084105 | -0.0016821 | -0.0025231 | -0.0026966 | -0.0028701 | -0.0030436 | -0.0032171 | -0.0033906 | -0.0035641 | -0.0037376 | -0.0039111 | -0.0040846
Average Actual | #N/A | -0.022153 | -0.022153 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A