| Meeting Date | 24 September 2024 |  | Agenda Item |  |  | 4.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Planned Care Performance Update |  |  |  |  |  |
| Report Author | Craige Wilson, Deputy COO |  |  |  |  |  |
| Report Sponsor | Deb Lewis Chief Operating Officer |  |  |  |  |  |
| Presented by | Deb Lewis Chief Operating Officer |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | In May 2022, Welsh Government set out its ambitious intention for planned care recovery. The output of that ambition was a requirement for Health Boards to submit recovery trajectories against two specific priority areas: - No patient will wait more than 52 weeks for a first outpatient appointment by end of 2022. - Patients will wait less than 104 weeks for treatment within most specialties by the end of 2022/23 These targets were subsequently revised to October 2023 for 52 weeks outpatient waiting times and March 2024 for 99% of 104 week waiting times at all stages. The new target is for zero 104 week waits by the end of March 2025 This paper provides an update on improvement plans to deliver against these targets. |  |  |  |  |  |
| Key Issues | SBUHB achieved the delivery of the 52-week target and maintained this position since October 2023. The HB Achieved a 97.8% compliance against the required 99% of patients waiting less than 104-weeks by the end of March 2024. The Health Board has cleared all 156 waits at the end of August 24. The revised waiting time target for zero 104 week waits by March 2025 represents a considerable challenge and risk without additional investment. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☒ | ☒ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to: To note the progress made to date to achieve the 2024/25 Ministerial Targets and the associated risk |  |  |  |  |  |

Planned Care Performance Update

- INTRODUCTION

In May 2022, Welsh Government set out its ambitious intention for planned care recovery. The output of that ambition was a requirement for Health Boards to submit recovery trajectories against two specific priority areas:

- No patient will wait more than 52 weeks for a first outpatient appointment by end of 2022.

- Patients will wait less than 104 weeks for treatment within most specialties by the end of 2022/23

These targets were subsequently revised to October 2023 for 52 weeks outpatient waiting times and March 2024 for 99% of 104 week waiting times at all stages. The new target is for zero 104 week waits by the end of March 2025

This paper provides an update on improvement plans to deliver against these targets.

- BACKGROUND

The Recovery and Sustainability (R&S) Plan 2022-25 was endorsed by Management Board on March 2022, approved by Board, and subsequently submitted to Welsh Government for consideration.

One of the core components of the R&S Plan was the recovery of planned care, which had been impacted significantly by the pandemic. The WG recovery plan ask assumed that planned care activity levels have resumed to pre-pandemic levels (19/20) and will be exceeded as a result of the additional recovery funded provided.

The Health Board submitted initial trajectories but highlighted that further work would be undertaken to refine the modelling and strengthen the plan in the following areas:

- Strengthening GP led services to prevent referral to secondary care and diagnose and/or treat at source.

- Developing demand management solutions across our systems of care.

- Considering the application of referral management criteria to be applied to existing lists and new referrals.

- Increasing core capacity for open pathways by diverting capacity previously assigned to follow up pathways as a result of:

  - modernisation of follow up system,

  - better use of clinic slots through partial bookings,

  - individual consultant productivity and

  - rigorous enforcement of DNA protocols

- The opening of further planned capacity in our system at Neath and Port Talbot

The Health Board achieved the delivery of the 52-week target by the end of October 2023, as required. This has been maintained on a monthly basis since October 2023. The HB Achieved a 97.8% compliance against the required 99% of patients waiting less than 104-weeks by the end of March 2024.

The focus for Quarter 2 of 2024/25 is to ensure that there is no deterioration in the position and that a month-on-month improvement with a focus is on achieving zero 156 week waits; this has been achieved.

For the remainder of 2024/25 the target will be to maintain the current position and move towards zero 104 week waits by the end of March 25.

- CURRENT POSITION

# Stage 1

At the end of October 2023 zero-breach position for 52 weeks for a first outpatient appointment was achieved and this has been maintained for the past 10 months as demonstrated in the below:

# All Stages

The confirmed position for the end of August at all stages for156 weeks and 104 -weeks is as follows:

| Specialty | 156 weeks | 104 weeks |
| --- | --- | --- |
| Gynaecology | 0 | 340 |
| T&O | 0 | 516 |
| Plastics | 0 | 117 |
| Spinal | 0 | 47 |
| ENT | 0 | 111 |
| General Surgery | 0 | 116 |
| Urology | 0 | 27 |
| Oral/Maxillo facial Surgery | 0 | 1 |
| Total | 0 | 1275 |

The trajectory of improvement is broadly in line with that submitted to Welsh Government at the beginning of the year. However, continued improvement will dependent on additional resources being available across a range of specialties for the remainder of 2024/25. A request for additional support to achieve the 104 week target has recently been submitted to Welsh Government.

The improvement in the 104-week position (1275 breaches) is above our submitted trajectory for the first time this financial year (1223 v 1275).  However, it is the lowest reported position of all University Health Boards in Wales.

  - Scrutiny and Assurance Process

The dynamic nature of the recovery necessitates scrutiny and monitoring, both internal and external to the organisation. The following outlines the monitoring and reporting structure that is in place and the mechanism for directorates to be held to account for delivery.

External Monitoring

Monthly monitoring meetings are scheduled with WG / NHS Executive officials and HB is represented at the monthly meetings by the COO and Deputy COO.

The monthly meetings focus on:

  - Validation

  - Treat in turn

  - Plans for longest waits

  - Detailed speciality discussions / issues / areas of concerns

  - Progress on HB transformation measures

  - Progress on developing patient support and communication

Internal Monitoring

There are fortnightly meetings led by the Service Groups where service leads are held to account for delivery of the trajectories. Escalation for the non-delivery against the submitted levels will be to the Chief Operating Officer in the first instance.

- Operational monitoring - the current performance management meetings:

  - monitor delivery of the trajectories and the areas of efficiency noted above

  - ensure core capacity is at or above 2019/20 levels

  - ensure robust housekeeping is in place for RTT pathways

  - further develop recovery plans as required for approval via Planned Care Board

- Formal monitoring / assurance

  - Service Group Performance Reviews

  - Planned Care Board

  - Management Board via the Performance Report

  - Performance & Finance Committee

To help support directorates a Planned Care Dashboard has been developed with specialty level performance information.

Risks

The Health Board has achieved the 52-week target and services are expected to maintain this position. An improvement trajectory for 156 was set for the end of June 2024 this was achieved at the end of August with all outstanding gynaecology patients cleared.

The Health Board is working to achieve the target of achieving zero patients waiting over 104 weeks by the end of March 2025. However, there are still some notable challenges across a range of specialties to achieving this target. Recent correspondence to Welsh Government has set out the challenges for those specialties and the level of additional resource that would be required to assure the delivery of the target. Without this additional investment, achieving this target by the of March will not be possible, given the inability of the Health Board to commit any additional funding to Planned Care.

- FINANCIAL IMPLICATIONS

As a result of the additional funding secured for the NPTH development £38.4m allocated to Planned Care Recovery in 2023/24, however approximately £2m of this allocation was not spent as a result of a reduction in insourcing and outsourcing in Q4 to support the overall financial position of the Heath Board.

Given the financial challenge the Health Board faces in 2024/25. The Director of Finance has requested that only 50% of £15.2m allocation for planned care is spend and that £2.5m is saved from NPTH and endoscopy allocation.

This reduced level of funding will not allow the Health Board to insource and outsource activity to the extent that is required to eliminate all 104 week breaches. An additional allocation from Welsh Government as outlined above is required.

- RECOMMENDATION

To note the progress made to date to achieve the 2023/25 Ministerial Targets and the risks associated with the new 104 week waiting time target

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| The successful implementation of the plans outlined have the ability to improve the quality and safety of services and in turn patient experience. However, the report has outlined a number of risks, which have the potential to delay benefit realisation. |  |  |  |
| Financial Implications |  |  |  |
| There is a significant risk that the financial allocation in 2023/24 for the Planned Care Recovery Programme will limit the progress that the Health Board is able to make in reducing waiting times further. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| There are no legal implications to consider as a direct result of this report. |  |  |  |
| Staffing Implications |  |  |  |
| A number of the improvement plans are facing challenges with recruitment and the availability of re-current funding. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| This paper outlines how service areas within the Planned Care Programme are working in collaboration not only to look at the short term, but also to develop services across Swansea Bay in the long-term including the new theatres and the plans to enhance innovation and new ways of working. |  |  |  |
| Report History |  | May 23 – Planned Care Update |  |
| Appendices |  | Nil |  |