| Meeting Date | 23 September 2025 |  | Agenda Item |  |  | 2.3 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Performance and Finance Committee |  |  |  |  |  |
| Report Title | Monthly Recovery & Sustainability Programme Update |  |  |  |  |  |
| Report Author | Deborah Longman – Head of Recovery and Sustainability Samantha Moss – Deputy Director of Finance |  |  |  |  |  |
| Report Sponsor | Darren Griffiths, Executive Director of Finance and Performance |  |  |  |  |  |
| Presented by | Samantha Moss – Deputy Director of Finance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The report is provided to update the committee on the current actions and work in progress of the Recovery & Sustainability Board. |  |  |  |  |  |
| Key Issues | The report invites the Performance & Finance Committee to note the work undertaken by the Recovery & Sustainability programme, overseen by the Recovery & Sustainability Board. The report includes an overview of the key actions arising from the latest Recovery & Sustainability Boards as well as an update on the six thematic programmes. It also provides high level information on the delivery regarding the Health Board savings. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - - ACKNOWLEDGE the updated report for ASSURANCE of ongoing delivery associated with the Recovery and Sustainability Programme |  |  |  |  |  |

MONTHLY RECOVERY & SUSTAINABILITY PROGRAMME UPDATE

- PURPOSE

The paper provides the monthly formal update to the committee regarding the actions and progress within the Recovery and Sustainability programme.

- INTRODUCTION

The external support commissioned by the Health Board in collaboration with Welsh Government commenced in July. This support (Deloitte) has been prioritised to 5 main areas:

- Testing the quality and effectiveness of the Board’s delivery structures;

- Further work on the control environment, in key material expenditure and risk areas such as workforce;

- Urgent and emergency care;

- Continuing Healthcare;

- External planning and delivery expertise to stress-test the health boards plan for 2025/26.

Aligned to the 5 areas above the Deloitte team have focused on the identification and delivery of in year savings to support the Financial Plan Update submitted to WG on 11 September and presented to Board.

- UPDATES R&S PROGRAMME

  - R&S Board 27th September 2025

Focus of the meeting was on the work of the 6 Thematic programmes and the schemes within these. Key points:

- Deloitte confirmed that the next phase of the work required detailed articulation of the interventions underpinning each theme and the emphasis was placed on the need for:

  - Clear descriptions of each intervention.

  - Defined timeframes for implementation.

  - Financial analysis covering both full-year and in-year (part-year) effects.

  - Identification of risks and key decision points required to realise benefits.

  - 29 Aug 2025: Initial draft scheme summaries to be reviewed.

  - 1-2 Sept 2025: Refinement of narratives and financial assumptions.

  - 3 Sept 2025: Executive Team session to review and sign off schemes.

- Colleagues from Deloitte and the Recovery & Sustainability Team were actively supporting scheme development.

- Delivery leads and executive sponsors were expected to contribute to the narrative and financial articulation of each scheme.

- Schemes must deliver a sustained improvement to the financial run rate. One-off technical adjustments, cost avoidance, or balance sheet movements are excluded from thematic submissions.

- Focus is on approximately 20 high-impact schemes capable of delivering significant savings over a four-year period.

- Part-year savings must be realistically achievable within the current financial year. Schemes must balance ambition with feasibility.

- Each scheme must include a clear description, implementation milestones, risk assessment, and financial assumptions. Initial estimates may be high-level but must be refined promptly.

  - R&S Board 10th September 2025

Focus of the meeting, building on the requirements from of 27 August and the delivery of the Updated Plan by 11 September was on further review and update on some of the Thematic Programmes and the journey to achieve the £55.4m savings, which was recognised and noted by the R&S Board. Key points:

- Progress against sickness absence management has seen some positive strides forward – including an increase in Occupational Health referrals.

- The vacancy control process has been tightened following workstream approaches with new approach live from Monday 15th September, which is now utilising the TRACs system and ceasing the reliance on paper approval.

- Executive Directors provided updates on the Thematic Programmes focusing on Workforce, CHC and UEC.

- Deep dive on the Executive oversight of Nursing Variable Pay focusing on the Stand-up of the Nursing Workforce Hubs, which will:

  - Twice daily review of acuity, staffing deficits, and redeployment options

  - Coordinate cross-cover/ redeployment before escalation to temporary staffing

  - Scrutinise and approve all bank and agency requests

  - Apply consistent challenge to ensure clinically safe and cost-effective decisions

- R&S board will continue to track performance against the themes and the service group trackers, with details on the actions aligned to the Annual Plan Finance Update to be assessed at the next meeting on 24 September.

  - Update Thematic Workstreams

Each of the Thematic Workstreams have detailed Project Initiation documents. These are live documents but a version at 16th September is provided in the Appendix 1 for reference.

  - Savings Delivery and £55.4m

Full details on the savings assessment at 11 September was provided in the papers that supported the Board meeting on that date. A summary of the key components of the plan is provided below.

Graph 1: Components of £55.4m Savings

Each part of the Savings is made up of:

- Part B

  - Part B1 Operational underspends

  - Part B2 N/R Opportunities and uncommitted expenditure

  - Part B3 Savings Trackers planned Schemes (Green and Amber only) at 4th September

- Part C

  - Part C1 Savings Trackers planned Schemes (Red) at 4th September

  - Part C2 Savings Trackers planned Schemes (Pipeline) at 4th September

  - Part C3 In year impact of the Thematic Schemes, excluding those planned values within the Savings Trackers

- Further Actions

  - Additional intervents to close the savings gap focusing on:

    - Executive oversight of variable pay

    - Additional capacity reduction

    - Non pay bans / restrictions for remainder 2025/26

- GOVERNANCE AND RISK ISSUES

The work detailed in section 3.4 provides the Heath Board with a line of sight to £55.4m savings required, which addresses the plan submitted on 31 March 2025. From the 11 September paper and submission to WG, which provided plans with a combined savings value of £55.4m, work must now commence to deliver these in full. Details on next steps are to be presented to Management Board on 17 September, setting out the action needed for the next R&S Board on 24 September.

The 11 September paper also incorporates the full level of financial risks both national and local, and at Month 5 three of these risks were materialising through the position.

- RECOMMENDATION

Members are asked to:

- ACKNOWLEDGE the updated report for ASSURANCE of ongoing delivery associated with the Recovery and Sustainability Board.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High-Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| No Implications |  |  |  |
| Financial Implications |  |  |  |
| No Implications |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| No Implications |  |  |  |
| Staffing Implications |  |  |  |
| No Direct Implications |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| No Implications |  |  |  |
| Report History |  | Routine report to Performance and Finance Committee |  |
| Appendices |  | Appendix 1 – Full schedule of PID @ 11 September |  |

APPENDIX 1 – PROJECT INITIATION DOCUMENTS @ 11TH SEPTEMBER