Quality and Safety Committee Action Log

| Open Actions |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action No. | Minute Ref. | Date | Agreed Action | Lead | Timescale | Status |
|  | 127/23 | 25.07.2023 | Service Group Highlight Report – MHLD An update on the ICF funding continuation for the Memory Service at Ty Garngoch be provided within the next service group highlight report | Nurse Director – Mental Health and Learning Disabilities | November 2023 | To be included within the service group highlight report in November 2023. |
|  | 129/23 | 25.07.2023 | Health Inspectorate Wales Prison Action Plan Gareth Howells to share information on the work under way to establish nursing resource from within mental health services. | Director of Nursing and Patient Experience/ Nurse Director PCC | August 2023 | Plan is still as previously agreed – hand over at the end of September to CTMUHB with the agreed resource moving to cover Swansea. This is delayed from April at CTMUHB’s request. |
|  | 79/23 | 25.05.2023 | External Inspections A report on progress of the actions to address the HEFA inspection in Fertility services to be received via the next Neath Port Talbot and Singleton Service Group Report Highlight Report. | Service Group Director NPTSSG and Director of Therapies and Health Science | August 2023 | To be in included in the report due to August’s Committee. |
|  | 62/23 | 15.05.2023 | Patient Story – Carol’s Story Sharron Price to gain the information on the gynaecology waiting lists and relay to members outside of committee. | Interim Nurse Director – NPTSSG | July 2023 | Completed. Information shared with committee independent members via email. |
|  | 66/23 | 15.05.2023 | Referral to Workforce, OD and Digital Committee. The issue of staff deficiencies across many areas within the NPTSSG, be referred to the Workforce, OD and Digital Committee. | Chair/Director of Corporate Governance | October 2023 | Referred to the Workforce and OD Committee. |
|  | 54/23 | 15.05.2023 | Referral Workforce, OD and Digital Committee. Assurance sought from the Workforce, OD and Digital Committee, on the issue of retention of staff members we have trained and what the health board does to ensure they remain with us. | Chair/Director of Corporate Governance | October 2023 | Referred to the Workforce and OD Committee for discussion |
|  | 49/23 | 28.03.2023 | Quality and Safety Group Report To provide a structure chart of the groups feeding into the Quality and Safety of Patient Services Group with details of each group’s purpose and the members of each group. | Interim Head of Quality and Safety | September 2023 | A presentation of the framework will be due in September 2023. |
|  | 50/23 | 28.03.2023 | Quality and Safety Dashboard The committee to receive a live demonstration of dashboard when launched. | Nurse Director, Morriston | Ongoing | To be placed on a future agenda. |
|  | 31/23 | 23.02.2023 | Training Courses/ESR issues To identify non-crucial training courses to be referred to Workforce and OD Committee. ESR issues relating to completed courses not appearing on the system to be referred Workforce and OD Committee. | Chair/Director of Corporate Governance | October 2023 | Referred to the Workforce and OD Committee. |
| Closed Actions |  |  |  |  |  |  |  |
| Action No. | Minute Ref. | Date | Agreed Action | Lead | Timescale | Status |  |
|  | 74/23 | 23.05.2023 | PCCPTS – Highlight Report A detailed report to a future committee on access to NHS dentistry and GP’s. | Service Director - PCCTS | September 2023 | Added to Work Programme |  |
|  | 77/23 | 23.05.2023 | Falls Prevention An update on Falls Prevention to be provided to committee in November 2023. | Director of Nursing and Patient Experience | November 2023 | Added to Work Programme |  |
|  | 78/23 | 23.05.2023 | Quality and Safety of Patient Services Group Update Suicide Prevention; a ‘deep dive’ review to be placed on the agenda for the committee in July 2023; | Nurse Director, Mental Health and Learning Disabilities | August 2023 | Complete On agenda for August 2023. |  |
|  | 269/22 | 22.11.2022 | Maternity Update to be provided regarding Birthing Centre, Midwifery Staffing levels and Safeguarding training numbers in Maternity Services. | Service Group Nurse Director, Singleton and Neath Port Talbot | August 2023 | Complete. On agenda for August 2023. |
|  | 78/23 | 25.05.2023 | Quality and Safety of Patient Services Group Update Gareth Howells to feedback the outcome of the bid for the tissue viability nurse at a future committee. | Director of Nursing and Patient Experience | July 2023 | Complete. |
|  | 130/23 | 25.07.2023 | Performance Report The Neurodevelopment Disorder report submitted to Performance and Finance Committee to be shared with Anne-Louise Ferguson. | Corporate Governance | August 2023 | Complete. |
|  | 127/23 | 25.07.2023 | Service Group Highlight Report MHLD Independent Members to visit Garngoch Hospital and the Community Mental Health Team as part of the Independent Member Visits schedule. | Corporate Governance | TBC | Complete. Will be added to the the Independent Member Visits schedule. Arrangements to be confirmed. |
|  | 62/23 | 15.05.2023 | Patient Story – Carol’s Story Sharron Price to gain the information on the gynaecology waiting lists and relay to members outside of committee. | Interim Nurse Director – NPTSSG | July 2023 | Completed. Information shared with committee independent members via email. |