SBUHB Maternity Services Actions from HIW Improvement plan

Actions in order of timescales

November 2023

| Risk/Finding/Issue | Service Action | Responsible Officer | Date Completed |
| --- | --- | --- | --- |
| Breast feeding Support 4. Women told us (in person and via the questionnaire) that there was not always support available to women in feeding their babies. | Provide feedback to staff regarding women’s comments to ensure they are aware- to be included in safety briefs/hand over/ walk-around | Ward Managers/Matron /HOM/DHOM | Completed |
| Timely care 10. Some women on postnatal ward told us that they pain relief was not always given in a timely manner. | The Lead Governance Midwife will direct staff that all missed or delayed administration of pain relief must be reported via Datix and managed in accordance PTR. | Lead Governance Midwife | Completed and being monitored via datix |
| 19 Staffing | Weekly Friday meetings will continue to be added to the diary giving staff an opportunity to keep up to date with senior managers. The weekly status presentation shared discussed during the meetings will be emailed to all staff. Any actions from the meetings to be logged and feedback given at future meetings. Ensure all staff groups including cross-cutting staff groups are included in weekly staffing updates and invites. | - HOM & Womens Health Divisional Manager - HOM & Womens Health Divisional Manager | Completed – dates in place and weekly presentation emailed to staff As above |
| 21. Escalation | Recirculate the current Maternity Services Escalation Policy, highlighting the actions and escalation process required ensure continued provision of safe services. Continue with daily safety huddles to look at staffing and acuity and escalation meetings to highlight concerns. | - DHOM - HOM/DHOM, Womens Health Divisional Manager & Singleton & NPT Service Group Directors | Awaiting final version |
| 22 Antenatal Assessment | Ensure that two telephone numbers are available to all women during pregnancy. | Community Matron | Complete numbers sent out to all staff |
| 27 Incidents | Staff to be advised that incidents are reported within the Datix system. Following completion of the investigation feedback is provided to the reporters by email within the Datix system. | Lead Governance Midwife | Completed – sent via Feedback to all staff |
| 29 IPC | Ward managers and senior staff to ensure adherence to the uniform policy and bare below the elbow policy. | Ward managers & Maternity Matron | Completed |
| 33 out of date equipment | Share the findings with staff and reinforce the procedures for monthly checking and documentation of stock items for expiry dates. | Ward managers & Maternity Matron | Completed |

December 2023

| Risk/Finding/Issue | Service Action | Responsible Officer | Date Completed |
| --- | --- | --- | --- |
| 1 Staffing | Keep the Maternity Voices Partnership (MVP) forum updated with staff recruitment and plans for ongoing plans to attract staff into the service. | Head of Midwifery & Consultant Midwife | Completed 18th December 2023 |
| 4 Breast Feeding Support | Agree dedicated PALS time to undertake weekly face to face surveys on the unit to encourage feedback on patient experience | Head of Quality Safety & Risk for Singleton & Neath Port Talbot Service Group/PALS | Started December 2023 – awaiting feedback from Pals – request made for weekly updates |
| 5 Environment | To Share findings of report with HB Estates Team and make plans to implement quarterly IPC audits | DHOM | Completed – date to commence January 25th 2024 |
| 7 BBU | Review the current layout of rooms in the BBU. | DHOM & Maternity Matron | Completed December |
| 7&8 Bay Birthing Unit | The Maternity service will risk assess the availability of the one resuscitaire in the BBU and monitor for any incident where more than one baby required resuscitation at any time, escalating the incident and reassessing the risk. In addition to the above, all the normal birthing rooms have access to standard baby resuscitation equipment – as in homebirths and Free Standing Birth Centre – this will be maintained and checked regularly. | DHOM & Bay birthing Unit Lead midwife | Completed - risk assessment being ratified in Q&S on 15th January 2024 |
| 9 Patient Choice | Feedback relating to the lack of documented birth plans to be shared with community midwives and the wider obstetric team. | HOM & Obstetric Lead/ Maternity Matron |  |
| 12 & 13 Communication Language & Listening | The service will share this feedback with staff at the weekly communication meetings – followed up by sharing of the presentation Email maternity staff to advise of the Health Board Welsh language training available. | HOM & Obstetric Lead DHOM | Completed – process in place Completed – information circulated to staff |
| 14 Other Languages | Reminder to be sent out to all staff regarding the importance of asking women their preferred language and ensuring this is documented. Remind staff of translation services available to the health board Submit request for WPAS amendment to ensure that ethnicity and preferred language is mandatory. | DHOM HOM HOM with support from the HB Information Lead | Completed Posters shared with staff and in clinical areas. Completed |
| 18 Risks | Maternity services will re-review the health board risks to ensure that the risks are up-to-date. | HOM & Womens Health Divisional Manager | Review of risks undertaken December 2023 |
| 22 AAU | Reinforce the requirement of AAU staff to escalate to the labour ward coordinator when activity is increasing. | Maternity Matron | Completed |
| 25 ITU Transfers | The recorded risk will be reviewed with reference to the current incident data and clinical reviews and if any increase in transfers will be escalated to agree actions as necessary. | Lead Governance Midwife/ Divisional Manager/ HOM | Monthly risk register reviews include monitoring number of incidents relating to critical care environment needs. In December 2023 – I reported incident review is underway |
| 26 Lifts | Continue to monitor via the risk register Service Group will link with Estates to look at a more permanent solution to maintaining functional lifts. | Divisional manager Singleton Hospital Site Manager with support of the Estates Department | Complete – risk review 29th December 2023 SOP in place for transferring women to labour ward when lift not functioning. Divisional management team to discuss future plans for the lifts |
| 28 Incidents | Agree a revised process for timelier incident management and identification of themes and develop an action plan for completion of the backlog. | HOM/ Lead Governance Midwife | Process in place – monitoring will be via Q&S forum |
| 29 IPC | Continue with local spot check IPC audit and reinforce the message that it is everybody’s responsibility to challenge non-adherence to this policy. | Ward Managers & Maternity Matron | December 2023 audit undertaken by midwifery matron – audits are being submitted for monitoring via the Maternity services IPC meetings |
| 30 Inappropriate location for placentas | Review and agree an alternative locations for placenta storage. | Maternity Matron with support of IPC lead | completed |
| 34 Patient Records | Findings in relation to standards of record keeping highlighted in the HIW report will be communicated to staff, and expectations re- affirmed with notice of planned record keeping audit arrangements. When reviewing records for reported incidents or teaching sessions any examples of poor record keeping by individuals will be escalated to the line manager. | Lead Governance Midwife & Lead Obstetrician for Governance Governance Lead Midwife & Lead Obstetrician for Governance | Completed Plan for CSFM to discuss standards of record keeping with midwives. Medical leads will share expectations of record keeping with team- named stamps to be ordered |
| 37 Staff told us that leaders were not always visible and that communication between senior management and staff is ineffective. | In future staff meetings- establish from staff what further senior leaders can do to support them and the service. | HOM/DHOM | Completed – to be monitored via feedback at the staff meetings |
| 41 People engagement feedback & learning | Corporate patient feedback team now provide a monthly report for Maternity Services and this will be shared with all staff. CSFM and medical education leads to continue to promote the importance of reporting concerns. Senior clinical managers to encourage concerns to be shared at each contact with staff members. The guardian service will continue to be promoted via email and shared at staff meetings across the maternity service. | DHOM CSFM HOM/DHOM/Obstetric medical Lead/ Service Group Nurse Director HOM/Obstetric medical lead | December feedback report being shared with staff Jump calling policy shared with staff – plan is to update the policy to direct staff to the HB website on how to raise concerns. |
| 42 Information Governance | Maternity Services have requested support from the Corporate Information Governance team on implementing more robust storage of confidential patient identifiable information. | DHOM | Meeting held with corporate IG representative. Risk assessment completed awaiting approval at Maternity service Q&S forum January 15th. Risk to be discussed at IG meeting in January 2024 |

January 2024

| Risk/Finding/Issue | Service Action | Responsible Officer | Date Completed |
| --- | --- | --- | --- |
| 1 Staffing | Explore the option to reintroduce volunteers back onto Ward 20 & Ward 19 as they can often provide very basic support to women and staff. The outcome of the review to be feedback at the Head of Midwifery & Matrons meeting. | DHOM | DHOM has contacted the volunteer services to discuss – application form to be completed. Meeting arranged for April when volunteer lead returns from leave |
| 2 Health Promotion | The health board website has a functionality that translates text into other languages when selected by the user (and a user’s browser settings can also automatically translate pages into the language of their choosing). However, the service will review all information provided to patients in other languages. | Public Health Midwife | Awaiting confirmation from specialist |
| 3 Unicef Baby friendly | Regularly share the HB BFI accreditation level at staff teams meetings, including HB breast feeding rates and adherence to guidance. | Infant Feeding coordinator | Awaiting confirmation from specialist |
| 5 Environment | Implement quarterly Infection Prevention Control surveys to include maternity/infection control leads and Estates in all clinical areas. | DHOM, with support from Infection Control Lead & Estates representative | Planned audits commencing 25th January 2024 |
| 6 Location of Bereavement room | The maternity service will review alternative location of labour ward bereavement room – ensuring the clinical safety of the woman is also maintained and provide feedback to the Service Group Directors. | Bereavement midwife, Clinical Team, with support from representative from MVP and Estates lead | Initial review of the current room has been undertaken with plans being developed to improve the access of the room for women and their families. |
| 6 Bereavement Room | Update the risk register to reflect the mitigations used due to the lack of dedicated bereavement area. | Divisional manager & HOM | Risk reviewed in December 2023 |
| 9. Patient Choice | Evidence of Birth Plans being discussed with women and documented in their maternity records to be in monitored via monthly notes audit. These discussions should include birthing options, pain relief and feeding choices. | DHOM/Infant Feeding Lead Midwife/ CSFM | Need to identify a member of staff to complete audit |
| 12 Communication and listening | Monitor monthly feedback at Maternity service Q&S Forum | HOM |  |
| 14 Other Languages | Monitor via record keeping audits that language preferences are being discussed and documented | Ward Managers & Clinical Supervisor of Midwives | Need to identify a member of staff to complete audit |
| 15 Signage | Link in with estates and MVP representatives to identify and address areas for improved signage. As a priority, the health board is going to look for a sign to be placed on the side of the building as you approach via the main access route, so it will be visible for people attending by car and /or walking. The date for delivery is to be confirmed (anticipated January 2024). Any further changes and timescales will be agreed following wider review of signage on site with the operational management team. | DHOM, Divisional Manager Hospital operations DHOM, Divisional Manager Hospital operations | Email sent to MVP chair for a member to attend – awaiting confirmation of date Awaiting update from divisional management team |
| 18 Risk Management | Link regularly with the corporate risk lead and ensure that we escalate updates regularly. | HOM & Divisional Manager & with support from Assistant Head of Risk & Assurance | Monthly update meetings planned for 2024 |
| 19 Staffing | Continue with progress already made with the recruitment campaign in Swansea Bay and provide a progress update to the Divisional Business Meeting. | Workforce Lead, HOM & Womens Health Divisional Manager |  |
| 20 Ultrasound scanning | Until compliance is achieved, review the criteria for scanning to ensure capacity is targeted at the highest risk women and continue to report any adverse impact of non-compliance. | HOM/Clinical Lead for Obstetrics/ Radiology Services Manager | Meeting arranged 10th January 2024 to agree key plans for scanning provision |
| 21 Escalation | Following the final outcome of the OCP process and approval of new the arrangements which is expected in December 2023, we will implement an escalation plan which will include the minimum staffing levels for the unit. | HOM with support of Workforce Lead | New escalation policy being ratified Q & S meeting 15th January – meeting postponed due to Ind. Action. Policy being circulated electronically for ratification. Policy being sent to staff as a working draft. |
| 23 & 24 Obstetric Theatres | Undertake an infection prevention control review of the second obstetric theatre and agree action to mitigate risks identified. This is already on the risk register. Any incidents are reported and jointly reviewed with theatre management. Discuss with Theatre division the options to safely staff a second theatre | Theatre lead/ IPC team/intrapartum lead/matron. Governance Lead with support of the Theatre Lead. HOM, Clinical Lead, Intrapartum Lead, with support of the Theatre Lead and Divisional Manager | Intrapartum lead to contact theatre lead Site manager has confirmed this is one of the priority areas in maternity for review. Site meeting with maternity being organised |
| 26 Lifts | To explore with Estates the option of having an override system for Labour Ward use in at least one lift. | Singleton Hospital Site Manager with support of the Estates Department | Over ride Key kept in the Antenatal Assessment Unit. |
| 29 IPC | Request additional planned audits with the HB IPC team to monitor standards. | Maternity Matron with the support of the HB IPC team |  |
| 35 Governance & Leadership | Continue with plans for substantive posts to be advertised | Service Group Nurse Director and Women Health divisional Manager | VCF’s for HOM & DHOM awaiting approval prior to advertising |
| 37. Staff told us that leaders were not always visible and that communication between senior management and staff is ineffective. | Involve the Clinical Supervisors to further discuss the support staff would like from their senior leaders and share the themes from HIW staff survey with the senior maternity leaders | HOM/CSFM | HOM has shared staff experiences with senior team. Themes to be discussed as agenda item on next senior team meeting. CSfM to be invited to meeting to support. |

February 2024

| Risk/Finding/Issue | Service Action | Responsible Officer | Date Completed |
| --- | --- | --- | --- |
| 1 Staffing Some comments provided by patients indicated that staffing problems had negatively impacted their experience. | Develop a plan to further promote user feedback and ensure all feedback is shared and acted upon. | Deputy Head of Midwifery (DHOM)/ Consultant Midwife |  |
| 2 Health Promotion | Explore options for auto-response to cover other language choices in the new the digital patient referral system. | Divisional service manager with the support of the Health Board Digital Services |  |
| 3 Unicef baby friendly | Share level of HB accreditation on adverts and recruitment website. | Infant Feeding Lead with support of Workforce lead |  |
| 4 Breast Feeding | The service to review the option of reintroducing breast feeding peer supporters back into the postnatal ward with the local peer support group - feedback outcome of the review at HOM & Matrons meeting. | DHOM and Infant Feeding Lead Midwife |  |
| 10 Timely care Some women on postnatal ward told us that they pain relief was not always given in a timely manner | Fully implement self-administration of medicines across the service. | DHOM, Intrapartum lead Matron with the support of the Pharmacy Lead for Maternity. |  |
| 13 Welsh Language | Review posters/leaflets and other information provided to women and request any not currently in welsh are translated | DHOM |  |
| 19 Staffing shortages | We will use social media as a two way communication channel between staff and senior leaders. | DHOM | Whatsap group available for staff to communicate regarding shifts. Operational Phone in place for staff to contact. |
| 21 Escalation | Finalise the escalation policy, which is currently being updated and share with staff. | HOM |  |
| 22 Antenatal assessment Unit | Current guidance will be reviewed to ensure that a process is in place in AAU to follow up women who DNA AAU appointments and that this is being complied with. | Clinical Supervisor of Midwives and Maternity Matron/ Ward Manager. DHOM/Obstetric Matron |  |
| 27 Incidents | Recommence the monthly newsletter for updates and ask staff for feedback on its structure and content. | Lead Governance Midwife |  |
| 31 Blood Management | An audit of incidents relating to delays in obtaining blood results for obstetric patient for the previous 6 months (May to November 2023) will be undertaken to identify the level of risk. | Lead Governance Midwife | Bloods now marked urgent and placed in specific bags so identified as urgent by Path lab. |
| 34 Patient Records | A sample spot check will be undertaken of a subset of items (legibility of signatures and capital letters) following the above reminder. | Lead Midwife Quality, Safety and Risk |  |
| 38 Policies & Guidelines | Development of a Guideline and Policy group that will look at a RAG rated policy document to keep track of outdated or soon to be outdated policies | Consultant MW, Intrapartum Lead and Clinical Lead | Forum developed, TOR written. 1st meeting 1st November 2023 |

March 2024

| Risk/Finding/Issue | Service Action | Responsible Officer | Date Completed |
| --- | --- | --- | --- |
| 2 Health Promotion | Review and update maternity website and consider wider opportunities for information sharing (Inc. public health information). | Informatics Lead Midwife/Public Health Midwife/ Service Manager with the support of the support of the Health Board Digital Services. |  |
| 4 Breast Feeding Support | With the support of the Clinical Supervisors for Midwives (CSFM) the Infant Feeding midwife will ensure all staff are confident in providing breast feeding support to women – specific training to be provided to meet any identified needs Regular bank and agency staff (Inc. HCSW) will be provided an update on SBUHB infant feeding training and BFI updates | Infant Feeding Lead Midwife & Clinical Supervisors for Midwives DHOM & Infant Feeding Lead Midwife |  |
| 5 Environment | The service will escalate IPC reports of unresolved issues via the Service Group Infection Control meeting. Risks associated with unresolved environmental matters will be recorded within the service risk register and escalated through service group and corporately in accordance with the health board risk appetite. | DHOM, with support from Infection Control Lead & Estates representative |  |
| 6 Location of Bereavement room | The Health Board will Benchmark facilities with other health boards Seek the support of a woman or family to share their experience in a story which may help to assist staff to support parents during this sad time. | Bereavement midwife, Clinical Team, with support from the MVP Bereavement midwife |  |
| 12 Communication & Language Listening | The less favourable feedback from women in relation to communication and listening is to be shared with staff and subsequent feedback at future staff training & induction sessions which will include a patient story. | Practice Development Lead/ Medical training lead |  |
| 13 Welsh Language | Monitor Welsh language mandatory training uptake as part of the commitment to improving on the Welsh Language Standards. | Maternity Services Managers |  |
| 16 Rights & Equality | Ensure Mandatory diversity and equality training is attended and compliance is shared with the teams on a monthly basis via the Training and education forum. | Matrons, Divisional Manager |  |
| 17 Engagement with minority groups | The Health Board will explore opportunities to seek the views of women from minority groups via face-to-face discussions | HOM |  |
| 20 Ultrasound Capacity | Review the evaluation of the current midwifery scanning provision. | DHOM & Womens Health Divisional Manager |  |
| 22 Antenatal Assessment Unit | Quarterly audit of calls against individual records will be conducted to monitor calls verses women seen and any delays to 30 minute target. | Clinical Supervisor of Midwives and Maternity Matron |  |
| 32 Management of medical devices and equipment | Wide scale review of asset register to be undertaken to include service, repair, cleaning and decontamination. | DHOM & Intrapartum Lead Midwife |  |
| 36. It was difficult to establish clear lines of reporting and accountability, no organisational structure could be produced. | Once appointed into posts, a new organisational chart will be finalised and shared. | Divisional Manager |  |
| 39 Cannulation | Train the trainers have been implemented which will support the roll out of cannulation training for all midwives. | Maternity Matron |  |
| 40 Specialist midwife roles in place are not fully embedded into health board structures. | Role descriptors for the specialist roles will be shared to provide clear information on how these posts are embedded into the maternity and wider HB services and groups to support the maternity vision. | DHOM |  |
| 41 People engagement, feedback and learning | The HB will explore any opportunities to provide cultural training/support for the maternity services. | Womens Health Divisional Manager/HOM and Organisational Development Lead |  |

April 2024

| Risk/Finding/Issue | Service Action | Responsible Officer | Date Completed |
| --- | --- | --- | --- |
| 6 Location of Bereavement room | To seek out other opportunities to maximise the privacy of the room. | Bereavement midwife, Clinical Team, with support of reps from MVP & Estates lead |  |
| 11 delays in induction of labour | The service aims to re-open the NPT Birth Centre which will assist with patient flow in Singleton. Undertake a unit flow project and identify opportunities to improve safe, timely transfer out to the community. | Consultant Midwife and wider Maternity Management Team DHOM & Quality Improvement Lead |  |
| 14 Other languages | Explore the feasibility of implementing a new language translation app – Language line solutions and provide outcome of the review at the divisional business meeting. | Informatics Lead Midwife |  |
| 22 Antenatal Assessment Unit | Undertake a review of the AAU service and its current location in the unit. The review will include ensuring referral criteria/ timeliness of assessments/ previous incidents reported to identify themes and gain Feedback from women. The terms of reference for this review will consider each of the areas highlighted by HIW. Completion of the OCP process and implementation of proposed arrangements will ensure that an additional midwife is available on Ward 19 to also support AAU when required. A review of the telephone assessment process/information recording and sharing will be included in the TOR indicated in the AAU review. Audit admission to assessment times to ensure current AAU guidance is being adhered to. | DHOM/Service Manager/ Matron HOM with support from the Workforce Lead Clinical Supervisor of Midwives and Matron Matron and Ward 19 manager |  |
| 25 ITU | The location of ITU is already on the Health Board Risk Register reflecting cross site working. The Health Board will undertake a review of the current arrangements for transferring a woman requiring ITU care and gain support from the wider specialist Heath Board Teams. | Obstetric Clinical Lead & Lead Midwife for Governance with the support of The Obstetric Anaesthetic and ITU Lead Obstetric Clinical Lead & Lead Midwife for Governance with the support of The Obstetric Anaesthetic and ITU Lead |  |
| 34 Patients Records | Commence the annual peer review record keeping audits in April 2024 and request all staff complete the audits by June 2024 in order to provide assurance of the standards for record keeping and share findings and any identified improvement as soon as possible. | CSFM / All Midwives & Obstetric medical Staff |  |

June 2024

| Risk/Finding/Issue | Service Action | Responsible Officer | Date Completed |
| --- | --- | --- | --- |
| 17 Engagement with women and families from minority groups and diverse backgrounds, especially in relation to their feedback on care. | Continue with the work Swansea Bay’s MVP have commenced to increase representation of women from minority and diverse groups. Report on progress at the Maternity Voices forum. Ensure the Swansea Bay University Health Board website is developed to support easy access to pregnancy information in other languages- (similar to the pregnancy 111 website) | HOM & with support from MVP Lead Consultant Midwife MVP lead with support from HB Communication team representative |  |
| 20 Ultrasound capacity | Identify the current gaps in provision and liaise with radiology services to develop a business case to achieve full compliance. | HOM & Womens Health Divisional Manager with the support of the Radiology Services Manager |  |

July 2024

| Risk/Finding/Issue | Service Action | Responsible Officer | Date Completed |
| --- | --- | --- | --- |
| 4 Breast feeding support | Recruit via research funding for a 12 month fixed term contract for HCSW (band2/B3) specifically trained to provide breast feeding support. Monitoring the impact of this post to use for future business case bids. | Research Midwife & DHOM |  |
| 8 Bay Birthing Unit Resuscitaires | Benchmark against other units and review the standards | Consultant Midwife |  |
| 34 Patient Records | Report the findings of the annual peer review records keeping audits | CSFM |  |

September 2024

| Risk/Finding/Issue | Service Action | Responsible Officer | Date Completed |
| --- | --- | --- | --- |
| 4 Breast feeding support | Embed the new MCA role within Maternity Services to support women with breast-feeding. | Midwife Facilitator/Workforce Transformation Midwife |  |
| 7 Bay Birthing Unit | Set up a project group to review the overall layout of the maternity unit on Singleton site (including the suitability of the 2nd Maternity Theatre – see Recommendation 23) to improve the environment of care and facilities | Consultant Midwife, HOM, Clinical Lead for O&G & Divisional Manager |  |
| 22 Antenatal Assessment Unit | Plan implementation of new AAU pathways and documentation process (BSOTS- Birmingham Symptom Specific Obstetric Triage System) | Maternity Matron, Ward 19 Manager |  |
| 23 Obstetric Theatres | The suitability of the second obstetric theatre will be included as part as the project referred to in recommendation 7. | HOM, Clinical Lead, intrapartum Lead and Divisional manager |  |

October 2024

| Risk/Finding/Issue | Service Action | Responsible Officer | Date Completed |
| --- | --- | --- | --- |
| 22 AAU | Continue with future plans to implement a new telephone system with one number for the whole service which will direct patients to the correct phone line first time. | DHOM / Womens Health Divisional Manager |  |

January 2025

| Risk/Finding/Issue | Service Action | Responsible Officer | Date Completed |
| --- | --- | --- | --- |
| 3 Unicef Baby Friendly | Work towards 95% compliance of staff attending two day BFI training. | Infant Feeding Lead Midwife/ Service Manager/DHOM |  |