Board Effectiveness Action Plan 2024

Quality & Safety Committee Extract

| Quality |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Progress Level: Maturity |  | Criteria to Support this level The health board has a quality strategy, with clear quality priorities, that integrates into and drives our overall organisational strategy. All staff are aware of the quality priorities. A quality impact assessment process is embedded and all major decisions are made based on quality impact considerations. The health board receives high quality intelligence and information through both soft and hard sources to provide assurance that services are safe, and takes account of patient experience, outcomes, and quality improvement. Assurance sources are both internal and external and reinforce the same picture. Information on quality is of high quality, with no data quality issues, is well summarised and triangulated to provide assurance around quality of care. |  |  |  |
| No | Recommendation |  | Action | Lead Comm. Lead Exec(s) Target Date | Progress/Status |
| 22 | Baseline review of resources to support quality across the organisation in order to consider our structures against those required to meet our responsibilities under the Duty of Quality. |  |  | Q&S Comm. Dir of Nursing Dir of Corp Gov. Service Groups September 2024 | February 2024: The Director of Corporate Governance is currently taking forward a piece of work in support of this action. |

| Performance Reporting |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Progress Level: Maturity |  | Criteria to Support this level The board systematically receives reports from stakeholders providing feedback of impact of plan implementation. A line of sight links lower level objectives with high level strategic objectives Corporate and service group individual performance measures are connected to the corporate performance measurement framework The organisation reports integrated performance and cost information The board uses ‘value for money’ information to make strategic decisions about whether or not to engage in areas of activity |  |  |  |
| No | Recommendation |  | Action | Lead Comm. Lead Exec(s) Target Date | Progress/Status |
| 28 | Although some improvements have been made, there remains room for improvement in the way in which the quality and safety of services are scrutinised. The Health Board should ensure that the Clinical Executive Directors responsible for quality and safety present the Integrated Performance Report (IPR) to the Quality and Safety Committee. |  | Discuss the presentation of the Q&S elements of the performance report and agree future presenters to the Q&S Committee. | Q&S Comm. Dir of Nursing Exec Medical Dir Dir of Therapies March 2024 | February 2024: Discussions are taking place regarding the format and nature of the feedback required and the Clinical Executives will commence this from April 224. |

| Patient and Public Involvement & Engagement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Progress Level: Maturity |  | Criteria to Support this level The benefit of patient and public involvement is well understood and embedded across the organisation. Collaborative behaviour is embedded within the organisation. A range of tools commonly used to engage and involve patients and the public. Ongoing patient and public engagement takes place for all significant service changes (and many non-significant service changes), co-producing outcomes. Patient and public involvement is ongoing and embedded into how the health board operates. |  |  |  |
| No | Recommendation |  | Action | Lead Comm. Lead Exec(s) Target Date | Progress/Status |
| 29 | External facilitator be commissioned to develop the patient and stakeholder experience and engagement sub-group to expand areas of focus from ‘friends and family’ to enable more engagement undertaken around the annual plan and priorities for future years. |  |  | Q&S Comm. Dir of ICE T.B.C. |  |
| 30 | Tools and techniques be created for staff to measure staff experience, patient experience and outcomes to understand their services to identify problem areas. |  |  | Q&S Comm. Dir of WOD Dir of ICE T.B.C. |  |