POSITION IS BASED ON UPDATES APPROVED BY SERVICE DIRECTORS UP TO END NOVEMBER 2025

| Inspection | HIW Ref | Date of Inspection | Areas to Improve (Recs) | Actions Agreed | Actions Complete | Actions Ongoing | Actions Overdue | Expected completion date for all | Other Notes/Comments in respect of remaining actions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MENTAL HEALTH & LEARNING DISABILITIES SERVICE GROUP |  |  |  |  |  |  |  |  |  |
| Cefn Coed Hospital (Tawe) | 21193 | Mar 2022 | 21 | 36 | 35 | 1 | 0 | 2026/27 | One action remains – linked to Strategic Outline Case & dependent upon capital funding availability from WG |
| Ward F, NPTH | 03367 | May 2023 | 33 | 66 | 61 | 5 | 5 | End Dec 2026 | Actions remaining are linked to estates issues and are dependent upon capital funding |
| Caswell Clinic, MHLD | 03642 | Sep 2023 | 15 | 15 | 12 | 3 | 3 | End Feb 2026 | Actions remaining are associated with estates work and roofing issues |
| Tonna Hospital Suite 2 | 03690 | Oct 2024 | 17 | 37 | 27 | 10 | 8 | End Apr 2026 | Actions remaining are linked to estates issues and are dependent upon capital funding. |
| Laurels & Briary | 04072 | Apr 2025 | 16 | 24 | 23 | 1 | 1 | End Nov 2025 | Nov 25: Three further actions signed off as complete in November. One remains to be confirmed. |
| PRIMARY COMMUNITY & THERAPIES SERVICE GROUP |  |  |  |  |  |  |  |  |  |
| HMP Swansea | n/a | Aug 2021 | 29 | 38 | 37 | 1 | 1 | - | One action remains – it relates to staffing numbers in HMP Swansea. This is recorded on the service and Board risk registers. Discussions continue to consider opportunities, but without additional funding or transfer of resources, a completion date cannot be indicated currently. |
| MORRISTON SERVICE GROUP |  |  |  |  |  |  |  |  |  |
| IR(ME)R: DI Dept, Morriston | 03297 | Feb 2023 | 16 | 49 | 43 | 6 | 6 | End Apr 2026 | Some outstanding actions are dependent on MPCE service and ongoing RISP project and workforce redesign. |
| IR(ME)R: Nuclear Medicine, Morriston | 03707 | Jun 2024 | 13 | 23 | 12 | 11 | 11 | End Apr 2026 | Some actions dependent on RISP project and workforce redesign. |
| ED Morriston | 03716 | Nov 2024 | 15 | 44 | 20 | 24 | 24 | End Jan 2026 | Most actions will be completed by the end of December 2025. However, addressing hand hygiene training, PADR compliance and ensuring mandatory and statutory training achieves >85% compliance will be challenging while management time us reduced to cover staffing gaps – so later date of January 2026 indicated for overall completion. |
| Diagnostic Imaging, Singleton | 03653 | Feb 2025 | 21 | 23 | 12 | 11 | 11 | End Apr 2026 | Some actions are dependent on a national workstream via the All Wales Quality forum. |
| Minor Injury Unit, NPTH | 03903 | May 2025 | 16 | 25 | 10 | 15 | 6 | End Jan 2026 | Nov25: Position reflects the update provided to HIW on 14/11/2025. A further update is being coordinated for submission to HIW early in February, following which this position will be updated. |
| NEATH PORT TALBOT SINGLETON SERVICE GROUP |  |  |  |  |  |  |  |  |  |
| Paediatric Services: Ward M & Oakwood Ward, Morriston | 03294 | Jan 2023 | 10 | 12 | 9 | 3 | 3 | - | Of the three remaining actions, two are subject to review currently for signoff in November 2025. The final action relates to the refurbishment of the environment, for which progress made and action remaining (and associated timescales) are subject to internal discussion. |
| Birth Centre, NPTH | 03750 | Feb 2025 | 8 | 12 | 11 | 1 | 1 | End Nov 2025 | The one action remaining relates to the update of clinical policies, the last of which will be ratified in November 2025. |