| Date of Inspection | Inspection | SG | HIW Ref | Nbr Report Rec’ns | Nbr Actions Agreed | Nbr Actions Complete | Nbr Actions Ongoing | Nbr Actions Overdue | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sep 2023 | HIW Clinical review of death in custody JSR | PCT | DIC21/10/2022 JSR | 3 | 3 | 1 | 2 | 2 | The two open action have been completed. Timelines extended to February 2024 to obtain evidence of completed actions through governance structures. |
| June 2021 | HIW Independent Investigation into the death of DJ | PCT | DIC/2021/06 | 16 | 16 | 11 | 5 | 5 | All outstanding actions are for the Prison Governor – updates have been requested |
| 21/2/23 - 10/03/2023 | Prison and Probation Service | PCT | HMIP Inspection | 13 | 13 | 2 | 11 | 11 | Outstanding actions - 9 for the Prison Governor - 2 for Prison Healthcare (one is complete but deadline extended to obtain evidence of completion through governance structures / one requires additional funding and opportunities are being explored) |
| 30/06/2022 | HIW review of HMP governance arrangements | PCT | HIW/30/06/2022 | 28 | 35 | 28 | 7 | 7 | Outstanding actions - 2 for MHLD service group – update requested - 4 for Prison Healthcare (2 are complete and deadline extended to obtain evidence through governance structures and 2 actions are outstanding due to additional funding requirements which are being explored) - 1 outstanding action relates to the completion of the health care needs assessment – there are 8 actions outstanding from a total of 28 recommendations. Prison healthcare are responsible for two of these outstanding actions – both of which are due for completion by end of January 2024. |