| Meeting Date | 25th July 2023 |  | Agenda Item |  |  | 3.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Updates on progress against the 2022 HIW action plan for HMP Swansea and the wider combined Action |  |  |  |  |  |
| Report Author | Karen Gronert, Head of Nursing |  |  |  |  |  |
| Report Sponsor | Brian Owens, PCT Service Group Director |  |  |  |  |  |
| Presented by | Karen Gronert, Head of Nursing |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | - To provide an update on progress against the 2022 Inspection by HIW of HMP Swansea and the Health, Care and Wellbeing Development Plan - To provide and update on the progress of the Death in Custody and Article 2 Action plans for HMP Swansea - To highlight the risks associated with the loss of the temporary funding - To provide initial feedback from the HMIP and HIW Inspection on week commencing 6th March 2023 |  |  |  |  |  |
| Key Issues | - Progress against HIW action plan and outstanding actions. - Financial deficit and the risks with removing the temporary partial head room |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☒ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - Note the contents of this report |  |  |  |  |  |

TITLE OF REPORT

- INTRODUCTION

This report is intended to provide assurance of the ongoing multi agency work to deliver on the recommendations from Health Inspectorate Wales (HIW) action plans.  The progress to date is documented in the appended action plans and identifies areas of improvement in the clinical and quality governance arrangements within HMP Swansea.

- BACKGROUND

In July 2022, HIW published their ‘Local review of the Quality Governance Arrangements in place within Swansea Bay University Health Board, for the delivery of healthcare services to Her Majesty’s Prison, Swansea’

The review identified that the quality governance arrangements in place at Swansea Bay University Health Board did not adequately support the delivery of good quality, safe and effective healthcare services to the population of HMP Swansea.

The report also concluded ‘We are not assured that effective oversight is in place to ensure that prison residents receive a safe and equitable healthcare service, consistent with that provided to people within the community.’

The report culminated in 29 recommendations centred mainly on improved governance arrangements and measures to raise the profile of prison healthcare within the health board, to ensure that the quality of prison healthcare is designed, delivered, and monitored effectively.

The recommendations were focused on the following themes: governance, access, workforce, risk management and health improvement.  A working group was established on a fortnightly cycle to drive forward the improvement work required to progress the actions and provide assurance to the Health Board and the Prison Partnership Board. The group was multi agency and worked to complete/close all 29 HIW recommendations. Following a report to the Prison Partnership Board in December 2022, assurance was given that all the recommendations had been developed into an action plan to support implementation.

- GOVERNANCE AND RISK ISSUES

HIW 2022 Action Plan

A copy of the recommendations and action plan from the HIW 2022 inspection is attached (Appendix 1). Many actions were immediately completed and closed.  At the time of writing this report there are 8 actions partially closed, these will take additional time to achieve due to the resource requirements needed for implementation. And complexity. These relate to:

- Provision of nursing establishment

- Formalisation of pathways and audit processes

- Successful implementation of the HCWDP

- Reporting updates through quality and safety structures

- Mental Health In Reach resource

- Patient feedback to inform continual improvement for the Mental Health In Reach service

- Health promotion activity

- Updating the prisoner induction pack to include reference to Putting Things Right complaints policy

Resource & Nursing Establishment

In response to the HIW report a full capacity analyses was undertaken to identify the resource and staff requirement needed to implement required and ongoing improvements. Significant financial implications for the full implementation of the recommendations to be achieved have been identified. As of 4th July 2023, temporary funding is still being utilised to fund the nursing workforce while other sustainable options are explored within the health board and more widely. Capacity issues are recorded on Health Board risk register (Risk score 20).

In respect of Mental Health In-Reach service in particular, the Service Level Agreement (SLA) between SBUHB and Cwm Taf Morgannwg University Health Board (CTMUHB) has been extended until September 2023. This extension was driven by CTMUHB difficulties in recruitment to the posts for HMP Parc Prison In Reach (PIR) Team.

SBUHB Mental Health PIR Secondary Care Services have been successful in securing Mental Health Service Improvement Funds (MHSIF) to expand the PIR Secondary Care Service for HMP Swansea. The MHSIF funding in addition to the allocated percentage of resource that will be derived from cessation of the SLA will provide a significant improvement in service delivery, with anticipated improvements in assessment and intervention for secondary care patients within HMP Swansea. It will also support continued service developments and quality improvement initiatives for improved patient experiences. A revised target for completion of MHIRT funding action is 30th September 2023.

Pathways and Audit Processes

An operational group to review the clinical pathways has been established. Early focus has been on emergency response and review of Standard Operating Procedures (SOPs). A New TEAMS channel has been developed to enable staff to access and input into the development of new SOPs, pathways and policies prior to publication to the shared drive and COIN. A revised target date of 31st December 2023 has been indicated for completion.

In respect of audit activity, a joint Improvement Plan is in place, developed by PCT/MHLD, which is updated via the HIW working group. This was presented to the Prison Partnership Board (PPB) in Dec 2022.

The Audits for Mental Health Prison In Reach Secondary Care Service (PIR) for HMP Swansea will be discussed and agreed in the MHLD SG Clinical Audit Group as part of a standing agenda item. Audit outcomes are reported to the SBUHB Mental Health and Learning Disabilities (MHLD) Quality & Safety Group.

Health representatives from MH PIR Secondary Care Service attend the HMP Clinical Operational Group for oversight of the HMP Audits. A revised target date of 30th November has been identified to agree arrangements for reporting & review of audit activity at the PPB.

Health, Care and Wellbeing Delivery Plan (HCWDP) 2022-25

The working group was subsequently repurposed into 2 operational task and finish groups, to oversee the implementation of the Health, Care and Wellbeing Delivery Plan (HCWDP) 2023-25 (Appendix 2).  The successful implementation of the HCWDP is one of the outstanding recommendations from the HIW 2022 action plan.  The HCWDP has 28 actions, of which 19 actions are completed.  The Prison Partnership Board and the Service Group Patient Safety and Compliance Meeting monitor progress against the nine open actions.  The nine remaining open actions are due to complete by the end of August 2023.

Death in Custody/Article 2 Investigation Action Plans

Actions and recommendations resulting from investigations by the Prison and Probation Ombudsman and HIW into deaths in custody and article 2 investigations have been developed into one combined action plan with timescales for completion and responsible officers identified.  This action plan includes actions for prison healthcare, the prison, the mental health in-reach team and Local Authority.  The table below details the outstanding actions and the responsible person, it is to note there are no outstanding actions for prison healthcare on the existing combined action plan; the remaining open actions are the responsibility of HMP Swansea.

There were two deaths in custody, which occurred last year, and are under investigation.  These will follow the Health Board’s serious incident investigation process alongside the Prison and Probation Ombudsman and HIW investigation, the timescales of completion are unknown due to them being led externally.  On receipt of the reports, actions will be agreed and learning and recommendations will be identified.  These will then be included in the combined action plan for implementation and completion.

| Report | Responsible person |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Governor | Head of Prison Healthcare | Governor/Head of Prison Healthcare | Inreach Manager | Head of Nursing LA |
| SI/2014/PPO (article 2) | 1 |  |  |  |  |
| DIC/2021/06 | 1 |  |  |  |  |
| DIC/2019/12 | 3 |  |  |  |  |
| DIC/2020/09 | 1 |  |  |  |  |

HMIP and HIW Joint Inspection 2023

There has also been a HMIP and HIW joint Inspection of the Prison week commencing 6th of March 2023. The full report will be submitted to the Health Board after it has been through the formal Welsh Government and Prison routes.

Areas of Risk

There is a risk on the Health Board’s Risk Register ID3071 in view of Healthcare Nursing Staff levels: current risk score = 20 (Target 4).

The health nursing team numbers are not able to meet the full service demands. There is a risk that care and support will not be delivered to the men in a consistent and safe way. This is because there is no headroom built into the establishment, which means that during times of leave, sickness, and study there is no funded backfill. During times of short staffing only basic levels of service can be delivered, which impacts on the wellbeing and safety of the men. In addition, compliance with the Health Board’s Controlled Drugs policy in relation to 2 registrant checking and / or 1 registrant and a competent HCSW is variable given the number of drugs rounds undertaken each day, the volume of methadone dispensed and the number of men in the Prison on any given day requiring medication.

When there is low staffing the healthcare leads can only focus on clinical and operational aspects to support the delivery of services to the men and performance/assurance work is unable to be prioritised. On occasions, the Governor has had to alter the Prison regimen to accommodate low nurse staffing, which affects the running of the Prison and the opportunities the men get to work and socialise outside of the cells.

The associated costs to meet the gaps in the staffing to meet the requirements of the Health Improvement Plan have been identified and shared within the Health Board and with Welsh Government. PC&T SG have put short-term mitigation in place, although no long term funding has been agreed.  There are ongoing discussions with MH&LD SG in relation to whether resource from HMP Parc Prison In Reach (PIR) Team can be shared with the Prison to support bridging the nurse staffing gap.

More information on the financial elements are detailed in the next paragraph.

- FINANCIAL IMPLICATIONS

Through the development and implementation of the HIW action plan and HCWDP, additional resource requirements were identified, evidenced, and the increase in resource required was shared with both SBUHB Management Board and Welsh Government.  As an interim measure Primary Community and Therapies Service Group has identified temporary funding to support increasing the resource and mitigate the risks as far as possible, however, this does not cover the totality of resource required.  The funding will cease in the near future, as identified above there are discussions with MH&LD SG, to consider shared resource.   This presents a risk to the ability of the team to provide assurance on full delivery of recommendations from HIW.

It is acknowledged that without investment to support prisoner healthcare, the Health Board will be unlikely to fully implement the required actions nor meet in a meaningful way the recommendations in the report.

- RECOMMENDATION

- Note the work underway, which has achieved partial completion of the HIW 2022 recommendations, and the ongoing improvement work required to fully meet the outstanding recommendation.

- Note the completion of the Death In Custody and Article 2 recommendations in the combined action plan summary

- Note the financial deficit and the  risks with removing the temporary  partial head room

- Note the informal feedback from the Inspection undertaken in March 2023

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☐ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| Assurance of the quality and safety situation for HMP Swansea |  |  |  |
| Financial Implications |  |  |  |
| The HB have identified that additional resources are needed to ensure improved governance and improvements to service delivery are achieved |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Compliance with external auditors and inquests |  |  |  |
| Staffing Implications |  |  |  |
| Included in service risk registers |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Quality and Safety |  |  |  |
| Report History |  |  |  |
| Appendices |  | Appendix One – HIW 2022 action plan Appendix Two – HCWBDP |  |