## Infection Improv Plan 24_25
Infection Prevention Improvement Plan 2024/25
Strategic aim: Development of a One Bay Infection Prevention Way to support the board's 10 Year Vision of being a High Quality Organisation with a focus on improvement and performance to deliver high quality care and patient experience • Deliver the best outcomes for our population, preventing illness and harm caused by communicable infections and healthcare associated infections; • Become a centre of excellence for research and innovation in infection prevention & control, with staff receiving excellent teaching and training on how to prevent avoidable infection and to care for those with unavoidable infections to ensure optimal outcomes; • Develop leadership and empowerment to drive improvement in reducing harm for themselves and the population of Swansea Bay; • Strengthen an integrated, equitable service to reduce harm caused by infections, patient service user at the centre
Goal | Key Metrics | Outcome | Responsibility | Q1 Progress | Q2 Progress | Q3 Progress | Q4 Progress
Improving the Culture
All staff are trained, educated and competent in IPC as appropriate for their role | Achieve compliance with national training target for infection prevention & control-related mandatory training (all available staff). Working toward IP&C Training, Level 1 and Level 2 – ≥85% (available staff) by staff groups | ≥85% compliance with mandatory training | Service Group Directors | Level 1 - 91.28% Level 2 - 77.90% (on track to achieve within timeframe) | Level 1 - 91.10% Level 2 - 82.16% (on track to achieve within timeframe) | Level 1 - 91.57% Level 2 - 84.85% (on track to achieve within timeframe) | Level 1 - 89.11% Level 2 - 78.88%
| Staff who undertake aseptic technique are trained and can demonstrate competency | ≥85% compliance with ANTT training in staff who undertake aseptic technique and these staff have been assessed as competent | Service Group Directors | 27.68% ESR unreliable measure | 29.02% ESR unreliable measure | 29.74% ESR unreliable measure | 30.60% ESR unreliable measure
| IPC Team will provide bespoke ward-based and online training on C. difficile, with supplementary materials, which will be targeted to areas of high incidence | IPC Team have provided training to local Hand Hygiene Competence Assessors | Corporate IPC Lead | Delivered and completed | Available as online presentation and delivered as required | Available as online presentation and delivered as required. | Available as online presentation and delivered as required.
Staff have access to evidence-based Infection Prevention and Control policies | Evidence-based Infection Prevention and Control policies are in place, are accessible and are reviewed regularly | All IPC Policies will be reviewed, will be up-to-date and will be accessible to staff | Corporate IPC Lead | All policies current | All policies current | All policies current & accessible on the IPC SharePoint pages | All policies current & accessible on the IPC SharePoint pages
There is an organisational culture that promotes reporting of infection-related and decontamination-related incidents | Infection-related, and decontamination-related incidents within the Service Group are reported, monitored and investigated in a timely way | Infection-related, and decontamination-related incidents are reported, monitored and investigated appropriately, with learning shared across the organisation | Service Group Directors | Monitored in Service Group level meetings and at Decontamination Sub-Group | Monitored in Service Group level meetings and at Decontamination Sub-Group | Monitored in Service Group level meetings and at Decontamination Sub-Group | Monitored in Service Group level meetings and at Decontamination Sub-Group
| Service Groups feedback lessons learned from the investigation of incidents through their Quality & Safety Groups | Service Group Quality & Safety meeting minutes | Service Group Directors | Governance structures and processes in place | Governance structures and processes in place | Governance structures and processes in place | Governance structures and processes in place
| Multi-disciplinary reviews of healthcare associated infections (HCAI) are undertaken in a timely way, with engagement of relevant clinical leads, that demonstrate an understanding of avoidability, with key lessons learned shared across Service Groups and the Health Board | MDT reviews of HCAI is undertaken and lessons learned shared | Service Group Directors | Regular Director-led scrutiny meetings | Regular Director-led scrutiny meetings | Regular Director-led scrutiny meetings | Regular Director-led scrutiny meetings
| Acute Service Group Directors have oversight of Service Group performance against Tier 1 reduction goals and progress against their Infection Reduction Improvement Plans | There is a process of high level assurance relating to HCAI | Service Group Directors & Corporate IPC Leads | Executive-led HCAI Scrutiny meetings held with Service Group Directors | Executive-led HCAI Scrutiny meetings held with Service Group Directors | Executive-led HCAI Scrutiny meetings held with Service Group Directors | Executive-led HCAI Scrutiny meetings held with Service Group Directors
The Health Board will review the anticipated Code of Practice for the Prevention and Control of Healthcare Associated Infections when published | A gap analysis will be undertaken in relation to the Health Board's position against the anticipated updated Code of Practice and this will be reported to Management Board | Health Board will understand its position against the updated Code of Practice for the Prevention and Control of Healthcare Associated Infections and will work towards meeting the relevant standards | Corporate IPC Lead | Assessment completed | Reviewing actions | All Wales Code of Practice is still in consultation phase. | All Wales Code of Practice is still in consultation phase.
Leadership
Service Groups have a governance structure and processes for Infection Prevention & Control and Decontamination of re-usable medical devices | Service Group confirmation of Infection Prevention & Control Groups, co-chaired by Medical Director and Nurse Director, with multi-disciplinary engagement, meeting quarterly as a minimum | Established Service Group governance structures and management systems for IPC are in place | Service Group Directors | Service Group IPC Meetings established |  | SG meetings continue to take place each week. | SG meetings continue to take place each week.
| There are designated Service Group Leads for Infection Prevention & Control and Decontamination | There is a clearly identified Service Group lead for Decontamination and there are appropriate governance structures in place | Service Group Directors | Progressing within Service Groups within timeframe | Established within all Service Groups | Established within all Service Groups | Established within all Service Groups
There is a programme of regular IPC-related audit | Infection Prevention & Control-related audits (Hand Hygiene, Standard Infection Prevention & Control Environment are undertaken and reported locally, and there is a system in place to monitor associated recommendations and actions | The IPC audit programme is established on AMaT and Service Groups review, monitor and track progress | Corporate IPC Lead and Service Group Directors | Progressing within Service Groups within timeframe | Audits upload to AMaT and available. AMaT training rolling out across Service Groups. | AMaT IPC audits are being undertaken across all of acute services. | AMaT IPC audits are being undertaken across all of acute services.
Service Groups develop leadership and empowerment to drive improvement in reducing episodes of harm | Review specific areas for the training, learning and development of the IPC specialist workforce in line with All Wales Education, Learning and Development Framework for Specialist Infection Prevention and Control Workforce. | The Health Board will understand the requirements to meet the All Wales Education, Learning and Development Framework | Service Group Directors supported by IPC lead | In progress | Review actions and move to workforce planning by Q4 | Review actions and move to workforce planning by Q5 | Review actions and move to workforce planning by Q6
| Service Groups identify Link Champions for IPC and Decontamination | As a minimum, Link Champions are identified for areas of high risk | Service Group Directors & Corporate IPC Leads | IPC Leads identified in each Service Group | Link Champions identified for Decontamination and in number of high areas for IPC | Link Champions identified for Decontamination in number of areas considered to be high risk for IPC. Morriston has also sent out requests for champions at ward level. | Link Champions identified for Decontamination in number of areas considered to be high risk for IPC. Morriston has also sent out requests for champions at ward level.
| Redesign of Corporate IPC Service to strengthen leadership in IPC across the organisation by establishing a senior IPC Quality Improvement Partner for Service Groups | Equitable, resilient and sustainable IPC Service, working in partnership with Service Groups, to strengthen leadership and empowerment and support improvement in infection reduction | Corporate IPC Lead & Associate Nurse Director | Outcome of IMTP bid under review | IMTP bid not fully funded and Service Group IPC Partner not feasible within current financial envelope
Clean & Safe Healthcare Environment
The physical environment is maintained and cleaned to a standard that facilitates effective IPC and minimises the risk of infection | Review the new National Standards of Cleanliness and identify any gaps | Management Board will be presented with a briefing paper outlining the Health Board's position in relation to the updated national standards of cleanliness | Head of Support Services & Corporate IPC Lead | Updated National Standard of Cleanliness - publication delayed Outside HB control | Updated National Standard of Cleanliness - publication delayed Outside HB control | Updated National Standard of Cleanliness Draft circulated for consultation amongst IPC leads. | Awaiting publication of National Standard of Cleanliness
| Cleanliness compliance scoring matrix >95% | Maintain >95% compliance with cleaning scores | Head of Support Services | 97.5% | 98% compliance | Overall HB score Oct-Dec, 98.56% Oct 98.43 Nov 98.6 Dec 98.63 | Overall HB score Jan- Mar, 98.31% Jan 98.00% Feb 98.59% Mar 98.45%
| Service Groups to review options for workforce redesign to strengthen standards of cleanliness within wards | Improvement in Standard Infection Control Precautions compliance scores | Service Group Directors | HB current financial position impacts on this goal | HB current financial position impacts on this goal | HB current financial position impacts on this goal | HB current financial position impacts on this goal
| Establish a collaborative review of cleaning and surface disinfection products that are available within National Procurement Frameworks, with a particular focus on solutions that are safe and effective against C. difficile. | Optimum product selection for safe and effective to ensure the effective cleaning and disinfection | Head of Support Services, Service Groups, Procurement, & Corporate IPC Lead | Products under review | Extending scope of review to include cleaning items and materials | Review of cleaning materials continues | Review of cleaning materials continues
| Ensure safe systems exist for providing safe storage, distribution, monitoring and decontamination of foam mattresses and bed frames | There is a certificate of decontamination for every bed and mattress that provides assurance for Service Groups that every patient will be assured of having a clean mattress | Service Group Directors | Processes being reviewed within service groups | Area identified in Morriston for conversion to mattress storage | HBW T&F group meeting established to standardise process. Areas in Singleton & Morriston identified for mattress storage. | HBW T&F group meeting established to standardise process.
Infection prevention and control is considered as a core element at the planning and design stages of a new builds, refurbishments, repurposing and redesign schemes | The IPC team is involved at every stage of new builds, refurbishments, repurposing and redesign schemes to facilitate IPC being "designed-in" | IPC and related risks are considered at all stages of new builds, refurbishments, repurposing and redesign schemes | Service Group Directors, Assistant Director of Capital Planning, Corporate IPC Lead | IPC team involvement in capital programmes | IPC team involvement in capital programmes | IPC team involvement in capital programmes | IPC team involvement in capital programmes
| Service Groups ensure that increasing unsuited single room accommodation is considered in new build, refurbishments, redesign and repurposing schemes. | Appropriate single room capacity has been identified in capital planning schemes for inpatient accommodation. | Service Group Directors & Assistant Director of Capital Planning | Consideration given within planning stages | Consideration given within planning stages. | Consideration given within planning stages. | Consideration given within planning stages.
There is an annual programme of decant and deep clean within Service Groups | Service Groups will develop an annual programme of decant and deep clean. | A programme of decant and deep clean is established | Service Group Directors, Estates and Support Services | Underway in Morriston and included within ward moves at Singleton. Occupancy at NPT has not provided opportunity for decant and deep clean to date. | Nearing completion in Morriston and included within ward moves at Singleton | Nearing completion in Morriston and included within ward moves at Singleton | Planned programme completed in Morriston. Also proactive UV-C decontamination undertaken during ward refurbishments in Singleton
Antimicrobial Stewardship
Reduce volume of antibiotics prescribed to reduce risks associated with antimicrobial resistance and C. difficile | Reduce the volume of antibiotics prescribed across the health board, but particularly within Primary Care | Minimum 5% year-on-year reduction | Group Medical Directors | Audits in development and Service Groups working towards reduction in timeframe | Audits in development and Service Groups working towards reduction in timeframe | Audits in development and Service Groups working towards reduction in timeframe | Audits in development and Service Groups working towards reduction in timeframe
Improve clinical understanding of the role of antibiotic prescribing in development of C. difficile infection | Where there are Periods of Increased Incidence of C. difficile, associated medical teams undertake an audit of antibiotic prescribing within the ward / speciality using the audit tool in AMaT (Antibiotic audit_ QIP package.docx (sharepoint.com)). | Improved compliance with Start Smart Then Focus standards | Group Medical Directors | Audit available in AMaT. Minimal uptake of voluntary audit | Audit available in AMaT. Minimal uptake of voluntary audit | Audit available in AMaT. Minimal uptake of voluntary audit | Audit available in AMaT. Minimal uptake of voluntary audit
Reduce risks of C. difficile and antimicrobial resistance | Improve compliance with the 72-hour switch from intravenous to oral antibiotics to equal the Welsh average as a minimum. | Equal the Welsh average as a minimum | Group Medical Directors | Pilot Board Round Tool for 72-hour IV-to-Oral switch in development | Pilot commenced in Acute Medical Unit in Morriston | Pilot audit of Hospital acquired pneumonia underway | Hospital acquired pneumonia (HAP) audit completed in Morriston. 83 HAP audits competed to date. NPTH also undertaking HAP audit. Sharepoint has audit tools and other ket documents available to staff.

## 2024_25 Tier 1 outcome measures
Infection Prevention Improvement Plan Swansea Bay University Health Board 2024/25
Goal | Method | Baseline position | 3 month | 6 month | 9 month | 12 month | Outcome | Responsibility | Q1 Progress | Q2 Progress | Q3 Progress | Q4 Progress
Infection Prevention & Control Infection Prevention and Control (IPC) and reduction of HCAIs as per the Health Board refreshed IPC Improvement plan 2024/25 | Achieve reduction in 5 key healthcare associated infections through application of evidence-based practice and best practice guidance | Baseline for 23/24: C. difficile: 258 cases | Cumulative total to Q1: C. difficile: 29 cases | Cumulative total to Q2: C. difficile: 53 cases | Cumulative total to Q3: C. difficile: 74 cases | Cumulative annual total: C. difficile: 95 cases | Cumulative annual total: C. difficile: 95 cases | All Service Groups, reporting via Infection Prevention & Control Groups | 61 cases (+32) | 132 cases (+79) | 206 cases (+132) | 276 (+181 above goal)
|  | Baseline for 23/24: Staph. aureus bacteraemia: 154 cases | Cumulative total to Q1: Staph. aureus bacteraemia: 20 cases | Cumulative total to Q2: Staph. aureus bacteraemia: 38 cases | Cumulative total to Q3: Staph. aureus bacteraemia: 56 cases | Cumulative annual total: Staph. aureus bacteraemia: 71 cases | Cumulative annual total: Staph. aureus bacteraemia: 71 cases |  | 27 cases (+7) | 60 cases (+22) | 98 case (+42) | 134 (+63 above goal)
|  | Baseline for 23/24: E. coli bacteraemia: 265 cases | Cumulative total to Q1: E. coli bacteraemia: 65 cases | Cumulative total to Q2: E. coli bacteraemia: 123 cases | Cumulative total to Q3: E. coli bacteraemia: 178 cases | Cumulative annual total: E. coli bacteraemia: 234 cases | Cumulative annual total: E. coli bacteraemia: 234 cases |  | 52 cases (-13) | 117 cases (-6) | 170 cases (-8) | 224 (-10 below goal)
|  | Baseline for 23/24: Klebsiella bacteraemia: 93 cases | Cumulative total to Q1: Klebsiella bacteraemia: 23 cases | Cumulative total to Q2: Klebsiella bacteraemia: 43 cases | Cumulative total to Q3: Klebsiella bacteraemia: 57 cases | Cumulative annual total: Klebsiella bacteraemia: 71 cases | Cumulative annual total: Klebsiella bacteraemia: 71 cases |  | 34 cases (+9) | 60 cases (+17) | 90 cases (+33) | 120 (+49 above goal)
|  | Baseline for 23/24: Pseudomonas aeruginosa bacteraemia: 26 cases | Cumulative total to Q1: Pseudomonas aeruginosa bacteraemia: 5 cases | Cumulative total to Q2: Pseudomonas aeruginosa bacteraemia: 10 cases | Cumulative total to Q3: Pseudomonas aeruginosa bacteraemia: 15 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 21 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 21 cases |  | 1 case (-4) | 7 cases (-3) | 13 cases (-2) | 18 (-3 below goal)

## 2024_25 MHSG Reduction Goals (hidden)
Infection Prevention Improvement Plan Morriston Hospital Service Group 2024/25
Goal | Method | Baseline position | 3 month | 6 month | 9 month | 12 month | Outcome | Responsibility | Q1 Progress | Q2 Progress | Q3 Progress | Q4 Progress
Infection Prevention & Control Infection Prevention and Control (IPC) and reduction of HCAIs as per the Health Board refreshed IPC Improvement plan 2024/25 | Achieve reduction in 5 key healthcare associated infections through application of evidence-based practice and best practice guidance | Baseline for 23/24: C. difficile: 130 cases | Cumulative total to Q1: C. difficile: 15 cases | Cumulative total to Q2: C. difficile: 27 cases | Cumulative total to Q3: C. difficile: 39 cases | Cumulative annual total: C. difficile: 51 cases | Cumulative annual total: C. difficile: 51 cases | Service Group Directors, reporting via Infection Prevention & Control Groups | 26 cases (11 > ) | 65 cases (38>)
|  | Baseline for 23/24: Staph. aureus bacteraemia: 45 cases | Cumulative total to Q1: Staph. aureus bacteraemia: 10 cases | Cumulative total to Q2: Staph. aureus bacteraemia: 19 cases | Cumulative total to Q3: Staph. aureus bacteraemia: 28 cases | Cumulative annual total: Staph. aureus bacteraemia: 37 cases | Cumulative annual total: Staph. aureus bacteraemia: 37 cases |  | 9 (1 <) | 27 cases (8<)
|  | Baseline for 23/24: E. coli bacteraemia: 90 cases | Cumulative total to Q1: E. coli bacteraemia: 21 cases | Cumulative total to Q2: E. coli bacteraemia: 40 cases | Cumulative total to Q3: E. coli bacteraemia: 58 cases | Cumulative annual total: E. coli bacteraemia: 76 cases | Cumulative annual total: E. coli bacteraemia: 76 cases |  | 14 (7 <) | 27 cases (13<)
|  | Baseline for 23/24: Klebsiella bacteraemia: 35 cases | Cumulative total to Q1: Klebsiella bacteraemia: 9 cases | Cumulative total to Q2: Klebsiella bacteraemia: 18 cases | Cumulative total to Q3: Klebsiella bacteraemia: 24 cases | Cumulative annual total: Klebsiella bacteraemia: 30 cases | Cumulative annual total: Klebsiella bacteraemia: 30 cases |  | 9 (=) | 24 cases (6>)
|  | Baseline for 23/24: Pseudomonas aeruginosa bacteraemia: 12 cases | Cumulative total to Q1: Pseudomonas aeruginosa bacteraemia: 2 cases | Cumulative total to Q2: Pseudomonas aeruginosa bacteraemia: 5 cases | Cumulative total to Q3: Pseudomonas aeruginosa bacteraemia: 8 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 11 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 11 cases |  | 1 (1<) | 5 cases (=)

## 2024_25 NPTSH SG Reduction Goal (hidden)
Infection Prevention Improvement Plan Neath Port Talbot & Singleton Hosptals Service Group 2024/25
Goal | Method | Baseline position | 3 month | 6 month | 9 month | 12 month | Outcome | Responsibility | Q1 Progress | Q2 Progress | Q3 Progress | Q4 Progress
Infection Prevention & Control Infection Prevention and Control (IPC) and reduction of HCAIs as per the Health Board refreshed IPC Improvement plan 2024/25 | Achieve reduction in 5 key healthcare associated infections through application of evidence-based practice and best practice guidance | Baseline for 23/24: C. difficile: 32 cases | Cumulative total to Q1: C. difficile: 5 cases | Cumulative total to Q2: C. difficile: 9 cases | Cumulative total to Q3: C. difficile: 12 cases | Cumulative annual total: C. difficile: 15 cases | Cumulative annual total: C. difficile: 15 cases | Service Group Directors, reporting via Infection Prevention & Control Groups | 11 | 26 cases (14>)
|  | Baseline for 23/24: Staph. aureus bacteraemia: 35 cases | Cumulative total to Q1: Staph. aureus bacteraemia: 4 cases | Cumulative total to Q2: Staph. aureus bacteraemia: 7 cases | Cumulative total to Q3: Staph. aureus bacteraemia: 9 cases | Cumulative annual total: Staph. aureus bacteraemia: 10 cases | Cumulative annual total: Staph. aureus bacteraemia: 10 cases |  | 7 | 9 cases (2>)
|  | Baseline for 23/24: E. coli bacteraemia: 46 cases | Cumulative total to Q1: E. coli bacteraemia: 10 cases | Cumulative total to Q2: E. coli bacteraemia: 18 cases | Cumulative total to Q3: E. coli bacteraemia: 25 cases | Cumulative annual total: E. coli bacteraemia: 32 cases | Cumulative annual total: E. coli bacteraemia: 32 cases |  | 11 | 19 cases (1>)
|  | Baseline for 23/24: Klebsiella bacteraemia: 14 cases | Cumulative total to Q1: Klebsiella bacteraemia: 4 cases | Cumulative total to Q2: Klebsiella bacteraemia: 7 cases | Cumulative total to Q3: Klebsiella bacteraemia: 9 cases | Cumulative annual total: Klebsiella bacteraemia: 11 cases | Cumulative annual total: Klebsiella bacteraemia: 11 cases |  | 8 | 11 cases (4>)
|  | Baseline for 23/24: Pseudomonas aeruginosa bacteraemia: 8 cases | Cumulative total to Q1: Pseudomonas aeruginosa bacteraemia: 2 cases | Cumulative total to Q2: Pseudomonas aeruginosa bacteraemia: 3 cases | Cumulative total to Q3: Pseudomonas aeruginosa bacteraemia: 4 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 6 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 6 cases |  | 0 | 1 case (2<)

## 2024_25 PCTG Reduction Goal (hidden)
Infection Prevention Improvement Plan Primary Care, Community and Therapies Group 2024/25
Goal | Method | Baseline position | 3 month | 6 month | 9 month | 12 month | Outcome | Responsibility | Q1 Progress | Q2 Progress | Q3 Progress | Q4 Progress
Infection Prevention & Control Infection Prevention and Control (IPC) and reduction of HCAIs as per the Health Board refreshed IPC Improvement plan 2024/25 | Achieve reduction in 5 key healthcare associated infections through application of evidence-based practice and best practice guidance | Baseline for 23/24: C. difficile: 97 cases | Cumulative total to Q1: C. difficile: 9 cases | Cumulative total to Q2: C. difficile: 18 cases | Cumulative total to Q3: C. difficile: 24 cases | Cumulative annual total: C. difficile: 29 cases | Cumulative annual total: C. difficile: 29 cases | Service Group Directors, reporting via Infection Prevention & Control Groups | 20 cases | 38 cases (20 >)
|  | Baseline for 23/24: Staph. aureus bacteraemia: 72 cases | Cumulative total to Q1: Staph. aureus bacteraemia: 6 cases | Cumulative total to Q2: Staph. aureus bacteraemia: 12 cases | Cumulative total to Q3: Staph. aureus bacteraemia: 18 cases | Cumulative annual total: Staph. aureus bacteraemia: 24 cases | Cumulative annual total: Staph. aureus bacteraemia: 24 cases |  | 10 cases | 23 cases (11>)
|  | Baseline for 23/24: E. coli bacteraemia: 123 cases | Cumulative total to Q1: E. coli bacteraemia: 27 cases | Cumulative total to Q2: E. coli bacteraemia: 55 cases | Cumulative total to Q3: E. coli bacteraemia: 82 cases | Cumulative annual total: E. coli bacteraemia: 109 cases | Cumulative annual total: E. coli bacteraemia: 109 cases |  | 25 cases | 64 cases (9>)
|  | Baseline for 23/24: Klebsiella bacteraemia: 50 cases | Cumulative total to Q1: Klebsiella bacteraemia: 10 cases | Cumulative total to Q2: Klebsiella bacteraemia: 18 cases | Cumulative total to Q3: Klebsiella bacteraemia: 24 cases | Cumulative annual total: Klebsiella bacteraemia: 30 cases | Cumulative annual total: Klebsiella bacteraemia: 30 cases |  | 14 cases | 20 cases (2>)
|  | Baseline for 23/24: Pseudomonas aeruginosa bacteraemia: 4 cases | Cumulative total to Q1: Pseudomonas aeruginosa bacteraemia: 1 case | Cumulative total to Q2: Pseudomonas aeruginosa bacteraemia: 2 cases | Cumulative total to Q3: Pseudomonas aeruginosa bacteraemia: 3 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 4 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 4 cases |  | 0 cases | 1 case (1<)

## 2024_25 MH&LD Reduction Goal (hidden)
Infection Prevention Improvement Plan Mental Health & Learning Disabilities Service Group 2024/25
Goal | Method | Baseline position | 3 month | 6 month | 9 month | 12 month | Outcome | Responsibility | Q1 Progress | Q2 Progress | Q3 Progress | Q4 Progress
Infection Prevention & Control Infection Prevention and Control (IPC) and reduction of HCAIs as per the Health Board refreshed IPC Improvement plan 2024/25 | Achieve reduction in 5 key healthcare associated infections through application of evidence-based practice and best practice guidance | Baseline for 23/24: C. difficile: 1 case | Cumulative total to Q1: C. difficile: 0 cases | Cumulative total to Q2: C. difficile: 0 cases | Cumulative total to Q3: C. difficile: 0 cases | Cumulative annual total: C. difficile: 0 cases | Cumulative annual total: C. difficile: 0 cases | Service Group Directors, reporting via Infection Prevention & Control Groups | 0 cases | 0 cases
|  | Baseline for 23/24: Staph. aureus bacteraemia: 0 cases | Cumulative total to Q1: Staph. aureus bacteraemia: 0 cases | Cumulative total to Q2: Staph. aureus bacteraemia: 0 cases | Cumulative total to Q3: Staph. aureus bacteraemia: cases | Cumulative annual total: Staph. aureus bacteraemia: 0 cases | Cumulative annual total: Staph. aureus bacteraemia: 0 cases |  | 0 cases | 0 cases
|  | Baseline for 23/24: E. coli bacteraemia: 0 cases | Cumulative total to Q1: E. coli bacteraemia: 0 cases | Cumulative total to Q2: E. coli bacteraemia: 0 cases | Cumulative total to Q3: E. coli bacteraemia: 0 cases | Cumulative annual total: E. coli bacteraemia: 0 cases | Cumulative annual total: E. coli bacteraemia: 0 cases |  | 1 case | 1 case (1>)
|  | Baseline for 23/24: Klebsiella bacteraemia: 0 cases | Cumulative total to Q1: Klebsiella bacteraemia: 0 cases | Cumulative total to Q2: Klebsiella bacteraemia: 0 cases | Cumulative total to Q3: Klebsiella bacteraemia: 0 cases | Cumulative annual total: Klebsiella bacteraemia: 0 cases | Cumulative annual total: Klebsiella bacteraemia: 0 cases |  | 1 case | 1 case (1>)
|  | Baseline for 23/24: Pseudomonas aeruginosa bacteraemia: 0 cases | Cumulative total to Q1: Pseudomonas aeruginosa bacteraemia: 0 cases | Cumulative total to Q2: Pseudomonas aeruginosa bacteraemia: cases | Cumulative total to Q3: Pseudomonas aeruginosa bacteraemia: 0 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 0 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 0 cases |  | 0 cases | 0 cases