| Meeting Date | 26 November 2024 |  | Agenda Item |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Winter Preparedness and 50-Day Integrated Care Winter Challenge. |  |  |  |  |  |
| Report Author | Deb Lewis, Chief Operating Officer / Executive Director of Primary Care & Mental Health |  |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer / Executive Director of Primary Care & Mental Health |  |  |  |  |  |
| Presented by | Deb Lewis, Chief Operating Officer / Executive Director of Primary Care & Mental Health |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This report presents to the Quality and Safety Committee, the West Glamorgan response to the Care Action Committee’s 50- day Challenge. The 50-Day Integrated Care Winter Challenge and the subsequent Winter Plan, set out actions that Swansea Bay UHB along with our Regional Partners will take to maintain system resilience and delivery of high-quality Health and Social Care services during the winter of 2024/25. |  |  |  |  |  |
| Key Issues | In line with Welsh Government requirements, a regional partnerships approach to winter planning has been established within the West Glamorgan region to lead the development of integrated plans and arrangements. Within the current climate, maintaining system flow and resilience remains a challenge across health and social care, particularly in relation to finance, demand and workforce. The Winter Plan outlines the arrangements partner organisations have in place to maximise current organisational and regional resources to meet Welsh Government priority actions. Opportunities to increase system capacity and flow are outlined in the plan. Funding is dependent on a number of factors, including the availability of additional central funds. Further discussion at an organisational and partner level is required. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☒ |  |
| Recommendations | Members are asked to: - To be assured on the response provided to 50-Day Integrated Care Winter Challenge - To be assured on the monitoring and governance arrangements. |  |  |  |  |  |

Regional Winter Plan – Winter Preparedness and 50-Day Integrated Care Winter Challenge.

- INTRODUCTION

The 50-Day Integrated Care Winter Challenge and the subsequent Winter Plan, set out actions that Swansea Bay UHB along with our Regional Partners will take to maintain system resilience and delivery of high-quality Health and Social Care services during the winter of 2024/25.

- BACKGROUND

West Glamorgan has had strong partnership and governance arrangements in place and has led on the development of the Regional Winter Plan for a number of years.

In 2024/25 Welsh Government set an additional requirement for regional partners to submit a response to the 50-Day Integrated Care winter challenge to Welsh Government. The 50-Day Challenge supports the delivery of the Winter Plan, accelerating the implementation of 10 high impact actions focussed on urgent and emergency care. (Appendix 2)

The backdrop to this winter remains challenging, both from a financial point of view and the continued pressures within the system aligned to flow and capacity.

The majority of initiatives developed over the previous winter period are still operational and outlined within our Annual Plan and regional plans. With continued pressure on services, these are supporting flow all year around.

The region aims to deliver the Winter Plan within current resources whilst seeking opportunities to improve efficiencies, utilise capacity effectively and flex resources as required.  However, solutions that meet this aim are limited and therefore the plan also contains potential supportive solutions that could be implemented if additional funding is made available.  The detail in the plan should not be seen in isolation to the delivery the GMOs within our Annual Plan.

The key focus this winter will be on ensuring that we have robust Business Continuity Plans in place, that we are maintaining the wellbeing of our population and workforce through the delivery of our vaccination programme and robust IPC processes and that we are maximising planned developments and delivery across critical programmes such as the 6 Goals for Emergency Care, Further Faster and Care Action Committee priorities. This approach will support the system to remain resilient, flexible and sustainable over winter.

  - Focus of the Challenge

The ask in respect of the 50-day challenge is specifically to consider acceleration of evidence based, high-impact actions that are proven to work but not standardised across Wales, to further bolster system resilience in the lead up to the turn of the year.   These actions are outlined below:

The HB response to the Challenge was submitted on Monday 11th November and weekly updates are required to be submitted.  The return is included in Appendix 1.

It should be noted that the majority of actions are considered to be “business as usual” responses to winter pressures but the added scrutiny of the Care Action Committee serves to reinforce these across the boundaries of Health, Social Care and Third Sector services.

However, there are two actions, considered by the majority of HBs, that will have the biggest positive impact on services this winter:

- 7-day working

- Increased capacity for domiciliary / bridging care

The first action is noted within the 10 actions (#2) and the second is a major factor in systems being able to implement at least six of the remaining.

However, neither is able to be implemented on a sustainable basis in advance of winter and “short-term” support for this can only be achieved with additional resource and with a work-force willing to undertake the additional work.

It is anticipated that additional, non-recurrent funding maybe available to support these winter initiatives but at the time of writing this report, this has not been confirmed.

- GOVERNANCE AND RISK ISSUES

  - Governance

Monitoring and reporting of the Winter Plan and 50-day challenge will be led by The West Glamorgan Team.

Within the Health Board the COO has executive oversight of the delivery of the plan.

Monitoring and Reporting arrangements:

- Daily Huddle meetings: Health and Care staff review the position and risks across the region,

- Weekly Regional Operational Assurance Group meetings: Review activity and performance including reviewing the Pathways of Care Delays and Action Plan,

- Bi-monthly reports to the Reginal Communities and Older People’s Programme, within the Regional Partnership Board. This is chaired by Dr. Anjula Mehta,

- Monthly reports to the Health Board’s Urgent and Emergency Care Board/ Management Board.

  - Risks

Local risks to delivery of the 50-day Challenge, dovetail with those associated with the delivery of the overall winter plan.  These have been assessed in the context of the National Risks – overseen by the National Health and Social Care Winter Resilience Group. Key risks to delivery are summarised below:

- Workforce: challenges with the retention and recruitment of care staff across all settings. Sickness levels remain high and there are extremely high pressures and demands across health and social care services, which will be compounded by the winter period,

- Financial constraints: Reducing our deficit will require difficult choices to be made – balancing the range of options to increase system capacity and reduce risk with partner financial positions,

- Care home capacity: Maintaining flow of patients out of acute care; known fragilities in care home and domiciliary care sector,

- Maintaining Third sector capacity, especially with increased demand over the festive period and potential financial implications budget changes to employer contributions,

- Uptake of Vaccinations especially within vulnerable groups,

- Impact of proposed Industrial action of Band 2 HCSW,

- Impact of Princess of Wales service closures due to the critical state of the estate.

- FINANCIAL IMPLICATIONS

Within the current climate, maintaining system flow and resilience remains a challenge across health and social care, particularly in relation to finance, demand and workforce.

The winter plans outline the arrangements partner organisations have in place to maximise current organisational and regional resources to meet Welsh Government priority actions.

Opportunities to increase system capacity and flow are outlined in the Winter Plan.  Resourcing these solutions is dependent on a number of factors, including the availability of additional central funds. Further discussion at an organisational and partner level is required. Confirmation on additional resource being made to RPBs to support winter initiatives is anticipated within the next few weeks.  No additional financial commitment is being made prior to this confirmation.

- RECOMMENDATIONS

Members are asked to:

- To be assured on the content of the report

- Approve the Regional Winter Plan for submission

- Approve the 50-Day Integrated Care Winter Challenge

- To be assured on the options outlined in this paper and requirement for further discussion

- To be assured on the monitoring and governance arrangements.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Quality, Safety and Patient Experience agenda is central to support the implementation of and delivery of our strategic objectives - both internally and across the partnership space. |  |  |  |
| Financial Implications |  |  |  |
| Financial Implications are outlined within the body of the report. Recommendations and action plan developed with align to current work priorities – internally and across the partnership space |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| .There are no known legal implications |  |  |  |
| Staffing Implications |  |  |  |
| Workforce implications are outlined within the body of the report |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The detail within the report aligns to the 5 Ways of working and the delivery of integrated services and collaboration across the region. |  |  |  |
| Report History |  |  |  |
| Appendices |  | Appendix 1: 50 Day Integrated Care Winter Challenge |  |

50 Day Integrated Care Winter Challenge

APPENDIX 1

System assurance readiness template

| Region | West Glamorgan |
| --- | --- |
| Regional Partnership Board Chair | Cllr Steve Hunt (Chair), Steve Spill (Vice Chair) |
| 10 best practice interventions |  |

| Number | Intervention | Planned additional action | Executive lead / sponsor | Link to existing plan (provide copy) |
| --- | --- | --- | --- | --- |
| 1 | Refresh focus on embedding the Optimal Hospital Flow Framework to include a proactive emphasis on rehabilitation and reablement across the H&SC system | There is an ongoing focus on the delivery of actions to reduce Pathways of Care Delays (POCD), including the rolling out of SAFER/ Red2Green within Board Rounds, COP deep dives and the recording of D2RA pathways on our SIGNAL digital system to enable increased understanding of bottlenecks within the system. The roll out of the Integrated Discharge Hub (IDH) also assisting in facilitating timely discharge. The SIGNAL system and is used across all SBUHB Sites by HB and Local Authority Staff. A system is also in place to refer to the 3rd Sector Community Wellbeing Service. As part of the SAFER/ Red2Green (R2G) roll-out there was an initial focus on medical wards and SAFER compliance is recorded/ reported via SBUHB’s SAFER dashboard. Board rounds and huddles have been implemented via an MDT approach. SIGNAL being used as the ‘engine’ for Board Rounds to record SAFER, D2RA and R2G status either in real time or shortly after Board Rounds have been completed. The 4 questions of: What is wrong with me?; What is going to happen to me today?; What needs to happen to get me home and what can I do to speed things up?; When can I go home?; being utilised to drive said Board Rounds. This data (gathered via Board Rounds) then used in daily operational meetings to drive daily activity and improve overall grip and control re; patient flow e.g. how many patients are listed as COP and have a EDD occurring on that day – this then driving activity by Ward Matrons/ staff to encourage discharge on that day. | Deb Lewis Andrew Jarrett Dave Howes | POCD Action Plan |
| 2 | Apply 7-day H&SC working to enable discharge of patients during the weekend | A range of services to support flow currently operate across a 7-day working week, where resources and contractual arrangements permit. For example: ACT, District nursing, Domiciliary Care, Community Reablement Teams. Any further enhancements to this would require funding. Current contractual arrangement do not require Social Workers to work 7 days a week. Health Board and Local Authorities have senior decision makers available on call to support discharge. In addition, we have senior operational staff who also support the weekend rota. In the community we have 7-day working in community therapies with a specific focus on supporting flow over the weekend. Additionally secondary care therapists also support an on call and weekend working rota. The community equipment store has satellite equipment pods across the region where equipment can be accessed 7 days a week. The Intergrated Discharge Hub pilot commenced July 24 has been delivered with no additional resource – currently functions Monday to Friday as a discharge backdoor service. As part of the seasonal planning a business case is being written to support sustainable embedding of this model across 7 days. Our trusteed assess model works across 7 days. Reablement is available with senior care assistant rota’d to commence reablement packaged 7 days a week. The Inhouse Services for Domically Care is available 7 days a week. Commissioners to discuss with external dom care providers to continue discharges over the holiday /surge period to ensure continued flow We have clear leadership and collaborative escalation throughout the week and robust planning for weekend discharged for services that are available as the scale of service available over a weekend is less than Monday to Friday and robust planning is essential to support successful flow. Transport is available to support discharge over 7 days. Pharmacy is available over a 7 day period but is scaled back on a weekend for out of hours there is access to a WP10 in the admission area to facilitate discharge and flow, in addition there are pre pack available for any indivuals that have had surgery. Finally there is also a pharmacist on call for out of hours. |  | Seasonal Plan being drafted |
| 3 | Undertake Decision Support Tool (DST)/CHC process in the community | West Glamorgan recognises the importance of providing suitable step-down provision and facilitates DST (Decision Support Tool) and CHC (Continuing Healthcare) assessments in the community. During the COVID-19 pandemic, West Glamorgan created a funding agreement for older people, which remains operational. Under this agreement, partners have committed to 50/50 funding for individuals while a DST (Decision Support Tool) is undertaken at the individual’s home within an agreed two-week period. This ensures there are no delays in individuals receiving their assessments. Ensuring the availability of community professionals who are suitably skilled and trained to undertake the DST/CHC assessments is crucial. West Glamorgan has had integrated teams since 2012. These teams are skilled, trained, and experienced in conducting DST/CHC assessments, ensuring a high standard of care and support. Nurses and Social workers undertake CHC training which is jointly delivered by the Long-Term Care Team for nurses and social workers. Discussions always include individuals and their representatives and kept informed throughout. In addition, we employ translators where necessary to ensure that we support individuals in the language of their choice. To support discharge West Glamorgan does not currently have any commissioned step-down beds in care homes due to these challenges presented in previous years. However, we are actively investigating other opportunities to address the need for appropriate discharge options. The lessons learned and challenges include: - Availability of Beds: Ensuring a sufficient number of suitable beds were available when needed. - Quality of Care: Maintaining high standards of care in step-down facilities. - Coordination: Effective coordination between hospitals, care homes, and community services. - Funding and Resources: Securing the necessary funding and resources to support this model. |  |  |
| 4 | Regional collaboration to ensure that ‘integrated navigation hubs’ exist to facilitate discharge for acute hospital sites and admission avoidance in the community | As part of our navigation activity, we have implemented an Integrated Discharge Hub (IDH) to facilitate timely discharge from our hospitals (back door) – this is work in progress and further work is planned to streamline operations and make more efficient. The Integrated Discharge Hub: - Went live in July as a pilot on Morriston site - Will be extended to NPT/Singelton from 1/12 - Has a multi agency triage and discharge planning function - Can demonstrate positive impact on reducing POCD Regarding admission avoidance we have: - Scoping a UEC Care Co-ordination Hub to proactively manage any community demand providing an urgent community response and streamline access to the 3 x front doors, through improved triage and pathway management. - Common Access Point in Swansea Council - Single Point of Access in NPT. Other projects as examples including: - Regional projects that support prevention in the community eg Our Elders, Good Neighbour Scheme, Wellbeing Hubs; Community Wellbeing Services; Dance to Health; Care and Repair - Regional Preventative Approaches: Building Community Assets, Social Prescribing and Local Area Coordination Activity West Glamorgan through its intermediate care offer aligns Information, Advice, and Assistance (IAA) services means ensuring that the services provided by local authorities are well-coordinated. The services providing clear information, offers tailored advice, assists with access, collaborating with other services and focuses on well-being. West Glamorgan also has an Acute Clinical Team that supports people in the community and avoids the need for conveyance to hospital. For acute hospital care navigation we have recently stood up a ‘UEC Care Co-ordination Hub Task & Finish Group’. This Task & Finish Group has been established to develop a service model for pre-hospital triage and clinical management of patients. The multi-agency group have been established to develop and implement a service model aimed at appropriate streaming of patients into the various UEC pathways within Swansea Bay and to improve admission avoidance and to reduce ambulance conveyance to hospital where clinically appropriate. The aim of the ‘UEC Care Co-ordination Hub’ is to be a central point that focuses on avoiding conveyance and admission avoidance ensuring people have timely and safe alternatives to attendance at emergency departments (the previously mentioned IDH providing discharge coordination and support). Implementation to be over the winter period with a desire to provide 7-day provision (subject to funding). Where funding is a challenge, it is anticipated that existing services such as GPOOH will be utilised. The UEC Care Co-ordination Hub will when implemented provide: - Multi professional assessment of need and oversight of subsequent care plans that meets the holistic and complex needs of the population it serves. - Ensure that high risk cohorts are flagged and a shared record (proportionate) available to all professionals involved in the persons care. - Accept referrals from local health and social care professionals for assessment and consideration of escalated needs (includes discharge from hospital, care homes, WAST) to mitigate risk of crisis and provide a safe alternative to hospital (e.g. Enhanced Community Care and / or reablement) where it is safe and appropriate to do so. - Accept referrals from ‘999’ / ‘111’ and other health care professionals - Direct access to pathways that facilitate diagnostic assessment e.g. direct referral to SDEC/ Older Persons Assessment Unit etc. |  | WGRP-Story-of-Change-Communities-and-Older-People-2023-24.pdf |
| 5 | Regional H&SC weekly review of LOS 21-28 days and 20 longest LOS patients with focused actions to progress discharge | To tackle our Clinically Optimised Patient position, we have in place weekly multi agency Clinically Optimised Group Meetings on all hospital sites and this includes a further weekly focus into all longer stay hospital patients. A daily huddle takes place with both Health and Care Staff to review the position and risks across the region. A Regional Operational Assurance Group also meets weekly to review activity and performance this include the review of the and Pathway Of Care Delays Action Plan. These groups - identify constraints and ensure robust actions are implemented. - produce clear actions with accountability to support discharge for individual patients. - Is made up of a wide multi-disciplinary team including the HB, LA’s and 3rd Sector and is over seen by the Integrated Head of Service. Reports are submitted to both the Community and Older Peoples Programme within the Regional Partnership Board and the HB’s Urgent and Emergency Care Board Furthermore, we recently completed diagnostic assessments of our flow challenges. Specifically completed a Mult Agency Discharge Event (MADE), 6A’s Audit and 21-day LOS review- this was undertaken across all sites including Gorseinon and Bon-y-Maen House. This has identified the key issues that we need to tackle specifically: - Significant pathway delays - Lack of Internal standards for pathway events - No escalation framework for COP pathway delays - Limited D2RA model - Admission avoidance opportunities - No differentiated bed pools for rehabilitation - Limited trusted assessor model - Exemplar Board Rounds We are using these diagnostic assessments to drive activity over the winter period and beyond, with a focus on improving back-door flow and by having a frailty focus at the front door limiting the opportunities for longer LOS patients. |  | POCD Action Plan (please see section one for details) |
| 6 | Proactive management of identified 0.5% high risk population group by clusters and multiprofessional community teams | Frailty registers have been implemented in GP practices. These have enabled the identification of the 2% most frail patients within their practice population using the electronic frailty index. High Risk patients are also identified following front door attendance or admission, and details shared with Virtual Wards. This allows the GP and Virtual Wards to proactively manage this high risk/ vulnerable patient group, optimise existing comorbidities and prevent further admission. |  |  |
| 7 | GP Enhanced Service rollout for care homes and Proactive Care / Urgent Care provision for ‘High Risk Cohorts’ | West Glamorgan currently has 30 surgeries across the region that are actively participating in the Care Home (pandemic) Directed Supplementary Service. Piloting the Roll out of Consultant Connect Technology to Care Homes in partnership with Welsh Govt and providers. |  |  |
| 8 | Trusted Assessor model for all care settings | We have a strong Trusted Assessor model that assess for: Community Reablement; Bedded Reablement; EMI Resettlement Assessment Beds. Action for the next period is to develop stronger trusted assessor role with external care home providers and long-term dom care. West Glamorgan promotes “Home First” where possible and uses the discharge to recover then assess model extensively Our current trusted Assessor model promotes a proportionate assessment and discharge to domiciliary care reablement and short-term bedded reablement, to promote recovery pending full assessment for those with ongoing care and support needs. Changes to the structure of the assessment and care management functions have been designed to increase the review function to support the undertaking of timely and agile reviews. Discussions have recently started to explore the opportunities for Hospital based physio or OT use proportionate assessment to step down to a care home or commission Reablement or bridging community services. Trusted Assessors / Community Discharge Liaison Nurses are working closely with Care Homes to develop relationships and support the acceptance of their trusted assessment to facilitate discharges for individuals returning to a care home. There is a long-standing Trusted Assessment approach to support nonregistered therapy staff to prescribe equipment. Trusted Assessors / Community Discharge Liaison Nurses work to support step down to our inhouse reablement service. Some of our Community services (community DLN team) have been aligned to deliver the integrated discharge hub to pull patients from the wards. As part of IDH roll out a specific work strand on developing TA model at P3 will be taken forward. |  |  |
| 9 | Home First default for all patients clinically optimised – Health and Social Care discharge planning begins on admission | Across West Glamorgan the D2RA Pathways are fully embedded into practice. The Integrated Discharge Hub review and agree referral once patient is clinically optimised for care in the community. Here are some good practice points for embedding D2RA (Discharge to Recover then Assess) Pathways into practice: All service users are being assigned their pathway of care within 24 hours of admission following a “what matters to me” conversation with the patient, their relatives, or carer, and discharge planning begins. D2RA pathways are reviewed daily at board rounds and corresponding actions and engagement takes place to support effective discharge planning. Pathways of Care are reviewed daily with corresponding actions and accountability identified to progress discharge. West Glamorgan’s default position is to discharge patients to their home first, whenever possible. This includes utilising a proportionate assessment for discharge. Rehabilitation and Reablement Services are available to ensures continuity of care and support during the transition from hospital to home. For individuals with ongoing care and support needs, a full assessment is undertaken at home following a period of recovery. This allows for a more accurate understanding of their needs in their usual environment. Patients on Pathway 0 are discharged the same day, with prior arrangements made with services for those returning to pre-admittance services. The integrated services aim to support individuals on Pathways 1, 2, and 3 to be discharged within 48 hours of being clinically optimised, this is however challenging as some individuals require best interests assessments, court of protection systems that take far longer than 48 hours. The current Pathway of Care Delays workstream is looking at the granular data and reviewing individual cases to expedite discharge where possible. Our integrated teams provide joint health and social care arrangements to support discharge planning. West Glamorgan in-reach discharge service will identify high risk patients and starts early communication with community professionals and family. The standard operating procedure for Pathway of Care Delays is being further developed and will join up escalation mechanisms to ensure consistency across the hospital sites and to support individuals who are waiting for discharge. A daily huddle takes place with both Health and Care Staff to review the position and risks across the region. West Glamorgan Community Services provided deliver single handed care provision training to its workforce. |  |  |
| 10 | Integrated community services to focus on 7-day community-based falls response pathways | SBUHB will be part of the 6 Goals National Falls Taskforce and as part of that work-stream have undertaken a baseline review of current falls service provision across the Swansea Bay region. As part of said work-stream/ baseline review we recognise that SBUHB do not currently have a level 2 falls response service. We are currently developing a short, medium and long term plan to provide a level 2 service and make our current level 1 offer more robust and equitable. Both level 1 and level 2 service development plans will be based on the following good practice points: - Ensure all community falls responders are appropriately trained to attend level 1 and level 2 falls - Ensure there is full geographic coverage for falls response service 12 hours a day between 8am and 8pm - Ensure an urgent care response is provided within 2 hours, in line with NICE guidelines - Ensure clear referral pathways into falls services that initial responders can access. Said plan(s) will where possible be cost neutral whilst possible options that may require funding will also be noted. Current activity already underway which we could be built on includes: - Swansea – Rolling out of iStumble during November with Dom Care providers internal and external – supports for non-injurious fall outside of hospital (avoiding conveyance). Work is ongoing with Improvement Cymru. The initial provider Simply Safe continue to deliver the service. Two providers have recently completed the training and have the equipment and are planning to commence the service in the next couple of weeks. The third phase will roll out to a further 4 providers giving us 7 providers in total who between them support around 750 clients. We have also taken part in a podcast with Improvement Cymru to recognise the project and its potential it’s called A local collaboration community project to help reduce 999 calls and can be found here: Talking Improvement - NHS Wales Executive - Live in NPT – Mobile Response Service - Falls Prevention workstream active within the Communities and Older Peoples Programme. There are further plans to have direct access pathways for level 1 and 2 falls to virtual wards to provide assessment and follow up care. Falls Prevention workstream active within the Communities and Older Peoples Programme. There are further plans to have direct access pathways for level 1 and 2 falls to virtual wards to provide assessment and follow up care. |  |  |