SWANSEA BAY

UNIVERSITY HEALTH BOARD

Increasing our ability to offer to deliver Clinical Consultations in Welsh: First Phase Implementation Plan 2024-2029

Contents

4			Background

4			Themes

5	Mental Health, Learning Disabilities and Dementia Care

9			Care of the elderly

10			Stroke Services

14			Children and Young people

15		Speech and language therapy

18	Appendices

BACKGROUND

Context

The Welsh language (Wales) Measure was given approval by the then National Assembly for Wales in December 2010. Passed into law by Royal Assent in February of 2011, the measure:

- gave official equal status to the Welsh language in Wales,

- created a system of placing duties on public bodies and some private companies to provide services through the medium of Welsh.

- created the office of the Welsh Language Commissioner, giving powers to enforce the measure and protect the rights of Welsh-speaking people to be able to access services in the language of their choosing.

- allows the Welsh Language commissioner to investigate instances where they may have been attempts to interfere with the freedom of Welsh speaking people to use the language.

During 2018, Swansea Bay University Health Board, along with other Health Boards in Wales were issued with a compliance notice containing standards with which we would be expected to comply. By November of 2019, all 124 of the standards imposed by the commissioner became active and we have been maintaining an action plan to monitor compliance since this date.

As part of the requirements of our compliance notice, we produce and publish an annual report relating to the Welsh language and the latest edition of that report can be accessed here: Welsh Language - Swansea Bay University Health Board (nhs.wales)

Standard 110

Standard 110 of our compliance notice requires that we publish a plan for each 5-year period which sets out the extent to which we are able to offer to carry out clinical consultations in Welsh, along with the actions we intend to take to increase our ability to carry out the same. These actions must be accompanied by a timetable for those actions.

This document will outline the considerations we have taken in order to comply with Standard 110, whilst ensuring that any actions we take are meaningful and will lead to greater positive experiences for our patients. This document will include an honest analysis of the information we hold on the current demand for Welsh language services as well as our ability to meet that demand.

Our approach to this task

It is important to us that any action we take in relation to the Welsh language is meaningful and will lead to an increase in our ability to deliver quality services. This Health Board offers a wide range of services to a population which resides across the City and County of Swansea, Neath Port Talbot County Borough and the wider South and West Wales region.

With this in mind, a strategic decision has been taken to focus our work in relation to this standard in areas outlined as Key Priority Areas within Welsh Government’s More Than Just Words framework.

Those Key Priority Areas are:

- Services for Children and Young People

- Services for Older People

- Dementia Services

- Mental Health Services

- Services for those with Learning Disabilities

- Speech and Language Therapy Services

- Stroke Services

The vision for these services is that over the course of the 5-year period 2024-2029 we will improve the ability of patients to access provisions in Welsh where they need it.

We will:

- Publish a 5-year plan which shows the actions we will take to increase our ability to deliver services to patients in Welsh.

- Take steps to improve how we capture information about the Welsh language abilities of our staff and ensure that that information is used proactively to improve availability of services in the Welsh language.

- Outline the steps we will take to improve the data we hold on the language needs of the patients we serve.

- Take priority steps to understand the linguistic profile and needs of the people we are serving.

- Offer detailed actions within each Key Priority Area which will lead to us being able to offer an improved experience for Welsh speaking patients.

- Ensure that the reporting and monitoring of progress against actions within this plan are embedded into the extant governance and scrutiny processes of the Key Priority Areas.

It is our desire that by the end of this 5-year plan, we will have improved our ability to offer to carry out clinical consultations in Welsh across services in our Key Priority Areas.

To achieve this, we have identified three themes and have tasked our Key Priority Areas with developing actions within these themes in order to deliver change.

The themes are:

- Recruitment and upskilling the existing workforce

- Technology, Systems and Data

- More positive experiences for Welsh speakers

Actions should challenge current practices and drive change, ensuring that the language needs of the patient are a key component in planning services. Managers will be expected to solidify our baseline. We will understand what we are doing well and where we need to improve, and we will develop effective mechanisms to monitor progress against agreed actions.

Each Key Priority area have developed an action plan designed to challenge current practices and ensure that the Welsh language is a key consideration of service planning and provision. Whilst publishing these actions will allow us to report compliance with the standard in question, these actions will move us towards achieving our longer-term aspirations of being able to deliver clinical consultations in Welsh to all those who need them.

The second aspect of this work will see departments consider how they can implement these actions on a micro level within their areas of work. This will allow the impact to be monitored and any learning shared across the wider Health Board. We have asked each one of the Key Priority Areas to identify one existing service provision which will undergo Welsh language evaluation, sustainability assessment and development over the life of the 5-year plan so that by the end of the period we will be able to evidence meaningful change across a range of smaller projects.

The aim of this plan is to consider the required pathway and outline milestones to being able to deliver clinical consultations in Welsh to all patients who need or want the service (without the use of interpreters).  The outcome being that we can offer an equivalent service to both English speakers and Welsh speakers.

Governance Arrangements

The action plans published with this strategy are live documents and will be updated and added to as work progresses. Monitoring progress against the actions will become a standing agenda item at existing scrutiny panels within each of the Key Priority Areas.

Reports from each of these areas will be received by the Quality and Safety group every 6 months, and summaries included in reports to both the Quality and Safety Committee and the Health Board.

External reporting of progress against published actions will take place every 3rd and 5th year from publication of this plan, as required by our Welsh language standards compliance notice.

Context

Swansea Bay University Health Board is the local health board of the National Health Service which serves the populations of the City and County of Swansea and Neath Port Talbot County Borough. The Health Board was formed in 2019 when health board boundaries were amended and responsibility for healthcare provision in the Bridgend area was passed to Cwm Taf Morgannwg.

We provide secondary care services to patients from our three major hospital sites, Morriston, Singleton and Neath Port Talbot. We also operate a community hospital and primary care resource centres which provide both clinical and wellbeing services. Our mental health and learning disability services are provided both in hospital and community settings.

We are home to the Welsh centre for burns and plastic surgery which offers specialist services for south and mid Wales, but also the South West of England. Our hospital at Morriston is also home to one of the two Welsh cardiac surgery centres. Other areas of specialism include Cleft lip and palate, renal, fertility and bariatric services.

The values of an organisation are those things which define our culture. They are a clear indicator of the things which are important to us. We’ve built our values by engaging with our staff and patients. Our workforce of around 14,000 people serves a population of 390,000. We strive to uphold these values whilst delivering our services to them.

Caring for each other - in every human contact in all of our communities and each of our hospitals.

Working together - as patients, families, carers, staff and communities so that we always put patients first.

Always improving - so that we are at our best for every patient and for each other.

What are Clinical Consultations?

The Welsh Language Standards (No. 7) Regulations 2018 define a clinical consultation as “a health provision interaction between one or more individuals and a body”. Thousands of these interactions take place between our clinical staff and Allied Health Professionals across our services every week.

THEMES

The themes our Key Priority Areas will consider.

Recruitment and upskilling the existing workforce

A key consideration for this work are the challenges to provision of Welsh language services, including workforce factors.

We need to look at our existing workforce and consider if staff are appropriately skilled. Where there are gaps, we must be proactive in offering staff the opportunity to upskill and develop their Welsh language abilities. Due consideration needs to be given to how we determine what level of Welsh language ability is required for each of our roles.

Whilst we are committed to upskilling staff, we must recognise that it can take years for a new Welsh speaker to be sufficiently confident and competent to use that language effectively. Bringing more advanced Welsh speakers into our workforce will complement the work we will do in-house, supported by external partners, to offer learning opportunities for staff. This will involve more than bringing new speakers into the fold. We must also support staff who have a good understanding of Welsh but lack the confidence to either use it in a professional setting, or for some - use it at all.

There is a misconception that all ‘Welsh Essential’ jobs must be filled with appointees who have skills at level 5. For most roles across our services, confident conversational skills at level 3 could be deemed appropriate to meet the needs of the majority of patients. We must look in more depth at how we assess our posts and consider adopting a more detailed categorisation method.

Inadequate information also presents challenges. In order to build on something, you must have a solid base. At present, the information we hold about the demand for services in Welsh, and our ability to meet that demand is incomplete. This will need to be addressed with some urgency for us to start making positive progress. We need to better understand where our patients need to access services in Welsh and ensure that our staff with Welsh language skills are effectively rostered, so that everybody is in the right place, at the right time.

Technology, Systems and Data

Across this Health Board and across the wider NHS multiple digital systems are in use. Often, and even within one department or service group more than one system may be used to administer patient care. Many of these systems are legacy systems, meaning that they are older, but still adequate for the tasks being carried out.

The array of systems in use, and the inability of many these systems to share information is a known issue, and colleagues at DHCW are considering how this could be improved upon into the future. Any potential changes to systems are likely to be costly and will affect all health boards, not just Swansea Bay. Research and development to deliver new digital solutions is a lengthy process and it is unlikely that any major improvements to the systems discussed in this plan will be delivered before 2029. Our Key Priority Areas will therefore have to consider how we can make best use of the systems already in use and where local solutions can be implemented to ensure that we are making best use of the data we capture in order to improve services.

More positive experiences for Welsh speakers

We’ve asked our Key Priority Areas to consider and evaluate their current performance in relation to the Welsh language. Our organisation is committed to delivering high quality care to all our patients. To achieve this, we must be able to deliver care to those who are Welsh speakers. For many of our patients, communicating in Welsh is not a want, but a need.

We are under no illusion. There are multiple areas for development. Our services have been asked to consider how their provision currently looks, and what actions could be taken over the next 5 years to improve our Welsh language offering. Our ambition is that each of the areas will be able to evidence progress. This will include improving our use of data so that we allocate patients to Welsh speaking staff as well as showcasing services which can be promoted as bilingual.

We will engage regularly with patients over the course of the next five years in order to conduct patient satisfaction surveys and capture digital stories of their experiences using our services. The learning gained here will enable us to further enhance our action plans.

MENTAL HEALTH, LEARNING DISABILITIES AND DEMENTIA CARE

The Mental Health and Learning Disabilities Service Group is broken into 3 main divisions which include Mental Health Services, Learning Disabilities, Secure Services and Recovery Services.

The MH&LD Service Group provides support, care and treatment to patients within community settings and across the inpatient services.

The Mental Health Division is created of 4 different directorates, which include: Adult Mental Health Services, Older Persons Mental Health (OPMHS), Children and Adolescence Mental Health Services (CAMHS), Community Drug and Alcohol (CDAT).

To understand our starting position, a questionnaire was circulated to team managers within each division to establish the current baseline in relation to the use of the Welsh Language across our services.  Engagement with this type of activity is usually low, so we were pleased that 55% of recipients returned responses to us.

The responses captured help us to give an idea of the current position within our services and whilst the information is useful, it should be remembered that it may not paint an accurate picture due to the method of capture and engagement rate.

The questionnaire was designed to capture information around current demand for services through the medium of Welsh and whether staff are able to utilise extant Welsh Language Skills to meet that demand.

The findings from the questionnaire are not factual and are based on a manager’s overview within their respective areas.

Analysis of findings:

Demand

The results suggest that there is currently little to no demand for services in Welsh within the Service Group. This seems unrealistic and is likely indicative of a lack of appropriate recording and reporting measures. We must also consider that service users may assume that services are not available to them in Welsh and, therefore do not request it. 79% of respondents noted that a service in Welsh is never requested. This is something that we are working to overcome with the implementation of the ‘Active Offer’.

95% of the managers who responded stated that there is currently no demand for services in Welsh. The 5% of managers who responded that there is a demand for Welsh medium services are based within the Children’s and Adolescent Mental Health Service (CAMHS), particularly the School In-Reach Team. This team work closely with Welsh Medium schools and Welsh speaking service users. Managers in this area stated that between 11 and 15 service users had requested a service from us in Welsh.

39 areas of work across the service group stated that no service users had requested services in Welsh within the last 12 months. Even though this number is high, the results highlighted that there had been requests made within the Perinatal, Ward F and the Care Home In-Reach Team within Older Peoples Mental Health Services. Each of these areas reported that between 1-5 patients had requested a service from us in Welsh over the 12 months prior.

65% of respondents noted that they do ask their service users their language preference, however, inconsistency in how this is captured and recorded across the service group may explain why 35% noted that they do not ask.

Capacity

As part of this exercise, we asked managers to give a summary of the ability of their area of work to provide a Welsh language service, helping us to understand the different levels of ability within teams across the service group.

Over half of the responding managers stated that they have at least one staff member based within their team who are able to speak Welsh. Managers of 11 teams have no staff members with the skill. This suggests that demand may be able to be met in some areas, and not others. This will result in an inconsistent level of service for Welsh speaking patients. Teams who have no staff with identified Welsh Language skills will be required to upskill their staff, or when positions within the team become vacant, advertise those posts with Welsh language skills as essential.

Over half of the responding managers are unsure whether they have any staff members within their team who are able to conduct a clinical consultation in Welsh. This would suggest that there is a disconnect between the work happening across the organisation to capture detailed information from staff about their Welsh language abilities, and the accessing of this information by managers to plan and develop service provision.

It is positive that 91% of managers stated that their staff are able to use basic Welsh phrases. The impact of using Welsh phrases with service users can change the care they receive, especially if the service user is a Welsh speaker and may not have specified that they are able to speak Welsh initially. This may allow staff to better identify their needs and ensure that care is given to them in Welsh if preferred. Knowing which staff have advanced Welsh skills to deliver clinical consultations will therefore be crucial to developing this offering further.

29 managers stated that they do have specific staff members based within their team who are approached to support with any Welsh Language needs. This suggests that identifying Welsh Language Champions across the Service will allow better support and better promotion of the Welsh Language. This will be considered within our action plan.

The questionnaire further explored what measures teams have in place to be able to meet the needs of a service user if a service in Welsh was required and they didn’t have the ability to meet that need. Many teams responded that they would either identify a Welsh speaking staff member from another team, or utilise language line. All teams were able to demonstrate an understanding of process to follow to ensure a Welsh speaker can access a Welsh service. We must now take action to improve the quality of the service, which is being delivered to those patients, making the process seamless with fewer interventions by third party interpretation services such as Language Line.

Summary of key findings:

- 32 teams noted that they have between 1 and 5 staff members who are able to speak Welsh.

- 11 teams stated that they have no staff who are able to use Welsh.

- 40% of teams felt that there are staff within their team who are confident to conduct a clinical consultation in Welsh.

- 60% of teams either do not have Welsh speaking staff or are unsure whether their staff are able to conduct a clinical consultation in Welsh.

- 47% of teams stated they have staff who are confident in using the Welsh Language when needed. Furthermore, 91% of teams responded that staff members are able to use basic Welsh phrases such as “Bore Da, Prynhawn Da, Diolch, Hwyl Fawr”

- 29 teams have an individual or group of staff within their team who are approached specifically to provide support with the Welsh Language.

Data Capture and recording

We asked managers across our service group how they capture information from patients around their language preference. 77% of respondents noted that teams were recording the patient's language preference, however, it has become apparent that there is inconsistency as to where this data is being recorded.

The information is currently being recorded in the following locations:

  - Assessment Documents

  - Referrals

  - Patient notes

  - Positive Behaviour Support Plans (PSPB)

  - WCCIS

  - WPAS

  - CTP – Care Treatment Plan

This indicates that there is an inconsistency in the approach to the recording of the Welsh Language preference between teams, and between divisions. The lack of structured approach within the Service Group for this process could be due to the different areas of work using and having access to different computer systems. This is an area which needs attention.

Recently the MH&LD Service Group has begun a rollout of digital systems across our services. In comparison to other Service Groups at Swansea Bay UHB, we are behind digitally. We will require time to adapt to the implementation of these new systems, therefore it is difficult to identify a standard recording mechanism for the Welsh Language at present.

Our action plan will establish steps we will take to implement localised methods that can be utilised in recording and capturing data until such a point that a corporate or national solution to recording this information is developed. A uniform approach should be the aim so that the sharing of information across services and health organisations is seamless.

Delivering an Active Offer.

- 63% of managers are either unsure what the “Active Offer” is or do not provide service users with the offer.

37% of managers state they do provide service users with the “Active Offer”

- 58% of managers are unsure why the “Active Offer” is not provided to service users.

These figures are both surprising and a little concerning when we consider that 84% of staff within our Service group have completed Welsh language awareness training. A significant portion of this training module is dedicated to the ‘Active Offer’. This would suggest that staff need additional support to fully understand the importance of the ‘Active Offer’ and how to successfully deliver it to every patient.

Elsewhere in this report, we have noted that 65% of respondents do “ask language preference”. The difference in the responses could indicate here that further would needs to be done to develop the ‘Active Offer’ as a brand or campaign. If asking staff if they deliver an active offer, they may respond ‘no’, but by asking a slightly different question “Do you ask the patient if they speak Welsh at home” the response may be positive. Again, the results of this survey must not be considered in isolation. We believe the actual picture to be more positive than the results of the survey present.

The MH&LD Service Group provide care and services to patients and service users with a vast range of needs. These could be social, emotional or physical. There may be occasions where staff will not be able to provide service users with an Active Offer. An example would be when service users are non-verbal. In such circumstances, the team would not be able to seek this information from the individual. Nevertheless, there is an importance to clarify a patient’s natural language use by communicating with the service user’s family, friends or primary carer.

The purpose of the Active Offer is to highlight to service users that we are striving to meet their needs in Welsh. It is envisaged that by delivering an active offer, it may encourage more people to seek services in Welsh, which in turn may highlight a growth in demand for services in Welsh across our Service Group. Failing to deliver the active Offer will mean the current position does not change, we do not grow the data we hold on patient language preference and the assumption that our services are not available in Welsh remains.

Where the Active Offer is not currently being practiced regularly, managers are unable to advise as to why this is the case. This could be due to there being no standardised recording mechanism in place, the variety of documents and systems being used across the Service Group and/or staff not being prompted by the documents and systems to deliver the offer.

These are all issues which will be explored in our action plan, with a view to making significant progress.

CARE OF THE ELDERLY

At Swansea Bay, Care of the Elderly forms part of the Department of Medicine. We provide inpatient services as well as outpatient clinics at Morriston, Singleton and Neath Port Talbot Hospitals.

Our Older Persons Assessment Service will identify patients on admission to our Emergency Department who have presented with frailty syndromes. Those patients then receive a comprehensive geriatric assessment by a multi-disciplinary team which consists of Clinical Nurse Specialists, Physiotherapists, Consultants, Associate Specialists, Advanced Nurse Practitioners. This specialist OPAS team work collaboratively with the ED Occupational Therapy and Nursing Team to ensure the best possible outcomes for each patient.

In starting this task, we distributed a survey to all staff working in Care of the Elderly and the Older Persons Assessment Service in an attempt to gain a better understanding of the demand on our area of specialism for services to be delivered in Welsh. The survey was distributed to 40 senior team members across the service. 11 responses were received (27.5%)

Whilst the information collected from the survey will give an indication of the demand placed on our services and our current ability to meet that demand, it will not paint a true picture, due to the method of capture and limited responses.

Demand

73% of respondents noted that there was currently no demand placed on their services for consultations in Welsh. Only 3 of the 11 respondents stated that patients had requested their care or treatment through the medium of Welsh.

The same number of respondents stated that their service does ask patients and service users what their language preference is. 27% are not currently asking.

The results of this survey imply that our services are not experiencing a demand for clinical consultations in Welsh. This could be due to the assumption by service users that we are unable to provide services in Welsh and therefore they do not highlight their language preference to us. Whilst analysis of the feedback received from departments show that service users are being asked their language preference, there is no certainty that this is happening with every patient, every time.

Capacity

Managers reported that their ability to offer services in Welsh was good overall. 90% of the teams that responded stated that they have staff who are confident in using Welsh when needed. Furthermore, 81% of the respondents noted that staff across the wider team were able to use basic Welsh phrases to greet and interact with colleagues and service users.

Of the 5 clinical areas that responded to the survey, 4 felt that they had sufficient language skills within their teams to be able to deliver clinical consultations in Welsh when required, with the fifth area noting that this “may be possible”

Only one area of work responded noting that they had no member of staff within their area of work who would be able to interact with a service user in Welsh. The other 10 areas that responded noted that they had between 1 and 5 team members who were confident Welsh speakers. Within those 10 teams, the Welsh speakers are widely identified so that non-Welsh speaking staff can easily seek support when needed.

This snapshot of a section of our service suggests that we have capacity within the service to be able to meet the current reported demand. It is encouraging that 90% of respondents stated that staff in their area of work are confident and willing to use basic Welsh phrases. This sets a solid foundation for further skills developments, enabling our teams to deliver a proactive offer of Welsh clinical consultations to all patients.

Data Capture and Recording

Whilst managers have told us that asking a patient’s language preference is a regular practice across the service group, only 64% of those who responded could offer assurance that the information captured during interactions with patients was being recorded.

When the information is recorded, there is significant variation in where that happens. Some areas record the information on medical notes or clinic lists, with other teams recording the information either on the Welsh Patient Administration System or the Welsh Nursing Care Record. Some teams noted that the information was captured, but not formally recorded and relayed verbally during staff handover.

This inconsistency between teams and divisions stems from teams having to use different software and systems based on the tasks they administer and sometimes their physical locations and environments. This lack of structured approach has presented challenges and will continue to restrict our ability to develop our ability to assess demand or uptake of Welsh services until a more effective method of recording the data is established.

Delivering the Active Offer

Some interesting responses were received in relation to delivery of the Active Offer. Whilst a good number of respondents (73%) stated that they do ask a language preference, The same number of respondents told us that they were unsure as to what the ‘Active Offer’ is.

27% of respondents honestly told us that they do not deliver an Active Offer, and the reasons given for this vary. Some stated that they lacked sufficient information about what an ‘Active Offer’ entailed. Others were concerned that they could potentially be offering something that they would not be able to deliver. It is evident that more work needs to be done in these areas to raise awareness of the Active Offer and its importance in improving experiences for Welsh speaking patients.

Some managers could not give a firm reason as to why the ‘Active Offer’ was not being delivered, however some did suggest that the lack of uniform recording process for the data could be a contributing factor.

Delivering an Active Offer could encourage more people to seek their healthcare in Welsh which will in turn have an impact on the demand for our services. Breaking the cycle of patients not requesting and staff not offering is the Health Board’s responsibility and we will address this in our action plan.

STROKE SERVICES

Morriston Hospital is the home of our Health Board’s stroke services. It comprises a team of Consultants, Clinical Nurse Specialists, Advanced Nurse Practitioners, Physiotherapists, Physician Associates, Junior Doctors, Ward Based nurses and an Admin Support Team.

This team offers high quality care to patients’ resident in Swansea and Neath Port Talbot as well as the wider South and West Wales regions. Many of them are receiving treatment from us when they are at their most vulnerable.

To understand how well we are currently serving patients who use the Welsh language, we have engaged with our team members to learn about the demands placed on our service and how effective we are in meeting those demands.

39% of the team members who were invited to participate in the engagement activity responded with information from their specific area of work. As the response rate is low, and the data collection method informal, we must consider this information as indicative rather than a factual representation of the overall performance of the service in relation to the Welsh language.

Analysis of findings:

Demand

The responses captured during our engagement activity have indicated that there is currently no demand from patients for Welsh language care through our stroke services. The information presented to us during our enquiries suggests that over the last 12 months, there have been no requests for consultations in Welsh within the areas of work where team members responded to our requests for information.

The informal nature of the capture of this information means that the data gathered cannot be relied upon as accurate, and it should be considered indicative rather than factual. The response rate to the engagement activity was low, and not all staff were engaged so there could be multiple instances of Welsh language provision unaccounted.

Capacity

Participants were asked to consider how their area of work would be able to respond to a request from a patient for a Welsh language consultation. We asked participants to consider the extent to which members of their teams would be able to confidently support patients in Welsh, or for those team members who are not Welsh speakers, how well the Health Board’s procedures for securing a Welsh language service for a patient is understood.

78% of those who responded told us that they have either an individual or a group of staff within their area of work who would be approached to support with aspects of service related to the Welsh language. 50% of respondents told us that they have staff members who would be confident in conducting a clinical consultation in Welsh.

4 areas of work that responded noted that they have more than one member of staff that speaks Welsh confidently. Only 1 area of work noted that they had no members of staff with Welsh language skills.

44% of those areas of work that responded noted that they had staff who were confident in using Welsh when required and 56% noted that staff members were able to use basic Welsh phrases

The findings suggest that in the areas that responded, current demand is being met and a small increase in that demand could also be met. Further consideration needs to be given to what actions are being taken to ‘expose’ demand by positive implementation of the ‘active offer’.

Data capture and recording

There is currently no uniform process for recording a patients language preference across stroke services and this needs to be addressed as a matter of urgency. When a patient visits our outpatient clinics, staff are encouraged to capture and record language preference into WPAS.

The lack of a clearly defined process or procedure for capturing language preference means that this is difficult to enforce.

22% of the teams that responded to this engagement noted that they do record language preference. Some noted that it is recorded in patient notes, others stated that it is recorded on the Welsh Nursing Care Record.

The lack of consistency of approach across the service and multiple recording locations is causing frustration. The technical limitations of systems means that although preference is recorded in one location, it may not be transferred to all locations. It has also been noted that language preference could be made more prominent on a patient’s data file, prompting staff to take action when a Welsh preference is identified.

Delivering an Active Offer

- 89% of team members across the service are either unsure what an active offer is or do not regularly provide an active offer.

Managers were unable to give us a definitive reason as to why an active offer is not routinely offered across the service. It has been suggested that the lack of a standardised process and location for recording the information could be a contributory factor. It was also suggested that the need for staff to check multiple systems for information relating to a patient’s language preference, with no certainty that the information would be held could also be presenting a barrier.

Staff members across the service who are able to converse in Welsh are encouraged to wear the orange ‘iaith gwaith’ badge as a visual identifier of their willingness to speak with others in Welsh. This is in line with Health Board policy.

Increasing visibility of Welsh speakers and effectively implementing the active offer is the minimum standard of service our Welsh speaking patients can expect from us. Only once this is achieved will we begin to have a better understanding of the true demand on our services, our ability to meet that demand and the actions we can take to increase that ability. These issues will be addressed in our action plan, and we look forward to improving experiences for our Welsh speaking service users.

CHILDREN AND YOUNG PEOPLE

The specialist care services we offer aim to promote the health and welfare of children and young people living in the Swansea and Neath Port Talbot areas. The services we offer are comprehensive and range from treatment for allergies, support with communication difficulties, treatment for heart conditions, to epilepsy and much more.

We are the home of both the Welsh Centre for Cleft Lip and Palate and the Welsh Centre for Burns and Plastic surgery and our teams at both these centres liaise with teams across the wider region and further afield to ensure the highest quality care for our younger patients.

We provide services in the community and at our hospital sites. Emergency and Acute care is delivered at Morriston, with elective and other outpatient services including post operative care provided by teams at Singleton and Neath Port Talbot hospitals. Our community teams work in partnership with allied health professionals, education, social services and the voluntary sector to achieve the best outcomes for all the patients we serve. Our community teams may be able to provide support to children and young people and their families who are concerned about development, communication, disabilities, bedwetting or other complex health needs.

Safeguarding is a high priority for us across all these services. Our staff are highly trained and are supported by our Corporate Safeguarding Team to ensure that all our patients are kept safe

Analysis of findings:

Demand

A small percentage of respondents to a recent survey indicated that they were aware of instances where patients, or guardians of patients had requested to have their interactions with us in Welsh. 6.5% of the staff members who responded had either experienced a patient requesting a service in Welsh or had the offer of an interaction in Welsh accepted.

There are currently no formal procedures in place to record information relating to the language in which a clinical consultation is carried out. Gathering of this information has been reliant on the recollection of staff across our services. Because of this, caution should be exercised in relying too heavily on this data.

Capacity

We are fortunate that we do have Welsh speakers located throughout most of our services. We regularly remind those who are able to speak Welsh with patients and their families to proudly wear their ‘iaith gwaith’ badge and we embroider it to uniforms where appropriate.

Our teams have reached the target of 85% compliance with the Welsh language awareness module and there is good understanding amongst teams of the importance of being able to deliver care in Welsh. Staff have been further supported to use more Welsh at work with training offered to paediatric outpatient reception staff and vocabulary resources cascades to all teams.

Data Capture and Recording

The process for capturing language preferences of outpatients differs across our services. Some will be asked during their initial engagement and for some, we will be advised on referral. Different systems are used by different teams and as a result staff may not always be confident of where this information can be found.

When our inpatients are asked their language preference, we record this information in the patient health record.

The range and age of the systems we use across our services presents a challenge in ensuring that reliable information on the language needs of a patient is shared effectively. This has the potential to hinder attempts at active planning of care and the allocation of Welsh speaking staff to Welsh speaking patients. Whilst resolving these digital inefficiencies may not be within the gift of this service, we will attempt to identify possible interim solutions to improve the status quo.

Delivering an Active offer.

Our staff have a good understanding of the importance of being able to access care in Welsh, and the positive effects this can have on an individual’s healthcare experience.

The Active Offer is one of many themes covered in the mandatory Welsh language awareness training that all staff are required to complete. However, it does not appear that an Active offer is being delivered by all staff across all services. We need to better understand why this is not happening and put support mechanisms in place so that staff feel empowered to confidently deliver that offer, every time.

SPEECH AND LANGUAGE THERPAPY

The speech and language therapy service within Swansea Bay spans all the Health Board’s service groups. Our therapists have been trained to assess, diagnose, treat and offer advice to people who need support with their speech and use of language, communication, voice, swallowing, eating and drinking difficulties. This support is offered from cradle to grave for those who need it.

In broad terms, the services we offer tend to be divided into three categories. Paediatrics, adults and adults with learning disabilities. We work collaboratively with other areas of the Health Board and can offer provisions within the following areas.

Neonatal

Paediatrics

Neuro Medicine (Including both inpatient and outpatient, as well as rehabilitation services)

Neurodevelopmental Services (Including early year, schools, and the Integrated Autism Service)

Head and Neck Cancer

Transgender Services

Learning Disability

Traumatic Brain Injury Services

Memory Assessment

Youth Justice

Flying Start

Cleft lip and palate

Community Based Services

We have attempted to gather information about the current level of need for Welsh language services across our remit by engaging with staff across these services. Staff were asked to consider the extent to which they were currently delivering services in Welsh. They were also asked for suggestions as to how we could improve the availability and visibility of Welsh services.

Analysis of findings

Need

The speech and language therapy department lacks the digital infrastructure to effectively capture information related to clinical consultations delivered in Welsh service wide. Patient language preference is recorded in patient records as part of a case history, but technical limitations do not allow us to retrieve this information as a report. Gathering this information manually would be a labour-intensive task for which resource is not available. Some isolated areas of the service do have the capability to record this information digitally and those areas offer appointments in Welsh to patients who speak Welsh wherever possible. The ability to offer this is dependent on availability of staff so the offer can be inconsistent, especially is highly specialist areas.

There is no set process for recording the level of need for SLT paediatric services in Welsh at present, and where we do have that information, it is usually as a result of a referral from the education sector or as a result of additional learning needs interventions.

Within adult services, our Neuro Medicine service teams do capture and record a person’s first language, but as previously mentioned, as it is not held centrally within a digital system using it effectively to pre-plan provision is difficult. Our Head and Neck service told us that no records of Welsh language interactions are kept, but a localised system to capture and record this information could be implemented relatively easily.

Our staff within Learning Disability and Memory Assessment Services have told us that patient language preference is routinely recorded in their services, either as part of a patient’s referral, or during an assessment. This information came with a caveat from both services that the information was not always reliable. It was also felt that sometimes a record of a patient’s language preference can be overlooked and highlighting the information is often dependant on a Welsh speaking staff member being allocated to that particular patient.

Capacity

107.7 whole time equivalent staff members work across Swansea Bay’s Speech and Language Therapy services. Our work to capture the skills of our staff has only identified a small number of proficient or higher-level Welsh speakers, whilst many staff members with basic language skills also became known to us. These staff members will be supported to develop their language skills, and we will evidence this in our action plan.

With the information available to us at this time, it does appear that we currently have sufficient Welsh speaking staff to be able to offer care in Welsh to those who need it. However, as we do not currently have an accurate picture of the linguistic needs of the patients we are serving, it is difficult to say confidently if we would have sufficient capacity within our current workforce to respond to that demand if there was a sudden significant growth in the number of patients needing delivery of care in Welsh.

Data Capture and recording

Our staff are regularly asking patients their language preference. 71% told us that this was embedded in their practice. What we do with that information once we have captured it, needs to improve. The current practice of recording the information in the patient record is useful, however it does not allow us to collate that information to build a service wide picture of need. If this were possible, it would enable us to more effectively plan our workforce and our services, and it turn offer a more positive experience for the service user.

It is unlikely that a new digital service wide solution will become available in the near future, so our plan will consider how we can implement local processes and procedures to improve the way we record and use the data we capture.

Implementing the ‘Active Offer’.

78% of our team members told us that they understood the concept of an ‘Active Offer’ and why it is important. Following the roll-out of mandatory Welsh language awareness training, further training was offered service wide to ensure that staff were comfortable with the requirements and to share with them examples of how an ‘Active Offer’ Could be delivered. This included a virtual session with the Health Board’s Welsh Language Officer who offered practical tips on how use of incidental Welsh could also prompt a Welsh speaker to use their language with us.

Further areas for development have been identified so that we can embed the ‘Active Offer’ into all our interactions, and we will outline these in our action plan.

APPENDIX

Action Plans

Page		Key Priority Area

24		Mental Health, Learning Disabilities, Dementia Care

36			Care of the Elderly

44			Stroke Service

49			Children and Young People

53		Speech and Language Therapy

MENTAL HEALTH, LEARNING DISABILITIES AND DEMENTIA CARE - Action Plan

The following plan outlines actions to be taken over the next 5-year period. The actions have been listed under three separate themes.

- The recruitment and upskilling of the existing workforce.

- Improving technology, systems and data collection

- Providing more positive experiences for service users

- Recruitment and upskilling the existing workforce.

These actions will be taken by our Key Priority Areas to increase the number of staff who can carry out clinical consultations in Welsh.

| No. | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
|  | Utilising the service groups “Lunch and Learn” sessions which will help in providing education around the “More Than Just Words” strategy and the “Active Offer”. Following this, holding monthly Lunch and Learns around Welsh Language dialect to upskill the current workforce. | Hold monthly Lunch and Learn sessions and engage with staff members who attend the sessions. | Increase awareness of the Welsh Language to staff Reiterate the importance of providing the “Active Offer” to service users. Allowing staff to become more familiar with using Welsh phrases as part of their day to day activities. This could potentially increase the number of service users engaging in Welsh, which we can record. | Lunch & Learn sessions, arranged by Aimee Morgan. Facilitator to be identified within the Service Group or within the Welsh Language Team. (Discussion has taken place with the WLO, and the team would be willing to support these sessions). | To begin from January 2024 – which will be ongoing. | Staff may not engage with the sessions. Staff may not want to learn and/or use the language. Staff may not see or understand the value. There is no recording mechanism in place currently to capture to number of Welsh conversations taking place. |
|  | Identifying Welsh Language Speakers and nominate a champion within each team. This allows the identified staff member to support with any Welsh Language queries, Welsh language speaking service users and promotion of the language within their respective area. A monthly meeting to be held to provide support to the Welsh Language Champions to understand whether there are any issues, challenges and success stories. | Identify at least 1 person within each team within the Service Group to be a Welsh Language Champion. | Database to be held locally within all teams identifying the staff who can use the language. Increase in the use of the Welsh Language. Increase in the “Active Offer” being utilised. Promotion of the Welsh Language and providing support to other team members. Reduction in dependence on use of language line, as more staff will be able to use Welsh Language skills. | Support from Directorate Managers to create a database and feed the information to teams within their respective areas. Team managers to identify a staff member within their team who can use their Welsh Language skills. Identify individual to hold the monthly support meeting to the Welsh Language Champions. | Begin from November 2024 | There may be a team with no Welsh Language speaking staff. Even though there will be a potential increase in the use of the Welsh Language and the use of Active Offer, however this is not currently being recorded anywhere, therefore the risk will be that it will not be evidenced or measured. Individuals may not put themselves forward to become a Welsh language champion. Currently only between 30%-40% of staff have identified on ESR their Welsh Language skills. By collating a database annually of Welsh Language speaking staff members, there is risk that the data may not be accurate and will require additional resource to produce the database. |
|  | Provide staff with the skills and encouragement to greet and communicate with service users / member of the public in Welsh at every given opportunity. The skills and encouragement can be provided through the “Lunch and Learn” sessions. Assurance will need to be provided to staff that there is no expectation of them to hold full conversations in Welsh. | To increase the use of the Welsh Language between staff and service users / visitors. Staff to become more confident and comfortable in using their Welsh Language Skills. | More use of the Welsh Language between staff and service user / visitor Staff using Welsh Language naturally in a confident way. Staff encouraging each other to use the language. Service users / visitors to feel more valued if they wish to converse in Welsh. This could be captured through service user feedback forms, querying whether they had any interactions in Welsh through entering our services. | Welsh Language Team Lunch and Learn sessions – Facilitators. Staff Patient Feedback Team. |  | There is no method in recording the number of Welsh interactions. Not all staff will be comfortable in using the language. Welsh speaking member of staff may not be available to handle the call if Welsh language is requested. If there is only one staff member within the team who speak Welsh, who is off duty / unavailable, this reduces the ability to provide service through conversing in Welsh. Staff may forget to use the greeting cards. |
|  | Encourage staff to compete the “Work Welsh” Course, which is fully funded. Provided to individuals over a 5-day period (either residential or virtual). There are sessions for 3 different levels: - Intermediate - Advanced - Proficiency Staff would require approval of study leave to complete the course (whether it be virtual or residential). | 10 staff (minimum) to engage and complete the training and utilise skills with other staff members and service users. | Feedback forms to capture the difference in their skills / confidence prior to the training and after the training and to understand how frequent they use Welsh compared to previously. | Staff within the Service Group HR Managers (to approve study leave) Welsh Language Officer Head of Nursing for Quality and Governance Work Welsh Team | January 2024 – Ongoing (Waiting for new dates for the next year to become available for the training course) | Staff may not be authorised study leave to complete the course. No recording mechanism in place currently to record outcomes of completing the course. Staff potentially may not find the training beneficial and may not use their new skills to their advantage. The course potentially may not be a permanent training programme due to government funding. |
|  | Recruiting staff who have Welsh Language skills and abilities. This will help the service to provide a better continuity of service provision in Welsh. To advertise job roles in Welsh, and to specifically ask for individuals who have the appropriate Welsh language skills. We will be linking in with the Welsh Language Comprehensive Schools & (6th Forms), Recruitment Job Fairs and local colleges to promote the Welsh Language and encourage students to pursue careers in the Health Board through the Welsh medium. Linking with Schools – providing students from Year 10 – 6th Form with information on working within the NHS and the importance of utilising their Welsh Language Skills with service users. To provide sessions to the students, we will link in with colleagues from Learning and Organisational Development as they will have relevant resources etc. | To increase the number of new Welsh speaking staff members within the Service Group. | To increase the compliance of staff recording their Welsh Language capabilities via ESR. To increase the “Active Offer” provided to service users. To increase the opportunities to implement the action plan successfully with a larger Welsh speaking workforce. | Recruitment HR Recruiting Managers New Staff Head of Nursing for Quality and Governance HR Business Partner | November 2024 – Ongoing | Advertising roles for Welsh Speakers only will potentially limit the number of candidates applying, resulting in potentially not appointing to roles. |

- Technology, Systems and Data

The following actions will be taken by our Key Priority Areas to effectively capture, record and report data relating to the provision of clinical consultations in Welsh, with a view to increasing our ability to offer to carry out clinical consultations in Welsh, over the life of the plan.

| No. | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Increase the number of staff members specifying their Welsh Language Abilities on ESR. Regular communication on how to upload via ESR, and updated compliance figures to be circulated across the Service Group on the current compliance target. | To increase the number of staff who have recorded their Welsh Language Abilities from 33% to 95%. Over the reporting periods of August 2023 – September 2024 the average % of staff recording their Welsh Language Abilities has increased: - August 2023: 33% - September 2024: 56% | For all staff within the SG to provide their skill capability on ESR The % of staff to increase across the Service Group Measured through a monthly report downlaoded via ESR. | Head of Nusring for Quality and Governance ESR Team | June 2023 – Ongoing | Staff potentially won’t engage in recording their skills and abilities on ESR. Staff may not have the confidence to upload their skills, as they may be fearful of what this may lead too. i.e. using the Welsh Language in complex situations. |
| 2. | Increase the number of staff who undertake the Welsh Language Awareness ESR E-Learning Module “More Than Just Words” Regular communication on how to access the E-Learning module via ESR, and updated compliance figures to be circulated across the Service Group on the current compliance target. | To ensure 85% compliance of staff within the MH&LD Service Group. We are increasing the compliance within MH&LD Service Group, which is seen over the reporting period August 2023 – August 2024: - August 2023: 79% - September 2024: 93.05% (The progress made with the completion of the module is very pleasing) | For all staff within the SG to be compliant with the ESR module. Measured through a monthly report downloaded via ESR. | Head of Nusring for Quality and Governance ESR Team | June 2023 – ongoing | Staff potentially won’t have capacity to complete the e-learning module due to workload, commitments and time constraints. |
| 3. | PADRs – managers to clarify with their staff their capabilities with the Welsh Language and ensure that it is recorded on the ESR system. Enquire the possibility to include a prompt on the PADR template regarding Welsh Language capabilities, when the HB Policy is next reviewed. (Review due November 2023) | All managers with have the local knowledge of all staff members within their respective area of their Welsh Language capabilities. To increase the number of staff who have recorded their Welsh Language Abilities from 40% (as of October 2023) to 95%. In the most recent reporting month, the below figures have been recorded. September 2024. Listening/Speaking; 56.53%. Reading; 55.93%. Writing; 55.39%. Prompt to possibly be included within the PADR template. | Increase in compliance on ESR of staff who can speak / read / write in Welsh. Managers will have a better understanding of their staff who can use Welsh Language skills. | Managers ESR Team HR Head of Nursing for Quality and Governance HR Business Partner | November 2023 – ongoing | Review outcome of the PADR policy remains the same with no alterations. Compliance doesn’t increase. Managers may not query with staff their Welsh Language capabilities during the PADR process. |
| 4. | For all managers to hold a local record of all staff within their team who are able to speak Welsh. This can be adopted from the above point. | To ensure that managers are aware of their staff members who can speak Welsh within their respective teams. To create a meaningful database and utilise staff skills accordingly. | Managers to utilise the staff who can speak Welsh and ensure that they are rostered appropriately on shifts. | Managers HR | To be introduced within the next 12 months – will be ongoing and reviewed on an annual basis | Managers won’t keep the record keeping up to date. No central resource to record. There may not be any member of staff within the respective team who is able to use any Welsh skills. |
| 5. | As a Service Group to support the Health Board to find opportunities and a solution for centrally recording the “active offer” being offered to all service users entering our services. | To have a corporate solution for Health Board staff to record Welsh Language preferences and the implementation of the “Active Offer” at each consultation. | A means of recording will be identified by the Health Board. The Welsh Language preference of service users and offer of the “Active Offer” is recorded | Corporate Colleagues Service Groups Health Board Wide Welsh Language Team | 5 year | Corporate Solution is not identified. Other Service Groups may not be engaged with the idea. Service Groups may have alternative solutions and ideas. |

- More positive experiences for Welsh speaking patients

The following actions will be taken to ensure growth of positive experiences for Welsh speaking patients.

| No. | Aon | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Increase the number of patient and staff stories through the Welsh medium with help of the patient feedback team based within the MH&LD Service Group. | Record 1 patient story annually around the delivery of care in Welsh. Look to increase this following | To produce 1 story annually regarding the devliery of care through the Welsh medium. Shared wider within forums across the MH&LD Service Group and Health Board. | Patient Feedback Team Staff / Service Users Welsh Language Team | November 2024 – Ongoing | Lack of staff / service users willing to share stories through the Welsh Medium. |
| 2. | Creating therapeutic activities to use with service users to aid recovery. Need to liaise with nursing and therapy colleagues to query whether there are any members who are willing to support creating therapeutic activities through the Welsh Medium for therapeutic recovery and to aid positive outcomes. | To work with various professional colleagues to create a therapeutic activity in Welsh to use with service users. To engage with service users across the Service Group to undertake therapeutic activities and improve recovery and outcomes. To pilot the activity in an inpatient Mental Health Ward to trial the process and review the service user outcomes. | Increase in engagement with the Welsh Language between staff and service user. Increasing the opportunity for service users and staff to practice using the Welsh Language Allows staff who are learning to speak Welsh to build their confidence in using the language more frequently. | Nursing Staff Occupational Therapy Welsh Language Team Service Users | November 2024 – ongoing | Nursing staff / OT staff may not be willing to create an activity through Welsh. The pilot may prove to be unsuccessful with service users. Engagement may be poor. |
| 3. | Increasing the use of the Welsh Language on patient boards within Wards. Ensuring all information boards and information leaflets are bilingual. | Ensure all information display boards and information leaflets are bilingual within every setting across the Service Group. | All Information boards that are on display along with information leaflets are translated into Welsh. | Ward and Department Managers Welsh Language Team | November 2024 – Ongoing | Information will require to be updated regularly due to information changing. Welsh Language Team may not be able to provide services to translate all information within teams i.e. Copyrighted information outside of Wales. |
| 4. | To identify a Welsh Language Champion within each team across the Service Group. | To identify at least one individual within each team to be a Welsh Language Champion | To improve the engagement and interactions with service users through the Welsh medium. Provides service users with accessibility to Welsh Language Encourages more conversations to take place in Welsh. | Welsh Language Champion Staff Managers Service Users |  | There may not be a Welsh Language Champion identified within the team, due to lack of engagement. As the role of the Welsh Language Champion is new, there will be time required to review the role and make any amendments. A description has been drafted and will require to be reviewed to ensure that the role is completing the expectation of a “Welsh Language Champion” |

CARE OF THE ELDERLY - Action Plan

The following plan outlines actions to be taken over the next 5-year period. The actions have been listed under three separate themes.

- The recruitment and upskilling of the existing workforce.

- Improving technology, systems and data collection

- Providing more positive experiences for service users

- Recruitment and upskilling the existing workforce.

These actions will be taken by our Key Priority Areas to increase the number of staff who can carry out clinical consultations in Welsh.

|  | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| A1 | Encourage staff to learn Welsh – Courses, workshops, training, refresher sessions etc. | Increase members of staff Welsh speaking ability/skills within the department and to increase the use of the Welsh language between staff and service users. | Feedback forms for service users. Reiteratie the importance of providing the “Active Offer” to service users. Local Welsh Language Officer will be able to advise on Welsh language competencies, skills development, and training opportunities available within the organisation. | All Staff (Clinical and Admin) | To begin from January 2025 | Time spent away from Clinical duties – Affect waiting list targets. Staff may not want to learn and/or use the language. With the service and Morriston currently under severe pressure – staff may not have enough time or energy to commit to courses etc. Staff may not be authorised study leave to complete the course. |
| A2 | PADR’s – Promote the values of Welsh to the individual and service users in order to provide the opportunity to develop professionally and help members of the team that don’t speak Welsh. | Staff to become more confident and comfortable in using their Welsh Language Skills. | Increase the opportunities for the staff that want to learn Welsh. | All Staff (Clinical and Admin) | To begin from January 2025 | Staff may focus on the more realistic fundamental targets of their role within their PADR targets. |
| A3 | Identify Welsh language speakers and promote a Welsh Language Champion within each team. | Identify at least 1 person within each team within the Service Group to be a Welsh Language Champion. | Database to be held locally within all teams identifying the staff who can use the language. Increase in the use of the Welsh Language. Increase in the “Active Offer” being utilised. Promotion of the Welsh Language and providing support to other team members. Reduction in dependence to use language line, as more staff will be able to use Welsh Language skills. | All Staff (Clinical and Admin) | To begin from January 2025 | There may be a team with no Welsh Language speaking staff. A large proportion of staff are international junior doctors. |
| A4 | ESR – All staff to maintain Welsh training compliance and update any Welsh language skills. | Refresh staff’s importance of the Welsh Medium for themselves and services users | Mandatory training that will need to be completed and monitored. When staff Welsh language levels change, they should ensure that their correct level of competence is updated within their ESR record to reflect this change. | All Staff (Clinical and Admin) ESR Team | To begin from January 2025 | Staff will complete the training however may forget the skills learned if not conversing in Welsh every day. |
| A5 | Potentially look at recruiting staff who have Welsh language skills/abilities and also meet the person specifications of the role. | To increase the number of new Welsh speaking staff members within the Service Group. | To increase the opportunities to implement the action plan successfully with a larger Welsh speaking workforce. | Recruitment/HR | To explore with Recruitment/HR/Service Director’s | Advertising roles for Welsh Speakers only will potentially limit the number of candidates applying, resulting in potentially not appointing to roles, with more qualified experienced non-Welsh speakers not appointed into roles. |
| A6 | Workforce planning for Welsh language skills: will ascertain the Welsh language skills of the current workforce. There are 5 levels which can be used to give an indication of somebody’s Welsh language skills – • Level 0 – No Skills (Entry level) • Level 1 – Foundation • Level 2 – Intermediate • Level 3 – Advanced • Level 4 – Proficiency | Look to develop staff to higher skill levels across the Welsh medium. | Raise awareness of support for staff who do not speak Welsh. | Training providers | To begin from January 2025 | Staff may not have the confidence to learn new skills and a large proportion of clinical staff are international students. (F1/F2/SHO level) |

- Technology, Systems and Data

The following actions will be taken by our Key Priority Areas to effectively capture, record and report data relating to the provision of clinical consultations in Welsh, with a view to increasing our ability to offer to carry out clinical consultations in Welsh, over the life of the plan.

|  | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
|  | Integrate Teams Spreadsheet – Accessible to all within the department | All staff to show an interest in learning to speak Welsh | Grow our ability to offer to deliver clinical consultations in Welsh. | All staff within department | To begin from January 2025 | Time spent away from Clinical duties – Affect waiting list targets |
| B2 | Establish a mechanism for recording uptake of offers of conducting clinical consultations in Welsh. | Recording of all instances when Welsh consultations are; 1. offered and delivered 2. offered and not delivered | Grow our ability to offer to deliver clinical consultations in Welsh. | Service Groups Local Governance panels | To begin from January 2025 | Staff may not understand the value. Technical challenges |
| B3 | Reporting of Welsh language clinical consultations data will be embedded into departmental performance meetings. | Agree project development milestones and identify any training need. Collection of patient satisfaction surveys and reporting of outcomes | Focus on our baseline gap between demand and capacity to deliver clinical consultations in Welsh | Service Groups Local Governance panels | To begin from January 2025 | Due to service pressures, meetings may not be consistent |
| B4 | Collection of patient satisfaction surveys and reporting of outcomes | To be 100% complaint with all surveys recorded centrally | Identify how we currently meet the needs of patients who require services from us In Welsh |  |  | Lack of time for staff to update and record such data |

- More positive experiences for Welsh speaking patients

The following actions will be taken to ensure growth of positive experiences for Welsh speaking patients.

|  | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| C1 | Capturing any type of patient stories/experience both positive and negative. | Fluent Welsh Speakers within the department | Grow our ability to offer to deliver clinical consultations in Welsh. | All staff | 5 Years | Lack of time for staff to update and record such data |
| C2 | Provide a department that visually promotes Welsh speaking on arrival - i.e. Active offer Poster | Fluent Welsh Speakers within the department | Grow our ability to offer to deliver clinical consultations in Welsh. | All staff | 5 Years | No associated risks highlighted |
| C3 | Use of Welsh on temporary signs and posters throughout the hospital. | Support options available if staff have limited Welsh knowledge. SBU.WelshTranslation@wales.nhs.uk. Helpful Welsh Resources (sharepoint.com) | Make service users feel welcome when visiting SBUHB premises. | All staff | Already in place | No associated risks highlighted |
| C4 | SBU Welsh Language Services Intranet page | Advice and guidance in using the Welsh language as part of your role. This resource will grow with time | To help the workforce plan for Welsh language skills within the workforce and to ensure NHS Wales organisations are meeting all necessary Legal requirements. | Available to all SBUHB employees | Already in place | No associated risks highlighted |

STROKE SERVICES - Action Plan

The following plan outlines actions to be taken over the next 5-year period. The actions have been listed under three separate themes.

- The recruitment and upskilling of the existing workforce.

- Improving technology, systems and data collection

- Providing more positive experiences for service users

- Recruitment and upskilling the existing workforce.

Outline the actions that your department will take to increase the number of staff within your department who can carry out clinical consultations in Welsh.

|  | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| A1 | Encourage staff to learn Welsh – Taught courses, workshops, training, etc. | Fluent Welsh Speakers within the department | Grow our ability to offer to deliver clinical consultations in Welsh. | All Staff (Clinical, nursing and Admin) | 5 Years | Time spent away from Clinical duties – Affect waiting list targets |
| A2 | PADR’s – Promote the values of Welsh to the individual and service users and also ensure ESR is updated with staff Welsh language skills. Provide the opportunity to develop professionally. | Increase the skills of all staffing groups to be able to converse in Welsh through teaching session | Provide more access to opportunities for staff to learn Welsh | All Staff (Clinical, nursing and Admin) | 5 Years | This is reliant on staff wanting to take on this additional work |
| A3 | Promote a Welsh Language Champion | To have at least 1 Welsh speaking individual across each of the staffing groups to be a Welsh Language Champion. | This will provide support in each area where the is a demand on Welsh speaking – e.g. it would be useful to have Welsh speaking nurse who can support other nurses who will have more clinical knowledge and not only from an admin perspective | All Staff (Clinical, nursing and Admin) | 5 Years | Not all staffing groups will have Welsh speakers |
| A4 | Where staff are confident, ask the question at the beginning of a conversation with service users if they would like to converse in Welsh | For staff who are able to converse in Welsh, all patients should be asked if they would prefer to converse in Welsh | Record to be held within the patients notes during each Consultation | All Staff (Clinical, nursing and Admin) | 5 Years | Limited staff within the team have the skills to converse in Welsh |
| A5 | Where appropriate, recruit staff with Welsh Language skills, ensuring this specification is included within the Job Description | Increase the number of Welsh speakers in the team | Increased number of Welsh speaking staff, recorded through ESR | All Staff (Clinical, nursing and Admin) | 5 Years | Limiting the number of candidates |

- Technology, Systems and Data

Please indicate steps that your department will take to effectively capture, record and report data relating to the provision of clinical consultations in Welsh, with a view to increasing our ability to offer to carry out clinical consultations in Welsh, over the life of the plan.

|  | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| B1 | Teams Spreadsheet – Accessible to all within the department | All staff to show an interest in learning to speak Welsh | Grow our ability to offer to deliver clinical consultations in Welsh. | All staff within department | 5 Years | Time spent away from Clinical duties – Affect waiting list targets |
| B2 | Develop a method for recording the patients that have been offered to converse in Welsh – ideally within the patients notes/WNCR | Field to be available to record offer of a Welsh Language Consultation | Grow our ability to offer to deliver clinical consultations in Welsh. | All staff within department | 5 Years | Limited staff within the team have the skills to converse in Welsh |
| B3 | PROMs and PREMs feedback to be reviewed. | Inclusion of Welsh language questions to be included | See an increase in data available to review our improvements to provide Welsh Language consultations | Patients | 5 Years | Additional resource will be required to develop and review the data on a regular basis |

- More positive experiences for Welsh speaking patients

Please detail the actions your department will take to ensure growth of positive experiences for Welsh speaking patients.

|  | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| C1 | Encourage staff to learn Welsh. | Fluent Welsh Speakers within the department | Grow our ability to offer to deliver clinical consultations in Welsh. | All staff within department | 5 Years | Time spent away from their core duties |
| C2 | Capturing both positive and negative patient stories/experience | Fluent Welsh Speakers within the department | Grow our ability to offer to deliver clinical consultations in Welsh. | Patients | 5 Years | Additional resource will be required to develop and review the data on a regular basis |
| C3 | Provide a department that visually promotes Welsh speaking on arrival - i.e. Active offer Poster and signs | Fluent Welsh Speakers within the department | Grow our ability to offer to deliver clinical consultations in Welsh. | Management and Corpoprate team | 5 Years |  |

CHILDREN AND YOUNG PEOPLE – Action Plan

- Recruitment and upskilling the existing workforce.

Outline the actions that your department will take to increase the number of staff within your department who can carry out clinical consultations in Welsh.

|  | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| A1 | Encourage staff to complete Welsh Language Awareness course via ESR | 85% | Increased percentage of staff with compliance | Team/Ward Managers | December 2025 | None |
| A2 | Encourage all staff to record their Welsh Language skills on ESR | 90% | All staff have updated ESR with their Welsh Language Skills | Team/Ward Managers | December 2025 |  |
| A3 | Encourage staff who are Welsh speakers to wear the orange ‘iaith gwaith’ badge. | 100% | All new and existing Welsh speaking staff are displaying the ‘iaith gwaith’ logo | All staff | December 2025 |  |
| A4 | Encourage non-Welsh speaking staff to use some of the Welsh vocabulary (resources circulated January 2024) by undertaking entry level courses, attending taster sessions. | 50% | Discuss in team meetings | All staff | December 2027 | Unsure how this can be monitored to ensure compliance. To be agreed at T&F group. |
| A5 | Raise awareness of Welsh Language skills/support/Welsh Language Act | 100% | Member of Welsh Language Team to attend key staff meetings (DBM/CBM/A&C meetings) | All staff/Welsh Language Team | December 2025 | Availability of Welsh Language Team staff |

- Technology, Systems and Data

Please indicate steps that your department will take to effectively capture, record and report data relating to the provision of clinical consultations in Welsh, with a view to increasing our ability to offer to carry out clinical consultations in Welsh, over the life of the plan.

|  | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| B1 | Ask patients their language preference and document this in the patient record. | 100% | All patient records (electronic & paper) have language preference recorded | All staff | December 2025 | Process/methods of monitoring compliance to be agreed at T&F group. |
| B2 | Incorporate feedback around Welsh Language services/active offer within patient feedback | 100% | Feedback regarding Welsh language patient experience is gathered and reviewed | Deputy HON Matron Service Managers | December 2027 |  |
| B3 |  |  |  |  |  |  |

More positive experiences for Welsh speaking patients

Please detail the actions your department will take to ensure growth of positive experiences for Welsh speaking patients.

|  | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| C1 | Establish Task & Finish Group to coordinate actions associated with Welsh Language Standards |  | Agreed membership and ToR | ADM, HON, Matrons, Clinical Leads, Managers, CNS | December 2025 | Time/availability of key personnel |
| C2 | Ensure Welsh Speaking staff are clearly identified, displaying ‘iaith gwaith’ | 100% | Staff display iaith gwaith logo | Matrons, Clinical Leads, Service Managers, DBSM | December 2025 | None |
| C3 | Ensure all staff are using bilingual greetings when answering the telephone/on voicemail | 100% | Staff provided with documentation outlining key phrases in Welsh | Matrons, DHON, HON, Service Managers, DBSM | December 2025 | Changeover of staff – to be included within induction pack |
| C4 | Ensure there is clear guidance to support non-Welsh speaking when service users request consultations in Welsh | 100% | Staff provided with links to SB UHB Welsh Language SharePoint site and documentation outlining key phrases in Welsh | Matrons, DHON, Service Managers, DBSM | December 2025 | Changeover of staff – to be included within induction pack |
| C5 | Work with Consultants to agree an action plan to be able to undertake consultations in Welsh | 100% | T&F Group | Clinical Leads, Service Managers, DBSM | December 2027 | Availability/accessibility of IT equipment and/or interpreters |

SPEECH AND LANGUAGE THERAPY – Action Plan

- Recruitment and upskilling the existing workforce.

Outline the actions that your department will take to increase the number of staff within your department who can carry out clinical consultations in Welsh.

|  | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| A1 | 1. To improve compliance with Welsh language mandatory training module on ESR | 85% compliance | ESR report | Jo Bradburn – Head of SLT | 1 year | Staff availability and maternity leave/sickness absence |
| A2 | To ensure Welsh language capabilities are updated within ESR. | 85% compliance | ESR report | Jo Bradburn – Head of SLT | 1 year | Staff confidence and competence to update ESR |
| A3 | To scope and audit staff understanding of Welsh language standards by means of a survey | 75% compliance | Survey responses Identify gaps in knowledge. Generate ideas from staff about improving compliance | Helen Cunliffe – Clinical Lead SLT Jo Bradburn – Head of SLT All SLT staff Translation services | 1 year and then annually afterwards | Time to develop survey. Time for staff to complete. Time to translate survey |
| A4 | To promote Welsh language resources that are available e.g. translation service, Welsh spell checkers (cysill), Welsh language intranet site. | Min 85% team to be aware | Improved awareness and use of these resources – assessed through annual survey/audit. Encourage attendance at periodic training offered by Welsh language services team. Promote Welsh language Intranet page. Regular updates and promotion of resources available at team meetings | Helen Cunliffe – Clinical Lead SLT | 1 year | Limited awareness of range of resources available |
| A5 | To provide time for staff to learn key/important phrases in Welsh during team meetings | Included as a standard agenda item | Improved awareness and use of these resources – assessed through annual survey/audit | Jo Bradburn – Head of SLT Judith Williams – Business Support Officer Helen Cunliffe – Clinical Lead SLT Welsh speakers within the department | 1 year | Require competent/proficient Welsh language speakers to support |
| A6 | To develop a team of Welsh language champions to support Welsh language lead with operational implementation | 1 champion in each clinical/operational area | Records of champions Champions to report into senior leads about activity Descriptors of roles and responsibilities | Helen Cunliffe – Clinical Lead SLT Jo Bradburn – Head of SLT All SLT staff | 1 year | Staff willingness to participate |
| A7 | To work with All Wales SLT colleagues and adult education to develop bespoke Welsh language training for SLT focussed on vocabulary for the workplace | TBC – Establish priority areas to focus on | Training programme for SLT staff to attend specific to service area | Adult education colleagues Key leads from All Wales SLT Advisory Forum – Cara Spencer – Chair of WSLTAF Welsh Government | 5 year | Not in SLT gift to deliver – would need support from WG. Time to release staff to attend |
| A8 | To offer Welsh language placements to students | Need to identify demand for Welsh language clinical sessions and match students to priority areas | Established Welsh language placements | Cardiff Metropolitan University Emma-Louise Austin - Placement Educator Facilitator | 5 years | Demand for Welsh language sessions currently unknown |
| A9 | To promote Welsh language opportunities within SLT prior to registration e.g. support universities (Cardiff Metropolitan) to recruit Welsh language students onto SLT course, deliver careers advice and careers days to local population | Welsh speakers to be on interview panel for recruiting university places. Welsh language speaker to present at careers day. | SLT already actively involved in these programmes but to audit attendance of Welsh speaking SLT on these events | Cardiff Metropolitan University Jo Bradburn – Head of SLT Welsh speakers in SLT dept or those with interest in increasing awareness of Welsh language. | 3 year | Limited capacity in department |
| A10 | To develop crib sheets of Welsh language phrases by telephones to develop vocabulary | All telephones to have Welsh language phrases to support use of Welsh language on phone | Audit compliance with phones that have crib sheets. Self-assessment of crib sheets to measure effectiveness of them | Helen Cunliffe – Clinical Lead SLT Jo Bradburn – Head of SLT Translation Services SLT staff | 1 year | Development of crib sheets doesn’t equate to use |
| A11 | To work with national steering groups such as Welsh Language Cognitive Assessment Group | Influence strategic development of national policy/assessment relevant to SLT | Development of Welsh Language Cognitive assessment | Helen Cunliffe – Clinical Lead SLT Jo Bradburn – Head of SLT | 5 year | Part of wider piece of work so not in SLT gift to control but SLT key to process |
| A12 | To support succession planning of posts to ensure Welsh language changes made within department are sustainable and not based on skillset of individual therapists | To ensure action plan is sustainable for future years. | Ongoing review and implementation/updating of action plan | Jo Bradburn – Head of SLT | 5 years |  |

We are encouraging staff to undertake mandatory training to improve this. Staff have been advised to ensure that their out of offices are bilingual and email signatures are bilingual, but this is not consistent across the department. We do not routinely have bilingual information leaflets. Telephone calls are answered with a Welsh greeting although not consistently across the department. Job adverts are bilingual, job descriptions are in the process of being translated into Welsh. All JD include Welsh language as a desirable characteristic. SLT have contributed to recruitment videos through the medium of Welsh. Correspondence to parents in the paediatric service is bilingual. SLT department have identified a Welsh language lead.

*

- Technology, Systems and Data

Please indicate steps that your department will take to effectively capture, record and report data relating to the provision of clinical consultations in Welsh, with a view to increasing our ability to offer to carry out clinical consultations in Welsh, over the life of the plan.

|  | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| B1 | To have electronic case note records. | All SLT dept | Would allow collation of demand to shape models of service delivery to those in Welsh | Digital colleagues | 5 year | Not within SLT gift to deliver this so needs wider HB support and investment |
| B2 | To keep central SLT specific information on requests for Welsh language assessment | All SLT dept but in the interim build upon and strengthen the areas where there is already capability to deliver this such as MAS and ALN | Creation and dvelopment of centrally saved spreadsheet to record all requests for Welsh language assessment | Jo Bradburn – Head of SLT Judith Williams – Business Support Officer All SLT staff | 3 year | Reliance on individual staff members to update |
| B3 | To have access to reliable and robust software to support Welsh speakers to use Welsh language in a professional capacity | All Welsh speakers and Welsh learners in SLT dept Software packages already available to support staff. See Software Packages (sharepoint.com) | Sharing of Welsh language resources Use of Welsh in professional context | Digital Colleagues Welsh language officer | 5 year | Awareness of resources does not guarantee use of resources |
| B4 | Implement quality assurance processes for Welsh language and bilingual patient information leaflets and other resources which are available to the public To ensure there are quality assurance procedures in place to assure Welsh language resources that are shared outside of the department. | Use of grammatically correct and audience appropriate Welsh language correspondence and resources Opportunity for collaborative working here with SLT teams at other health boards via WSLTAF | Grammatically correct Welsh language correspondence | Translation services Helen Cunliffe – Clinical Lead SLT Jo Bradburn – Head of SLT | 5 year | Time and resource available |
| B5 | To understand what data is required. Identify and agree the data sets which need to be captured to inform the future development of this plan | To have a list of required data/KPI to demonstrate compliance with Welsh Standards The purpose of this plan is to grow our ability to offer to carry out clinical consultations in Welsh. The data we collect should inform decisions you take to enable that to happen. | Generated list of data and how it can be captured this will include: Numbers offered Welsh language service and numbers accepting a Welsh language service. Annual audit of SLT team compliance and awareness of Active Offer Audit of compliance with email signatures, out of offices Explore possibilities of incorporating whether patients had a Welsh language offer in our existing PREMs processes | Welsh language officer Jo Bradburn – Head of SLT Helen Cunliffe – SLT Clinical Lead | 1 year | Implementing plans or changes that do not provide a means |
| B6 | To establish electronic booking system across HB (would enable self-referral and patients to identify if they require Welsh language provision that can be pulled directly from IT system) | In the interim, the adult team are developing a self-referral form which will capture language preference and provide valuable data | Would allow collation of demand to shape models of service delivery to those in Welsh | Digital colleagues | 5 year | Not within SLT gift to deliver this so needs wider HB support and investment. |

- More positive experiences for Welsh speaking patients

Please detail the actions your department will take to ensure growth of positive experiences for Welsh speaking patients.

|  | Action | Target | Outcome measures | Key Personnel | Timeline | Associated Risks |
| --- | --- | --- | --- | --- | --- | --- |
| C1 | To review patient information leaflets and other resources to ensure availability in Welsh or bilingually and to embed this into practice so that new information generated will be available in Welsh | Library of bilingual resources across clinical areas Establish an assurance group to quality assure the content of all patient information and promotional resource developed by the SLT dept. to ensure this meets Welsh language requirements. | Library of bilingual resources across clinical areas | Jo Bradburn – Head of SLT Ann Milligan – Head of Paeds SLT Samantha Lloyd – Head of Adult SLT Translation services | 3 year | Capacity within service and translation team Resources changing and requiring regular review and updating. |
| C2 | To offer opportunities to capture patient feedback in Welsh e.g. patient stories, friends and family | To have process in place whereby patient experience can be captured through medium of Welsh | SOP in place Patient stories in Welsh – aim to capture at least 1 Welsh language patient story per year however we could aim to increase this to 3 per year if we had the support of the corporate patient experience team to support. This would enable us to demonstrate progress | Jo Bradburn – Head of SLT | 3 year | No HB training for patient stories |
| C3 | To scope out how patient experience is captured through the medium of Welsh. | Internal review of capturing patient feedback | Audit of how patient feedback is captured. Include Welsh language as a measure within patient feedback reporting mechanisms that currently exist – would need support of patient experience team to have this added to existing F&F system | Jo Bradburn – Head of SLT Ann Milligan – Head of Paeds SLT Samantha Lloyd – Head of Adult SLT | 3 year | Time |
| C4 | To consistently provide an active offer across SLT department | 85% staff | Improved awareness and use of these resources – assessed through annual survey/audit. Include Welsh language as a measure within patient feedback reporting mechanisms that currently exist – would need support of patient experience team to have this added to existing F&F system. Consider a targeted patient experience measure for those identified as Welsh language speakers to gauge their feedback on their experiences of the Active Offer | Jo Bradburn – Head of SLT Ann Milligan – Head of Paeds SLT Samantha Lloyd – Head of Adult SLT All SLT staff | 2 year | Difficult to measure impact. |
| C5 | To ensure patients are aware of what Iaith Gwaith logo means. | Staff to wear logo if they speak Welsh. Comms to patients what the logo means | Improved awareness and use of these resources – assessed through annual survey/audit | HB communications team | 5 year | Dependent on comms to team Dependent on lanyards/pin badges/uniforms with logo for staff |
| C6 | To offer bilingual social media pages and posts on SLT social media platforms | Content planned 1 year in advance to allow time for translation | Improved awareness and use of these resources – assessed through annual survey/audit. Early identification and planning of resources that require translation. Using local Welsh speakers within the department to start offering informal translations to grow confidence using Welsh in the workplace | Jo Bradburn – Head of SLT Ann Milligan – Head of Paeds SLT Samantha Lloyd – Head of Adult SLT Translation services | 2 year | Time |
| C7 | To participate and promote the department at prominent Welsh language events e.g. Eisteddfod, Shwmae Shwmae | To showcase and promote SLT dept. in Welsh language forums to improve patient experience and recruitment strategy | Records of attendance and impact Early identification and planning of resources that require translation. Using local Welsh speakers within the department to start offering informal translations to grow confidence using Welsh in the workplace | Jo Bradburn – Head of SLT Ann Milligan – Head of Paeds SLT Samantha Lloyd – Head of Adult SLT | 5 year | Awareness of events Time to attend. Funding to attend? |