## Infection Improv Plan 25_26
Infection Prevention Improvement Plan 2025/26
Strategic aim: Development of a One Bay Infection Prevention Way to support the board's 10 Year Vision of being a High Quality Organisation with a focus on improvement and performance to deliver high quality care and patient experience • Deliver the best outcomes for our population, preventing illness and harm caused by communicable infections and healthcare associated infections; • Become a centre of excellence for research and innovation in infection prevention & control, with staff receiving excellent teaching and training on how to prevent avoidable infection and to care for those with unavoidable infections to ensure optimal outcomes; • Develop leadership and empowerment to drive improvement in reducing harm for themselves and the population of Swansea Bay; • Strengthen an integrated, equitable service to reduce harm caused by infections, patient service user at the centre
Goal | Key Metrics | Outcome | Responsibility | Progress
Improving the Culture |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
All staff are trained, educated and competent in IPC as appropriate for their role. | Achieve and sustain compliance with national training target for infection prevention & control-related mandatory training (all available staff). Working toward IP&C Training, Level 1 and Level 2 – ≥85% (available staff) by staff groups. | ≥80% compliance with mandatory training | Service Group Directors | Level 1 82.34%, Level 2 90.23% | IPC Level 1 - 91% IPC Level 2 -85%
| Staff who undertake aseptic technique are trained and can demonstrate competency | ≥85% compliance with ANTT training in staff who undertake aseptic technique and these staff have been assessed as competent | Service Group Directors | Nursing - 61.09% Medical - 10.35% AHP's - 24.71% | Nursing -58.8% Medical - 9.98% AHP's - 24%
Staff have access to evidence-based Infection Prevention and Control policies | Evidence-based Infection Prevention and Control policies are in place, are accessible and are reviewed regularly | All IPC Policies will be reviewed, will be up-to-date and will be accessible to staff | Corporate IPC Lead | All policies are current | All policies are in date.
There is an organisational culture that promotes reporting of infection-related and decontamination-related incidents | Infection-related, innoculation exposure related, decontamination-related and environmental cleaning incidents are reported, monitored and investigated appropriately, with learning shared across the organisation. | All service groups will report on and monitor infection-related incidents such as innoculation exposure, decontamination-related and environmental cleaning incidents through their agreed governance structres | Service Group Directors |  | Inclusion in IPCSG quarterly reporting
| Service Groups feedback lessons learned from the investigation of incidents through their Quality & Safety Groups | Service Group Quality & Safety meeting minutes | Service Group Directors | Feedback shared within Service Group established meetings | Feedback shared within Service Group established meetings
| Multi-disciplinary reviews of healthcare associated infections (HCAI) are undertaken in a timely way, with engagement of relevant clinical leads, that demonstrate an understanding of avoidability, with key lessons learned shared across Service Groups and the Health Board | MDT reviews of HCAI is undertaken using a standardised approach and the lessons learned are shared across the organisation. | Service Group Directors | Three Service Groups have Director-led scrutiny meetings. MH&LD to review processes for scrutiny of infection. | Three Service Groups have Director-led scrutiny meetings. MH&LD to review processes for scrutiny of infection.
| Acute Service Group Directors have oversight of Service Group performance against Tier 1 reduction goals and progress against their Infection Reduction Improvement Plans | There is a process of high level assurance relating to HCAI | Service Group Directors & Corporate IPC Leads | Established processed in place. | Established processed in place.
Leadership
Service Groups have a governance structure and processes for Infection Prevention & Control and Decontamination of re-usable medical devices | Service Group confirmation of Infection Prevention & Control Groups, co-chaired by Medical Director and Nurse Director, with multi-disciplinary engagement, meeting quarterly as a minimum | Established Service Group governance structures and management systems for IPC are in place | Service Group Directors | All service groups have established governance structures for IPC | All service groups have established governance structures for IPC
| There are designated Service Group Leads for Infection Prevention & Control and Decontamination | There is a clearly identified Service Group lead for Decontamination and there are appropriate governance structures in place | Service Group Directors | All service groups have leads identified | All service groups have leads identified
There is a programme of regular IPC-related audit | Infection Prevention & Control-related audits (Hand Hygiene, Standard Infection Prevention & Control Environment, Invasive Devices, ANTT) are undertaken and reported locally, and there is a system in place to monitor associated recommendations and actions | The IPC audit programme is established on AMaT and Service Groups review, monitor and track progress | Corporate IPC Lead and Service Group Directors | IPC Audits for inpatient areas are in place. Next phase of project development and roll-out for departments underway. | IPC Audits for inpatient areas are in place. Next phase of project development and roll-out for departments underway.
| To ensure succession planning within the IPCT service, the IPCT will undertake a work force planning review in line with the HEIW framework. | The Health Board will understand the necessary training learning & development necessary to provide an effective specialist Infection Prevention & Control service. | Service Group Directors supported by IPC lead | Workforce redesign process commenced. | Workforce redesign process commenced.
Service Groups develop leadership and empowerment to drive improvement in reducing episodes of harm. | Service Groups identify Link Champions for IPC and Decontamination | Underdertake a scoping exercise to review the service group and IPC team resources to support an IPC and Decontamination link champions system | Service Group Directors & Corporate IPC Leads | Prrimary care, Community and Therapies Service has an established Champion group. Develop a stakeholder survey for the development of Champions in other service groups | Prrimary care, Community and Therapies Service has an established Champion group. Develop a stakeholder survey for the development of Champions in other service groups
Clean & Safe Healthcare Environment
The physical environment is maintained and cleaned to a standard that facilitates effective IPC and minimises the risk of infection. Cleaning & Disinfection of environmental surfaces is fundamental to reduce the Incidence of HCAI's. (CMO & CNO Oct 2023) | Establish a collaborative review of the National Cleaning standards to review the financial and resource implications for the Health Board. | Management Board will be presented with a briefing paper outlining the Health Board's position in relation to the updated National Cleaning Standards | Head of Support Services & Corporate IPC Lead | £5M investment required to meet the standards and this has been added to the Risk Register. | £5M investment required to meet the standards and this has been added to the Risk Register.
| Cleanliness compliance scoring matrix >95% | Maintain >95% compliance with cleaning scores | Head of Support Services | Q1 - 96.74% | Q2 96.73%
| Establish protocol for Frequent Touch Point (FTP's) enhanced cleaning in response to infection related incidents/ outbreaks of infection | Clear process, understood by staff and corresponding governance | Head of Support Services & Corporate IPC Lead | Protocols established for FTP. Trial currently on Ward V | Trial has been completed. Role out to other areas is being considered.
| Establish a collaborative review of cleaning and surface disinfection products that are available within National Procurement Frameworks, with a particular focus on solutions that are safe and effective against C. difficile. | Optimum product selection for safe and effective to ensure the effective cleaning and disinfection | Head of Support Services, Service Groups, Procurement, & Corporate IPC Lead | There is to be a national group set up to review this as a Once for Wales project. SBUHB will paticipate in the national group. | There is to be a national group set up to review this as a Once for Wales project. SBUHB will paticipate in the national group.
| Service Groups to ensure safe systems exist for providing safe storage, distribution, monitoring, decontamination and disposal of foam mattresses and bed frames. | There is a certificate of decontamination on every bed and mattress following patient discharge that provides assurance for Service Groups that every patient will be assured of having a clean mattress. | Service Group Directors | Appropriate mattress storage faciltiies are not available on hospital sites. To develop a standard operating protocol for the cleaning, disinfection and certification of cleaned mattresses. | Storage locations identifed. Some modifications required, Storage/ transportation trollies ordered - awainging delivery and will then redistribute acorss the SG's
Infection prevention and control is considered as a core element at the planning and design stages of a new builds, refurbishments, repurposing and redesign schemes | The IPC team is involved at every stage of new builds, refurbishments, repurposing and redesign schemes to facilitate IPC being "designed-in". | IPC and related risks are considered at all stages of new builds, refurbishments, repurposing and redesign schemes | Service Group Directors, Assistant Director of Capital Planning, Corporate IPC Lead | Capital Planning teams occassionally omit to include IPC in smaller projects. This has been escalated to the Assistant Director of Capital Planning. | IPC are aware of current schemes and projects
| Service Groups ensure that increasing en suite single room accommodation is considered in new build, refurbishments, redesign and repurposing schemes. | Capital Planning undertake scoping exercise in Morriston to estimate impact of increasing single room capacity. | Service Group Directors & Assistant Director of Capital Planning | Planned for Quarter 2
There is an annual programme of decant and deep clean within Service Groups | Service Groups will develop an annual programme of decant and deep clean. | A programme of decant and deep clean is established | Service Group Directors, Estates and Support Services | This is feasible in Singleton whilst they have unoccupied areas. Not currently feasible in other hospital sites with current service pressures. | This is feasible in Singleton whilst they have unoccupied areas. Not currently feasible in other hospital sites with current service pressures. Pro-active 4D cleaning is undertaken in toilets/bathrooms. Reactive 4 D cleaning of cubicles is achievable when there are no time constraints due to operational pressures.
Antimicrobial Stewardship
Reduce volume of antibiotics prescribed to reduce risks associated with antimicrobial resistance and C. difficile | Reduce the volume of antibiotics prescribed across the health board, but particularly within Primary Care | Minimum 10% reduction against the 2019 to 2020 baseline by 2029 to 2030. Minimum 5% reduction against the 2019 to 2020 baseline by 2029 to 2030 | Group Medical Directors | Nationally published reports are retrospective, but the most currently published report (Q4, 2024/25, showed improvements had been made | The end of Q 2 postion is being reviewed currently. Q1 position: SBU compliance to undertaking 72 hour reviews is 89% ( higher than the All-Wales average), Compliance to guidelines - 93% (higher than the All-Wales average). AMS QI project taking place in Admission unit to improve outcome from 72 hour review.
Improve clinical understanding of the role of antibiotic prescribing in development of C. difficile infection | Where there are Periods of Increased Incidence of C. difficile, associated medical teams undertake an audit of antibiotic prescribing within the ward / speciality using the audit tool in AMaT (Antibiotic audit_ QIP package.docx (sharepoint.com)). | Improved compliance with Start Smart Then Focus standards | Group Medical Directors | No assurance that these are being undertaken. | No assurance that these are being undertaken.
Reduce risks of C. difficile and antimicrobial resistance | Improve compliance with the 72-hour switch from intravenous to oral antibiotics to equal the Welsh average as a minimum. | Equal the Welsh average as a minimum | Group Medical Directors | Q4 2024/25 report- SBUHB 10% (Welsh average 7%) | Q1 position: SBU compliance to undertaking 72 hour reviews is 89% ( higher than the All-Wales average), Compliance to guidelines - 93% (higher than the All-Wales average). AMS QI project taking place in Admission unit to improve outcome from 72 hour review.

## 2025_26 Tier 1 outcome measures
Infection Prevention Improvement Plan Swansea Bay University Health Board 2025/26
Goal | Method | WHC 2024/038: Healthcare associated infections and antimicrobial resistance goals 2024 to 2025 | Baseline position: 2023/24 | 3 month | 6 month | 9 month | 12 month | Goal/Outcome | Responsibility | Q1 Progress | Q2 Progress | Q3 Progress | Q4 Progress
Infection Prevention & Control Infection Prevention and Control (IPC) and reduction of HCAIs as per the Health Board refreshed IPC Improvement plan 2025/26 | Achieve reduction in 5 key healthcare associated infections through application of evidence-based practice and best practice guidance. | Clostridioides difficile: • Improvement goal 7: all health boards to have fewer hospital onset C. difficile cases than they had in the 2023 to 2024 fiscal year. ◦ For health boards who had a rate of >30 cases / 100,000 population in 2023 to 2024 – a 20% reduction in hospital onset cases. • Improvement goal 8: all health boards should have no more community onset cases than in 2023 to 2024, aiming to reduce the overall burden towards 25 cases / 100,000 population. | C. difficile: 250 cases | Cumulative total to Q1: < 57 cases | Cumulative total to Q2: < 113 cases | Cumulative total to Q3: < 168 cases | Cumulative total to Q4: < 217 cases | Cumulative annual total: < 217 cases Incidence rate: 56.6/100,000 overall | All Service Groups, reporting via Infection Prevention & Control Groups | 53 cases | 122 cases
|  |  | Hospital onset (HO) 116 cases | Cumulative total to Q1: < 24 cases | Cumulative total to Q2: < 48 cases | Cumulative total to Q3: < 71 cases | Cumulative total to Q4: < 92 cases | Cumulative annual total: < 92 HO cases |  | 26 cases | 67 cases
|  |  | Community Onset (CO) 134 | Cumulative total to Q1: < 33 cases | Cumulative total to Q2: < 65 cases | Cumulative total to Q3: < 95 cases | Cumulative total to Q4: < 125 cases | Cumulative annual total: < 125 CO cases |  | 27 cases | 55 cases
|  | Staphylococcus aureus bacteraemia: • Improvement goal 9: all health boards to have fewer hospital onset MRSA (Methicillin-Resistant Staphylococcus Aureus.) and MSSA (Meticillin-Sensitive Staphylococcus. aureus) bacteraemia than they had in the 2023 to 2024 fiscal year. • Improvement goal 10: all health boards to develop plans to target reductions in community onset Staph. aureus bacteraemias, aiming for an overall rate of no more than 25/100,000 population. | Staph. aureus bacteraemia: 142 cases Hospital onset (HO) - 47 cases, Community Onset (CO) - 95 cases | Cumulative total to Q1: < 36 cases < 12 HO cases < 21 CO cases | Cumulative total to Q2: < 66 cases < 24 HO cases < 41 CO cases | Cumulative total to Q3: < 94 cases < 34 HO cases < 59 CO cases | Cumulative total to Q4: < 120 cases < 43 HO cases < 77 CO cases | Cumulative annual total: < 120 cases < 43 HO cases < 77 CO cases |  | 32 cases 14 HO 18 CO | 63 cases, 31 HO 32 CO
|  |  | MSSA Bacteraemia: 135 cases Hospital onset (HO) - 42 cases, Community Onset (CO) - 93 cases. | Cumulative total to Q1: < 12 cases < 12 HO cases < 21 CO cases: | Cumulative total to Q2: HO cases: CO cases: | Cumulative total to Q3: HO cases: CO cases: | Cumulative total to Q4: HO cases CO cases | Cumulative annual total: < 116 cases < 41 HO cases < 75 CO cases |  | 30 cases 13 HO 17 CO | 25 cases 12 HO 13 CO
|  |  | MRSA bacteraemia: Hospital onset (HO) - 5 cases, Community Onset (CO) - 2 cases | Cumulative total to Q1: HO cases:0 CO cases:1 | Cumulative total to Q2: HO cases: 1 CO cases: 1 | Cumulative total to Q3: HO cases: 1 CO cases: 1 | Cumulative total to Q4: HO cases:1 CO cases:2 | Cumulative annual total: < 4 cases < 2 HO cases < 2 CO cases |  | 1 HO 1 CO | 1 HO 2 CO
|  | E. coli bacteraemia: • Improvement goal 1: health boards to have fewer overall cases of E-coli bacteraemia compared to 2023 to 2024. • Improvement goal 2: health boards to have 10% fewer hospital onset cases of E-coli bacteraemia compared to 2023 to 2024. | E. coli bacteraemia: 265 cases Hospital onset (HO) - 77 cases Community Onset (CO) - 180 cases | Cumulative total to Q1: < 56 cases < 15 HO cases < 39 CO cases | Cumulative total to Q2: < 110 cases < 27 HO cases CO cases:78 | Cumulative total to Q3: HO cases:39 CO cases: 114 | Cumulative total to Q4: HO cases: 51 CO cases: 150 | E. coli bacteraemia Cumulative annual total: < 201 cases HO cases: < 51 cases CO cases: < 150 cases |  | 65 cases 18 HO 47 CO | 137cases 38 HO 99 CO
|  | Klebsiella spp. (Klebsiella pneumoniae) bacteraemia: • Improvement goal 5: health boards to have fewer overall cases of Klebsiella spp. bacteraemia compared to 2023 to 2024. • Improvement goal 6: health boards to have 20% fewer hospital onset cases compared to 2023 to 2024. | Baseline for 23/24: Klebsiella bacteraemia: 93 cases Hospital onset (HO) < 23 cases Community Onset (CO)< 65 cases | Cumulative total to Q1: < 24 cases < 6 HO cases < 18 CO cases | Cumulative total to Q2: < 42 cases < 12 HO cases < 30 CO cases | Cumulative total to Q3: < 63 cases < 18 HO cases < 45 CO cases | Cumulative total to Q4: < 88 cases > 23 HO cases < 65 CO cases | Cumulative annual total: < 88 cases < 23 HO cases < 65 CO cases |  | 27 cases 18 HO 9 CO | 60 cases 30 HO 30CO
|  | P. aeruginosa (Pseudomonas aeruginosa) bacteraemia: • Improvement goal 3: health boards to have fewer overall cases of P. aeruginosa bacteraemia compared to 2023 to 2024. • Improvement goal 4: health boards to have 10% fewer hospital onset cases of P. aeruginosa bacteraemia compared to 2023 to 2024. | Baseline for 23/24: Pseudomonas aeruginosa bacteraemia: 21 cases Hospital Onset (HO): < 10 cases Community Onset (CO): < 11 cases | Pseudomonas aeruginosa bacteraemia: Cumulative total to Q1: HO: 3 CO: 3 | Pseudomonas aeruginosa bacteraemia: Cumulative total to Q2: HO:6 CO:6 | Pseudomonas aeruginosa bacteraemia: Cumulative total to Q3: HO: 9 CO: 8 | Pseudomonas aeruginosa bacteraemia: Cumulative total to Q4: HO:9 CO:8 | Pseudomonas aeruginosa bacteraemia: Cumulative annual total: < 17 cases HO - < 9 cases CO - < 8 cases |  | 9 cases 7 HO 2 CO | 15 cases 10 HO 5 CO