Swansea Bay University Health Board
’Early and Weekend Discharge Winter Sprint Fortnight’ Monday 8th – Monday 22nd December 25

Introduction:
This document sets out Swansea Bay University Health Boards, Swansea and NPT Local Authority arrangements to deliver the requirements of the ’Early and Weekend Discharge Winter Sprint Fortnight’ 8th-22nd December 25.
Background:
The Director General of NHS Wales has written to the Chief Executive Officers of Local Health Boards/NHS Trusts and to the Directors of Social Services in our local authorities to set out an expectation that health and social services will work collaboratively to improve patient flow, reduce pathway delays and strengthen resilience across health and social care as we approach a challenging period in relation to urgent and emergency care services. The letter is embedded below:

This ’Early and Weekend Discharge Winter Sprint Fortnight’ is to ensure that patients at every hospital site in Wales can leave hospital in a timely and safe manner. This will require implementation of a focused and collaborative effort to:
Increase daily discharges and ensure at least 33% occur before midday.
Boost weekend discharge rates by 30%.
Embed Home First principles, ensuring discharge planning begins at admission.
- Strengthen front-door processes, including senior clinical decision-making in Emergency Departments, Same Day Emergency Care (SDEC), and Acute Frailty Services.
- Consider establishment of a dedicated in-hospital rehabilitation ward or unit focused on maintaining mobility and independence, reducing the risk of deconditioning during recovery.
Enhance collaboration to optimise community capacity in domiciliary care, reablement, and step-down provision.
What are we aiming to achieve?
A key outcome of this reset is the elimination of longer ambulance patient handover delays with the intent to eliminate delays experienced by patients beyond 45 minutes. The national Handover-45 clinical taskforce will issue correspondence to support health boards’ preparations in due course.
In addition to the action outlined above, achieving this requires:
Prioritising timely patient transfers from ambulances into ED and assessment areas.
Maximising SDEC and frailty pathways to safely avoid unnecessary admissions.
Daily operational oversight to ensure handover targets are met.
During the Winter Sprint Fortnight, Health and Social care partners are asked to measure and report against the required outputs daily, these are set out below. Swansea Bay Digital partners have developed a dashboard which will be made available to key stakeholders across the system. NHS Performance and Improvement will play a key role in monitoring the outputs, providing guidance and support throughout the reset fortnight.

Summary of Key Targets Area	Target
Ambulance patient handover	Aim for all completed within 45 minutes
Discharge rates	33% realised by 12:00 p.m.
Weekend discharge	Aim for 30% increase compared to September baseline
Longest stay patients	Daily review of top 20 longest stay patients
Front door flow	No patients to spend >24 hours in ED / Reduce volumes of patients spending >12 hours in ED
Acute frailty services and SDEC	Maximise 999 direct access; and throughput from ED. Operate 7 days, 12 hrs/day

How will our reset fortnight work?
Executive Team:
The Executive team have been provided with a rota and allocated to hospital sites and to specific wards each day, week commencing the 8th December for one week to attend the Board Rounds - Appendix 1.
The Executive team will report daily to their respective sites and will attend the ‘Manager of the Day’ base. They will be escorted to the Board Round by a member of the nursing/managerial team.
Following the Board Round, the Executive team are asked to attend the ‘Manager of the Day’ base and feedback their observations from the Board Round.
Hospital Operations: Manager of the Day co-ordination hubs daily 08:30-16:30 hrs, one central hub based at Morriston weekends only 08:30-16:30 hrs:
Manager of the Day hubs will be based on all hospital sites. Operational teams will develop local rotas to demonstrate the cover arrangements for this role.
The ‘Manager of the Day’ will collate the feedback from the Executives and will actively try to expedite any pathway delays/barriers that are escalated back to them.
Operational teams will remove non-essential diary commitments and will be mobilised to wards/departments to support flow activities including Board Rounds, Ward Rounds, the daily review of the longest 20 pts.
The named Manager of the Day will be supported by operational teams including nursing and medical colleagues who will work collaboratively with the Integrated Discharge Hub to expedite flow.
The Manager of the Day will attend the site-based meetings regarding capacity and flow in their respective sites and will attend the daily safety huddle meetings.
The daily wrap up will be included in the 4pm daily safety huddle meeting where Managers of the Day will report successes, challenges or areas requiring executive support.
The hubs on each hospital site are located as follows:
- Morriston: Major Incident Room, Ground Floor.
- Singleton: Seminar Room 1, first floor
- Neath Port Talbot: Board Room, 3rd floor (Management corridor)

Local Authority partners:
The letter issued via the Director General sets out a clear expectation in relation to joint working as follows:
Success depends on strong partnership between health and social care.
Local Authorities are asked to:
Provide daily in-reach to hospitals to progress discharge actions.
Utilise transitional care home placements and step-down facilities where appropriate.
Ensure capacity for reablement and domiciliary care across seven days of the week.
Organisations will wish to consider how resources can be reprioritised and streamlined to aid delivery.
Local authority partners will undertake the daily review of the ’20 longest waiting patients’ as part of the Integrated Discharge Hub. A daily TEAMS call with relevant representatives from the Manager of the Day hubs will undertake the review, escalate pathway delays and will measure the impact of this daily review on discharge/transfer of patients.
Swansea Local Authority will aim to provide some weekend cover to support the ‘Manager of the Day’ hub based at Morriston, working with the Patient Flow team, ward teams and dedicated discharge team to expedite flow where possible to contribute to the achievement of the increased weekend discharge numbers by 30% from September baseline. To support this aim Swansea Council will be prioritising the following:
- Further increase in domiciliary care reablement capacity (success measure – 130 individuals supported on caseload daily)
- Further reduction in social work assessments outstanding post COP(success measure: 50% reduction from last census)
Neath Port Talbot Borough Council will open further beds in Glyn-Nedd reablement unit to support increased discharges. Glyn-Nedd Local Authority OT will provide an in-reach function to NPT hospital to improve flow into Glyn-Nedd where possible. The Housing department will support with housing related issues including attending meetings if required this will be put in place via the SW team when needed. The Social Work team are currently moving individuals within CWT onto brokerage to ensure greater capacity within CWT during the re-set.
 NPT LA are unable to commit to providing weekend cover to improve weekend discharge activity or to contribute to the weekend rota. However, staff will support and work with CWT/ Reablement / Glyn-Nedd to plan weekend discharges during the week where possible.

Welsh Government Support Lead:
The support lead for Swansea Bay and Swansea and Neath Port Talbot Local Authorities is Rachel Taylor, Assistant Director of Transformation and NHS Performance Improvement.

Supporting documents:
Welsh Government published a document called, ‘Delivering optimal outcomes and experience for people in hospital’. The document provides operational guidance and a ‘toolkit’ to support professionals to improve patient flow and deliver timely pathways of care. The document is embedded below:

There is a section in the document that sets out the expected standards in relation to optimal flow. Operational teams may use these standards as a point of reference to support their actions during the rest fortnight.
Suggested standards (Page 15 of Delivering Optimal outcomes and experience for people in hospital)
• Every ward must undertake an early morning board round each morning, followed by an afternoon huddle. These need to be action focused.
• Actions need to be put in place to ensure that day adds value to the patient’s inpatient stay and is GREEN.
• Actions must be recorded at the morning board round including who is responsible, timescale for feedback and outcome and achievement of action reviewed at the afternoon huddle.
• All patients must have an expected date of discharge (EDD) that has been agreed with the patient and family and is a realistic date based on the patient’s current condition and requirements for discharge. This should link to the 4question conversation and D2RA pathway recorded in the patients notes on admission.
• Rehabilitation or other treatment from health professionals to reduce deconditioning and maximise optimisation must be provided as required.
• Once patients are clinically optimised, this must be documented, and the patient discharged or transferred as soon as possible. If a patient’s discharge or transfer be delayed by more than 48 hours, this needs to be escalated and recorded as a pathway of care delay
• Every patient must be allocated to a D2RA pathway that reflects the ongoing requirements for the patient and will guide discharge planning.
• Patients aged 65 and over must have a clinical frailty score (CFS) on arrival into urgent care and those that are frail must have rapid access to comprehensive geriatric assessment (CGA) and rehabilitation.
Data Collection
A locally developed dashboard is in place to capture the Welsh Government mandated high-level health measures (see key summary of measures on page 2).
Additional measures have been issued by Welsh Government. The full data set is attached (appendix 2). There is a requirement to submit the data sets on a daily basis by 10am.
The data form will replace the daily ODU return for the duration of the sprint fortnight. The information requirements remains broadly the same as the ODU with a proportion of measures requiring data to be generated manually. Arrangements have been put in place to capture any new data requirements.
Morriston Hospital Operations will collate the information on a daily basis. An update on the top 20 patients will be emailed by named staff to the operations team by 9.30am each day.
Subject to further clarification from Welsh Government, data for each day will be validated the following day and submitted in line with guidance from Welsh Government.
Hospital Operational Plans:
Neath Port-Talbot / Singleton.
Manager/ Nurse led Board Round
Week 1 (8th – 12 December)

Week 2 (15th – 19th December)

Silver Management Daily Rota

Morriston
Manager/ Nurse and Silver on Call arrangements (Including named weekend cover)
 Ext no: 23852

20 Longest patient selection & review process:
Process will be led by Swansea and Neath Port Talbot Local Authorities.
An integrated team review will take place daily of the top 20 patients that have been selected. This will take place via Teams meetings at 11am (Monday, Tuesday, Thursday and Fridays) and 10.30am on a Wednesday. The Local Authorities will take it in turns to chair these meetings.
Feedback on progress will be fed into the daily 4pm calls.
The rota for the fortnight is outlined below.

Week 1

Week 2

APPENDIX 1: Executive Board Round rota:
Hospital	Ward	Time of Board Round	Mon 8th Dec 25	Tues 9th Dec 25	Weds 10th Dec 25	Thurs 11th Dec 25	Fri 12th Dec 25
Morriston	C	09:00 hrs			All Executives are invited to attend the Stroke MDT via TEAMS which is held at 12:30-13:30 hrs. Invites will be forwarded to your diaries.		Elizabeth Rix	1
Morriston	D	09:00 hrs	Marie Davies					1
Morriston	E	09:00 hrs					Tina Ricketts	1
Morriston	F	11:30 hrs		Deb Lewis		Matt John		2
Morriston	G	08:30 hrs					Deb Lewis	1
Morriston	H	09:00 hrs	Darren Griffiths					1
Morriston	J	12:00 hrs
Morriston	K	09:00 hrs
Morriston	L	09:00 hrs
Morriston	R	10:00 hrs				Hazel Lloyd		1
Morriston	S	09:30 hrs	Deb Lewis				Richard Evans	2
Morriston	T	08:30 hrs					Richard Thomas	1
Morriston	V/SSS		Matt John				Darren Griffiths	2
Morriston	W	09:30 hrs		Matt John		Deb Lewis		2
Morriston	Anglesey	09:00 hrs	Hazel Lloyd	Marie Davies				2
Morriston	Cardigan	09:00 hrs (11:00 hrs Weds)	Tina Ricketts	Richard Evans				2
Morriston	Cyril Evans	09:00 hrs				Richard Thomas		1
Morriston	Dan Danino	10:00 hrs						0
Morriston	Powys	09:00 hrs						0
Morriston	AMU	10:00 hrs	Alison Clarke					1
Morriston	OPAU	10:00 hrs				Marie Davies	Hazel Lloyd	2
NPTH	B	09:00 hrs		Hazel Lloyd				1
NPTH	C	09:00 hrs				Elizabeth Rix		1
NPTH	D	09:15 hrs				Alison Clarke	Matt John	2
Singleton	3	09:00 hrs						0
Singleton	12	09:00 hrs				Richard Evans		1
Singleton	4	09:00 hrs					Alison Clarke	1

APPENDIX 2:
Copy of SBUHB Sprint fortnight daily reporting dataset.