| Meeting Date | 04 June 2026 | Agenda Item | 3.1 |
| --- | --- | --- | --- |
| Name of Meeting | Quality & Safety Committee |  |  |
| Report Title | Risk Report |  |  |
| Report Author | Assistant Head of Risk & Assurance |  |  |
| Report Sponsor | Director of Corporate Governance |  |  |
| Presented by | Assistant Head of Risk & Assurance |  |  |
| Freedom of Information | Open |  |  |
| FoI Closed detail | If closed, choose detail |  |  |
| Impact Assessment Summary Outcome |  | IA Completion date |  |
| N/A |  | Click or tap to enter a date. |  |
| Purpose of the Report | For Assurance |  |  |
| Report Summary; detailing any action required |  |  |  |
| The purpose of this report is to present extracts of the Health Board Strategic Risk Register (SRR) and Corporate Risk Register (CRR) to the Quality & Safety Committee (QSC) for oversight to support the provision of assurance to the Board in respect of the management of risks. |  |  |  |
| Key Issues |  |  |  |
| Since the last reporting cycle, improvements have been made to the articulation of risks, the alignment between risk registers, and the clarity of actions and controls in place. Following a dedicated meeting of the Executive Team on 30th March and the subsequent April review cycle, significant changes have been made to the Strategic (SRR) and Corporate Risk Registers (CRR). This has included the movement of risks from the SRR to the CRR with these developments contributing to further strengthening of the overall risk management framework. There are now three strategic risks within the SRR allocated to this Committee for oversight and nine risks within the CRR allocated to the Committee. While this number has not changed, the risks of which it is comprised have: four risks are new to the Committee; four risks have been de-escalated or transferred from the Committee’s oversight. The report summarises at a high-level, changes in risk scores and the status of risk targets and actions to bring risks currently above appetite to a more tolerable level. The report also indicates work done to align the Committee work plan to key risk areas. |  |  |  |
| Decision / Action required | No |  |  |
| Recommendations |  |  |  |
| Members are asked to: - Receive for Assurance the Risk Report. - Consider whether any additional information or action is required by risk owners or the Risk & Assurance team to provide assurance on the management of risks. |  |  |  |

RISK REPORT

- INTRODUCTION

1.1	The purpose of this report is to present extracts of the Health Board Strategic Risk Register (SRR) and Corporate Risk Register (CRR) to the Quality & Safety Committee (QSC) for scrutiny to support the provision of assurance to the Board in respect of the management of identified risks.

- BACKGROUND

2.1	The Strategic Risk Register (SRR) is intended to summarise the principle risks to the health board (at the strategic level) that could impact successful delivery of one of the organisation’s five strategic objectives, typically over medium to long-term timeframes (‘horizon 3’).

2.2	The Corporate Risk Register (CRR) is intended to record significant corporate or operational risks escalated by services to Executive / Corporate Director level and agreed for oversight at Board / Committee level. The timescales within which these risks are anticipated to impact are typically short to medium term (‘horizon 2’). The decision to escalate to the CRR is informed by consideration of the level of risk against the Board’s appetite statement (currently under review) alongside the following criteria:

- The risk is above tolerance level and there is nothing that the risk owner can do to reduce it within tolerance level within an acceptable timeframe.

- The risk is above tolerance and options to treat the risk are outside of the delegated levels of control assigned to the risk owners.

- The risk presents a significant threat to the achievement of health board objectives or targets.

- The risk is assessed to be of significant concern (typically prompted by a very high local assessment of risk level)

- The risk is shared across areas of the organisation and coordination of treatment may be complex.

2.3	Each Service Group and Corporate Directorate has an Operational Risk Register (ORR) recording risks to the delivery of their services. It is the responsibility of the risk owner within a service to escalate risks where required, via their Directors and local governance teams. The decision to escalate to the CRR is informed by consideration of the level of risk against the Board’s appetite statement (currently under review) alongside the following criteria:

- The risk is above tolerance level and there is nothing that the risk owner can do to reduce it within tolerance level within an acceptable timeframe.

- The risk is above tolerance and options to treat the risk are outside of the delegated levels of control assigned to the risk owners.

- The risk presents a significant threat to the achievement of health board objectives or targets.

- The risk is assessed to be of significant concern (typically prompted by a very high local assessment of risk level)

- The risk is shared across areas of the organisation and coordination of treatment may be complex.

For risks already on the CRR which may require escalation/de-escalation, the monthly CRR review cycle provides an opportunity for consideration by Board Directors.

2.4	The Executive Board is responsible for providing senior management oversight of risk management. To support this, it receives regular risk reports accompanied by the full Strategic Risk Register, Corporate Risk Register and summary of Operational Risk Register content (providing profile of significant risks recorded within service groups). Its role includes the approval of escalation and de-escalation of risks.

2.5	Board Committees scrutinize arrangements in place to manage risks to the achievement of the health board services and objectives, within the scope of their terms of reference, in order to provide assurance to Board in respect of the same. To support this, they receive extracts from board-level risk registers to consider at meetings and in advance to ensure their work programme and agendas include management reports on areas of significant risk.

2.6	The Audit Committee is responsible for providing assurance to the Board on the wider establishment, maintenance and effectiveness of the system of integrated governance, risk management and internal control across all organisational activities in support of achievement of its objectives. To support this role, while it may receive the full risk registers, it is not expected to replicate the scrutiny of individual risks done by other Committees, but to consider whether the overall framework is working effectively. This would include the provision made for assurance to the Board on risk management via other board committees. To support this, the risk report to the Audit Committee presents a high-level summary of key risk information, together with assurance on the risks considered by other committees.

- GOVERNANCE AND RISK ISSUES

3.1	Strategic Risk Register (SRR) Update

3.1.1	The Executive Team dedicated a meeting on 30th March 2026 to a review of the Strategic Risk Register. The focus of the meeting was to ensure it reflected the most significant strategic risks facing the organisation for 2026/7 and beyond and the meeting activity therefore prioritised the review of risk descriptions, scores and the most appropriate registers on which to monitor the risks going forwards. Further review and action were taken by lead Directors following that meeting resulting in changes to the register content, including the movement of risks between risk registers and the re-articulation and re-assessment of risks in some cases.

3.1.2	The Audit Committee and Board received information on changes made at their May meetings (this detail will not be repeated here). The revised April 2026 SRR contains 12 risks, three of which have been allocated to this Committee for oversight. See Appendix 1 for full detail.  The profile of these risks is summarised below (please see Glossary at back of this report for any abbreviations):

| SRR Ref | Strategic Risk | Lead | Risk Score |  |  | Current Overall SRR Assurance |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | I | C | T |  |
| Objective 2: Care is high quality, safe, efficient and delivers the best possible outcomes for people |  |  |  |  |  |  |
| 2.4 | Quality, Safety & Patient Outcomes | EDON | 20 | 16 | 12 | GOOD |
| 2.6 | Perinatal Service | EDON | 20 | 16 | 9 | GOOD |
| 2.7 | Mental Health | COO | 20 | 16 | 8 | GOOD |

There have been no risks added or removed from the SRR allocated to the QSC, but titles, scores and where appropriate, risk descriptions, have been adjusted.

Actions to improve control / assurance are assigned for two of the risks: SRR 2.4 Quality, Safety & Patient Outcomes and SRR 2.6 Perinatal Services. Progress has been updated and revised timescales provided where there is slippage.

The actions and targets for the third risk, SRR 2.7 Mental Health, will be highlighted for review by the Executive Risk Owner / supporting senior management as part of the next cycle of review and updated for the next meeting.

3.2	Corporate Risk Register (CRR) – QSC Risks

3.2.1	There are now 9 risks are assigned to the Quality & Safety Committee for oversight (See Appendix 2 for full detail). The profile of risk scores is presented below:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Number of Risks Last Report (Feb 2026) | 0 | 0 | 2 | 7 | 0 | 9 |
| Number of Risks This Report | 1 | 0 | 2 | 6 | 0 | 9 |

3.2.2	Key movements are:

| Change | Comment |
| --- | --- |
| New Risks | CRR53 Welsh Language Standards* CRR111 Listening to People (transferred from SRR) CRR114 Mental Health & Learning Disabilities Staffing CRR116 Maternity Services Site |
| Scores Increased | Nil |
| Scores Reduced | Nil (new risk CRR53 reduced as it was transferred to a current risk score of 12) |
| Risks De-escalated | CRR43 Deprivation of Liberty Safeguards CRR61 Paediatric Dental General Anaesthetic Provision CRR69 Adolescents Being Admitted to Adult MH wards |
| Risk Reallocated | CRR89 HMP Swansea (transferred to Workforce & OD Committee) |

3.2.3	The risks CRR53 Welsh Language Standards is not a new risk to the Health Board (it has been included in registers received by the full board) but was not assigned to a formal committee of the board previously.

3.2.4	Risks above Board appetite:

There are 7 of the 9 risks meeting or exceeding the Health Board’s risk appetite thresholds, for which action is required so that they may be reduced to acceptable levels. The table below highlights recent changes / actions of note for those risks that are currently meeting or exceeding the thresholds (please see Glossary at back of this report for any abbreviations):

| Ref | CRR Risk Title | Lead | Risk Score |  |  | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | I | C | T |  |
| 4 | Healthcare Acquired Infection | EMD | 25 | 20 | 20 | No change to current risk score. Actions are identified which include the development of improvement plans. However, the Gaps in Assurance section of CRR identifies challenges and constraints in generating lower target score currently. |
| 64 | Health & Safety Infrastructure | DOF | 25 | 20 | 20 | No change to current risk score. The phased approach to action to address the risk is indicated in the Register, and the target score has been revised to reflect the position based on the actions currently indicated. The Gaps in Assurance section of CRR identifies areas remaining to be addressed and indicates potential to review the target score following decision regarding of funding for the next phase of action. |
| 66 | Access to SACT (Systemic Anti-Cancer Therapy) | EMD | 25 | 20 | 10 | No change to current risk score. Actions have been identified, the target risk score reviewed and refreshed. A risk target date of 28/12/2026 has been indicated, by which the target score is anticipated to be achieved. |
| 80 | Clinically Optimised Patients | COO | 20 | 20 | 8 | No change to current risk score. Actions were identified (these will require review and refresh as part of the next cycle). No risk target date has been indicated currently. This will be highlighted as an area for consideration by the risk owner during the next register review cycle. |
| 85 | Non-compliance with Additional Learning Needs (ALN) Act | DAHPHS | 20 | 16 | 12 | The current risk score has been reduced from 20 to 16. The risk has been reviewed by the lead and significantly refreshed, including a reassessment of current and target risk scores, and refreshed actions. A risk target date of 30/09/2026 has been indicated, by which the target score is anticipated to be achieved. |
| 114 | Mental Health & Learning Disabilities Staffing | COO | 25 | 20 | 15 | This is a new risk. Actions have been identified. No risk target date has been indicated currently. This will be highlighted as an area for consideration by the risk owner during the next register review cycle. |
| 116 | Maternity Services Site | EDON | 25 | 20 | 20 | This is a new risk. Actions have been identified. The target score currently matches the current risk score and reflects the effect of current actions. One of the actions identified is an options appraisal. The register entry indicates following the options appraisal there may be opportunities to identify further action to reduce score and indicate a lower target. The target date for completion of the options appraisal is 31/03/2027. |

3.2.5	Risks within Board appetite:

The below table presents risks currently considered within the Board’s risk appetite and their current scores for information:

| Ref | CRR Risk Title | Lead | Risk Score |  |  | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | I | C | T |  |
| 53 | Welsh Language Act | EDON | 15 | 12 | 9 | Risk has been assigned to QSC. Current risk score reduced from 15 to 12. |
| 111 | Listening to People | EDON | 20 | 16 | 9 | Risk has been transferred by the Executive Team from SRR to CRR. Current risk score is unchanged. |

Across the risks within the Committee’s remit, there is variation in the extent to which actions and/or timescales anticipated to reduce risks are currently identified.

In a number of areas, achievement of target scores is contingent on factors such as workforce, capital investment, or service reconfiguration.  Progress in these areas will continue to be monitored through Executive and Committee oversight arrangements to support assessment of whether risks are likely to be reduced within appetite and the timescales anticipated.

The alignment of Strategic Risk Register and Corporate Risk Register is reflected in Appendix 3.

3.3 Operational Risk Registers

3.3.1	Each Service Group and Corporate Directorate has an Operational Risk Register (ORR) recording risks to the delivery of their services. There is work being undertaken by the Risk & Assurance team within risk owners within services to review the detail within operational risk registers, with particular focus being directed at those within service groups. At the beginning of May 2026, the service group operational risk registers were recording risks scoring 20 or above, categorized under the current risk types as below:

| Risk Type | Number of risks |
| --- | --- |
| Compliance & Legislation | 5 |
| Environment, Estates & Infrastructure | 12 |
| Financial Management | 1 |
| Governance & Assurance | 4 |
| Health & Safety | 3 |
| Information Governance | 1 |
| Medical Devices & Equipment | 9 |
| Patient Safety | 2 |
| Sustainable Services | 32 |
| Workforce & OD | 16 |
| Total | 85 |

This is presented for information for Committee members.

3.4	Committee Work Plan

3.4.1	Since the last report to the Committee, the Risk & Assurance team has reviewed the Committee Business Cycle against the content of the refreshed SRR and CRR. We noted most relevant high-scoring risks were covered, but identified some areas for further consideration within the Committee work plan and as part of the agenda planning process, as follows:

| Risk Ref | Risk Title | Comment and Action Agreed |
| --- | --- | --- |
| CRR64 | Health & Safety Infrastructure | There is a Health & Safety Management Report scheduled on the workplan, so this subject is covered, however, explicit consideration of this risk will be requested as part of the coverage. |
| CRR66 | Access to Systemic Anti-Cancer Therapy (SACT) | This was not explicitly covered in the work plan. It has been proposed to add a deep dive into Cancer Services to the work plan, to include coverage of SACT. |
| CRR111 | Listening to People | This was not explicitly covered in the work plan. It was agreed to add this as an item. |

Further consideration is to be given to the potential coverage of the CRR85 Additional Learning Needs Act risk.

- OPEN AUDIT RECOMMENDATIONS

4.1	Progress against internal audit recommendations in relation to the risk management framework is overseen by the Audit Committee. An update will be provided to its next meeting.

- FINANCIAL IMPLICATIONS

5.1	This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered within risk register. Where this is the case, they are highlighted within individual risk register entries or dedicated board/committee papers for information.

- RECOMMENDATION

Members are asked to:

- Receive for Assurance the Risk Report.

- Consider whether any additional information or action is required by risk owners or the Risk & Assurance team to provide assurance on the management of risks.

| Governance and Assurance |  |  |
| --- | --- | --- |
| Strategic Objectives |  |  |
| Strategic Objectives (please choose which is impacted) | People of Swansea Bay live healthier, fairer and more prosperous lives | ☒ |
|  | Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | ☒ |
|  | Care is delivered in partnership with our communities in safe and appropriate setting, supported by innovation | ☒ |
|  | The health board is a great place to work where staff feel valued and work together towards a common goal | ☒ |
|  | The health board is a resilient, sustainable and responsible organisation | ☒ |
| Health and Care Standards |  |  |
| Standards (please choose which applies) | Safe Care | ☒ |
|  | Timely Care | ☒ |
|  | Effective Care | ☒ |
|  | Efficient Care | ☒ |
|  | Equitable care | ☒ |
|  | Person-centred Care | ☒ |
|  | Staff and Resources | ☒ |
| Enablers (please choose which applies) | Whole Systems Approach | ☒ |
|  | Leadership | ☒ |
|  | Workforce | ☒ |
|  | Culture | ☒ |
|  | Information | ☒ |
|  | Learning, Improvement and Research | ☒ |
| Quality, Safety and Patient Experience |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |
| Financial Implications |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on risk registers. Where this is the case, they are highlighted within individual risk register entries for information. |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |
| Staffing Implications |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Board Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |
| The board level risk registers present the framework within which SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |
| Report History |  |  |
| This report updates on risk matters received by the Committee in February 2026 and provides further information on risks received by the Board in May 2026. |  |  |
| Appendices |  |  |
| Appendix 1 – Strategic Risk Register (April 2026) extract Appendix 2 – Corporate Risk Register (April 2026) extract Appendix 3 – Risks on a Page (April 2026) |  |  |
| Glossary of Abbreviations |  |  |
| Director Leads: COO Chief Operating Officer DICE Director of Insight, Communication & Engagement DOCG Director of Corporate Governance DODIG Director of Digital DOF Director of Finance & Performance DOPH Director of Public Health DOPP Director of Planning & Partnerships DOWOD Director of Workforce & Organisational Development DAHPHS Director of Allied Health Professions & Health Sciences EDON Director of Nursing & Patient Experience EMD Medical Director Committees: AC Audit Committee DDRIC Digital, Data, Research & Innovation PFC Performance & Finance PHC Population Health QSC Quality & Safety WODC Workforce & Organisational Development |  |  |

I=Inherent Risk; C=Current Risk; T=Target Risk

Assurance as expressed by Executive Risk Owner

HMP = His Majesty’s Prison

I=Inherent Risk; C=Current Risk; T=Target Risk

I=Inherent Risk; C=Current Risk; T=Target Risk