Report Point: 29/04/2026

| Ref | Date of Inspection | Inspection | HIW Ref | Report Rec’ns | Actions Agreed | Actions Complete | Actions Ongoing | Actions Overdue |  | Expected Completion Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MHLD |  |  |  |  |  |  |  |  |  |
| 1 | May 2023 | Ward F, NPTH | 03367 | 33 | 66 | 61 | 5 | 5 |  | TBC |
| 2 | Sep 2023 | Caswell Clinic, MHLD | 03642 | 15 | 15 | 12 | 3 | 3 |  | TBC |
| 3 | Oct 2024 | Tonna Hospital Suite 2 | 03690 | 17 | 37 | 27 | 10 | 9 |  | 30/04/2026 |
| 4 | Jul 2025 | Community MH Team (Swansea North) | 03871 | 32 | 79 | 23 | 56 | 56 |  | TBC |
| 5 | Oct 2025 | Tawe Clinic, Cefn Coed Hospital | 03641 | 39 | 89 | 0 | 10 | 79 |  | 30/11/2026 |
| New | Feb 2026 | Rowan House | 03938 | 13 | 37* | - | - | - |  | 30/06/2026 |
|  | NPTS |  |  |  |  |  |  |  |  |  |
| 6 | Jan 2023 | Paediatrics: Ward M & Oakwood Ward, Morriston | 03294 | 10 | 12 | 10 | 2 | 2 |  | TBC |
|  | Morriston |  |  |  |  |  |  |  |  |  |
| 7 | Feb 2023 | IR(ME)R: DI Dept, Morriston | 03297 | 16 | 49 | 43 | 6 |  | 6 | 30/04/2026 |
| 8 | Jun 2024 | IR(ME)R: Nuclear Medicine, Morriston | 03707 | 13 | 23 | 12 | 11 |  | 11 | 30/04/2026 |
| 9 | Nov 2024 | ED Morriston | 03716 | 15 | 44 | 21 | 23 |  | 23 | TBC |
| 10 | Feb 2025 | Diagnostic Imaging, Singleton | 03653 | 21 | 23 | 22 | 1 |  | 1 | 30/04/2026 |
| 11 | May 2025 | Minor Injury Unit, NPTH | 03903 | 16 | 25 | 22 | 3 |  | 3 | TBC |
|  | PCT |  |  |  |  |  |  |  |  |  |
| 12 | Aug 2021 | HMP Swansea | N/a | 29 | 38 | 37 | 1 |  | 1 | TBC |

SUPPORTING NOTES

MENTAL HEALTH & LEARNING DISABILITIES SERVICE GROUP

1) Ward F NPTH (ref 03367): The 5 outstanding actions relate to smoking cessation/policy, nurse call alarms (estates), fire extinguishers relating to Section 136 suites and estates work, and two actions relating to the model of care (linked to transformation work).

2) Caswell Clinic (ref 03642): There are 3 outstanding actions relating to policy, environment and alarm system. The service has been inspected more recently by HIW. The position will be reviewed against improvements required following finalisation of HIW’s more recent inspection (currently Draft stage).

3) Tonna (ref 03690): Actions remaining relate largely to capital and environmental factors, workforce, and training compliance of staff.

4) CMHT (ref 03871): The Risk & Assurance team has been informed that the service has made further progress further not yet recorded in the AMAT system, but that the update is subject to Service Group review and sign off and update. Arrangements are being made to facilitate that update.

5) Tawe Clinic (ref 03641): The 3-month progress against the manual improvement plan was submitted to HIW in April. Figures in the table reflect the position in AMAT which has not been updated yet. Arrangements have been made to facilitate that update.

Also: Rowan House has now been added to the system. The update position will be reported above after the first 3-monthly up-date submitted to HIW. Updates have been requested directly via the AMAT system so that the position is consistent with the one reported to HIW.

NEATH PORT TALBOT & SINGLETON SERVICE GROUP

6) Paeds (ref 03294): Two actions are subject to review currently with a view to closure. One of the remaining actions relates to the refurbishment of the environment. In respect of this the Service Group notes that a basic refurbishment of the ward has already completed since the visit in January 2023, and the paediatric ward environment remains on our corporate risk register. At this point, the only viable option would be to relocate the ward, which is a much wider and more complex piece of work.

MORRISTON SERVICE GROUP

7) Diagnostic imaging Dept Morriston (ref 03297): Further review is required to update actions remaining for this inspection in the service. This has been highlighted via Quality & Safety Group and the risk & assurance team will support as required.

8) Nuclear Medicine Morriston (ref 03707): Further review is required to update actions remaining for this inspection in the service. This has been highlighted via Quality & Safety Group and the risk & assurance team will support as required.

9) ED Morriston (ref 03716): Further review is required to update actions remaining for this inspection in the service. This has been highlighted via Quality & Safety Group and the risk & assurance team will support as required.

10) Diagnostic Imaging Singleton (ref 03653): All but one action complete. The last matter has been discussed at All Wales Quality Imaging Forum and has been queried with HIW (response awaited).

11) MIU NPTH (ref 03903): Progress has been indicated on 2 of the 3 remaining actions but they require sign off within the Service Group before confirmed complete. This has been highlighted via Quality & Safety Group and the risk & assurance team will support as required.

PRIMARY COMMUNITY & THERAPY SERVICE GROUP

12) HMP Swansea: One action remains: It is dependent upon allocation of further funding, which is not identified currently. The risk is on the Corporate Risk Register.