| Meeting Date | 18 April 2024 |  | Agenda Item |  |  | 3.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Management Report |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to inform the Workforce OD & Digital Committee of the risks within the Health Board Risk Register (HBRR) assigned to the Committee for scrutiny. |  |  |  |  |  |
| Key Issues | - The HBRR was last received by the Workforce OD & Digital Committee (WODC) in December 2023. - Since then risks have been subject to update by Executive Directors on a monthly basis. The HBRR for February 2024 was received by the Board in March 2024. This paper presents an extract of risks assigned to the WODC from that register. - The number of risks overseen by Workforce OD & Digital Committee is six in open session (an additional sensitive risk has been identified for review within closed session). |  |  |  |  |  |
|  | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Workforce OD & Digital Committee. - CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any. |  |  |  |  |  |

HEALTH BOARD RISK REPORT

- INTRODUCTION

The purpose of this report is to inform the Workforce OD & Digital Committee of the risks within the Health Board Risk Register (HBRR) assigned to the Committee for scrutiny.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular HBRR update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

Risk Register management is supported by a Risk Management Group (RMG) which meets quarterly and is responsible for overseeing the operational management of risk, ensuring local systems and processes are in place and are operating effectively to ensure appropriate reporting and escalation. The Group last met in January 2024.

Additionally, a Risk Scrutiny Panel is responsible for ensuring there is an appropriate and robust risk management system in place and working throughout the organisation. It is responsible for moderating new risks and risks escalated to the Health Board Risk Register (HBRR) and Board Assurance Framework (BAF) and recommending and advising the Management Board on the escalation and de-escalation of risks. The Panel last met in February 2024.

2.2 Risk Appetite

Risk appetite and tolerance provide clarification on the level of risk the Board is prepared to accept.

The health board approved a risk appetite statement in November, setting out a new approach to expressing the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, requiring risks scoring 16 or above to be overseen at committee level. The mechanism for reporting risk is developing to support this for board and committee updates.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

- GOVERNANCE AND RISK

3.1 Management of Health Board Risk Register (HBRR)

The HBRR was last received by the Workforce OD & Digital Committee (WODC) in July 2023. Since then risks have been subject to update by Executive Directors on a monthly basis. The full HBRR for February 2024 was received by the Board in March 2024. This paper is based on an extract from the same HBRR as attached at Appendix 1.

The number of risks overseen by Workforce OD & Digital Committee in open session is now six:

- HBR 3	Workforce Recruitment of Medical & Dental Staff

- HBR 27	Digital Transformation to Deliver Sustainable Services

- HBR 36	Electronic Patient Record (Paper Record Storage)

- HBR 37	Operational & Strategic Decisions are not Data Informed

- HBR 51	Nurse Staffing Levels Act

- HBR 90	GDPR Subject Access Requests

In addition, the following risk is deemed sensitive and will be overseen in closed session:

- HBR 60	Cyber Security and

- HBR 97 	Industrial Action is shared for information as the assuring

committee is Performance & Finance Committee.

A further three risks are overseen by other Committees, but reported to the Workforce OD & Digital Committee for information:

- HBR 64	H&S Structure

- HBR 81 	Midwifery: Critical Staffing Levels – risk level reduced from 25 to 20.

- HBR 89	HMP Swansea Nurse Staffing Levels

The profile of risk scores for seven risks assigned to WODC is as follows:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 |
| --- | --- | --- | --- | --- | --- |
| Number of Risks | 2 | 0 | 3 | 2 | 0 |

3.2 Risks Exceeding Appetite

Section 2.2 above indicated the risk level thresholds associated with the health board risk appetite statement approved in November 2022. There are 4 risks currently meeting or exceeding the Health Board’s appetite thresholds, for which action is required so that they may be reduced to acceptable levels. The tables below highlight recent changes / actions of note since the last meeting of the Committee for those risks that are currently meeting or exceeding the thresholds:

| HBR3: Workforce Recruitment Risk of failure to recruit medical & dental staff |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Workforce and Operational Development | 20 | 20 | 12 |  |

| HBR 51: Non Compliance with Nurse Staffing Levels Act (2016) There is a risk that we might not be able to maintain safe staffing levels due to staff unavailability, vacancies and sickness levels. The potential impact of this maybe avoidable harm, suspension of services, non-compliance with the Nurse Staffing Act. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Executive Director of Nursing | 20 | 16 | 12 |  |

| HBR 90: Non-compliance with UK-GDPR Article 15 regarding Subject Access Requests (SARs), along with other health records requests for disclosure of personal data The Health Board does not have adequate resources to deal with the sustained increase in volume and complexity of subject access /access to health records requests received from requestors. The ICO are already involved with a number of breaches and complaints in this area and there is the potential for future enforcement action if significant improvements are not made. Misfiling and redaction are major issues for Health Records, IG and Health Professionals. SAR breaches have led to successful compensation claims and media interest. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Digital | 16 | 16 | 12 |  |

Further detail on the above risks can be found at Appendix 1.

In addition, HBR50 Cyber Risk exceeds the Board’s risk appetite with a score of 20 currently. The full risk entry is reported separately within Closed session to the Committee.

3.3 Other Risks Assigned to this Committee

When the Board’s risks appetite was agreed in November 2022, it was the Board’s aspiration that thresholds could be reduced in the future. In view of this, additional risks assigned to this Committee which are not currently meeting the appetite threshold are presented below for information:

| HBR 27 Digital Transformation Inability to deliver sustainable clinical services due to lack of Digital Transformation. There are insufficient resources to: - Invest in the delivery of the ABMU Digital strategy, - Support the growth in utilisation of existing and new digital solution - Replace existing technology infrastructure and the end of its useful life. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Digital | 16 | 20 | 12 |  |

| HBR 36 Paper Record Storage Lack of a single electronic record means there is greater reliance on the provision of the paper record. If we fail to provide adequate storage facilities for paper records, then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. There is an increased fire risk where medical records are stored outside of the medical record libraries. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Digital | 16 | 20 | 9 |  |

| HBR 37 Operational and strategic decisions are not data informed - Business intelligence and information already available is not utilised - Users are unable to access the information they require to make decisions at the right time - Gaps in information collection including patient outcome measures |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Digital | 12 | 20 | 8 |  |

Further detail on the above risks can be found at Appendix 1.

3.4 For Information – Risks Assigned to Other Committees

There are four  risks which are assigned to other Committees in terms of overseeing actions to mitigate the risks, as outlined in the table below, noted here for information. As noted earlier, the detailed HBRR entries are also included in Appendix 1 for information.

| Ref | Description of Risk Identified (Summarised) | Exec Lead | Committee | Current Score |
| --- | --- | --- | --- | --- |
| 64 | H&S Infrastructure | Director of Finance & Performance | Q&S Committee | 16 |
| 81 | Critical staffing levels – Midwifery: | Executive Director of Nursing | Q&S Committee | 20 |
| 89 | HMP Swansea Nurse staffing levels | Executive Director of Nursing | Q&S Committee | 20 |
| 97 | Industrial Action – In Committee | Executive Medical Director | Performance & Finance Committee | 16 |

3.5 Operational Workforce OD & Digital Risks

Each Service Group and Directorate hold their own risk registers, which outline the operational risks facing them. Any operational risks relating to Workforce OD & Digital services can be escalated to the Risk Scrutiny Panel which may co-opt a member of the Workforce team or seek the views of an Executive Director to consider the risk, controls in place and action to be taken to mitigate the risk, and whether the risk should be considered for inclusion on the Health Board Risk Register.

- FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information.

- RECOMMENDATIONS

Members are asked to:

- NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Workforce OD & Digital Committee.

- CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - The last WODC risk report was received in November 2023. This report reflects risks recorded in the February 2024 Risk Register, received by the Board in March 2024. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) extract |  |