| Meeting Date | 18 April 2024 |  | Agenda Item |  |  | 3.4 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Midwifery Workforce Transformation Action Plan: Progress Update |  |  |  |  |  |
| Report Author | Catherine Harris, Interim Head of Midwifery |  |  |  |  |  |
| Report Sponsor | Gareth Howells, Executive Director of Nursing and Patient Experience |  |  |  |  |  |
| Presented by | Sharron Price, Interim Group Nurse Director Catherine Harris, Interim Head of Midwifery |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of the paper is to provide Workforce & OD Committee with a progress update in relation to the Midwifery Workforce Transformation action plan. |  |  |  |  |  |
| Key Issues | This report includes updates on the actions from the Midwifery Workforce Transformation Plan, developed following an observational and listening review reported to Management Board March 15th 2023. A paper outlining the proposed phased plan to reinstate community intrapartum pathways was presented to Management Board on the 16th August 2023. The plan is to present a gateway paper that sets out the key risks and the process for the assessment of these risks. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: Note: - Note the contents of the report - The plan to recruit into a Clinical Director of Midwifery post - The progress against the recommendations set out in the Midwifery Workforce Transformation Paper |  |  |  |  |  |

Midwifery Workforce Transformation Action Plan: Progress Update

- INTRODUCTION

The purpose of the paper is to provide the Workforce & OD Committee with a progress update in relation to the Midwifery Workforce Transformation action plan, following the paper presented on the 15th November 2023.

- BACKGROUND

On the 15th March 2023, a report was presented to Management Board following a listening and observational review of the midwifery workforce. The report set out the workforce pressures as a result of high unavailability of staff due to recruitment and retention challenges, higher than average maternity leave and sickness absence (risk ID 2788 score 25).

This was further compounded by increased workload and acuity within the obstetric unit linked to the suspension of community intrapartum pathways in order to mitigate staffing constraints.

The review identified 6 key workforce themes and made 36 recommendations for development of the workforce which Management Board approved. A Midwifery Workforce Transformation Board was established to progress the recommendations and monitor the action plan.

On the 3rd May 2023, a paper was presented to Management Board outlining the 2023 Birth Rate Plus® (BR+) gap assessment, and proposal for changes to staffing models and skill mix. A £750K investment was confirmed to meet the BR+ gap.

On August 16th 2023, Management Board received a paper outlining the plan to reinstate home births, and the Neath Port Talbot Birth Centre against agreed indicators to enable safe staffing.

- GOVERNANCE AND RISK ISSUES

  - Midwifery Workforce - Risk Score and Mitigation

The Risk Score for Critical Midwifery Staffing remains at 20 (ID 2788) with community intrapartum pathways remaining suspended to mitigate staffing constraints. There were a number of control measures and actions already in place to mitigate staffing shortfalls with additional actions put in place to support safe staffing. The following continue:

- Continued enhanced bank rate with rolling recruitment advert

- Proactive engagement with agencies to determine agency capacity and block bookings

- Central resourcing team fast tracking on-boarding recruitment

- Open rolling advert for registered midwives

- Twice weekly oversight at 1pm Safe Staffing Huddle, chaired by HOM or DHOM

- Addition of a focused Safety Huddle at 9.30 am attended by Ward Managers, Matrons, Deputy Head of Midwifery, Head of Midwifery, Lead Midwife for Quality and Intrapartum Lead Midwife to highlight safety events, emerging risks, acuity

- An agreement to “over establish” in the coming months to provide further support during this period of transition.

  - Workforce Investments

A phased investment of £750K, was confirmed following the May 2023 Management Board paper outlining the funded establishment gap following the 2023 BR+ review.

    - Clinical Midwifery Director

An interim Head of Midwifery and Deputy Head of Midwifery have been in post since February 2023 to provide immediate stabilisation of the leadership structure whilst options were explored for optimum workforce design.

To strengthen midwifery leadership, and in line with the Royal College of Midwives manifesto to introduce Director of Midwifery posts, the post of an Associate Director of Midwifery will be introduced as part of the Service Group structure to strengthen strategic and operational delivery of maternity services.

This was a key investment that progressed at pace during November 2023, unfortunately no one was appointed to the post and a further review of the post was undertaken, and the position for a Clinical Director of Midwifery will be out for advert in March 2023.  The recruitment into the substantive Head of Midwifery position has be advertised and interviews are planned for 29th February 2024.

  - Vacancy position

The registered and unregistered vacancy position within the obstetric unit is noted in Table 1, and clarifies the number of unregistered vacancies which are currently being recruited into.

The roster should range at 14 midwives during the day and 15 at night and weekends, this has been achieved with the initial £500K investment.  The further £250K will support compliance within the Antenatal clinics.

Table 1.

| Obstetric Unit |  |  |
| --- | --- | --- |
| Band | Title | Vacancy |
| Band 7 | Ward Manager | 0.74 WTE |
| Band 5/6 | Registered Midwife | 0 |
| Band 3 | Maternity Care Assistant | 0 |
| Band 2 | Health Care Assistant | -7.21 WTE |

Table 2 identifies predicted vacancies within community midwifery services. This position is predicated on the implementation of a redesigned community workforce model.

The new model is in the implementation stage following conclusion of an Organisational Change process. This position is based on the paper presented to Management Board in May 2023 and fits into a robust rostering template. The band 2 post have been calculated outside of this as they are not factored into the BR+ report

Table 2.

| Community Midwifery |  |  |
| --- | --- | --- |
| Band | Title | Vacancy |
| Band 7 | Team Manager | 2.36 WTE (New Posts) |
| Band 6 | Registered Midwife | 0 |
| Band 3 | Maternity Care Assistant | 0.56 WTE |
| Band 2 | Health Care Assistant | 2.40 WTE |

Despite a positive trend in reducing the number of vacancies, staffing pressures continue due to the levels of staff unavailability which are due to sickness absence and maternity leave.

Whilst the Service is fully established (excluding antenatal clinics) with Registered Midwives, due to the unavailability

To mitigate this the following actions are progressing:

- Over-recruit to provide cover for parental leave

- Focus on supporting staff and sickness management supporting staff to safely return to work

  - Plan to re-introducing Home Births and Neath Port Talbot Birth Centre

The Service Group provided a plan for re-opening birth pathways on the 16th August 2023 and work is in progress towards this plan. The plan will be to establish a gateway review process that ensures re-opening of the Birth Centre is done safely and robustly and this will be shared with Management Board for assurance.

  - Workforce Transformation Action Plan: Progress Update

The Service Group established a Midwifery Workforce Transformation Board to oversee the actions plan. The group reports into the Service Group Senior Management Team and Quality, Safety and Risk Group.   In 2024 the structure of this meeting changed, with a Maternity Services Improvement and Assurance Group being established with a remit to provide oversight on the Midwifery Workforce Transformation as well as monitor the implementation of a number of improvement plans.  These meeting commenced in January 2024.

There were 36 recommendations within the workforce transformation which were categorised into 6 themes:

- Developing the maternity support workforce

- Maximising productivity through technological solutions

- Staffing at peak acuity

- Strengthening clinical leadership and supporting career progression

- Redesigning the community midwifery staffing model

- Listening to the workforce and nurturing a positive culture

The recommendations translated into 61 individual actions; 7 of these remain as not yet started as they are longer term actions which will need either additional investment or are reliant on external organisations to support.

36 actions have been now been completed, 18 are in progress and being monitored via the Midwifery Workforce Assurance and Performance Board.

Risks: There are currently 0 actions on the improvement plan which are ‘red’

Risks: There are currently 18 actions on the improvement plan which are ‘amber’:

Recommendation: Maximising productivity through technological solutions

Actions:  3 amber in progress.

Recommendation: Developing the maternity support workforce

Actions: 9 amber in progress through the Unregistered Workforce Planning workgroup.

Recommendation: Strengthening Clinical Leadership and supporting career progression

Actions: 4 amber in progress

Recommendation: Listening to the workforce and nurturing a positive culture

Actions:  2 amber in progress through the Engagement/Staff experience and wellbeing sub group.

- FINANCIAL IMPLICATIONS

There are financial implications within this paper, the Service Group are able to confirm that the £750k investment will bring the midwifery funded establishment into compliance with the Birth Rate Plus® 2023 review. With the initial 500K investment within 23/24 supporting the Obstetric and Community teams and the further 250K in 24/25 allowing Antenatal clinics to work towards compliance.

It is noted that once the rosters are set and compliance for BR+ for Bands 3-7, and ensuring adequate band 2 HCSW cover there will be no surplus funding from the £750K investment.

The approval and recruitment of the Clinical Director of Midwifery is not covered within that and will require a further investment at a cost of up to £124k

- RECOMMENDATION

Members are asked to:

NOTE

- Note the contents of the report and the corresponding appendices

- The plan to recruit into a Clinical Director of Midwifery post

- The progress against the recommendations set out in the Midwifery Workforce Transformation Paper

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☐ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| This paper outlines the progress which supports the health board in meeting the objectives of the strategic vision for maternity services in Wales and bring maternity service delivery model back in line with national recommendations. |  |  |  |
| Financial Implications |  |  |  |
| The recruitment of the Clinical Director of Midwifery has a cost of up to £124k. NPTSSG recognises that recruitment to this post is likely to add a cost pressure but this will be partially mitigated by corporate financial investment. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| None anticipated |  |  |  |
| Staffing Implications |  |  |  |
| Previously agreed at Management Board |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Best start in Life |  |  |  |
| Report History |  | Midwifery Workforce Transformation Action Plan: Progress Update 15th November 2023. |  |
|  |  | Appendix 1 |  |