| Meeting Date | 10th April 2025 |  | Agenda Item |  |  | 5.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Workforce and OD Committee |  |  |  |  |  |
| Report Title | Revised action plan and risks associated with the limited assurance internal audit report on Speaking Up Safely |  |  |  |  |  |
| Report Author | Julie Lloyd, Head of Culture, OD & Staff Experience |  |  |  |  |  |
| Report Sponsor | Sarah Jenkins, Interim Director of Workforce & OD |  |  |  |  |  |
| Presented by | Julie Lloyd, Head of Culture, OD & Staff Experience |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide assurance through evidencing delivery of actions set out in the Internal Audit report on Speaking Up Safely agreed by the end of March 2025. This includes a revised action plan to mitigate against risks associated with limited assurance. |  |  |  |  |  |
| Key Issues | - Swansea Bay University Health Board is committed to enabling our people to feel safe and confident to speak up and ensuring that when they do, we listen and act. It is the cornerstone of our People Strategy; People Aim 1 – Engaged motivated and Healthy. - The Speaking Up Safely priority also supports us deliver our Strategic Objective which commits to the Health Board being a great place to work, where staff feel valued and work together towards a common goal. - The January 2025 internal audit report was issued with a ‘limited assurance’ rating. This recognised the need for organisation-wide ownership of this agenda. - This paper aims to provide assurance through detailing the progress made against the Internal Audit Report recommendations and Workforce & OD actions committed to being completed by the end of March 2025. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - BE ASSURED by the progress reported against the Internal Audit Report recommendations and actions committed to be completed by the end of March 2025. - BE ASSURED by the next steps planned aligned to the revised Speaking Up Safely Action Plan for 2025-6. |  |  |  |  |  |

REVISED ACTION PLAN AND RISKS ASSOCIATED WITH THE LIMITED ASSURANCE INTERNAL AUDIT REPORT ON SPEAKING UP SAFELY

- INTRODUCTION

The purpose of this report is to provide assurance through evidencing delivery of actions set out in the Internal Audit report on Speaking Up Safely agreed by the end of March 2025.  This includes a revised action plan to mitigate against risks associated with limited assurance.

- BACKGROUND

Swansea Bay University Health Board is committed to enabling our people to feel safe and confident to speak up and ensuring that when they do, we listen and act. It is the cornerstone of our People Strategy; People Aim 1 – Engaged motivated and Healthy. It also supports us deliver our Strategic Objective, which commits to the Health Board being a great place to work, where staff feel valued and work together towards a common goal.

During February’s Workforce & OD Committee, a report was presented on Speaking Up Safely, including the Internal Audit Report issued in January 2025. The purpose of the audit was to ‘review the implementation of the National Speaking Up Safely Framework and assess its impact in promoting a culture that enables staff to raise concerns’.  The report was issued with a ‘limited assurance’ rating, recognising the need for organisation-wide ownership of this agenda.

It was noted during February’s Committee that whilst Speaking Up Safely sits under the Director of Workforce & OD as the accountable Executive Officer with the Chair as the Non-Executive Sponsor, that it is everyone’s responsibility and stakeholder engagement across the Health Board is therefore essential for successful delivery of the National Framework and its requirements.

In line with this it was agreed that initial awareness raising and engagement of stakeholders on the Internal Audit Report and actions set out the Management Response would need to take place via all key Governance Committees.  Reporting has since taken place, via the Speaking Up Safely Working Group on 21st March 2025, Workforce & OD Delivery Group on 25th March and engagement with Service Groups has also been driven via the HRBP’s following attending the HRBP Huddle on 5th February 2025 and the COO/Service Group Directors Meeting on the 9th April 2025.  Quality & Safety Group have also received this report on 8th April 2025.

  - Delivery of IA Report Actions

Table 1 below details completed actions and those on track actions (due from June 2025 to March 2026) to implement the National Speaking Up Safely Framework and as part of promoting a culture that enables staff to raise concerns.  It is important to note that the progress outlined has been completed in collaboration with stakeholders, particularly those part of the Speaking Up Safely Working Group.

*To note, the management response to 3.2 detailed in the original report has been amended with agreement from Corporate Governance and Internal Audit to:

“Work with Service Groups in collaboration to agree a proposal for the reporting process for Speaking Up Safely on a rotational basis, a minimum of twice yearly.  Reports from Service Groups are to amalgamate the detail of concerns raised (themes, trends, actions taken, lessons learned) and be reported to Workforce & OD Delivery Group and Workforce & OD Committee as part of the overarching Speaking Up Safely Monitoring and Reporting schedule, providing assurance that the national Framework Requirements are being adhered to.”

This is reflected in the table below.

Table 1.

| Action | Status / Progress | Responsible Lead | Timeframe |
| --- | --- | --- | --- |
| IA Action 1.1 Revisit and refresh the action plan to ensure the actions remain appropriate, including consideration to incorporate the recommendations raised by the Guardian Service End of Year Report. The revised action plan will be approved by the Speaking Up Safely Working Group. | COMPLETED See appendix 1 for a copy of the original action plan and the review undertaken, confirming the status of each action. Appendix 2 provides a copy of the revised action plan for 2025/6. Consideration has been given to incorporating the recommendations raised by the Guardian Service and 1 action identified as appropriate for inclusion. A review against each recommendation has taken place with the Guardians and is detailed in appendix 3. | Interim Director of WOD | 31st March 2025 |
| IA Action 1.2 Outputs of the Speaking Up Safely Working / Stakeholder Group are to be monitored and reported quarterly via the Workforce & OD Delivery Group and 6-monthly via the Health Board Workforce & OD Committee. | ON-TRACK Speaking Up Safely Working Group established in November 2024, meeting bi-monthly. Reporting to commence in line with the reporting structure outlined in next steps below. | Interim Director of WOD | July/August 2025 |
| IA Action 1.3 Work with Corporate Governance to develop a risk for the risk register to be monitored by Workforce & OD Committee. | COMPLETED See appendix 4 for a copy of the risk assessment. | Interim Director of WOD | 31st March 2025 |
| IA Action 2.1 Finalise the review and launch of training modules and information on Speaking Up Safely, including the development of the ‘Brilliant Basics’ bitesize learning opportunities. | ON-TRACK Work has commenced in partnership as part of the Speaking Up Safely Working Group to enhance our Raising Concerns SharePoint pages and develop resources as part of ‘Brilliant Basics’, as well as our revised Leadership Development offering. | Interim Director of WOD | 30th June 2025 |
| IA Action 3.1 Development of an integrated report including data from all sources that receive concerns should be finalised to empower the health board to have complete oversight of all concerns, themes and trends. | ON-TRACK Investigations commenced, connecting with other NHS Wales organisations to understand their provision and how they gather concerns raised, as well as a demonstration held with provider of the digital platform, Work in Confidence, on 14th March 2025. | Interim Director of Workforce & OD | 31st March 2026 |
| *IA Action 3.2 Service Groups should amalgamate the detail of concerns raised (themes, trends, actions taken, lessons learned) and report to an appropriate Board-level committee to have an organisation-wide understanding of incidents arising. The reporting should also provide assurance that policy requirements, including timescales etc, are being adhered to. | ON-TRACK The first round of rotational reporting will embed local reporting from Service Groups into the overarching Speaking Up Safely Report and take place a minimum of twice yearly. | Interim Director of Workforce & OD and Service Groups | July/August 2025 |

  - Next Steps

Aligned to the revised Speaking Up Safely Action Plan 2025-6 provided in appendix 1, the next steps will be to focus on completing delivery of the action plan and those actions detailed as on-track in the above table, in line with the timeframes committed to.

The first round of rotational reporting will embed local reporting from Service Groups and progress from the Speaking Up Safely Working Group into the overarching Speaking Up Safely Report and will take place on 29th July 2025 at WOD Delivery Group, then through to WOD Committee on 14th August 2025.

- GOVERNANCE AND RISK ISSUES

- Delivery of Section 6 requirements of the national Speaking Up Safely Framework is reliant on Service Delivery Groups taking action to respond.  Capacity and operational pressures may therefore present a risk in Service Delivery Groups being able to respond and deliver in the agreed timeframes. The agreed reporting process resulting from Internal Audit Recommendation 3.2 will enable these risks to be surfaced, discussed and addressed.

- FINANCIAL IMPLICATIONS

There are no financial implications relating to this report.

- RECOMMENDATION

Members are asked to:

- BE ASSURED by the progress reported against the Internal Audit Report recommendations and actions committed to be completed by the end of March 2025.

- BE ASSURED by the next steps planned aligned to the revised Speaking Up Safely Action Plan for 2025-6.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☐ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Our Speaking Up Safely offerings, including the Guardian Service aims to improve staff experience through helping to create a culture of openness and honesty. The direct correlation between patient experience and staff experience is well documented. The previous Raising Concerns process with no dedicated pathway or infrastructure to support staff created risk to staff, patients and the wider organisation. |  |  |  |
| Financial Implications |  |  |  |
| There are discussions currently taking place around financing the Guardian Service via Charitable funds. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is important to consider the internal policies and the legislation which are linked to the provision of a confidential, safe and effective pathway and process for staff to raise concerns. Internal policies include but are not limited to – -Respect & Resolution -Disciplinary Policy -Procedure for NHS Staff Raising concerns -NHS Wales Speaking Up Safely Framework Public Interest Disclosure Act 1998 If workers bring information about a wrongdoing to the attention of their employers or a relevant organisation, they are protected in certain circumstances under the Public Interest Disclosure Act 1998. This is commonly referred to as 'blowing the whistle'. The law that protects whistle-blowers is for the public interest - so people can speak out if they find malpractice in an organisation. Blowing the whistle is more formally known as 'making a disclosure in the public interest'. Duty of Candour, 2023 The duty of candour is a legal requirement for all NHS organisations in Wales. It requires them to be open and transparent with service users when they experience harm whilst receiving health care. They will be required to: - talk to service users about incidents that have caused harm - apologise and support them through the process of investigating the incident - learn and improve from these incidents - find ways to stop similar incidents from happening again |  |  |  |
| Staffing Implications |  |  |  |
| Delivery of Section 6 requirements of the national speaking up safely requirement is reliant on Service Delivery Groups taking action to respond. Capacity and operational pressures may therefore present a risk in Service Delivery Groups being able to respond and deliver in the agreed timeframes. In turn, this may result in delayed improvements towards a culture that enables staff to raise concerns and a continued limited assurance assessment. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Briefly identify how the paper will have an impact of the “The Well-being of Future Generations (Wales) Act 2015”, 5 ways of working. The paper impacts on the Well-being of Future Generations (Wales) Act 2015 as it will impact on the long-term culture and behaviours of the organisation and its staff now and in the future. It aims to support staff, through working together to improve staff wellbeing and improve the quality of patient care and outcomes through early raising of concerns, intervention and nipping concerns in the bud before they escalate. |  |  |  |
| Report History |  | - Presented to Partnership Forum, 18th March 2019 - Addressing concerns around bullying in ABMU – Freedom to Speak up Service & ACAS Training - Presented to Executive Team, 3rd April 2019 - Enhanced Raising Concerns – Appointment of The Guardian Service Ltd - Presented to Partnership Forum, 3rd June 2019 - #LivingOurValues campaign - Presented to Audit Committee – 15th July 2019 – Raising Concerns Report - Presentation from The Guardian Service Lt, Dr Simon McRory, Founder/Director - 16th July 2019, Special Partnership Forum - Presented to Partnership Forum, 24th September 2019 - #LivingOurValues & Guardian Service Up-date - Presented to Senior Leadership Team, 2nd October 2019 - #LivingOurValues & Guardian Service Up-date - Presented to Local Negotiating Committee, 7th November 2019 – Guardian Service Up-date & #LivingOurValues - Presented to WOD Forum, 14th November 2019 - Guardian Service up-date & #LivingOurValues - Presented to Audit Committee, 21st November 2019, Guardian Service & #ShapingSBUHB - Presented to Senior Leadership Team, 4th December 2019 – Retendering of an independent service for Staff to Raise Work-related Concerns - Presented to IBG, 19th December 2019 - Retendering of an independent service for Staff to Raise Work-related Concerns - Presented to Partnership Forum, 13th March 2020 - #LivingOurValues & The Guardian Service Up-date - Presented to Partnership Forum, 22nd October 2020 - The Guardian Service Ltd. End of Year Report - Presented to SLT, 4th November 2020 – The Guardian Service Ltd. End of Year Report and Decision to Contract - Presented to Audit Committee, 12th November 2020 – The Guardian Service Ltd. End of Year Report - Presented to Full Board, 26th November 2020 - The Guardian Service Ltd. End of Year Report - Presented to Executive Board, 28th April 2021 – The Guardian Service Ltd End of Year Report - Presented to LNC, 18th May 2021 – The Guardian Service Ltd End of Year Report - Presented to Quality & Safety Committee, 25th May 2021 – The Guardian Service Ltd End of Year Report - Presented to WOD Committee, 15th June 2021 - The Guardian Service Ltd End of Year Report - Presented to Executive Team, 22nd September 2021 - The Guardian Service Ltd. Up-date Report – 1st April 2021 to 31st August 2021 - Presented to WOD Committee, 12th October 2021 – A Deep Dive into the Guardian Service Ltd. - Presented to LNC, 18th January 2022 – Speak Up Safely Up-date - Presented to Audit Committee, 19th May 2022 – The Guardian Service End of Year Report, 1st April 2021 to 31st March 2022 - Presented to Workforce & OD Committee, 14th June 2022 - Deep Dive into Speaking Up Safely in SBUHB, 2021-22 - Presented to Workforce and OD Committee, 13th of October 2022 – Bi- Annual Update The Guardian Service, April 2022-August 2022 - Presented to Audit Committee, 17th of November 2022 - Bi- Annual Update The Guardian Service, April 2022-August 2022 - Presented to Workforce Delivery Group 15th of June 2023 - Presented for Audit Committee, 13th July 2023 - Annual Guardian Service Update for Audit Committee, April 2022 to March 2023 - Presented to Board, 11th September 2023 – Quality & Safety Systems Review - Presented to Management Board, 23rd October 2023 – Quality & Safety Systems - Presented to Quality & Safety Committee, 24th October 2023 – Quality & Safety Systems - Presented to WOD Delivery Group, 21st November 2023 - Speaking Up Safely - Presented to WODD Committee, 20th June 2024 - Speaking Up Safely & Guardian Service End of Year Report, 2023-2024 - Presented to Quality & Safety Committee, 9th July 2024 - Speaking Up Safely & Guardian Service End of Year Report, 2023-2024 - Presented to Audit Committee, 11th July 2024 - Speaking Up Safely & Guardian Service End of Year Report, 2023-2024 - Verbal up-date at HRBP Huddle, 5th February 2025 – Speaking Up Safely Internal Audit Report - Presented to WOD Committee, 20th February 2025 - Speaking Up Safely Report, including Internal Audit Report and Guardian Service 6-month Activity Report - Verbal up-date to Speaking Up Safely Working Group, 21st March 2025 – Speaking Up Safely Internal Audit Report - Presented to Quality & Safety Group, 8th April 2025 – Speaking Up Safely Quality & Safety Systems - Verbal up-date at COO/Service Group Directors Meeting, 9th April 2025 – Speaking Up Safely IA Report |  |
| Appendices |  | Appendix 1 – Original Speaking Up Safely Action Plan Review Appendix 2 – Revised SBU Speaking Up Safely Action Plan 2025-6 Appendix 3 – Review of Guardian Service Recommendations for Action Appendix 4 - Speaking Up Safely Risk Assessment, March 2025 |  |