| Meeting Date | 08 August 2023 |  | Agenda Item |  |  | 2.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Management Report |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Interim Director of Corporate Governance |  |  |  |  |  |
| Presented by | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to inform the Workforce & OD Committee of the risks within the Health Board Risk Register (HBRR) assigned to the Committee for scrutiny. |  |  |  |  |  |
| Key Issues | - The HBRR was last received by the Workforce & OD Committee (WODC) in April 2023. - Since then risks have been subject to update by Executive Directors on a monthly basis. The HBRR for June 2023 was received by the Board in July 2023. This paper presents an extract of risks assigned to the WODC from that register. - The number of risks overseen by Workforce & OD Committee is six in open session (an additional sensitive risk has been identified for review within closed session). |  |  |  |  |  |
|  | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Workforce & OD Committee. - CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any. |  |  |  |  |  |

HEALTH BOARD RISK REPORT

- INTRODUCTION

The purpose of this report is to inform the Workforce & OD Committee of the risks within the Health Board Risk Register (HBRR) assigned to the Committee for scrutiny.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular HBRR update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

Risk Register management is supported by a Risk Management Group (RMG) which meets quarterly and is responsible for overseeing the operational management of risk, ensuring local systems and processes are in place and are operating effectively to ensure appropriate reporting and escalation. The Group last met in May 2023.

Additionally, a Risk Scrutiny Panel is responsible for ensuring there is an appropriate and robust risk management system in place and working throughout the organisation. It is responsible for moderating new risks and risks escalated to the Health Board Risk Register (HBRR) and Board Assurance Framework (BAF) and recommending and advising the Management Board on the escalation and de-escalation of risks. The Panel last met in July 2023.

2.2 Risk Appetite

Risk appetite and tolerance provide clarification on the level of risk the Board is prepared to accept.

The health board approved a risk appetite statement in November, setting out a new approach to expressing the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, requiring risks scoring 16 or above to be overseen at committee level. The mechanism for reporting risk is developing to support this for board and committee updates.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

- MANAGEMENT OF HEALTH BOARD RISK REGISTER (HBRR)

3.1 Action to Update the HBRR

The HBRR was last received by the Workforce & OD Committee (WODC) in April 2023. Since then risks have been subject to update by Executive Directors on a monthly basis. The full HBRR for June 2023 was received by the Board in July 2023. This paper is based on an extract from the same HBRR as attached at Appendix 1.

The number of risks overseen by Workforce & OD Committee in open session is now six:

- HBR 3	Workforce Recruitment of Medical & Dental Staff

- HBR 27	Digital Transformation to Deliver Sustainable Services

- HBR 36	Electronic Patient Record (Paper Record Storage)

- HBR 37	Operational & Strategic Decisions are not Data Informed

- HBR 51	Nurse Staffing Levels Act

- HBR 90	GDPR Subject Access Requests

In addition, the following risk is deemed sensitive and will be overseen in closed session:

- HBR 60	Cyber Security

A further two risks are overseen by other Committees, but reported to the Workforce & OD Committee for information:

- HBR 81 	Midwifery: Critical Staffing Levels

- HBR 82 	Closure of Burns Service

The profile of risk scores for seven risks assigned to WODC is as follows:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 |
| --- | --- | --- | --- | --- | --- |
| Number of Risks | 1 | 0 | 3 | 2 | 0 |

3.2 Risks Exceeding Appetite

Section 2.2 above indicated the risk level thresholds associated with the health board risk appetite statement approved in November 2022. There are 4 risks currently meeting or exceeding the Health Board’s appetite thresholds, for which action is required so that they may be reduced to acceptable levels. The tables below highlight recent changes / actions of note since the last meeting of the Committee for those risks that are currently meeting or exceeding the thresholds:

| HBR3: Workforce Recruitment Risk of failure to recruit medical & dental staff |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Workforce and Operational Development | 20 | 20 | 12 |  |
| The actions to address this risk remain as previously reported: Ongoing Actions: Action 1: Medical training initiatives pursued in a number of specialties to ease junior doctor recruitment Action 2: The Medical Workforce Board continues to monitor recruitment and junior doctor’s rotas. Action 3: Continue to recruit internationally. Action 4: Continue to work with head hunters (Target Date: 31/03/2024) Additional Notes/Updates: The costs associated with overseas recruitment have become more visible in the last financial year once central reserves were not able to keep pace with the changes to how the Health Board recruits due to UK market forces. The introduction of the single lead employer has further complicated this element. It will be critical that this is appropriately funded for the next financial year or this will lead to a slowing or cessation of recruitment when the budget becomes overspent. This is still being looked at as so far no additional funds have been allocated to the recruitment of medical staff. |  |  |  |  |

| HBR 51: Non Compliance with Nurse Staffing Levels Act (2016) There is a risk that we might not be able to maintain safe staffing levels due to staff unavailability, vacancies and sickness levels. The potential impact of this maybe avoidable harm, suspension of services, non-compliance with the Nurse Staffing Act. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Executive Director of Nursing | 20 | 16 | 12 |  |
| Action 1 (monthly ongoing): Student Streamlining and Overseas recruitment (Target Date: 31/12/2023 refreshed) Action 2 (expanded): Review of workforce, consider more diverse skill mix, including development of Band 3 and Band 4 roles. Bi-annual re-calculations of inpatient wards have resulted in the addition of Band 3 and 4 roles within the NSA templates. These posts are being recruited into, there is a need for training and supervision for these new posts. (Target Date: 31/07/2023 refreshed) Additional Notes/Updates: The Corporate risk score remains as 20, despite all reasonable steps from NSA Statutory guidance being followed and all controls utilised. All Wales Nurse Staffing Assurance Paper has been presented at Management Board on 3rd May and to Board on 25th May; this is an All Wales agreed template and reporting timetable. June bi-annual acuity in underway, corporate scrutiny panels have been arranged for September. |  |  |  |  |

| HBR 90: Non-compliance with UK-GDPR Article 15 regarding Subject Access Requests (SARs), along with other health records requests for disclosure of personal data The Health Board does not have adequate resources to deal with the sustained increase in volume and complexity of subject access /access to health records requests received from requestors. The ICO are already involved with a number of breaches and complaints in this area and there is the potential for future enforcement action if significant improvements are not made. Misfiling and redaction are major issues for Health Records, IG and Health Professionals. SAR breaches have led to successful compensation claims and media interest. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Digital | 16 | 16 | 12 |  |
| Action 1: Implement key tasks outlined within the action plan within agreed timescales (Target date: April 2024) Additional Notes/Updates: A high level action plan has been completed: On-going challenges with capacity and resources across key departments has required re-prioritisation of actions, resulting in the following three actions deemed to be priority: - The requirement for a dedicated Information Governance Manager responsible for SARs (and other individual rights under UK GDPR) has been identified and outlined in IMTP. Recruitment to post to be considered in new financial year. - Re-establish the task and finish group as a longer term working group with adequate resources to consider the improvements/actions required over a longer term period. Detailed improvement plan to be developed and implemented following recruitment to IG Manager Post. - Development of high-level SAR Policy to support the management of SARs across the Health Board for completion by April. An organisational-wide SAR Policy has been developed to support the compliant and effective management of SARs across the Health Board. Monies have been identified to recruit for a new Band 7 Information Governance Manager to lead on SARs. The vacancy control form has been approved and processed onto TRAC. This will take up to 3-6 months to put into place and all possible mitigations are taking place in the interim period to manage the ongoing risk. |  |  |  |  |

Further detail on the above risks can be found at Appendix 1.

In addition, HBR50 Cyber Risk exceeds the Board’s risk appetite with a score of 20 currently. The full risk entry is reported separately within Closed session to the Committee.

3.3 Other Risks Assigned to this Committee

When the Board’s risks appetite was agreed in November 2022, it was the Board’s aspiration that thresholds could be reduced in the future. In view of this, additional risks assigned to this Committee which are not currently meeting the appetite threshold are presented below for information:

| HBR 27 Digital Transformation Inability to deliver sustainable clinical services due to lack of Digital Transformation. There are insufficient resources to: - Invest in the delivery of the ABMU Digital strategy, - Support the growth in utilisation of existing and new digital solution - Replace existing technology infrastructure and the end of its useful life. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Digital | 16 | 20 | 12 |  |
| Action 1: Continue to develop the 10yr investment plan that has been submitted to WG, which will inform the Health Board IMTP submission. (Target Date: 31/12/2023 refreshed) Action 2: Access the impact of COVID on the resources required to support the increase in devices and software and the change in complexity of the support model required. (Target Date: 31/07/2023 Work has commenced) Additional Notes/Updates: Actions above have been updated to reflect continued review of resource requirement & plans. |  |  |  |  |

| HBR 36 Paper Record Storage Lack of a single electronic record means there is greater reliance on the provision of the paper record. If we fail to provide adequate storage facilities for paper records, then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. There is an increased fire risk where medical records are stored outside of the medical record libraries. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Digital | 16 | 20 | 9 |  |
| Action 1: Re-develop a joint outline Business Case for centralisation of the health records and the scanning model. (Target date: 30/09/2023 refreshed) Action 2: Welsh Government sign off for long term conditions retention of records (Target Date: 29/09/2023) Additional Notes/Updates: Two actions completed: the assessment of the impact of the Records Management code of practice; the development of a revised destruction plan. A potential suitable unit has been discovered with building work requirements currently being scoped for architects in order to acquire costings for a business case to be submitted to Business Case Assurance Group. Destruction of initial 100 boxes commences from June onwards. |  |  |  |  |

| HBR 37 Operational and strategic decisions are not data informed - Business intelligence and information already available is not utilised - Users are unable to access the information they require to make decisions at the right time - Gaps in information collection including patient outcome measures |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Digital | 12 | 20 | 8 |  |
| Action 1: Establishment of data literacy programme educating users on data concepts, skills and tools (Target Date: 31st December 2023 refreshed) Action 2: Establishment of certified training programme for trained users to create their own dashboards – March 2023 (Target Date: 29th December 2023 – date for review following commencement of module) Action 3: Commencement of Digital and Data Module on Manager’s Pathway (Target Date: 30th June 2023) Additional Notes/Updates: Action completed: Natural Language Process capability to allow users access to clinic letter/documents converted into meaningful analytics. An Audit was carried out on the BI Strategy with a result of substantive assurance. At this time it is felt that this audit does not impact the current risk score. First self-serve dashboard relating to admissions has been launched with future dashboards planned. Management pathway module taking place in June. |  |  |  |  |

Further detail on the above risks can be found at Appendix 1.

3.4 For Information – Risks Assigned to Other Committees

There are two  risks which are assigned to other Committees in terms of overseeing actions to mitigate the risks, as outlined in the table below, noted here for information. As noted earlier, the detailed HBRR entries are also included in Appendix 1 for information.

| Ref | Description of Risk Identified (Summarised) | Exec Lead | Committee | Current Score |
| --- | --- | --- | --- | --- |
| 81 (2788) | Critical staffing levels – Midwifery: Unplanned absence resulting from Covid-19 related sickness, shielding and isolation, alongside other current absences, has resulted in critical staffing levels, further reductions in which could result in unsafe service provision, poor patient outcomes and/or experience. In turn, poor service quality or reduction in services could impact on organisational reputation. | Executive Director of Nursing | Q&S Committee | 25 |
| 82 (2554) | Risk of closure of Burns service if Burns Anaesthetic Consultant cover not sustained There is a risk that adequate Burns Consultant Anaesthetist cover will not be sustained, potentially resulting in closure to this regional service, harm to those patients would require access to it when closed and the associated reputational damage. This is caused by: • Significant reduction in Burns anaesthetic consultant numbers due to retirement and long-term sickness • Inability to recruit to substantive burns anaesthetic posts • The reliance on temporary cover by General intensive care consultants to cover while building work is completed in order to co-locate the burns service on General ITU • Reliance on capital funding from Welsh Government to support the co-location of the service | Executive Medical Director | P&F Committee Also Q&S Committee for information | 16 |

3.5 Operational Workforce & OD Risks

Each Service Group and Directorate hold their own risk registers, which outline the operational risks facing them. Any operational risks relating to Workforce & OD can be escalated to the Risk Scrutiny Panel which may co-opt a member of the Workforce & OD team or seek the views of an Executive Director to consider the risk, controls in place and action to be taken to mitigate the risk, and whether the risk should be considered for inclusion on the Health Board Risk Register.

In addition to the above, the Risk & Assurance team will be reviewing workforce risks recorded within operational services shortly for consideration by the Director of Workforce & OD and her team.

- GOVERNANCE AND RISK

This report and appendix present information on each of the risks assigned to the Committee for oversight. Within the report, particular attention is drawn to those risks exceeding the Board’s appetite, together with updates on action being taken to treat them by lead Directors and management.

- FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information.

- RECOMMENDATIONS

Members are asked to:

- NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Workforce & OD Committee.

- CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - The last WODC risk report was received in April 2022. This report reflects risks recorded in the June 2023 Risk Register, received by the Board in July 2023. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) extract |  |