Strategic Risk Register

July 2026

| SRR Ref | Strategic Risk | Lead Director | Risk Score |  |  | Overall Assurance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Previously | Currently | Target | Previously | Currently |
| Objective 1: People of Swansea Bay live healthier, fairer and more prosperous lives |  |  |  |  |  |  |  |
| 1.1 | Population Health Approaches to Address Health Inequity | DOPH | 16 | 16 | 16 | Moderate | Moderate |
| 1.2 | Partnerships & Collaboration | DOPP | 12 | 12 | 8 | Good | Good |
| Objective 2: Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  |  |  |  |  |  |
| 2.4 | Quality, Safety & Patient Outcomes | EDON | 16 | 16 | 12 | Good | Good |
| 2.6 | Perinatal Service | EDON | 16 | 16 | 9 | Good | Good |
| 2.7 | Mental Health | COO | 16 | 16 | 8 | Good | Good |
| 2.8 | Access to Services | COO | - | 16 | 12 | - | Moderate |
| Objective 3: Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation |  |  |  |  |  |  |  |
| 3.2 | Estates | DOF | 20 | 20 | 12 | Moderate | Moderate |
| 3.4 | Digital Transformation | DODIG | 15 | 15 | 10 | Good | Good |
| Objective 4: The health board is a great place to work where all staff feel valued and work together towards a common goal |  |  |  |  |  |  |  |
| 4.1 | Staff Health & Wellbeing and Organisational Performance New | DOWOD | - | 12 | 8 | - | Moderate |
| 4.4 | Culture New | DOWOD | - | 12 | 9 | - | Moderate |
| Objective 5: The health board is a resilient, sustainable and responsible organisation |  |  |  |  |  |  |  |
| 5.1 | Recovery & Sustainability | DOF | 25 | 25 | 15 | Good | Good |
| 5.2 | Workforce (Sustainability) New | DOWOD | - | 20 | 10 | - | Moderate |

Strategic Risk Register

July 2026 Detail

Risks assigned to the

Workforce & OD Committee

| Risk ID Number SRR-4.1 | Risk Label – Staff Health & Wellbeing and Organisational Performance New Risk Description – There is a risk of a negative impact to staff wellbeing due to the psychological and physical impact of the working environment and the challenge in reconciling continued high levels of clinical and non-clinical demand with available resources. This could lead to high levels of sickness absence, reduced staff availability, reduced organisational and individual effectiveness, higher staff turnover and staff burnout. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | The health board is a great place to work where all staff feel valued and work together towards a common goal |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 4 | 4 | 16 |  | Lead Director / Risk Owner | Director of Workforce & OD |
| Current Score | 4 | 3 | 12 |  | Monitoring Committee | Workforce & OD Committee |
| Target Score | 2 | 4 | 8 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 25 | Dec 25 | Feb 26 | Apr 26 | May 26 | July 26 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - | - | - | - | - | 12 |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | People Strategy aligned to organisational priorities |
| 2 | Staff Health & Wellbeing Plan |
| 3 | Managing attendance at work national policy and escalation processes |
| 4 | Workforce performance dashboard (including Sickness absence reporting, turnover, vacancies, agency usage) |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | People Strategy progress reports coordinated by corporate Workforce and monitored through Executive Board. |  |  | Reasonable |
| 2 | Health & Wellbeing Plan developed through Staff Health & Wellbeing Group, approved by and progress with implementation of initiatives reported by the Director of Workforce to Executive Board. |  |  | Reasonable |
| 3 | Adherence to Managing Attendance at Work policy reported by Service Groups through monthly performance meetings with Executive Directors | Policy compliance audits undertaken by corporate Workforce function and reported to Executive Board and Workforce & OD Committee |  | Limited |
| 4 | Trend data included in Integrated Performance Report for review by Executive Board. |  |  | Reasonable |
|  | Current Overall Assurance Rating |  |  | Moderate |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Gaps in reporting on staff who have met the triggers/who are on formal stages of the policy | Reporting solution in place. Data quality being reviewed. | Director of Workforce & OD | 30/09/26 | On track |
| 2 | Variation in management capability impacting staff experience | Targeted leadership development and assurance framework | Director of Workforce & OD | 31/12/26 | On track |

Additional Comments

13/08/2026: Risk added following discussion and approval at Executive Board

| Risk ID Number SRR-4.4 | Risk Label – Culture New Risk Description – There is a risk that we will not deliver on our corporate objectives and priorities due to areas of the Health Board not demonstrating a high performance culture |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | The health board is a great place to work where all staff feel valued and work together towards a common goal |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 4 | 4 | 16 | - | Lead Director / Risk Owner | Director of Workforce & OD |
| Current Score | 4 | 3 | 12 |  | Monitoring Committee | Workforce & OD Committee |
| Target Score | 3 | 3 | 9 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 25 | Dec 25 | Feb 26 | Apr 26 | May 26 | July 26 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - | - | - | - | - | 12 |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | People Strategy |
| 2 | Intentional culture change programme (in development) |
| 3 | Organised for Success Programme |
| 4 | Leadership and management development programmes |
| 5 | Speak Up / Raising Concerns framework |
| 6 | Engagement through partnership forums and staff groups |
| 7 | Staff survey |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | Reporting on delivery against People strategy to Executive Board and WOD Committee. |  | Internal Audit Review: Staff Retention 2025/26 (Reasonable Assurance) | Reasonable |
| 2 | Reporting on Culture Change Programme to Executive Board, WOD Committee and Board. |  |  | Unsatisfactory (Not started) |
| 2 | Staff survey outputs reviewed and reported to Executive Board, WOD Committee and Board. |  |  | Reasonable |
| 3 | Reporting on Organised for Success Programme to Executive Board, WOD Committee and Board |  |  | Reasonable |
| 4 | Monitoring of concerns raised by corporate Workforce. |  | Internal Audit Review: Speaking Up Safely 2024/25 (Limited Assurance) | Reasonable |
| 5 | Partnership forum governance & oversight |  |  | Reasonable |
|  | Current Overall Assurance Rating |  |  | Moderate |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Lack of consistent culture metrics | Develop culture dashboard & KPIs | Director of Workforce & OD | 31/03/27 | On track |
| 2 | Variation in leadership capability | Targeted leadership interventions | Director of Workforce & OD | 31/12/26 | On track |
| 3 | Limited triangulation of intelligence | Integrate survey, ESR & Speak Up data | Director of Workforce & OD | 31/03/27 | On track |

Additional Comments

13/08/2026: Risk added following discussion and approval at Executive Board

| Risk ID Number SRR-4.5 | Risk Label – Workforce (Sustainability) New Risk Description – There is a risk that services within the Health Board will not be sustainable into the future due to the workforce not being the right size and shape with unaffordable and/or unstainable staffing models. There are also skills gaps in our workforce which is impeding our ability to transform and improve services. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | The health board is a resilient, sustainable and responsible organisation |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 5 | 4 | 20 | - | Lead Director / Risk Owner | Director of Workforce & OD |
| Current Score | 5 | 4 | 20 |  | Monitoring Committee | Workforce & OD Committee |
| Target Score | 5 | 2 | 10 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 25 | Dec 25 | Feb 26 | Apr 26 | May 26 | July 26 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - | - | - | - | - | 20 |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |
| 3 | Recruitment of Consultant Medical and Dental Staff Due to national shortages, there is a risk that that the health board will be unable to recruit consultant medical & dental staff into particular hard-to-fill roles which may result in difficulties fulfilling rotas on all sites, and adverse impact upon patient safety, service provision, quality and financial matters. | 16 |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Annual workforce planning process |
| 2 | Establishment control including approval processes for posts and recruitment panels through workforce boards |
| 3 | Use of variable pay monitored through workforce boards |
| 4 | Organised for success programme |
| 5 | Service redesign and new care models |
| 6 | Annual skills gap analysis |
| 7 | Annual Training Plan |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | Development of workforce plans by services, consolidated by corporate workforce and reported to Executive Board. |  |  | Reasonable |
| 2 | Corporate workforce reporting to Executive Board of recruitment activity and application of approval process |  |  | Reasonable |
| 3 | Corporate workforce reporting on bank and agency staffing to Executive Board |  |  | Reasonable |
| 5 | Oversight of service redesign and delivery of change through Delivery Unit |  |  | Limited |
| 6 | Completion of annual skills gap analysis |  |  | Unsatisfactory (not started) |
| 7 | Development of annual training plan |  |  | Limited |
|  | Current Overall Assurance Rating |  |  | Moderate |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Lack of long-term workforce modelling including skills gap analysis | Develop strategic workforce plan | Director of Workforce & OD | 31/10/26 | On track |
| 2 | Reliance on temporary staffing | Reduce agency dependence programme | Director of Workforce & OD, Director of Nursing, Medical Director | 31/03/27 | On track |
| 3 | Mismatch of workforce to demand | Align workforce planning with demand modelling | Director of Planning / Director of Workforce & OD | 31/12/26 | On track |
| 4 | Limited link to outcomes | Develop metrics linking staffing to quality outcomes | Director of Workforce & OD | 31/03/27 | On track |

Additional Comments

13/08/2026: Risk added following discussion and approval at Executive Board

Key / Convention / Glossary

| Strength of Control |  | Level of Overall Assurance |
| --- | --- | --- |
| Substantial – The identified control(s) provide a strong mechanism for controlling the risk. Few matters require attention, which are advisory or compliance in nature. |  | Significant – Key governance, risk management and control processes in place provide significant assurance that the risk(s) is/are being managed effectively. Evidence demonstrates that systems and processes are being consistently applied and implemented. Outcomes are consistently achieved across all relevant areas. |
| Reasonable – The identified control(s) provide a reasonable mechanism for controlling the risk, albeit there is scope to strengthen this further. Some matters require management attention in control design or compliance. |  | Good - Key governance, risk management and control processes in place provide a good level of assurance that the risk(s) is/are being managed effectively. Evidence is available to demonstrate that systems and processes are generally being applied and implemented, but no across all relevant areas. Outcomes are generally achieved, but with inconsistences in some areas. |
| Limited – The identified control(s) provide only limited/partial mechanisms for controlling the risk. There are notable weaknesses which require management attention. |  | Moderate – Key governance, risk management and control processes in place provide moderate assurance that the risk(s) is/are being managed effectively. Evidence is available to demonstrate that systems and processes are being applied, but is insufficient to demonstrate implementation across all relevant areas. There is some evidence that outcomes are being achieved, but this is inconsistent and/or there are risks to current performance. |
| Unsatisfactory – The identified control(s) is/are not effective in providing a mechanism for controlling the risk. Action is required to address the whole control framework in this area. |  | Weak – Key governance, risk management and control processes in place provide only weak assurance that the risk(s) is/are being managed effectively. There is only limited evidence available that systems and processes are being applied or implemented. |

Lines of Assurance

First - This is the internal control environment put in place by Managers. It will typically include reports which detail their plans, performance monitoring data, and the results of local checks and reviews of controls within departments performing relevant day-to-day operational activities. Examples would include: - Results of compliance reviews undertaken within Departments/Functions, and reported to senior management - Progress and/or performance reports received by SDG Boards / Committee Sub-Groups

Second – This level of assurance is often referred to as organisational oversight. It is typically provided by Health Board corporate departments and functions which do not directly manage or deliver specific services, but which oversee and report on how controls are operating, thus providing a greater separation from day-to-day management. Typically, this level of assurance is typically provided to the Board or one of its committees (which allows Independent Members to bring an additional level of challenge and scrutiny), as well as to senior management groups (e.g., Management Board). Examples would include: - Reports on the results of Infection Control Audits undertaken by the IP&C Team - Reports on Fire Safety Audits - Progress and/or performance reports received by the Board or one of its committees

Third – This is independent assurance, which typically comes from outside the organisation. Examples would include reports received from: - NWSSP Audit & Assurance - Audit Wales - Healthcare Inspectorate Wales - Llais - Royal colleges

| Glossary of Register Fields & Their Use |  |
| --- | --- |
| Table / Field | Considerations for completion |
| Key Controls | What key controls/systems/processes/governance mechanisms do we already have in place to manage this risk? |
| Assurance on Control | What information do we have about the adequacy, effectiveness and application of each of our controls, where is it coming from, and what is it telling us? |
| Current Overall Assurance Rating | The Lead Director and/or nominated representative should state the overall level of assurance that can be taken and given regarding the effective management of this risk, having considered all of the information available regarding the adequacy, effectiveness and application of each of the controls in place, and any gaps identified. A convention is provided. |
| Gaps in Control and/or Assurance | Do we require further assurance that the key controls / systems / processes / governance mechanisms we have in place are working effectively? What more do we need to do to control this risk, that we are not already doing? |
| Actions to Address Gaps in Control and/or Assurance | What are we going to do, by when, to further manage and mitigate this risk? |