## Slide 1
Personal Appraisal Development Review Improvement Plan |  |  | Date Agreed: TBC Programme Lead: Donna Hole, Sade Bewsher - Griffiths |  |  |  | 
1. Problem Statement |  | 2. Scope |  |  |  |  | 
Background: PADR compliance across SBUHB is 73.73% (Dec 2025), below the Welsh Government Tier 1 target of 85%. Compliance varies widely from 64.64% in Morriston to 83.82% in NPTS, and from 10.53% in DICE to 93.10% in the Medical Director’s Directorate. Although improving PADR completion has been a focus for over a decade, progress has been inconsistent. Key contributing issues include inaccurate or missing ESR line management structures, managers with limited time and capacity, the administrative effort needed to complete and record PADRs, and staff who have not received a PADR for several years. Problem: Inconsistent PADR processes and limited managerial capacity continue to create gaps in compliance. The time and administrative effort needed to complete PADR paperwork and record outcomes in ESR reduce engagement and lead to delays or missed actions. Inaccurate or incomplete hierarchical data often due to Staff Changes Forms not being completed correctly result in outdated ESR records, misaligned reporting lines, and PADRs not being distributed or recorded properly. As a result, current PADR compliance figures are unreliable, and persistent variation continues to hinder progress toward the 85% target. Impact: Low and inconsistent PADR compliance, combined with unreliable recording, reduces confidence in reported data and limits the organisation’s ability to understand workforce development needs, identify talent, and plan staff support. Missed or inconsistent PADRs weaken staff engagement, reduce visibility of performance and development conversations, and limit organisational assurance. These issues increase the risk of not meeting Welsh Government and regulatory expectations. |  | In Scope: All A4C staff groups |  | Out of Scope: Medical & Dental Volunteers Temporary agency staffing |  |  | 
 |  | 3. Programme Goal(s) |  |  |  |  | 
 |  | 1.Strengthen PADR Data Quality - Ensure ESR data is correct and up to date by confirming records, auditing hierarchical structures, and aligning Identified staff to the correct line managers. 2. Modernise and Enhance PADR Resources, Paperwork, and Infrastructure -Refresh and modernise the PADR SharePoint site to create a clear, accessible, and user centred PADR Hub. Review and update all PADR paperwork, templates, and guidance, and expand virtual training resources to strengthen manager capability and reduce administrative burden. 3. Improve Oversight of PADR Compliance Risks - Identify underperforming areas and staff without recent PADRs to prioritise support, improve oversight, and address persistent compliance gaps. 4. Evaluate targeted interventions in priority areas and identify those approaches suitable for wider implementation across the organisation.- Assess the impact of targeted interventions in underperforming areas, identifying what has worked and where further refinement is needed. Scale successful approaches across the organisation to support consistent delivery, improved PADR quality, and progress toward achieving the Welsh Government 85% Tier 1 target. |  |  |  |  | 
 |  | 4. Key Exit Criteria (what will success look like) |  |  |  |  | 
 |  | 1.ESR Data and Structures Accurate and Complete - All staff identified have a confirmed and correct line manager in ESR, and hierarchical structures fully match the agreed organisational structure. 2.Clear Understanding of PADR Compliance Risks – Underperforming areas are identified. Staff without a recent PADR are flagged for priority completion. 3.Modern, User Focused PADR Resource Hub Is Live - The refreshed PADR SharePoint site is launched and actively used, offering updated, easy to navigate tools, guidance, and virtual learning resources. Updated PADR paperwork and templates are in place, and user feedback confirms improved usability and reduced administrative burden. 4.Targeted Interventions Show Demonstrable Improvement - The three underperforming areas show clear and measurable improvement in PADR compliance. Learning from targeted interventions is captured, evaluated, and informs next phase planning. Successful approaches are ready for rollout and adoption across the wider organisation. |  |  |  |  | 
5. Short term objectives 2026/27 | 6. Medium term objectives 2027/28 | 7. Key Programme Milestones |  |  |  |  | 
1.Review ESR Data Identify Staff Without Recent PADRs Generate a list of staff who have not received a PADR. Share findings with relevant directorate leads and managers, and request completion or scheduling of overdue PADRs, and update hierarchical structure where anomalies are identified. 2. Complete Baseline Review Using updated and corrected ESR data, complete a refreshed baseline assessment of PADR compliance across SBUHB, reporting performance against the Welsh Government 85% Tier 1 target. 3. Strengthen Manager Capability Through PADR Resource, Paperwork, and Platform Refresh Refresh and modernise the PADR SharePoint site to create a more accessible and user centred PADR Hub. Review and update all PADR paperwork, templates, and guidance to streamline processes, reduce administrative burden, and ensure consistency of use across SBUHB. Expand and enhance virtual learning resources including videos, quick guides, and step by step instructions to strengthen manager capability and support effective PADR completion and recording. | 1. Highlight and Prioritise Non-Compliant Areas Work with HR Business Partners to identify and prioritise three underperforming service areas with the lowest PADR compliance. Provide focused, structured improvement support to these areas, informed by baseline and ESR data review. 2. Evaluate Impact of Targeted Interventions Assess the effectiveness of PADR improvement activities within the three targeted areas. Evaluate what has worked well, what needs adjustment, and identify opportunities to scale successful approaches across the wider organisation. | Milestones |  | Lead | Lead | By When | Status
 |  | Complete ESR Data Review & Validation –Review and verify accuracy of data, including line manager assignments. Identify and document gaps, anomalies, including staff with multiple year lapsed PADRs and validate lists with directorate leads and service group managers. |  |  | Sade/ ESR Team/Directorate Leads/HR BP’s | December 2026 | In progress
 |  | Identify and Prioritise Underperforming Areas – Working with HR BPs and Directorate Leads, highlight underperforming areas and target for prioritisation and early engagement. |  | EO | Sade/Directorate Leads/HR BP’s | April 2027 | In progress
 |  | Refresh and Relaunch the PADR SharePoint Hub - Modernise the PADR SharePoint site to create a user centred, easy to navigate PADR Hub. Launch updated PADR paperwork, templates, guidance, and bitesize training resources to strengthen manager confidence and reduce administrative burden. |  | EO | Sade | March 2027 | In Progress
 |  | Evaluate Impact of Targeted Interventions - Assess the effectiveness of targeted PADR improvement interventions within the three priority areas. Identify changes in compliance, what worked well, areas requiring refinement, and opportunities to scale successful approaches across the wider organisation. |  |  | Sade & Directorate Leads/HR BP’s | September 2027 | Planned
8. Key Risks | 9. Driver metrics | 10. Impact: planned benefits relating to Health Board Strategic Objectives |  |  |  |  | 
1.Impact of Organisational Change - Ongoing O4S structural changes may delay or disrupt the auditing and correction of ESR hierarchical structures. Misalignment between evolving organisational structures and ESR updates could impact PADR allocation, compliance reporting, and the ability to deliver early programme milestones 2. Service Pressures Limiting Capacity to Complete PADRs - High operational pressures, staffing shortages, and competing priorities may limit managers' capacity to complete PADRs, even with improved systems and resources. This may slow progress in low compliance areas and affect the reliability of compliance data. 3. Engagement Challenges in Underperforming Areas - Some of the underperforming service groups or directorates may be difficult to engage due to workload pressure, cultural barriers, or limited managerial capacity. This may impact the effectiveness of targeted interventions and reduce opportunities to scale successful approaches across SBUHB. 4. Data Quality Regression After Initial Cleanup - Without clear ownership and ongoing monitoring, ESR data quality may deteriorate again after initial corrections, affecting sustainability and long-term reliability of PADR reporting. 5. Variability in Manager Capability, Prioritisation, and Cultural Factors Despite improved resources and updated processes, some managers may still lack the capability, confidence, or capacity to deliver and record PADRs effectively. Wider cultural perceptions of PADRs as low priority or administrative tasks may further reduce prioritisation, limiting the impact of improvement efforts in low compliance areas. | 1.Percentage of staff who have a recorded PADR in the last 12 months. | Increased Compliance with Statutory & Mandatory Requirements - Consistent Compliance above 85% |  |  |  |  | 
 |  | Strategic aim 1 Engaged Motivated & Healthy - Improved staff experience and reinforce a positive organisational culture that values development and wellbeing. |  |  |  |  | 
 |  | Strategic aim 2 Attract & Recruit - Culture of continuous improvement and Improved performance management supporting retention and progression. |  |  |  |  | 
 |  | Strategic aim 5 Excellent Learning & Education - Stronger connection between PADR outcomes, training, development, and career development |  |  |  |  | 
 |  | Strategic aim 6 Leaders that Live Our Values - Strengthened leadership behaviours aligned to organisational values providing greater consistency and capability in performance and development management |  |  |  |  | 
 |  | Through accurate ESR structures, consistent PADR practice, improved digital resources and strengthened accountability, the programme enhances our ability to deliver safe, effective, timely and people centred services in line with the One Bay Way ethos and the core capabilities required to achieve our long term organisational ambition. |  |  |  |  | 
Notes: Project Charter: Service Ready
Date Agreed:
Start Date:
End Date:
True North Strategic Themes
Population and System
Patient Experience
Quality Outcomes and Safety
Sustainable Services
Our People
1. Problem Statement
2. Scope
Background:
Problem:
Impact:
In Scope
Out of Scope
3. Project Goal
4. Exit Criteria
5. Sponsor and Project Team
6.Governance Structure
7.Project Roadmap and Timescales
Executive Sponsor:
SRO:
Process Owner(s):
CI Support:
Subject Matter Experts:
Patient Group:
Responsible: to directly manage and deliver the project
Action
Lead
By When
Status
Accountable: to oversee the project and ensure delivery of the stated objectives and outcomes
Consulted: to be engaged in the development and delivery of the project. To ensure engagement with the wider organisation
Informed: to be assured about progress towards the delivery of the project
8. Critical Success Factors and Key Risks
9. Project Targets and KPIs
10. Impact: planned benefits relating to True North strategic priorities
Population and System:
Our People:
Patient Experience:
Quality Outcomes and Safety:
Sustainable Services:

## Slide 2
A3 – Plan on a Page |  | Owner: | 
Step 1: Problem Statement PADR compliance across SBUHB is 73.73% (Dec 2025), below the Welsh Government Tier 1 target of 85%. Compliance varies significantly across service groups and directorates, with issues rooted in: Inconsistent PADR completion and recording practices. Inaccurate or incomplete ESR hierarchical structures. Managerial capacity challenges. These issues result in staff being incorrectly assigned or not assigned at all to line managers, preventing PADRs from being initiated or recorded effectively. This limits the organisation’s ability to maintain clear oversight of workforce development needs, talent pipelines and the quality and consistency of performance and development conversations. | Step 3 Vision & Goals Vision: A clear organisational vision for consistent PADR practice, supported by accurate ESR data and aligned managerial accountability. Goals: Accurate ESR data structures, with identified staff assigned to the correct manager. Clear visibility of compliance gaps, risks, and priority areas at a glance. Demonstrable improvements in the three underperforming areas. A revitalised, digitally enabled PADR Hub, offering modern tools, guidance and virtual training. PADR compliance trending above 85%, contributing to improved staff engagement and organisational assurance | Step 5: Refined Problem Statement PADR compliance across SBUHB remains below the Welsh Government Tier 1 target, with variation across teams and service areas. Contributing factors include inaccurate ESR data, inconsistent PADR processes, limited manager capacity, and under‑developed digital support. Inconsistent or incorrect line manager assignments can delay or prevent PADRs from being initiated or recorded, while unclear expectations contribute to overdue reviews. Limited access to a modern, easy‑to‑use PADR hub means managers do not always have timely access to clear guidance and tools. Collectively, these factors reduce organisational visibility of workforce development needs and PADR compliance risks, making it difficult to sustain a consistent, high‑quality PADR culture. | Step 7: Action Plan Achieve accurate ESR data structures: line manager assignments and validate organisational hierarchies. Improve visibility of compliance gaps: strengthen reporting so leaders can clearly see compliance levels, risks, overdue PADRs and priority areas. Improve performance in three underperforming areas: Provide targeted operational and managerial support to drive measurable improvement. Ensure identified staff without a current PADR are prioritised, with overdue reviews scheduled and completed through strengthened leadership accountability. Refresh, Revitalise and Digitalise the PADR Hub: Launch a modern, easy‑to‑use platform with updated tools, clear guidance, templates and high‑quality virtual training. Drive Compliance Above 85%: Monitor monthly trends and reinforce expectations to support improved engagement and organisational assurance.
Step 2 Current State Variation in compliance: 10.53% - 93.10% across service groups and directorates. ESR records contain inaccurate line management and hierarchical structures. PADR recording is inconsistent, with a number of staff having PADRs that are several years out of date or not recorded. Limited insight into low-performing areas and root causes. Lack of capacity to complete reviews Limited digital supported resources | Step 4: Top Contributor & Causes ESR Data: Incorrect or outdated line manager assignments; unvalidated hierarchical structures; incomplete records. Processes: Variation in PADR completion processes; inconsistent understanding of required recording steps. People / Capacity: Limited capacity for managers to complete quality PADRs; lack of accountability in persistent low-compliance areas. Systems / Resources: Dated PADR guidance tools; lack of central hub; limited user-friendly digital pathways | Step 6: Opportunities Improve ESR Accuracy: Clean and validate ESR data where incorrect hierarchical structures are highlighted. Support three underperforming compliance areas. Offer targeted help to areas with the greatest gaps to lift overall compliance. Enhance Digital Resources: Develop a modern PADR hub with accessible templates, guidance and on‑demand learning. Simplify PADR Processes: Create clearer steps and consistent expectations for reviewer and reviewee to make PADRs easier to complete. Increase Workforce Insight: Use better PADR data to understand development needs and improve workforce planning. | 
Step 9: Insights |  |  |