## HEIW Targeted Visit MAY 2026
Obstetrics & Gynaecology HEIW Action Plan May 2026
Date | Action No | Requirement OR Recommendations | Narrative of Action | Actions | Evidence | Current Status | Target Risk | Target Date | Action Lead
May 2026 | 1 | Requirements | The Health Board must ensure residents are not delivering specialist gynaecology or antenatal clinics without direct supervision. ​ | The department acknowledges that there have been gaps in consultant cover of specialist antenatal clinics due to Retirement/sickness/parental leave. Consultants now job planned to cover Fetal Medicine, Haematology/Medical clinic and Mental Health/ Substance Misuse clinics |  |  |  | COMPLETE | Madhu Dey & Abigail Morris
|  |  |  | A new obstetrician will be joining the department in August 2026 who will be job planned to undertake Antenatal Clinics once fully onboarded. |  |  |  | August 2026 | Madhu Dey & Abigail Morris
|  |  |  | Specialist gynaecology clinics are cancelled when the consultant is on leave or run by SAS grade doctors with specialist experience. RDiT (Resident Doctor in Training) are not scheduled to run these gynaecology clinics. |  |  |  | COMPLETE | Nagindra Das & Najiya Ali
| 2 | Requirements | The Health Board must ensure emergency gynaecology clinics are led by consultants or registrar grade equivalent doctors, with less experienced residents present for support and training purposes | Gynaecology consultant and Experienced SAS Doctor job planned to cover all Emergency Gynae Clinics |  |  |  | COMPLETE | Madhu Dey & Abigail Morris
| 3 | Requirements | The Health Board must maintain a record to evidence that requirements 1 and 2 are being met and sustained. | Emergency Gynae Specialist Nurses and the Gynaecology Clinical Lead to undertake an audit of emergency gynaecology staffing following the review. |  |  |  | Sept 2026 | Nagindra Das
|  |  |  | Undertake a review of antenatal clinics following implementation of consultant-led clinics. |  |  |  | Sept 2026 | Najiya Ali
|  |  |  | Undertake a workforce model review and develop sustainable job plans with clinical and HR colleagues from September onwards. Meetings planned from week commencing 29th of June 2026 to map service redesign. |  |  |  | Sept 2026 | Madhu Dey & Abigail Morris
| 4 | Recommendations | The Health Board should take steps to ensure that direct consultant support is available for Speciality Training (ST) residents’ year 4 and below, during general gynaecology and antenatal clinics. | Cover clinic gaps with locum consultants. Escalation Process in place for escalating concerns of clinics coverage |  |  |  | COMPLETE | Madhu Dey & Abigail Morris
|  |  |  | A new obstetrician will be joining the department in August 2026 who will be job planned to undertake Antenatal Clinics once fully onboarded. |  |  |  | August 2026 | Madhu Dey & Abigail Morris
| 5 | Recommendations | The Directorate should take further steps to proactively identify residents’ learning needs at the beginning of their placements to ensure individual training requirements are deliverable, with consideration for potential staffing challenges, trainers’ clinical duties and Less Than Full Time (LTFT) working pattens. | College Tutor will contact each RDiT prior to Induction to determine their learning needs/aspirations and ensure they are paired with the most suitable ES. |  |  |  | PLANNED FOR AUGUST ROTATION | Manju Nair & Louise Emma Shaw
|  |  |  | Individualised rota planning will be undertaken at the beginning of the rotation between the RDiT, the College Tutor and the rota manager, with a specific Job plan written for LTFT RDiTs. |  |  |  | PLANNED FOR AUGUST ROTATION | Manju Nair & Louise Emma Shaw
|  |  |  | The College Tutor will continue to conduct 2-4 weekly RDiT Forum meetings with “Training needs/requirements” being routinely added to the agenda. |  |  |  | PLANNED FOR AUGUST ROTATION | Manju Nair & Louise Emma Shaw
|  |  |  | Regular Rota Meetings with the Trainee Rep/ Rota manager / College Tutor |  |  |  | NORMAL PROCESS - MEETING ALREADY IN PLACE | Manju Nair & Louise Emma Shaw
| 6 | Recommendations | Educational Development Time should be consistently available to all resident grades in accordance with appropriate tariffs and guidelines. | The provision of EDT is built into the on call rota for Registrar grade RDiT at the start of the rotation to ensure the minimum requirement is received. We can confirm that all RDiT have received the minimum requirement with many receiving additional EDT sessions where there is capacity on the rota. |  |  |  | COMPLETE | Nagindra Das & Najiya Ali & Charity Knight
|  |  |  | Audit undertaken and one incident identified where a RDiT was required to cover Labour ward due to staff sickness. EDT was repaid. |  |  |  | COMPLETE
| 7 | Recommendations | A suitable individual should be identified, supported, and appropriately job planned to undertake the role of College Tutor, to ensure the department’s positive training environment is sustained. | Service has successfully appointed two College Tutor who will work together (job share) to undertake this role. |  |  |  | COMPLETE | Madhu Dey & Abigail Morris
|  |  |  | Job plan scheduled in July |  |  |  | 2026-07-01 | Madhu Dey & Abigail Morris
HEIW TO REVISIT IN 6 MONTHS (OCTOBER 2026)