| Meeting Date | 18 December 2024 |  | Agenda Item |  |  | 4.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Quarterly Maternity Services Report |  |  |  |  |  |
| Report Author | Liz Wonnacott, Head of Service – Medical Director Kathryn Greaves, Clinical Director for Midwifery Dr Raj Krishnan, Deputy Executive Medical Director |  |  |  |  |  |
| Report Sponsor | Richard Evans, Executive Medical Director |  |  |  |  |  |
| Presented by | Ceri Gimblett, Service Group Director, Singleton/Neath Port Talbot |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of the report is to set out the progress discussed as part of the gold command arrangements established for scrutiny and assurance of improvement within maternity and neonatal services. |  |  |  |  |  |
| Key Issues | - In December 2023, the health board’s maternity and neonatal services were placed by Welsh Government into enhanced monitoring; - The escalation status followed an unannounced inspection by Healthcare Inspectorate Wales (HIW) in September 2023 during which seven areas of immediate action were identified; - An action plan was shared with HIW, with a follow-up unannounced visit in April 2024 to review progress; - Alongside this are other external reports and inspections which require action, as well as open incidents to be closed; - To scrutinise and seek assurance that the work required is being undertaken, a gold command structure has been established; - The report sets out the latest reported position against all areas of focus. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - ACKNOWLEDGE the work to close additional actions raised during enhanced monitoring meetings; - BE ASSURED progress against the HIW action plan is on track; - BE ASSURED the actions to address the Health Education and Improvement Wales (HEIW) maternity and neonatal specific actions are in progress; - BE ASSURED the group has included within its remit the need to ‘horizon scan’ to look ahead to potential visits and/or reports which may require action. |  |  |  |  |  |

QUARTERLY MATERNITY SERVICES REPORT

- INTRODUCTION

The purpose of the report is to set out the progress discussed as part of the gold command arrangements established for scrutiny and assurance of improvement within maternity and neonatal services.

- BACKGROUND

In December 2023, the health board’s maternity and neonatal services were placed into enhanced monitoring by Welsh Government. This was because of concerns as to the quality and safety of the care provided raised by members of the Senedd and families who have accessed the services.

The escalation status followed an unannounced inspection by Healthcare Inspectorate Wales (HIW) in September 2023 during which seven areas of immediate action were identified. In addition, the formal report for the visit set out a number of recommendations for improvement, and an action plan was shared with HIW. HIW undertook a follow-up unannounced visit in undertaken in April 2024 to review progress and while some of work had been completed, there were still improvements required.

Alongside this are two Health Education and Improvement Wales (HEIW) targeted inspections of obstetrics and gynaecology in February and July 2024 as part of HEIW’s quality framework to identify areas working well or in need of improvement, as well as national reports which identify areas of improvement for maternity and neonatal services across the UK.

To scrutinise and seek assurance that the work required is being undertaken, a gold command structure has been established, led by the Deputy Medical Director as the senior responsible officer, supported by the Chief Operating Officer and Interim Director of Nursing and Patient Experience. Meetings are attended by members of the Singleton/Neath Port Talbot Service Group’s senior team under which sit maternity and neonatal services.

- GOVERNANCE AND RISK ISSUES

The main areas of focus for the group are enhanced monitoring, inspection action plans, open incidents, national reports and horizon scanning. Progress includes:

- Enhanced Monitoring

Senior members of the service group along with key members of the executive team meet with Welsh Government on a monthly basis to share progress to achieve de-escalation. During these meetings, actions additional to the criteria already set by Welsh Government can be allocated and these are reviewed within the gold command meetings to ensure completion. There is one outstanding action:

- Maternity dashboard – meetings are taking place between digital and maternity colleagues to commence populating the dashboard using the maternity e-reporting system BadgerNet. This system currently provides 250 datasets so discussions are ongoing as to which would be most relevant to include in the dashboard for meaningful reporting and to agree timescales to finalise this element of dashboard. Once this is in place, work can to progress to ESR (electronic staff record) for training data. The training data continues to be collated manually to monitor progress.

The health board was asked at the October 2024 enhanced monitoring meeting to provide an updated risk register at its next meeting. This was delivered in November 2024 and a discussion undertaken as to reducing the risk scores based on the progress which has been made. This is being taking forward as part of the current risk register cycle and the gold command will consider the revised risks when it next meets.

Focus has now turned to de-escalation and the framework which sets out the criteria has started to be populated with evidence. This will be shared at the next gold meeting.

- Inspection Action Plans

- HIW Inspections

As part of the work to address the recommendations made by HIW, the 2019 HIW improvement plan and 2019 Birth Centre Improvement Plan were revisited, and both have been closed in full.

In relation to the improvement plans for 2023 and 2024, the following progress has been made:

| Report | Actions |  |  |  |
| --- | --- | --- | --- | --- |
|  | Total | Open | Due in Dec. 2024 | Overdue |
| 2023 Singleton Hospital Immediate Improvement Plan | 41 | 0 | 0 | 0 |
| 2023 Singleton Hospital General Improvement Plan | 118 | 1 | 0 | 0 |

| Report | Actions |  |  |  |
| --- | --- | --- | --- | --- |
|  | Total | Open | Due in Dec. 2024 | Overdue |
| 2024 Singleton Hospital Immediate Improvement Plan | 6 | 0 | 0 | 0 |
| 2024 Singleton Hospital General Improvement Plan | 37 | 2 | 1 | 0 |

Of the outstanding, for the 2024 general improvement plan the following are expected to be closed in December 2024:

- The health board should review and improve feedback mechanisms for staff to feedback on leadership team – a Retention, Engagement and Wellbeing Plan has been developed and implemented, including Café Conversations. To close this action completely, a further piece of work in December 2024 will share with the wider team themes identified and the action taken to improve;

Work is on course for all improvement plans to be closed by the December 2024 deadline, with the exception of two actions:

- 95% compliance with Breast Feeding Initiative (BFI) training – staff have been rostered to undertake the training and this will be closed in January 2025. The BFI’s target of 80% has already been achieved (2023 General Improvement Plan);

- Recruitment of a women’s experience midwife - to be closed by April 2025. Funding has been identified and recruitment is anticipated to start before the end of 2024, with the successful applicant likely take up post in 2025 (2024 General Improvement Plan).

A key recommendation by HIW and enhanced monitoring was to improve staff availability. Although there was an improvement in sickness absence with a decrease from 11.99% to 6.5% between September 2023 to August 2024 in the Registered Midwifery workforce absence rates have increased during the months of September and October 2024 to 9.21%. The maternity management team continues to work through the planned improvements to effectively manage sickness absence across the service. A progress report will be shared with the Workforce and OD Committee early in 2025. In addition to this, a Maternity and Neonatal Leadership Development proposal is due to be approved at the gold command meeting on 16th December 2024.

- Health Education and Improvement Wales (HEIW)

Following two visits earlier in 2024, an action plan is place, the majority of which has already been delivered. There is one outstanding area relevant to obstetrics, which is job planning for consultants and the following progress has been made:

|  | Number of Consultants | Signed off | With Consultant to Sign Off | Booked |
| --- | --- | --- | --- | --- |
|  | 18 | 4 | 10 | 4 |

The timescales for completion are currently being worked through as they are dependent on when the meetings take place and the consultants subsequently sign-off their job plans.

Since the two visits, a new cohort of trainees have rotated to the service and no concerns have been raised, with a visit taking place by the Deputy Medical Director and Associate Medical Director for Children and Young People to seek assurance. Some of work to improve the experience of trainees has included:

- Providing feedback to resident doctors based on ‘You Say, We did’;

- Multi-disciplinary team lead appointed;

- Associate Medical Director for Children and Young People attending multi-disciplinary team meetings;

- Team lunches and time to come together to talk.

- Open Incidents

The HIW action to continue the work to reduce the backlog of open Datix incidents in a timely manner and monitor progress has been closed on the 2024 general improvement plan as the work to reduce the backlog is ongoing.

The service is now in a position where it is closing more incidents each month than are opened. For example, in November 2024, 127 incidents were reported, and 162 closed. This demonstrates the backlog is reducing.

|  | Maternity |  | Neonatal |  |
| --- | --- | --- | --- | --- |
|  | Open | Overdue | Open | Overdue |
| Incidents | 152 | 98 | 21 | 8 |
| Duty of Candour | 10 |  | 0 |  |
| Concerns | 12 | 11 | 0 | 0 |
| Redress | 38 |  | 3 |  |
| Claims | 57 |  | 5 |  |

Sprint sessions are taking place to close incidents as soon as possible where no harm has occurred, while the more serious are investigated by the midwifery team. Of those incidents which are overdue, the majority are from August 2024 onwards, with the few prior to this complex and some subject to legal proceedings.

The clinical leads for maternity and neonatal continue to prioritise the responses to concerns, redress and claims to sign-off the responses, but the majority of the ones open are complex and part of legal proceedings, with 22 of the 38 redress claims originating from incidents.

Two main themes have been identified from the incidents and/or concerns being raised:

- Delayed induction of labour – work to address this is taking place on a national level as it is a result of changes to the NICE (National Institute for Clinical Excellence) guidance;

- Communication – work is being undertaken to remind staff of the importance of providing consistent information across antenatal clinics and ward rounds as women often see different staff members over the course of their care.

- National Reports

- MBRRACE-UK (Mothers and Babies: Reducing Risk through Audits and Confidential Enquiries across the UK)

The ‘State of the Nation Report Saving Lives, Improving Mothers’ Care October 2024 Surveillance findings and lessons learned to inform maternity care from the UK and Ireland Confidential Enquiries into Maternal Deaths from thrombosis and thromboembolism, malignancy and ectopic pregnancy 2020-2022, and morbidity findings for recent migrants with language difficulties’ has been published. The service has benchmarked itself against the findings and this will be considered by the gold command at its next meeting after it has been discussed by the silver group and any actions required agreed. However, there are no immediate causes for concern or significant issues to note.

- Audit Wales Review of Operational Governance

The service had considered the recommendations made within the report around governance and leadership. The service group has recently undergone an organisational change process, resulting in a new leadership and governance structure, which address the findings of the report. These have been shared with the members of the gold command for assurance.

- Horizon Scanning

As part of the gold command’s role, it looks ahead to any potential reviews or reports relating to maternity or neonatal services. These could be regular national reports which are issued as standard or external reviews being undertaken either of the health board itself or other maternity and neonatal services from which there could be learning. The following two were identified for the near future:

- VON (International Vermont Oxford Network)

The VON report, which is a neonatal quality improvement review, is expected in the next few months.

- MBRRACE-UK

The national MBRRACE-UK report setting out how many stillbirths and neonatal deaths had occurred in 2023 is yet to be published. However, the maternity and neonatal services have worked through health board data to ascertain how many cases there have been. So far, there is nothing to suggest the health board is an outlier and all cases had been reviewed for learning and closure using the perinatal mortality review tool (PRMT).

- Internal Quality Assurance Visit

The health board’s quality improvement team has undertaken a review of the services against internal quality assurance indicators. Initial verbal feedback identified areas of good practice and where further work needs to be undertaken. An action plan is in development and will be shared with the bronze group first for confirmation of timescales, actions and leads, after which it will be taken though the silver and gold command in January 2025.

- FINANCIAL IMPLICATIONS

There are no financial implications associated with this report.

- RECOMMENDATION

Members are asked to:

- ACKNOWLEDGE the work to close additional actions raised during enhanced monitoring meetings;

- BE ASSURED progress against the HIW action plan is on track;

- BE ASSURED the actions to address the Health Education and Improvement Wales (HEIW) maternity and neonatal specific actions are in progress;

- BE ASSURED the group has included within its remit the need to ‘horizon scan’ to look ahead to potential visits and/or reports which may require action.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| The health board is dedicated to ensuring that pregnancy and childbirth is a safe and positive experience for all service users in order to support healthy life choices and to give children the best start in life. This requires safe and effective maternity and neonatal services. The actions identified by the reviews and external bodies will support the improvements needed to achieve this. |  |  |  |
| Financial Implications |  |  |  |
| There are no financial implications associated with the report. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| There are no legal implications associated with the report. |  |  |  |
| Staffing Implications |  |  |  |
| There are no staffing implications associated with the report. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The health board has a 10-year vision to be a high-quality organisation. Work being undertaken to address the concerns raised and to de-escalate from enhanced monitoring will not only support that vision but develop maternity and neonatal services which are safe and sustainable in the longer-term. |  |  |  |
| Report History |  | Regular report |  |
| Appendices |  | No appendices |  |