| Meeting Date | 18 December 2024 |  | Agenda Item |  |  | 4.3 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Job Planning Internal Audit Progress Report |  |  |  |  |  |
| Report Author | Liz Stauber, Head of Service – Medical Directorate |  |  |  |  |  |
| Report Sponsor | Dr Richard Evans, Executive Medical Director |  |  |  |  |  |
| Presented by | Dr Raj Krishnan, Deputy Executive Medical Director |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of the report is to provide a report on progress to address the recommendations of the job planning internal audit. |  |  |  |  |  |
| Key Issues | - Job planning was established as a critical part of the Consultant Contract following an amendment in 2003; - There are a number of risks if job planning is not undertaken effectively, the most significant being that the clinical workforce not being used correctly to provide safe and effective care; - An internal audit was commissioned to review job planning and provide a baseline for the improvements needed; - The outcome was one of limited assurance and an action plan is in place; - Progress is being made against the comprehensive action plan; - An improvement in job planning compliance from 20% to 69% since April 2024 has been recorded. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - ACKNOWLEDGE the progress made against the internal audit actions; - ACKNOWLEDGE the work to support the service groups to improve job compliance, resulting in an improvement from 20% in April 2024 to 69% in December 2024; - ACKNOWLEDGE the remainder of the work needs to be driven by the service groups, supported by the corporate functions, and the mechanisms in place to monitor progress. |  |  |  |  |  |

JOB PLANNING INTERNAL AUDIT PROGRESS REPORT

- INTRODUCTION

The purpose of the report is to provide a report on progress to address the recommendations of the job planning internal audit.

- BACKGROUND

Job planning is the process by which consultants agree their duties, responsibilities and outcomes for the coming year to meet the requirements of their role. It was established as a critical part of the Consultant Contract in Wales 2003.

Each job plan sets out the direct clinical care (DCC) sessions, in which patient care is provided, and supporting professional activities (SPA) sessions, such as carrying out appraisals, honorary contracts and clinical supervisor roles, a doctor will undertake over the following year. It also sets out the agreed service outcomes and the role the consultant will have in delivering these.

Job plans have a duration of 12 months, after which they are to be reviewed. This ensures they continue to meet the demands of the service and the consultant. Within Swansea Bay, job planning is undertaken using the electronic system Allocate.

The health board has a 10-year vision to be a high quality, clinically-led organisation. There are a number of risks to this if job planning is not undertaken effectively, the most significant being that the clinical workforce not being used correctly to provide safe and effective care. There is also the risk that the health board will not fill its contractual duties in relation to job planning and consultants may be incorrectly paid.

- GOVERNANCE AND RISK ISSUES

An internal audit was commissioned to review job planning and provide a baseline of improvements needed. The outcome was one of limited assurance and a comprehensive action plan presented to the Audit Committee and Workforce and OD Committee in May 2024 and August 2024 respectively.

Good progress has been made against the recommendations, with seven of the 10 actions due by the end of September 2024 closed by the deadline.

The majority of these required changes and updates to the health board’s job planning guidance. It was revised and an early draft discussed with the Local Negotiating Committee (LNC) Chair and Head of Relations for the British Medical Association (BMA) in April 2024, after which it was agreed by the LNC in June 2024 and the health board’s Management Board in July 2024. It is now available on the intranet, has been circulated to the service groups and is being used in job planning training sessions, along with an easy-read toolkit as a supporting document.

Of the three which passed the deadline, two have since had evidence submitted for the audit tracker to support closure:

- All job plans to be reviewed for completeness, quality and where paper-based, potential to include on Allocate – the service group medical directors have been advised of all consultants who do not have a job plan on Allocate, and Medical HR are supporting specialities to add any paper-based job plans onto the e-system. In addition, each speciality receives a ‘RAG’ rated status report for their areas, setting out the status of each doctor’s job plan. This now closes this recommendation as the work required by the service groups to improve compliance is covered by the open actions due in 2025.

- Service groups to submit CFRs to Medical HR with sufficient time for processing; and there will be an expectation for the job plan and payment to reconcile within a period of three months from the change date  - a new front sheet must now be completed and sent to Medical HR with any change form requests to set out the reasons for the increase/reduction in sessions and to confirm the job plan has been updated. Any requests without the form are returned and not processed. These are now being received within a more reasonable time-period and have updated job plans, closing the action.

This currently leaves one overdue action:

- Service groups to have a medical workforce forum to take assurance as to job planning compliance and to provide quarterly report would then be provided to Medical Workforce Group - service group medical directors are expected to present progress to the bi-monthly Medical Workforce Group on an alternate basis. A presentation was received from Mental Health and Learning Disabilities Service Group in October 2024 with the other three due to present at the December 2024 meeting, after which the action can be closed. Going forward, there will be two presentations per meeting, and the services groups are also asked to update on compliance as part of the quarterly performance reviews.

The longer-term expectation will be for the service groups to have their own Medical Workforce Groups where these issues can be discussed at length and reported back to the corporate forum. For some services groups, these are already in place and it is recognised that for those without, there may be resource implications that will need to be considered.

An improvement in compliance with job planning has been evident, with an increase of signed-off job plans on Allocate from 20% at the start of the financial year to 69%. The breakdown by service group is as follows:

- Morriston Service Group – 55%

- Neath Port Talbot Service Group – 83%

- Mental Health and Learning Disabilities Service Group – 73%

- Primary, Community and Therapies Service Group – 79%

Some of the actions taken to support this improvement include:

- A department must be fully job planned before the Executive Medical Director will approve a vacancy to be advertised;

- Reminders sent to service groups that once in post, new starters must have their job plan reviewed after six months to ensure the content meets the needs of the service and their own personal outcomes. As job plans are originally agreed as 7:3 split, with seven DCCs and three SPAs, this is an opportunity to review whether the 7:3 split needs to be maintained;

- More than 13 sessions have to be agreed by the service group medical director;

- A full audit of the job planning tracker which found around 50 anomalies of terminated or new doctors;

- Revised structures on Allocate to reflect recent service changes;

- Internally developed user guides for Allocate available on the Medical HR SharePoint for easy reference;

- Alongside the front sheet is a comparison between actual pay and signed off job plans held in the system showed 41 inaccuracies across all Service Groups.  Over and under payments are now being worked through or job plans are being amended to reflect correct working patterns and managers will be notified of any future discrepancies via email;

- Training and support being offered to the service groups by the Job Planning Manager and/or the Medical HR Administrator – this helps ensure managers have the right access in Allocate;

- Supporting services to add paper-based job plans to Allocate;

- Deep dives of each speciality to advise the service managers and clinical directors/leads of the position for their service.

- A dashboard provides current data for service groups to monitor compliance and measure progress available on the intranet.

While support and guidance to improve job planning can be provided at a corporate level, delivery of the remainder internal audit recommendations has to be by the service group medical directors, as they relate to compliance with the process. The target dates within the management response are for the end of the financial year, to take into account a full-year job plan cycle and to support their delivery, a job planning workshop has been arranged for January 2025. This will be an opportunity to set out the importance and principles of job planning as well as provide presentations from outside speakers such as Allocate and Welsh Government to share best practice and new developments on a wider basis. Breakout sessions will also provide a practical element. In addition, training and guidance sessions will continue with individuals and specialities.

To maintain progress, a Job Planning Governance Group is in place, led by the Deputy Executive Medical Director. A Job Planning Task and Finish Group has also been set chaired by the Associate Medical Director for Transformation to develop dashboard mapping for both job planning and activity. This group reports into the Medical Workforce Group.

The focus for 2024-25 has been improving the completion of job plans and updating Allocate accordingly. While good progress has been made, it remains to be seen as to whether compliance will reach 100% by the end of March 2025 and all the recommendations closed, given the enormity of the task. Any outstanding will be a focus for early 2025-26, as some may be newly expired or newly appointed. From April 2025, work will focus on matching the demand/capacity work with job planning as well as the quality and content of jobs plans.

- FINANCIAL IMPLICATIONS

There are no financial implications to this report. However, temporary resources were agreed to support the job planning work and these are due to end in March 2025, so consideration will need to be given to what resources are required going forward to support job planning across the organisation.

- RECOMMENDATION

Members are asked to:

- ACKNOWLEDGE the progress made against the internal audit actions;

- ACKNOWLEDGE the work to support the service groups to improve job compliance, resulting in an improvement from 20% in April 2024 to 69% in December 2024;

- ACKNOWLEDGE the remainder of the work needs to be driven by the service groups, supported by the corporate functions, and the mechanisms in place to monitor progress.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☐ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| High quality, robust job plans will ensure the clinical workforce is being used correctly to provide safe and effective care which will result in better patient experience and more effective services. |  |  |  |
| Financial Implications |  |  |  |
| There are no financial implications. However consideration is needed as to the level of resources to support job planning in the longer-term.. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| The health board has contractual duties in relation to job planning and consultants as part of the Consultant Contract 2003. |  |  |  |
| Staffing Implications |  |  |  |
| There are no staffing implications. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The health board has a 10-year vision to be a high quality, clinically-led organisation and compliant job planning is a key component to this. |  |  |  |
| Report History |  | Second report to the committee |  |
| Appendices |  | No appendices |  |