## Support Services Plan
Revised Support Services 1yr Plan (January-December25)
The purpose of the Improvement Plan is improve levels of attendance at work and reduce % of sickness absence across Support Services through objectives set within the Plan. The aim is to support health and wellbeing at work, sustain a high level of engagement and positive employee experience through the objectives and measures outlined below. The Senior Leadership Team and Operational Managers are responsible for delivery of the plan, supported by HR, Occupational Health and Trade Union colleagues. Performance against objectives will initially be monitored at monthly absence review meetings. Outcomes will be measured by staff survey results, % levels of absence. The outcome required from this plan is to support staff to receive any appropriate required support to enable sustained attendance at work and to improve the % of sickness absence across Support Services.
| Improvement Measure | Deliverables | Timeline for Completion | Lead Responsibility | Outcomes | Progress
1.1 | Bi-Monthly Senior meetings to montior effectiveness of improvement plan in reduction of sickness absence. | Managing Attendance at Work meetings have been arranged to monitor sickness absence; development of improvement plan and progress against plan. Consider targeted intervention for hot spot areas only. Extend invite to OH. Meeting frequency to be reviewed in 3-6mths to assess whether meetings can be moved to Quarterly, subject to decrease in absence levels. | Q2 | Departmental Managers/HR | 1. Evaluate impact of proposed measures on reduction of sickness absence; 2. Adjust measures accordingly. | Last meeting 19th November key actions noted in progress log Next meeting 18th Feb 2025
1.2 | Weekly caseload meetings to review absences on a case-by-case basis for high hot spot sickness absnece areas. | Weekly sickness absence surgeries held by HR to review all absences (LTS & STS) on a case-by-case with Operational Managers to ensure compliance with all aspects of MAAW policy (includes prompt closure of open ended absences, accurate absence reason coding, progression through MAAW policy) and proactive management of sickness absence. | Q2 | Operational Managers/HR | 1. Develop detailed understanding of sickness absence; 2. Develop targeted interventions to reduce sickness absence. | SHA has arranged monthly meetings. Plus monthly meetings held for Singleton, Morriston & NPT.
1.3 | Expansion of MAAW processes to assist with management of sickness absence | Appointment of additional Sickness Gorvenance Officer within Support Services at Morriston (Domestics & Portering) Support Services Golden Rules, Sickness absence newsletter | Q2/Q4 | Head/Deputy of Support Services/HR | 1. evaluate impact of proposed measures on reduction of sickness absence; 2. Adjust processed accordingly
1.4 | Regular sickness absence audits. | Audits to be undertaken quaterly/bi-annually to audit compliance with MAAW policy and sickness absence process. Introduce targeted intervention for areas of low compliance; adjust audit frequency according to improvement. | Q3 | HRBP/Operational HR/Governance Lead | 1. Improve compliance with MAAW policy. 2. Assessment of the impact of improved compliance on reduction of sickness absence. | Governance Team will lead on audits with support from HR. Audits to commenced in New year and Morriston Domestic & Porters will be first areas.
2.1 | Support development of management skills in MAAW. | Bespoke Toolbox talks/training on MAAW for managers to include coaching for difficult conversations; coaching staff to own and develop solutions to problems, coaching teams in responsibility for healthy working relationships; use of MAAW toolkit. Consider buddying/mentoring system for managers to support one another through action learning. | Q2-3 | HRBP/Operational HR/Head/Deputy of Support Services | 1. Support effective management of attendance at work. 2. Reduction in levels of sickness absence. | * Training has already been completed and to date 33 supervisors/managers have been trained. Further training to be arranged in NewYear * Sickness absence toolbox guidance to be developed and training sessions to be held in the New Year
2.2 |  | Encourage use of the Work Related Stress Risk Assessment tool in management of stress related absences; provide support/guidance/training in use if needed. | Q2-3 | Operational HR/Head/Deputy of Support Services | 1. Effective management of absences related to work related stress. 2. Reduced absences due to work related stress. | Bespoke training session has already been held. Review if further training is required.
2.3 |  | Managers to attend the mental health awareness training session delivered by the Wellbeing Team. | Q2-3 | Departmental Managers/HR/Wellbeing Team. | 1. Effective management of absences related to mental health. 2. Reduced absences relating to mental health. | Training has been provided establish if further training is required.
3.1 | Increase use of preventative measures to support improvement in reduction of sickness absence focused on health & wellbeing. | Managers to receive support & guidance from Occupational Health to strengthen referral process and quality of reports. Departmental managers to identify training needs of managers/supervisors. Where required managers to attend training sessions to ensure robust OH referrals are made. Develop closer working relationships with OH to establish areas for improvement. | Q2 | Departmental Managers/SHRM/Operational HR/OH | 1.Imroved quality of Occupational Health referrals. 2. Support management ability to effectively manage absence. | Training has been provided establish if further training is required.
3.2 |  | Ensure all managers responsible for MAAW are aware of staff wellbeing advice and support services and actively promote these services across their areas. | Q2 | Departmental Managers/SHRM/Operational HR | 1. Increased access to health & wellbeing support available to staff, supports self help in managing attendance at work. 2. Increased attendance at work. | Each department now has a Wellebing board and Managers are aware of the services available
3.3 |  | Increase the number of well-being champions within Support Services. | Q2-3 | Departmental Managers/SHRM/Operational HR/Wellbeing Team | 1. Increased awareness of health & wellbeing support available to staff. 2. Improve focus on self-help and responsibiity for individual health & wellbeing. 3. Increased attendance at work. | Total of 19 champions
3.4 |  | Trial of Workplace assessments | Q4 | Departmental Managers/OH/Wellbeing Team | 1. Increased awareness of staff health conditions 2. Fidings of assessment to influence any reasonable/tailored adjusment required | Meeting arranged for 7th January to discuss trial areas
3.5 |  | Awareness of flexible working policies to prevent absence and develop 'keep me in work' culture. Management Representation on Flexible Working Sub-Groups. | Q3-4 | Departmental Managers/HBRP/Operational HR | 1. Increased attendance at work.
3.6 |  | Increase PADR compliance; quality PADR's to be undertaken, to include health & wellbeing objectives and tools to support healthy working relationships. Introduce team objectives to support team working. | Q3-Q4 | Departmental Managers/SHRM/Operational HR | 1. Develop focus on responsibility for health & wellbeing. 2. Develop focus on healthy working relationships & teamwork. 3. Increased motivation and engagement. 4. Reduced absenteeism.
4.1 | Creation of tragerted sickness absence group which involve partnership working to reduce sickness absence in hot spot areas. | Quarterly focus group to discuss attendance at work, health & wellbeing. Engagement with trade unions, staff, Occupational health, health & wellbeing champions, HR, departmental managers to review and discuss attendance at work, consider new initiatives to improve attendance. | Q2-3 | Head/Deputy of Support Services/HR/Wellbeing Team/TUP's/OH | 1. Develop joint approach to proactive management of attendance at work. 2. Working together to develop new initiatives with continued focus on health and wellbeing. | * Morriston Porters TOR has been drafted 1 meeting already held
5.1 | Undertake benchmarking exercise to determine and establish realistic, intelligent sickness absence target for department. | Obtain absence rates across NHS Wales HB's; review cumulative absence for past 3yrs across support services; use information to determine relative absence target. | Q3-4 | HRBP | 1. Develop a comparative, realistic absence target for support services.
6.1 | Conduct 'deep dive' into hot spot sickness absence across support services,using an evidence based approach to further develop improvement plan. | Deep dive into sickness absence to establish underlying reasons for absence (using evidence based approach); identify trends, hot spots; conduct analysis using metrics - turnover, employee relations casework, cultural assessment, workforce profiling etc. adjust improvement plan to ensure measures are appropriate and impactful in reduction of sickness absence and increased attendance. | Q2-3 | Head/Deputy of Support Services/HRBP/OD | 1. A robust, evidence based approach to continuous improvement in attendance at work. | Morriston Domestic dive analysis &porters has been undertaken. Action plan has been developed.
6.2 | Measure staff engagement. | Use staff engagement scores -annual staff/ pulse surveys to further develop improvement plan. | Q3-4 | Head/Deputy of Support Services/HRBP/OD | 1. Assessment of workforce motivation and engagement scores. 2. Appropriate improvement measures to increase motiviaton and engagement that support attendance at work.

## Progress Log
Actions | Progress | Completed
Support Services sickness absence responsibility chart to be circulated for comment and implementation | Circulated | 8.1.25
Central consistent sickness tracker to be created & implemented | Circulated | 8.1.25
Central list of staff triggered ST final meetings to monitor progress | In progress
Central list of long term sickness cases | In progress
Managers to be involved earlier on sickness absence process i.e 6 months | Communicated & built into Responsibility chart | 8.1.25
TU representation staff responsibility to be included invite letters | In progress
Introduction of Golden Rules- basic sickness responsilbities for support services | Being amendeed with the aim of issuing at end of January
Sickness Absence Newsletter | Being drafted with the aim of circulating at the end of January
Flexiblity subgroup nominations | Confirmed | 2024-12-01
Sickness Absence Audit timetable | In progress
Weekly Caseload meetings arranged | Arranged and held
Promotion of Menshealth network | ongoing
Commencement of workplace trial assessments | Commencing 13.1.25