## PCT People Plan
| Objective | HB People Strategy Strand(s) | Planned Action | Success Criteria | Who | When | Impact/Development | Outcome/Progress | Status (RAG Rating)
WELLBEING AND MANAGING ATTENDANCE | To Improve and Support Line Manager’s confidence in using the MAAW Policy | Leaders That Live Our Values Excellent Learning & Education Well Planned | Provide Initial and Refresher Training on the MAAW Policy. | To achieve attendance at the Training Sessions of those Managers within the Service Group who are new or who have never previously attended training. | Line Mangers attendance – Training provided by Workforce / Asst HR BPs | Training dates scheduled: 16 April 2025 11 June 2025 17 July 2025 (priority for sickness hot spot areas) 6 August 2025 1 October 2025 26 November 2025 (priority for sickness hot spot areas) 3 December 2025 21 January 2026 20 March 2026 13 May 2026 17 June 2026 14 July 2026 2 September 2026 3 November 2026 9 December 2026 | Update knowledge, skills and ability for Line Mangers to undertake effective sickness management. | 10 Training Sessions held 2021 – 2023 with a total of 123 Manager attendees. | On track
|  |  | Training Sessions have been booked, and ongoing rolling Training Workshops are arranged. |  |  |  | Additional Absence Workshop to be arranged for follow up sessions. | 2024 - 6 Training Sessions held, total 68 Manager attendees.
2025 - 7 Workshops held including 2 for priority attendance for hot spot areas (total 48 attendees) - 94 staff now trained within PCT eff Nov 25. Update January 2026 - 95 staff currently trained
| Consideration to be given for MAAW workshop to be included as a mandatory objective for Management PADR | Leaders That Live Our Values Excellent Learning & Education Well Planned | Discussion with PCT Senior Management representatives. | Facilitate discussion on consideration for MAAW workshop to be mandatory objective for management PADRs | HR BP Team, Senior Management Team | June/July 2025 | Policy compliance, improved management education and awareness around managing attendance at work, increase in effectiveness in management of sickness absence within sickness hot spot areas | Discussion included as part of Absence Summits June 2025 and as part of PCT Senior Management discussions. | On track.
| Scruity and Assurance on Sickness Hot Spot Areas | Excellent Learning & Education Digitally Ready | Deep Dive Sickness Review of Hotspot Areas | To continue to conduct a review of highest sickness absence areas within the Service Group from the Hot Spot ESR RAG Report to ensure Management and Documentation on a monthly basis compliance with the MAAW Policy, and any learning outcomes from case management. | Line Managers within Hot Spot areas – Reviews to be undertaken by Operational Workforce Team/ Asst HR BP | Monthly basis. | Policy compliance and any learning outcomes reviewed. Increased scrutiny on long term sickness absence. | Continue as requested on monthly rolling basis. Monthly review meetings on long term sickness absence ongoing. Support offered to line managers and service leads as required. | On Track
Monthly review meetings between the Asst HRBP and the SHRAs to review long term sickness in hot spot areas
Action Plans to be drawn up from outcomes with recommendations.
| Undertake Sickness Hotspot Audits | Excellent Learning & Education | Following Deep Dive Sickness Reviews/Reports of Hotspot Areas, sickness audits will be undertaken on the ‘Hotspot Areas’ | To conduct an audit of the top sickness hotspot areas, to ensure sickness cases are being managed, and documentation is being completed and maintained. | Operational Workforce Team, in conjunction with the Lead Managers within the Hotspot Areas. Service Group Sickness Auditor. | 6 month programme commencing July 2025 | Policy compliance, themes and learning. | PCT Sickness Auditors identified, training undertaken in June 25, programme to commence July 25. Ty Olwen audit completed August 25 - mini follow up audit scheduled Dec 25. District Nursing July - Dec 25 across 11 areas. | On track
| Faciltate Absence Summits for Sickness Hotspot Areas | Leaders That Live Our Values Well Planned Motivated & Healthy Digitally Ready | Monthly Absence Summit for Sickness Hot Spot Areas | Improved oversight and scruity within sickness hot spot areas. Specific actions to be identified. | Deputy Head of Nursing or representative, HRBP team, HR Operations representative | June 2025 to continue on monthly basis | Policy compliance, improved management education and awareness around managing attendance at work, increase in effectiveness in management of sickness absence within sickness hot spot areas | Absence Summits held for sickness hot spot areas starting June 25. 10 Absence Summits held as of January 2026. | On track.
| Sickness Deep Dive Reports for Sickness Hotspot Areas | Well Planned Digitally Ready | Sickness Deep Dive Reports for sickness hot spot areas and areas who do not meet the criteria but are experiencing significant sickness | Improved insight and analysis to help inform direction of travel for local level sickness action plans. | Assistant HRBP | As and when | Insight into sickness trends and reasons for absence, triangelation of sickness as a driver of variable pay and the effectiveness of any sickness initiatives/interventions to date. | Deep dive reports completed Nov 25 - Ty Olwen, CRT, School Nursing, HMP, Flying Start (Neath), Sexual Health, Podiatry. Deep Dive reports completed Jan 26 for District Nursing, Singleton Ward 3 and SPC. | On track
| Hold Sickness Surgeries | Leaders That Live Our Values Excellent Learning & Education | Monthly Sickness Surgeries with Lead Nurse/Manager within Hot Spot Areas. | To discuss sickness cases within Surgery and to draft action plans for sickness cases. | Lead Nurses/ Managers within Hot Spot areas – Surgeries held with Operational Workforce Support | Monthly basis. | To ensure plans in place to support the Manager/Individual sickness absence cases. | Sickness Surgeries held and ongoing within each Hot Spot area | On track.
| Review Sickness Absence Reasons | Excellent Learning & Education | As part of Sickness Hotspot Review reasons for absences to identify any patterns. As part of the monthly long term sickness absence review, identification of any common themes, discussion and subsequent actions. | Ascertain any preventative or proactive support within a specific Team/ Dept | Deputy Heads of Nursing, Line Managers and Leads within Hot Spot areas. Assistant HR Business Partner / SHRA. | Monthly basis. | To ensure early intervention support offered and appropriate OH referrals and Wellbeing signposting. To ensure managers are best supported whilst managing attendance for their teams. | Monthly review meetings on long term sickness absence ongoing. Support offered to line managers and service leads as required. | On track
| Coordination of review of those staff who have reached nil pay and approaching nil pay whilst on long term sickness absence. | Well Planned Digitally Ready Engaged Motivated & Healthy | As part of the monthly long term sickness absence review, identification of any staff who have either reached nil pay or are approaching nil pay | To discuss those staff on nil pay or approaching nil pay on long term sickness absence and action plans. Support to be provided to line managers to ensure proper management and support is provided to identified staff. | Assistant HR Business Partner / SHRA | Monthly basis. | To ensure those individuals on long term sickness absence and either on nil pay or approaching nil pay are appropriately managed and supported. | Monthly review meetings on long term sickness absence ongoing. Support offered to line managers and service leads as required. | On track
| Review of short term sickness, to include absence prompts | Well Planned Digitally Ready Engaged Motivated & Healthy | A review of short term sickness using data from ESR, to include absence prompts. These are to be shared with services leads for action as appropriate. | To ascertain and support on any action in arising for those staff that have prompted within the Managing Attendance at Work Policy. | Assistant HR Business Partner | Monthly basis. | To ensure staff who have prompted within the Managing Attendance at Work Policy are appropriately managed and supported. | ESR Information circulated monthly | On track
| Create Sickness Improvement Trajectory Plan | Well Planned Digitally Ready | Development of a Sickness Improvement Trajectory Plan for 2025/26 | Development of a Sickness Improvement Trajectory Plan for 2025/26 | HRBP Team / PCT Leadership Teams | Commenced Spring 2025. | To ensure the Service Group and Managers are updated on the Sickness Improvement Trajectory Plan for appropriate action and engagement | BI Dashboard Trajaectory Plan completed. | On track
| Continue Offering Wellbeing Support | Engaged, Motivated & Healthy | As part of the Sickness Surgeries, to re-signpost Wellbeing Support available for staff and managers. To engage with Employee Wellbeing Team to review support available and share | To ensure current support is accessible as a preventative to absence or to support an early return to work. | Line Managers – Sickness Surgeries supported by Operational Workforce | Monthly basis during Sickness Surgeries | To ensure support is being signposted by Line Managers within areas. | Wellbeing information is forwarded to Managers when received, updated within Surgeries, and Team Brief within the Service Group, and shared within the bi-monthly Service Group Wellbeing Champion Meetings/ SBU Wellbeing Forum | On track
|  |  | Staff engagement & wellbeing actions have been drafted by Workforce Business Partners. | To maintain and update access to Wellbeing Support | Line Managers to circulate – Workforce to update/maintain Action Plan | Regularly update any staff engagement & wellbeing actions as required. | Signpost staff support offered within Wellbeing, in addition to intranet site.
| Hold Staff `Drop in’ Sessions | Engaged, Motivated & Healthy Excellent Learning & Education | To offer staff within Hot Spot areas the opportunity to meet with Manager/HR ad hoc drop in session to raise any concerns/ discuss absence management/ share good working practices/ wellbeing support. | Attendance at Sessions | Line Managers – Supported by Operational Workforce / Assistant HR Business Partner | Bi-monthly offer date/time to staff | To enhance good communications and promote staff support. | Staff `Drop In’ Sessions to be offered within Hot Spot areas. HR Clinic Sessions: 24 March, 28 May, 19 June 2025 - SPC/Ty Olwen, Gorseinon - 17 April, 29 May, 27 June 2025 | On track
| Hold Manager `Drop in’ Sessions | Engaged, Motivated & Healthy Excellent Learning & Education | To offer Heads of Service the opportunity to meet with Workforce Business Partner/Asst BP for session on ER queries/ absence management / share good working practices/ wellbeing support. | Attendance at Sessions | Workforce Business Partner/Asst Workforce Business Partner / HR Operations team | Bi-monthly Meetings | To enhance good communications and promote support for Heads of Service. | Manager Meetings to be arranged by Workforce. Sessions: Sexual Health held 14 January 2025 | On track
| Facilitate Absence Data Sharing | Excellent Learning & Education Digitally Ready | To circulate information to the Service Group Heads of Service and Managers regarding the sickness data from BI and ESR Reports for information and action. | Using data: Power BI Workforce metric data to be issued to the management team on a monthly basis via the Workforce Board Reports. Data issued to include: | Workforce Business Partner/ Asst Workforce Business Partner | Monthly basis / as and when | To ensure the Service Group and Managers are updated on their Sickness data for appropriate action. | BI/ESR Information circulated monthly. Deep dive data circulated on as and when basis | On track
Open ended sick (> 90 days – identifies employees on long term sick and who may be reaching half or nil pay)
RAG Report
Sickness absence ‘Hot Spot’ Areas
Breakdown of long and short term sickness to include reasons for absence
Creation of sharing of sickness deep dive reports for sickness hot spot areas with Service Group Managers and Leads
| Use the PADR process to help improve employee attendance and employee PADR | Leaders That Live Our Values Excellent Learning & Education Well Planned Digitally Ready | Continue to ensure via the PADR process that employees feel confident and competent to undertake their roles. Opportunity to have a conversation on Wellbeing, and support available. | Managers to continue to ensure PADR compliance, ensuring employee wellbeing `check in’ is part of the PADR discussion. | Service Group Managers/ Leads (Delegate to all line managers). | Monthly / Review as necessary | To ensure Managers comply with PADR for all staff, and support for staff within the PADR process, ensuring all mandatory and statutory training requirements are complete, and wellbeing discussion held. | PADR KPI’s monitored monthly to review compliance | On track
Workforce Business Partner to share PADR compliance Rates monthly with the Service Group Leads.
| Advise on absence/ attendance queries at Service Group E-Roster Scrutiny Panels | Leaders That Live Our Values Excellent Learning & Education | Workforce Business Partner / Asst Business Partner to attend all Roster Scrutiny Panels with Managers/ Leads. | Workforce support and advice on any sickness absences within the Roster, and ensure that the relevant Operational HR support has been sought by Managers. | Leads/ Managers – Workforce Support | Monthly Panels for all areas within the Service Group. | To promote early intervention for absences identified within the Roster. To ensure Managers supported to initiate an earlier return to work. | Ongoing attendance at monthly E-Roster Scrutiny Panels | On track
| Increase recording of Return to Work Conversations on Allocate and ESR | Digitally Ready | Promote recording of Return to Work Conversations on Allocate and ESR wherever possible | Increase in Return to Work Conversations being recorded on Allocate and ESR | Asst HR BP / HR BP | Monthly / Review as necessary | To promote and reinforce good practice on managing attendance at work and wellbeing support for staff | Email circular sent 19/01/1016, promotion in e-rostering scrutiny panels 02/02/2026, signposting and promotion in February's Team Brief and Workforce Report. | Increase from in month completion rate of 7.51% May 2025 to 17.88% Dec 2025.
| Attendance, Engagement and Support at SBU Wellbeing Forum | Excellent Learning & Education Equality, Diversity & Belonging | To engage across with Managers/Leads across SBU. | Promote wellbeing across the Health Board. | Asst HR BP, Nursing and Therapy Representatives attend from PCTSG held monthly. | Monthly meetings with Asst HR BP and Nursing and Therapy representatives attending from the Group. | To raise awareness of wellbeing support, and promote and share ideas. | Meetings continue to be held monthly for sharing and good practice. | On track
| Continue Faciltating and Support the PCT Wellbeing Champions Network | Engaged, Motivated & Healthy Excellent Learning & Education Equality, Diversity & Belonging | Continuation of the bi-monthly 'Lunch and Connect' sessions. | Attendance at Sessions | Asst HR BP, PCT Wellbeing Champions | Bi-monthly | To raise awareness of wellbeing support, and promote and share ideas. | Meeting continue to be held bi-monthly for sharing and good practice. Meetings scheduled for 2025 - 8 January, 12 March, 14 May, 7 July, 10 September, 12 November. Meetings scheduled for 2026 - 14 January, 11 March, 13 May, 8 July, 9 September, 11 November | PCT Wellbeing Champions MS Teams Channel metrics - 10/11/2025 - 07/02/2026 - 9 posts, 50 active users
|  |  | Continue to promote and engage the Wellbeing Champions Network via the MS Teams Channel (created 2024) | Regular posts on wellbeing initiatives both throughout the HB and within PCT | Asst HR BP, PCT Wellbeing Champions | As and when required but minimum monthly posting | To raise awareness of wellbeing support, and promote and share ideas. | Information to be shared to raise awareness on wellbeing initiatives
| Promote and Raise Awareness of Wellbeing and Inclusion Events | Engaged, Motivated & Healthy Excellent Learning & Education Equality, Diversity & Belonging | To raise awareness and understanding of wellbeing and inclusion events throughout the year, where possible aligned to priority HR KPIs | Regular communication via Team Brief, Workforce Report, email circulation and the PCT Wellbeing Champions Network | HR BP Team | Monthly | To raise awareness of wellbeing and inclusion events, signpost to resource and support for staff | Demonstrable evidence for communication on wellbeing and inclusion events throughout the year: Staff Wellbeing Month Jan 2025, Neurodiversity Celebration Week w/c 17/03/25, Sharing Hope workshops Spring/Summer 2025, Optimise Women's Development Programme 2025, Mental Health Awareness Week May 2025, Carers Week June 2025 | On Track
| Promotion and Awareness Raising of Staff Support Networks | Engaged, Motivated & Healthy Excellent Learning & Education Equality, Diversity & Belonging | To raise awareness and understanding of Staff Support Networks throughout the year | Regular communication via Team Brief, Workforce Report, email circulation and the PCT Wellbeing Champions Network | HR BP Team | Ongoing | To raise awareness of Staff Support Networks, signpost to resource and support for staff | Information to be shared to raise awareness on Staff Support Networks. Promotion of 'Staff Networks Day' via the PCT Wellbeing Champions MS Teams Channel on 15 May 2025 Guardian Service visits at Gorseinon Hospital on Monday 19th May, Tuesday 3rd June, Wednesday 18th June, Thursday 3rd July, Friday 23rd July , Wednesday 13th August | On track.
| HRBP team to coordinate response within Service Group – creating SG teams who will focus on absence | Leaders that Live Our Values Engaged, Motivated & Healthy Well Planned Digitally Ready | HRBP to liaise with SG and agree a SG team who will focus on absence. Team will consist of SG leaders, HRBP team, HR Ops, Audit lead. HRBP team will coordinate the team meetings to begin with - SG leaders to be present - with the aim of leaders taking the lead on absence meetings moving forward - look at hot spot areas, review workforce dashboard, review those who have reached nil pay, develop an action plan to address high short term and long term sickness levels | Creation of a sickness scrutiny SG team focusing on sickness hot spot areas. | HR BP Team | Ongoing | Will limit time to support SG on wider BP responsibilities e.g. workforce planning, recruitment, L & M support, coaching, hot spot support etc. | Update May 2025 - discussions ongoing with SG as to suitable Auditor. Monthly Sickness Scrutiny Meetings set up for District Nursing. Update July 2025 - Sickness Auditors appointed and trained, sickness audit programme to commence July 2025. Absence Summits commenced June 2025 in sickness hot spot areas - Deputy Heads of Nursing appointed as Leads. | Completed
| Facilitate the identification and training of a suitable Sickness Auditor with the Service Group | Engaged, Motivated & Healthy Well Planned Excellent Learning & Education | HRBP to liaise with SG to identify a suitable Sickness Auditor and facilitate training by Lisa Westermark (LW), Morriston SG | Suitable Sickness Auditor identified and appointed. Training to be completed by June 2025. | HR BP Team, Service Leads | May 2025 onwards | An increased focus and scrutiny on sickness absence within hot spot areas. Impact on service due to resource allocation on sickness audits. | Update May 2025 - 2 x Sickness Auditors appointed. Training completed June 25.. | Programme of sickness audits undertaken for DN - Aug 25 - Dec 25, Ty Olwen Aug 25, Sexual Health Feb 26, CRT Jan 26, School Nursing TBA, Flying Start - Neath TBA
| Create and publish a consistent report focusing on Service Group sickness absence which will be issued to Recovery & Sustainability | Well Planned Engaged, Motivated and Healthy Digitally Ready | A consistent report together with action plans submitted to Recovery and Sustainability on a monthly basis to invite information sharing, awareness and discussion | Assurance, improved awareness and understanding on the hot spot areas, influencing factors and action plans within PCT | HR Business Partner | April 2025 onwards on a monthly basis | Site by site comparisons, best practice identification, an increased focus on sickness absence within the Service Group | Reports submitted on a monthly basis from May 2025. | Completed
RETENTION, ENGAGEMENT AND CULTURE | Communicate Turnover Rate and Support with Action Plans in High Turnover Areas | Excellent Learning & Education Well Planned Digitally Ready | To circulate information to the Service Group Heads of Service and Managers regarding the turnover data from Power BI and ESR Reports for information and action. | Using data: Workforce metric data to be issued to the management team on a monthly basis via the Workforce Board Reports. Data issued to include: | Workforce Business Partner/ Asst Workforce Business Partner | Monthly | To ensure the Service Group and Managers are updated on their Sickness data for appropriate action. | BI/ESR Information circulated monthly | On track.
Overall turnover rate for PCT SG
Breakdown of staff turnover by staff group
Detailed breakdown of staff turnover for the previous 3 months
Staff turnover by leaving reason
|  |  | To support the development of action plans where high areas of turnover are identified | Development of service specific action plans | HR BP Team / Line Managers / Service Leads | As and When Required | To ensure relevant service areas are supported on managing high areas of staff turnover | Development of action plans where high areas of turnover are identified | On track.
| Report on Exit Questionnaires and Interview Themes | Attract and Recruit Excellent Learning & Education Leaders That Live Our Values | Exit Questionnaire / Interviews to be conducted when staff leave the Service Group or transfer posts internally. | To continue to promote the re-established exit questionnaire process with a clear advice for managers and staff to follow. | Line Managers / Assistant HR Business Partner | Provide all leavers with an exit questionnaire/ offer exit interview. | Information analysis to support staff retention and wellbeing. Identify any improvements to support with staff retention and attendance at work. Highlighting what is going well that supports staff wellbeing and attendance, and any improvements learning from feedback. | Exit Questionnaire Process introduced February 2022, and quarterly and annual Exit Questionnaire Reports being produced. In addition to reports feedback provided to Service Leads, where respondents consent. Update June 2025 - Presentation shared at June PCT LPF on the 2024/25 Exit Interview / Questionnaire results. | On track.
Follow up exit interview and report data analysis quarterly and annually to Service Group.
|  |  | Exit Questionnaire / Interview Tracker to continue to be populated when questionnaires are received and/or interviews are undertaken | Analyse exit data to provide valuable information to feed the employment lifecycle and any interventions that can be implemented to retain staff and improve staff experiences. | Assistant HR Business Partner | Data reviewed on a weekly basis. Quarterly reports to be submitted to the Monthly Operations Meeting. | Data readily accessible to support data analysis | Exit Questionnaire / Interview Tracker introduced 2024. Tracker to continue to be populated. | On track.
Promote the HB wide exit questionnaire on offer, from November 2025 onwards
|  |  | Explore the possibility of union intelligence to feed into the data collection for exit questionnaires and interviews. | Possibility of union feedback on staff leavers discussed and explored with union colleagues. | Assistant HR Business Partner | 2025-07-01 | Potiential for improved data and Information analysis to support staff retention and wellbeing. Identify any improvements to support with staff retention and attendance at work. | Update June 2025 - raised as part of PCT LPF following 2024/25 Exit Interview/Questionnaire Presentation | On track.
| Support Employee Feedback/ Voice | Engaged, Motivated & Healthy Digitally Ready Excellent Learning & Education Leaders That Live Our Values Equality, Diversity & Belonging | Pulse Surveys to be undertaken in hot spot areas | Pulse surveys to be circulated to staff as and when required to gain insight into staff experience, with actions following aligned to retention and wellbeing interventions | Assistant HR Business Partner/ HR Business Partner / Line managers | As per Pulse Survey Programme Dates (Oct 2024 to July 2025) | Information analysis to support staff retention and wellbeing. Identify any actions to support with staff retention and wellbeing at work. | District Nursing (Afan Cluster - Oct 2024, Llwchwr Cluster - Nov 2024, Neath Cluster - Jan 2025, Upper Valleys Cluster - Jan 2025, City Cluster - Jan 2025, Penderry Cluster - Feb 2025, Cwmtawe Cluster Feb 2025, OOH - April 2025, SPOA - April 2025), HMP - March 2025, Gorseinon - March 2025, LTC and DoLS - March 2025, Community Wound Clinic - April 2025, Sexual Health - May 2025, Ty Olwen and SPC - June 2025, Health Bowel and Bladder - July 2025 | Completed
|  |  | Inclusion of 'Speaking Up Safely' question in pulse surveys | Inclusion of 'Speaking Up Safely' question in pulse surveys | Assistant HR Business Partner | As per Pulse Survey Programme Dates (Oct 2024 to July 2025) | Data collation on if staff feel able to raise concerns | Speaking Up Safely' questions included on all pulse surveys from Feb 2025 | Completed
|  |  | Support, advice and guidance on action plans following pulse surveys. How to Guide for Managers to be developed and circulated. | Development of service specific action plans. How to Guide for Managers developed and circulated. | Assistant HR Business Partner / HR Business Partner / Line managers | As per Pulse Survey Programme Dates (Oct 2024 to July 2025) | Wellbeing, retention and engagement interventions developed. Positive score improvement markers on next Pulse Survey. | Overall District Nursing Wellbeing, Retention and Engagement Plan 2024/25 developed. Sub plans in progress for each of the eight clusters. Overall Nursing Wellbeing, Retention and Engagement Plan 2025 in development for Gorseinon, SPC/Ty Olwen, HMP, Sexual Health and Healthy Bladder and Bowel. How to Guides for Managers on creating a follow up action plan and engaging with staff developed and circulated. | Completed
| Communicate Appraisal Compliance and Support Low Compliance Areas | Leaders That Live Our Values Excellent Learning & Education Well Planned Digitally Ready | To circulate information to the Service Group Heads of Service and Managers regarding appraisal compliance from BI and ESR Reports for information and action. | Using data: Workforce metric data to be issued to the management team on a monthly basis via the Workforce Board Reports. Data issued to include: | Assistant HR BP / HR BP | Monthly | To ensure the Service Group and Managers are updated on their vacancy data for appropriate action. | BI/ESR Information circulated monthly | On track.
Overall PADR compliance rate for PCT SG
PADR compliance breakdown by staffing group
PADR compliance breakdown by cost code
PADR compliance breakdown by competence
|  |  | To support the development of action plans where areas of low PADR compliance are identified | Development of service specific action plans | HR BP Team / Line Managers / Service Leads | As and When Required | To ensure relevant service areas are supported on managing low PADR compliance | Support on development of action plans where areas of low PADR rates are identified | On track.
| Support on Wales NHS Staff Survey Feedback 2024 | Engaged, Motivated & Healthy Digitally Ready Excellent Learning & Education Leaders That Live Our Values Equality, Diversity & Belonging | Feedback following completion of Wales NHS Staff Survey 2024 | Assessing received feedback comments for the Service and reviewing any themes. | HEIW undertaking the National NHS Staff Survey and providing Feedback. HRBP team, Manager and Team Leads from all PCT areas | National NHS Staff Survey held 1 October to 29 November 2024. | Feedback expected from HEIW in March 2025, and reflection on responses received with action plan Spring 2025. | Feedback to be communicated March/April 2025 to staff via line manager cascade / Monthly Operations Meeting / Team Brief. Initial results for PCT shared at March Team Brief, fuller results shared at June Team Brief. Service area specific staff survey reports circulated June 2025. PCT Staff Survey Plan circulated June 2025. Updated Oct 2025 - Detailed HB wide summary and results fed back to SG via monthly Team Brief. | Completed
| Wales NHS Staff Survey 2025 Promotion and Engagement | Engaged, Motivated & Healthy Digitally Ready Excellent Learning & Education Leaders That Live Our Values Equality, Diversity & Belonging | Engage and raise awareness of the 2025 Wales NHS Staff Survey | Promotion of the 2025 Wales NHS Staff Survey | HRBP team, Manager and Team Leads from all PCT areas | National NHS Staff Survey anticipated to be scheduled October to November 2025. | Staff to engage in 2025 Staff Survey. Future reflection on responses with development of action plans as appropriate. | Staff engagement measured as response rate (2024 PCT response rate noted as 9.5%) Action plan to be drafted on key areas of improvement Spring 2026. Update October - Dec 2025 - promotion of staff survey via Oct Team Brief, email and intranet comms. Results to be released March 2026. | On track.
| Support from the L&OD Team | Engaged, Motivated & Healthy Excellent Learning & Education Leaders That Live Our Values Equality, Diversity & Belonging | To engage across with Managers/Leads across SBU. | Promote healthy working relationships and compassionate leaderships. | Monthly meeting held with HR BP and OD link to discuss priority areas. | 2025 onwards. | Promote healthy working relationships and compassionate leaderships. | Meetings scheduled with HRBP and OD monthly and are on-going. | Completed
[6 empty] | OD sessions provided to priority areas. |  | OD sessions ongoing with the following priority areas to date:
Bay Cluster. Update October 2025 - Bay Cluster OD support recalled due to Team Leader/ band 6 capacity issues. To be re-reviewed after the Community Review. OD support given to MCA/DoLS following Pulse Survey - leadership coaching provided from June to October 2025. Reflective Practice session for 8as within Podiatry scheduled for New Year 2026.
| Support on the Nursing Leadership Development Programme for band 6 and band 7 | Leaders That Live Our Values Excellent Learning & Education Well Planned | To support the Nursing Leadership team on the development of the Nursing Leadership Development Programme | Development of the Nursing Leadership Development Programme for band 6s and band 7s | Nursing Leads / HR Business Partner / Assistant HR Business Partner | Spring 2025 onwards | Development and ongoing support for staff within the band 6 and band 7 role in relation to their management capabilities | Development of the Nursing Leadership Development Programme - band 6s - anticipated late Spring 2025. Update October 2025 - on hold due to Community Review. New LEAD programme offered to band 6s and band 7s. To be reviewed once Community Review is complete. | On hold - Community Review underway Autumn/Winter 25/26
| Support on developing a Leadership Mentoring Framework pilot within Nursing | Leaders That Live Our Values Excellent Learning & Education Well Planned | To support the Nursing Leadership team on the development of a Leadership Mentoring Framework for band 6s and band 7s | Development of a Leadership Mentoring Framework | Leadership and OD Practitioner / OD team / Nursing Leads / Assistant HR Business Partner / HR Business Partner | Spring 2025 onwards | Development and ongoing support for staff within the band 6 role initially through a mentoring lens | Discussions with the OD team March 2025. Update October 2025 - on hold due to Community Review. New LEAD programme offered to band 6s and band 7s. To be reviewed once Community Review is complete. | On hold - Community Review underway Autumn/Winter 25/26
| Promotion of Civility Saves Lives Resources | Engaged, Motivated & Healthy Equality, Diversity & Belonging | To raise awareness and understanding of Civility Saves Lives throughout the year | Regular communication via Team Brief, Workforce Report, email circulation and the PCT Wellbeing Champions Network | HRBP team | Ongoing | To raise awareness and understanding of Civility Saves Lives | Demonstrable evidence for communication on Civility Saves Lives throughout the year: Shared within February - November 2025 Team Briefs, Workforce Reports and email circular. Promotion within management team meetings and PCT Wellbeing Champions MS Teams Channel. | On track.
| Promote Compassionate Leadership Ethos | Leaders That Live Our Values | To embed the ethos of Compassionate Leadership within all strands of the PCT Wellbeing, Recruitment and Retention Plan | Promotion, support, advice and guidance within the lens of Compassionate Leadership to management and staff | HRBP team / HR Operations team | Ongoing | To raise awareness and understanding and embed culturally the ethos of Compassionate Leadership | Ongoing work with team meetings and promotion where Compassionate Leadership can be applied. Update June 2025 - Climate and Culture Presentation by Margaret Lake and TRiM by Leon Murnieks for June Senior Management Development session, incorporation of compassionate management as part of 2025 MAAW workshops, incorporation of compassionaite management as part of Disciplinary Training (May to July 2025), Neurodiversity Presentation by Adrian Ayers scheduled for October Senior Management Development session (update October 2025 - did not go ahead due to staff sickness, to be rescheduled) Compassionate Management approach adopted by SHRAs as part of coaching and support to managers. | On track
| Promotion and Awareness Raising of 'Brilliant Basics' | Leaders That Live Our Values Excellent Learning & Education Well Planned Digitally Ready | To raise awareness and understanding of Brilliant Basics throughout the year | Regular communication via Team Brief, Workforce Report, email circulation and the PCT Wellbeing Champions Network | HRBP team | Ongoing | To raise awareness and understanding of Brilliant Basics | Demonstrable evidence for communication on Brilliant Basics throughout the year: Shared within February and June 2025 Team Brief, Workforce Report and email circular. Promotion within management team meetings and PCT Wellbeing Champions MS Teams Channel. | On track.
| Support on Workforce Planning | Attract and Recruit Leaders That Live Our Values Excellent Learning & Education Well Planned | To support PCT Leadership teams on Workforce Planning | Development of Workforce Plans across PCT | Workforce Planning team / Managers / Assistant HR Business Partner / HR Business Partner | Spring 2025 onwards | Development and support of Workforce Plans throughout PCT | Ongoing work with the Workforce Planning team. Plans have been developed throughout Nursing and Therapies. Nursing Workforce Planning Workshop held 11 February 2025, Therapies Workforce Planning Workshop held January 2025. | On track.
| Pilot PCT New Starter Questionnaire | Engaged, Motivated & Healthy Equality, Diversity & Belonging | Circulate New Starter Questionnaire to new staff for the previous quarter | Circulation of new starter questionnaire and submission of data from new starters | Assistant HR BP / HR BP | May 2025 - October 2025 | Information analysis to support staff retention and wellbeing. Identify any actions to support with staff retention and wellbeing at work. | Completion of pilot in October 2025 with summary report. Update October 2025 - delayed due to staff sickness and re-focus of PCT People Priorities. To be reviewed April 2026. | Delayed - to be reviewed April 2026
RECRUITMENT | Communicate Vacancy Data and Support Areas With High Vacancy Number | Attract and Recruit Well Planned Digitally Ready Excellent Learning & Education | To circulate information to the Service Group Heads of Service and Managers regarding the vacancy data from BI and ESR Reports for information and action. | Using data: Workforce metric data to be issued to the management team on a monthly basis via the Workforce Board Reports. Data issued to include: | Assistant HR BP / HR BP | Monthly | To ensure the Service Group and Managers are updated on their vacancy data for appropriate action. | BI/ESR Information circulated monthly | On track.
Breakdown of vacancies by staff group on an in month basis
Detailed recruitment report breakdown, open adverts, outstanding shortlists, outstanding interview outcomes, outstanding PECs, outstanding start dates and starting checks outstanding
|  |  | To support the development of action plans where high areas of vacancy / difficult to fill posts are identified | Development of service specific action plans | HR BP Team / Line Managers / Service Leads | As and When Required | To ensure relevant service areas are supported on managing high areas of vacancies / difficult to fill posts | Development of action plans where high areas of vacancies / difficult to fill posts are identified | On track.
WORKFORCE EFFICIENCIES | An increased focus on reducing variable pay | Well Planned Digitally Ready Engaged, Motivated & Healthy | To embed an increased focus on reducing variable pay within all strands of the PCT Wellbeing, Recruitment and Retention Plan | Awareness raising, support, advice and guidance on a HR perspective to reducing variable pay to management. | HRBP team | Ongoing | To raise awareness, understanding and influence where needed on interventions to reduce variable pay. | Ongoing work within team meetings and discussions with managers on interventions to reduce variable pay. Scheduled weekly Nursing Bank and Agency meeting in place with HR attendance. Monthly e-rostering meeting in place with HR attendance. Sickness as a driver of variable pay used as part of the deep dive reports into sickness hotspot areas across PCT (Nov/Dec 25/ Jan 26) | Ongoing

## Sickness Absence Action Plan
Action | Impact/Risk | Date | RAG Status | Comments/
Update
Deploy Business Partner (BP) teams to coordinate responses within Service Group (SG) – creating SG teams who will focus on absence | Will limit time to support SG on wider BP responsibilities e.g. workforce planning, recruitment, L & M support, coaching, hot spot support etc. | Immediate Effect | Update May 2025 - discussions ongoing with SG as to suitable Auditor. Monthly Sickness Scrutiny Meetings set up for District Nursing. Update July 2025 - Sickness Auditors appointed and trained, sickness audit programme to commence July 2025. Absence Summits commenced June 2025 in sickness hot spot areas - Deputy Heads of Nursing appointed as Leads. SHRAs undertake monthly review meetings on long term sickness absence ongoing and review LTS cases as part of Open Ended Report. Support offered to line managers and service leads as required. Updated Sickness Pathway in place June 2025 (SHRAs to support at 2nd Formal and from one month of LTS) | HRBPs to liaise with SGs and agree a SG team who will focus on absence. Team would consist of SG leaders, HRBP teams, HR Ops, Audit lead. HRBP teams will coordinate the team meetings to begin with - SG leaders to be present - with the aim of leaders taking the lead on absence meetings moving forward - look at hot spot areas, review workforce dashboard, review those who have reached nil pay, develop an action plan to address high short term and long term sickness levels
Pull dedicated support from HR operations team to work with SG Team to support the audit of 10 hot spot areas for sickness and confirm action plans | Will delay ER processes due to limited capacity within HR Operations team. Will mean other HR work may pause for a while. Impact on TU relations; | Immediate Effect | Update May 2025 - 2 x PCT Sickness Auditors appointed. Training underway. Update July 2025 - sickness audit programme commences focusing on sickness hot spot areas. HR Operations Team unable to support with sickness audits due to capacity. | Once we know which hot spot areas need focus we will approach the Ops team for dedicated sickness absence support - currently reviewing workload. The action plan will be reviewed in the Sickness Absence meetings. For now we will proceed with the support already in place
Deploy Corporate Nursing to coordinate roster managers on roster efficiency to engage in SG teams – focus of review on efficiency of roster scrutiny process |  | Immediate Effect
Deploy LW from Morriston SG to train SG teams on deep dive audits | Impact SG Morriston as other responsibilities. Capacity minimised if provided for a short period. | Immediate Effect | Completed June 2025 | Agreement from COO and SG Lead to deploy LW temporarily on a train the trainer basis (already completed) - I will begin to share the names we have so far with Lisa so she can begin the training
Each SG and Department to deploy someone to coordinate their deep dives and to be trained by LW | Suggest include roster managers as well as a coordinating manager within high hot spot sickness area. | Immediate Effect | Update May 2025 - 2 x PCT Sickness Auditors appointed. Training underway. Update July 2025 - sickness audit programme commences focusing on sickness hot spot areas. | Confirmation from each SG to be confirmed - the role of the audit lead will be to conduct audits following training delivered by Lisa as above. This won't be their full role but a requirement to complete in addition to their role
Dashboard Utilisation to help track and manage sickness absence | Minimal/to ensure one source of truth used to track performance. (Risk cross charging vacancies within Establishment Control Dashboard so have to agree principles to manage with Finance) | Immediate Effect | Already in place ESR/BI dashboard information used as standard. | All managers have access to dashboard - we have the opportunity to feedback on the dashboard with the ESR team to ensure it is fit for purpose in readiness for reporting to R&S
BPs to create and publish a consistent report which will be issued to R&S on a monthly basis | Site by site comparisons, best practice identification | w/c 14th April | Completed | The workforce dashboard will be used to report absence at R&S. Action plans will be shared - reports are to be consistent
Each BP team to coordinate a review of those staff who have exhausted sick pay (currently circa 59 on nil pay and 79 further approaching) | National impact of policy approach. Custom & Practice has been to allow to remain on. Therefore impact on TU relations. Already experiencing this following more recent proactive management. ET claims. | Immediate Effect | This work is undertaken by the HR Operations team on a monthly basis - Final Sickness Review Meetings arranged as appropraite. Monthly review meetings on long term sickness already in place with SHRAs and Asst HRBP, staff on half and nil pay reviewed as part of this. | As part of the SG absence team meetings (point 1 above) review all those on nil pay - BP teams to oversee action plan and ensure that the leaders to work with the Ops team to progress these cases
OH to prioritise nil pay group for review. BP team to ensure “effective” OH referral” and support to be given for longer term locum in OH to speed up timescales. | General staff engagement, presenteeism, disability discrimination, TU relations and ET claims | TBC (will depend on locum cover for PH being approved) |  | Will escalate discussions with OH team to review current status of cases - on a case by case basis the ops team and leader will review with OH where more clarity is required - overseen by the HRBP teams in line with the action plan