## HEIW Targeted Visit FEB 2024
Date | Action No | Requirement OR Recommendations | Narrative of Action | Actions | Current Status | Target Risk | Updates | October Update | End of October Update | November Update | 2025-03-01 | Target Date | Action Lead
Feburary 2024 | 1 | Requirements | The Health Board must ensure that behaviour within the department is always professional, and the Behaviours Champion should be readily accessible. | Trainees have been informed that Mr. Mike Hardway is the Workforce Behaviour champion within the department and is also the Workforce Behaviour Deputy Lead for Wales. Mr. Hardway is always accessible in the department. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (MAR 2024) | Charity Knight / Abdi Ali
|  |  |  | The department receives Civility in the Workplace Training Sessions yearly |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED & ONGOING (FEB 2024) | Michael Hardway
|  |  |  | An additional Civility in the Workplace Training session with Mr Mike Hardway has been arranged on 18th April where the service will record attendance. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLTE & ONGOING | Michael Hardway
|  |  |  | Reminder to all Trainees of the need to arrange a monthly meeting with Educational Supervisor. |  |  | Reminder in Gynae Training Forum on a frequent basis | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (MAR 2024) | All Education Supervisors
|  |  |  | In discussion with the Exec team who are aware to prioritise Gynae theatre capacity |  |  | Explained during HEIW visit that we are unable to increase additional theatres urgently as we require to undertake job planning and the changes made during COVID to the on-call rota has resulted less availlable time to cover the elective activity. We have however, increases theatre capacity for General Gynae by 5 sessions a week. A report was provided to HEIW on the day of the visit of the amount of theatres each trainee had since Feb 2024. We as a service feel the number of theatres each trainee has had has been a significant improvement in the previous year. Some registrar cannot be allocated to theatres due to leave and rota time off. |  | Plans to start operating out of NPTH - Equipment on order and job plans underway |  | Gynae services have increased theatre sessions - service has increased capacity at Singleton and NPTH | COMPLETE | Madhu Dey/ Abi Morris
|  |  |  | Psychological Safety Personnel External to department support - Agreements from Neonates to support. Agreement made with Cosnultant colleagues, |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (AUG 2024) | Charity Knight / Kate (Neonates Consultant)
2024-02-01 | 2 | Requirements | The Health Board must ensure that there is a significant increase in capacity for elective Gynaecology theatre. There should be one theatre session per week for each consultant with a Gynaecology interest, and the remainder with at least one each per fortnight. | Service has secured additional Theatre Sessions at NPT which commences 12th of March for several weeks |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Abigail Morris
|  |  |  | Laparoscopic stimulators are available in the department for Trainee’s to practice Laparoscopic Procedures (24 hour access.) |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Ahmad Nassar/ Charity Knight
|  |  |  | Additional work ongoing with Job Plans and Demand and Capacity planning |  |  | Update as of 4th of October 2024: The Health Board have set a target for all job plans to be completed by the end of October of which the service is currently working towards. This has been challenging due to commitments. Training opportunities have increased and trainees are rostered to attend theatre regularly as per individual training needs. The College Tutor meets with the Rota Co-ordinator on the weekly basis to ensure training sessions are prioritised. As shown in the below document: |  | The service is still working on the following however excellent progress has been made thus far, and completion of action should take place before the end of December: Allocation of further Theatres for Gynae services (additional lists in NPTH) Completion of Job Plan (18 out of 24) | Some meeting booked are second meetings and 1x due to BMA Rep needed to be in attendance. | All colleagues have recicved job plan meeting - will be updated yearly as normal job planning complaince | COMPLETE | Abigail Morris
2024-02-01 | 3 | Requirements | The Health Board must ensure that Antenatal clinics have direct consultant supervision, with those consultants not allocated to other duties. | Consultants are not allocated other duties when based at ANC, we recognise on rare occasions due to sickness and annual leave this may occur. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Abigail Morris / Sarah Madden
|  |  |  | Clinical Lead has liaised with all obstetric consultants to ensure their consistent presence in their antenatal clinics |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Madhu Dey
|  |  |  | College Tutor has worked with the Rota Manager to ensure trainees have consultant supervision for the majority of antenatal clinics. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Charity Knight / Abdi Ali / Sarah Madden
|  |  |  | The College Tutor has reminded the trainees that they have immediate access to the Obstetric consultant on call to discuss any cases where they require additional support. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (MAR 2024) | Charity Knight / Abdi Ali
2024-02-01 | 4 | Requirements | The Health Board must ensure that ST3 to ST5 trainees are not undertaking clinics without direct consultant supervision. | The College Tutor has liaised with the Rota Manager to ensure ST3 and ST4 level trainees have consultant supervision for all clinics. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Charity Knight / Abdi Ali / Sarah Madden
|  |  |  | We believe that a trainee with more than 4 years of training (i.e. ST5 level) is capable of undertaking a routine clinic without direct consultant supervision, (though this will be reviewed on an individual basis for each trainee.) |  |  | Clartiy from HEIW report - that if a trainee is clinically able from ST3 and above they are capable of | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (JULY2024) | Charity Knight / Abdi Ali
|  |  |  | The College Tutor has reminded ST5-ST7 trainees that they have immediate access to the Obstetric or Gynaecology consultant on call to discuss any cases where they require additional support. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (MAR 2024) | Charity Knight / Abdi Ali
2024-02-01 | 5 | Requirements | The Health Board must ensure that the induction is robustly delivered to all trainees, including those who rotate out of sync. | The College Tutor and SHO Tutor will provide a bespoke induction (similar to the induction delivered in August) for trainees who rotate out of sync of the August induction days. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Charity Knight / Abdi Ali
|  |  |  | The Postgraduate Medical Team will liaise with Medical HR to ensure out of sync trainees receive a copy of the HB induction programme |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (MARCH 2024) | Charity Knight/ Llinos Hodder
|  |  |  | Management team will also provide a presence to ensure all questions relating to Procedures and Policies are answered. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Abigail Morris / Sarah Madden
2024-02-01 | 6 | Requirements | The Health Board must ensure that Educational Supervisors meet their ST trainees formally every month, as required by the portfolio. | The Clinical Lead informed all consultants at the Consultant meeting in February (19/02/2024) that all ST trainees require a formal ES meeting every month which is to be recorded in their portfolio. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Madhuchanda Dey
2024-02-01 | 1 | Recommendations | The Health Board should ensure that the rota is better coordinated to ensure that training requirements are met on a regular basis. This could be achieved through a regular weekly rota meeting which involves consultants and trainees. | The College Tutor, the SHO Tutor and Mr J Gasson now meet with the Rota Manager on a weekly basis (Tuesday AM rotating through the 3 consultants) with input from one of the senior trainees in the department (Dr S.) |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE - Mr Gasson no longer in attendance due to retirement | COMPLETED (FEB 2024) | Charity Knight / Abdi Ali / Jeremy Gasson
2024-02-01 | 2 | Recommendations | The Health Board should ensure that Educational Supervisors who are unsure about their role attend a portfolio training day. | O&G Clinical Lead made all Consultants aware of the availability of ePortfolio training session, College Tutor informed all Consultants of the next available date in May. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Madhuchanda Dey
2024-02-01 | 3 | Recommendations | The Health Board should take steps to ensure that there is rostered time for Ultrasound training. | The Ultrasound Lead met with the Trainees, the College Tutor and the Rota Manager to discuss their concerns raised regarding USS training (07/03/2024.) |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Charity Knight / Abdi Ali / Jeremy Gasson
|  |  |  | A proforma/review has been created by the Management where a record of USS Training Days/Sessions are recorded and reviewed by SHO and Course Tutor on a bi-weekly basis |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Abigail Morris / Sarah Madden
2024-02-01 | 4 | Recommendations | The Health Board should ensure that trainees are not removed from training opportunities to cover service demand, apart from exceptional circumstances. | The College Tutor has met with the Rota Manager (22/02/2024) who will now ensure that trainees are not removed from training sessions, unless there are exceptional circumstances e.g. to cover for sick leave where there is no alternative cover. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Charity Knight / Abdi Ali / Sarah Madden
|  |  |  | Reduced the number of middle grade and SHOs who are on leave at any one time, which will increase the number present on "the shop floor" to increase training opportunities. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Abigail Morris / Sarah Madden
|  |  |  | Proforma has been created to capture when Trainees are pulled from Training opportunities and will be reviewed bi-weekly with SHO and Course Tutor |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Abigail Morris / Sarah Madden
2024-02-01 | 5 | Recommendations | The Health Board should consider increasing the number of middle grade doctors. | The department has been successful in appointing a clinical fellow (registrar level) to the department and is awaiting visa/occupational health checks before she can commence. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Charity Knight / Abdi Ali / Jeremy Gasson
|  |  |  | We are in the process of recruiting a second clinical fellow (registrar level) with approval for a short term locum registrar in the interim. |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | Charity Knight / Abdi Ali / Jeremy Gasson
2024-02-01 | 6 | Recommendations | The Health Board should consider making changes to job plans of non-training middle grade doctors to help balance training opportunities. | The department is currently undertaking Job Plan meetings with all Consultants and middle grade doctors within the department and will take this into consideration during discussions. |  |  | Update as of 4th of October 2024: The Health Board have set a target for all job plans to be completed by the end of October of which the service is currently working towards. This has been challenging due to commitments. Training opportunities have increased and trainees are rostered to attend theatre regularly as per individual training needs. The College Tutor meets with the Rota Co-ordinator on the weekly basis to ensure training sessions are prioritised. As shown in the below document: |  | The service is still working on the following however excellent progress has been made thus far, and completion of action should take place before the end of December: Allocation of further Theatres for Gynae services (additional lists in NPTH) Completion of Job Plan (18 out of 24) | Some meeting booked are second meetings and 1x due to BMA Rep needed to be in attendance. | All colleagues have recicved job plan meeting - will be updated yearly as normal job planning complaince | COMPLETE | Madhuchanda Dey / Abigail Morris
2024-02-01 | 7 | Recommendations | The Health Board should consider the development of a log to record training opportunities that are achieved or missed, including operating and ultrasound. | The Rota manager has agreed to keep a log of Training opportunities which are achieved/ missed within the department and the reason for this. (e.g. moved from theatre/ ultrasound session.) |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Abigail Morris / Sarah Madden
|  |  |  | Trainees are aware of weekly teaching sessions and are scheduled to attend/ participate in these with support from the College Tutor and Educational Supervisors (when they are not on call.) |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETED (FEB 2024) | Charity Knight / Abdi Ali / Jeremy Gasson
HEIW TO REVIEW IN 6 MONTHS TIME: DUE JULY 2024

## HEIW Targeted Visit JULY 2024
Date | Action No | Requirement OR Recommendations | Narrative of Action | Actions | Update on 15th of September | Current Status | Target Risk | Updates | October Update | End of October Update | November Update | March 2025 Update | Target Date | Action Lead
2024-07-01 | 1 | Requirements | The Health Board must ensure that further efforts are made to ensure that undermining behaviours and comments are eradicated, and that behaviour is always professional, in line with GMC standards and health board values. | The Clinical Director updated the Consultant body during our Consultant Meeting of the findings of the HEIW report and the responsibility of each colleague to ensure we all act in line with the HB values. |  |  |  | Gynaecology Service at Singleton Hospital won the RCOG - TEF 2023 Award. We have been rated as one of the top 10 performing units in the UK in our RCOG Training Evaluation Forms 2023 and were highly commended for Professional Development and Obstetric Training. | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Madhu Dey
|  |  |  | The new August cohort of doctors will receive a Civility in the Workplace session with Mr Mike Hardway (Workplace Behaviour Deputy Lead for Wales) on 08/08/2024 as part of their induction process. The trainees will be advised of the Workplace Behaviour champion within the department (Mr Mike Hardway) and how to contact him. |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Mike Hardway
|  |  |  | The College Tutor will inform all trainees of the new escalation pathway we have implemented and make them aware of who to contact both within and outside the department. |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Charity Knight
|  |  |  | The department will receive a Civility in the Workplace session with Mr Mike Hardway on a regular basis (Workplace Behaviour Deputy Lead for Wales) on with an attendance record to be kept. | Another Civility at Workplace presentation planned for 17th of September. This will be the third presentation presented to the department which includes the GMC Workshop |  |  | COMPLETE | Update as of 4th of October 2024: This action has now been completed with good attendances to the Audit on the 17th of September. GMC Professional at the Workplace Workshop is planned for November 2024. Associate Group Medical Director attended Consultant meeting on the 17th of September to make the Consultant body aware of their professional responsibilities in response to the HEIW feedback. Plans were made to address any outstanding actions. Medical Director will also visit the department in October. | COMPLETE | COMPLETE | COMPLETE | ONGOING | Mike Hardway
2024-07-01 | 2 | Requirements | The Health Board must ensure that efforts are made to improve communication and relationships between trainees and trainers, enabling an environment that allows concerns to be raised regarding behaviours, training, and patient safety. | The College Tutor will provide a more regular Trainee Forum meeting at the Thursday afternoon teaching sessions with the Clinical Director attending for part of the session, to ensure a prompt response can be made to any departmental issues that are raised. |  |  |  | Meetings established and was discussed in Induction | COMPLETE | COMPLETE | COMPLETE | COMPLETE | ONGOING | Charity Knight
2024-07-01 | 3 | Requirements | The Health Board must optimise theatre allocation for trainers in gynaecology, aiming for a weekly session for consultants with a Gynaecology interest and fortnightly for the remainder | Additional theatre capacity has been granted to the General Gynae Team since HEIW last visit. |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Abigail Morris / Madhu Dey
|  |  |  | Second round of job planning to commence in September | Most Consultants have been or will be job planned in September. Awaiting Dates for 3 Consultants and 1 Consultant booked for the 1st week of October |  |  | COMPLETE | Update as of 4th of October 2024: The Health Board have set a target for all job plans to be completed by the end of October of which the service is currently working towards. This has been challenging due to commitments. Training opportunities have increased and trainees are rostered to attend theatre regularly as per individual training needs. The College Tutor meets with the Rota Co-ordinator on the weekly basis to ensure training sessions are prioritised. As shown in the below document: | The service is still working on the following however excellent progress has been made thus far, and completion of action should take place before the end of December: Allocation of further Theatres for Gynae services (additional lists in NPTH) Completion of Job Plan (18 out of 24) | Some meeting booked are second meetings and 1x due to BMA Rep needed to be in attendance. | All colleagues have recicved job plan meeting - will be updated yearly as normal job planning complaince | COMPLETE | Abigail Morris / Madhu Dey
|  |  |  | A paper was written for HEIW attention of the amount of Theatre activity has been allocated to each trainee |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Abigail Morris / Madhu Dey
|  |  |  | A training programme guide was discussed in Consultant Meeting to ensure the Educational Supervisor meetings had a log of monthly training opportunities provided to each trainee |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE |  | All Educational Supervisors
|  |  |  | ATSM sessions will now be highlighted on the rota and trainee's will only be pulled as a last resort |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Abigail Morris / Sarah Madden
2024-07-01 | 4 | Requirements | The Health Board must ensure that the handover for post-operative patients is in person and part of the Obstetrics and Gynaecology handover. | Standard operating procedure being reviewed and will be re-written as appropriate | Standard Operating Procedure is currently being rewritten. There will be 2 SOPs, provisions for Singleton have been agreed and is signed off, handover issues that were highlighted have been resolved. |  |  |  | This action has now been resolved. Standard Operating Procedure is currently in place and handover issues that were highlighted have been resolved. |  |  |  | August 2024 | Abigail Morris / Madhu Dey
|  |  |  | The Clinical Director updated all senior clinicians of these requirements at the Consultant meeting on 15/07/2024 and reinforced the need for appropriate handover of all post-op patients. |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Madhu Dey
2024-07-01 | 5 | Requirements | The Health Board must ensure that ST2 (specialty training year 2) trainees have step up sessions on labour ward in preparation for ST3. | The current ST2 trainees have been provided with regular step up sessions between April-July but unfortunately one of the trainees took 6 weeks of leave in May and June 2024 (annual leave/study leave/ rota week off) and will receive 10 step up sessions by the end of July. The other trainee took 3 weeks of leave off in May and June (see attached summary document) and will receive 16 step up sessions by the end of July. |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Charity Knight
2024-07-01 | 6 | Requirements | The Health Board must ensure that sessions for ATSMs (Advanced Skills Training Modules) and the forthcoming replacement SITMs (Special Interest Training Modules)) are clearly identified on the rota to ensure there is minimal disruption of them. | The College Tutor has confirmed with the Rota Manager that all ATSM/ SITM sessions will be highlighted on the weekly rota and that these training opportunities will be prioritised. |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Charity Knight
2024-07-01 | 1 | Recommendations | The Health Board should continue to ensure that antenatal clinics are appropriately supervised according to trainee grade, experience, and confidence. | The College Tutor and the SHO Tutor will continue to meet the Rota Manager on a weekly basis to review the rota and ensure each trainee receives the appropriate level of support/ supervision in antenatal clinic (based on their individual training, experience and confidence.) |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Charity Knight / Abdi Ali
2024-07-01 | 2 | Recommendations | The Health Board should ensure that speciality trainees have their formal monthly Educational Supervisor meetings, which are recorded on the portfolio. Time should be available for trainees and trainers on the roster for these meetings. | The College Tutor has updated all Educational Supervisors (02/08/2024) to remind them of their HEIW (GMC) ES requirements including the need for an induction meeting within the first 2 weeks of trainees starting and monthly meetings from then onwards. The College Tutor will monitor this through informal enquires at Trainee Forum and review of trainee portfolios. |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Charity Knight
2024-07-01 | 3 | Recommendations | The Health Board should ensure that trainees are rostered to specialist clinics to ensure access to a breadth of training. | The College Tutor and the SHO Tutor will review this at the weekly meetings with the Rota Manager and ensure all trainees receive adequate opportunities to attend specialist clinics. |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Charity Knight / Abdi Ali
2024-07-01 | 4 | Recommendations | The Health Board should ensure that the Standard Operating Procedure (SOP) for Gynae-oncology out of hours is reviewed for clarity and monitored for compliance. | The SOP was introduced to ensure safe patient care out of hours in Singleton Hospital. The SOP was shared with all Consultants (ES) in April 2024 who were advised to discuss with their trainees, feedback received in an email from one trainee was considered and changes were made to the SOP accordingly. The Clinical Director discussed the introduction of the SOP for Gynae-oncology out of hours cover at the Consultant Meeting which has representative from the Registrar team on 21/06/24 and addressed the specific concerns raised by the Trainee Rep. Reassurance was given by the on call Consultant group, who will fully support the trainees with providing out of hours care. Discussed again in Consultant meeting following HEIW visit in July, expressed the importance of each Consultant to provide the support. |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Abigail Morris / Madhu Dey
2024-07-01 | 5 | Recommendations | The Health Board should ensure there is support for the College Tutor to aid them in improving the environment, culture, and communication with trainees. A meeting with HEIW will be organised to help facilitate this. | The College Tutor has been in contact with HEIW and will arrange a meeting with the Director of Quality Management. The College Tutor has met with the Head of School (EHK) to receive his input, advice and support. (24/7/24.) |  |  |  | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | August 2024 | Charity Knight
HEIW TO REVIEW IN 6 MONTHS TIME: DUE JAN 2025

## HEIW Targeted Visit APRIL 2025
Date | Action No | Requirement OR Recommendations | Narrative of Action | GMC Requirement Description | Actions | Current Status | Target Risk | Target Date | Action Lead
April 2025 | 1 | Requirements | The Health Board must ensure that handover is robust, comprehensive and effective at all times so that on-call residents are aware of patients on the ward. This includes:​ Patients who have had gynae oncology surgery.​ Patients commissioned by external teams.​ ​ | GMC Requirement R1.14 Handover of care must be organised and scheduled to provide continuity of care for patients and maximise the learning opportunities for doctors in training in clinical practice. | General gynaecology handover takes place as normal practice which is face to face. New handover process embedded for Gynae-Oncology Patients as per attached Standard Operating Procedure. An attachment is included to demonstrate the level of handover currently taking place which is also emailed to on-call Gynae along with a telephone call. Agreement for HEIW requirements to be raised in the Trainee Forum on a regular basis to ensure compliance with requirement is made. Directorate Manager is also copied in to all handover emails |  |  | COMPLETE | Nagindra Das & Madhu Dey
[5 empty] | Insourcing Team will hand over all patients to on-call teams over the weekend. Is now normal practice. |  |  | COMPLETE | Madhu Dey & Abigail Morris
[5 empty] | Private Patient List will handover all patients over the weekend. Is now normal practice. |  |  | COMPLETE | Madhu Dey & Abigail Morris
April 2025 | 2 | Requirements | The Health Board must make certain that concerns regarding inappropriate behaviours are managed effectively, with clear evidence of a positive change in behaviour with appropriate feedback provided in a timely manner.​ | GMC Requirement R3.3 Learners must not be subjected to, or subject others to, behaviour that undermines their professional confidence, performance or self-esteem. | Service has clear reporting structures in place for managing inappropriate behaviours and actions following raised concerns will be explicit and explained wherever possible, acknowledging confidentiality in some instances. Agreement is in place for Medical Director or AMD for Professional Concerns to visit the department and explain the process around raising concerns and HB approach when dealing with such concerns when escalated to Health Board level. Service to share governance structure and Educational Supervisors to discuss this as a part of ES Sessions. All Educational Supervisors have been informed of this responsibility in the consultant meeting on the 16th of April 2025. ESs will have ensure that resident doctors are able to raise any concerns through them as well as the college tutor and the clinical leadership team. Further discussion to be undertaken in consultant meeting in May 2025. A recent email is attached to evidence the 'You said, we did" approach used, where we are actively engaging with our trainees and informing them of the changes that have been made. |  |  | COMPLETE | Charity Knight, Madhu Dey & Abigail Morris
April 2025 | 3 | Requirements | The Health Board must ensure that where residents are allocated to theatre, training opportunities must be available and delivered. Theatre sessions in which training opportunities are not available should not have residents allocated, and where necessary, incidence should be minimised. | GMC Requirement R1.12 Organisations must design rotas to: a) make sure doctors in training have appropriate clinical supervision b) support doctors in training to develop the professional values, knowledge, skills and behaviours required of all doctors working in the UK c) provide learning opportunities that allow doctors in training to meet the requirements of their curriculum and training programme d) give doctors in training access to educational supervisors e) minimise the adverse effects of fatigue and workload. | Service has recently adopted '6:4:2 theatre scheduling' which will allows advanced theatre scheduling and to support planning in theatres and theatre opportunities. There has been discussion on converting some lists to be teaching only lists and to be reviewed as a part of the current rota meetings held with Course Tutor. Additional gynaecology theatre sessions have been implemented over the past 6 months to ensure trainees receive regular training opportunities (with a log book of all training sessions recorded by the Rota coordinator for each Resident doctor.) Where possible, training opportunities are offered to Resident doctors; however when cases are of a high complexity, the College Tutor has asked all Educational/Clinical supervisors to explain to trainees why they are not able to be actively involved in the procedure but can still gain valuable learning and reflection from observing or assisting in these procedures. |  |  | COMPLETE | ALL
April 2025 | 4 | Areas for Improvement | GPST Residents being moved away from clinics to support overrunning theatre lists. | Not Applicable | This is not a formal departmental policy however, our rota co-Ordinator to monitor this moving forward/complete an audit. Audit to be completed in July/August with high rate of leave to provide learning. On rare occasions, trainees will be requested to support in alterative sessions, all requests are discussed with trainees before making these arrangements. We will also raise this specifically in the trainee forum. |  |  | End of August | Charity Knight, Madhu Dey & Abigail Morris
April 2025 | 5 | Areas for Improvement | Departmental interactions within theatre settings. | Not Applicable | Discussed in Consultant Meeting in April 2025. Where possible, training opportunities are offered to Resident doctors; however when cases are of a high complexity, the College Tutor has asked all Educational/Clinical supervisors to explain to trainees why they are not able to be actively involved in the procedure but can still gain valuable learning and reflection from observing or assisting in these procedures. This will allow the team to manage expectations when attending theatres. |  |  | COMPLETE
April 2025 | 6 | Areas for Improvement | Recording of concerns and timely feedback following review. | Not Applicable | As described under requirement 2 |  |  | COMPLETE | Madhu Dey & Abigail Morris
April 2025 | 7 | Areas for Improvement | Prioritisation of learning opportunities during theatre procedures. | Not Applicable | As described under area of improvement 5 |  |  | COMPLETE
NEXT MEETING PLANNED AUTUMN 2025