| Meeting Date | 16 June 2026 | Agenda Item | 3.5 |
| --- | --- | --- | --- |
| Name of Meeting | Workforce and Organisational Development Committee |  |  |
| Report Title | Organised for Success Programme Update |  |  |
| Report Author | Dr Matt Lewis Programme Lead |  |  |
| Report Sponsor | Executive Director of Workforce and Organisational Development |  |  |
| Presented by | Tina Ricketts, Executive Director of Workforce and OD |  |  |
| Freedom of Information | Open |  |  |
| FoI Closed detail | Confidential – Workforce |  |  |
| Impact Assessment Summary Outcome |  | IA Completion date |  |
| In development |  | 30 June 2026 |  |
| Purpose of the Report | For Assurance |  |  |
| Report Summary; detailing any action required |  |  |  |
| This report provides an update on the Organised for Success (O4S) programme and sets out the proposed reset and forward plan. It seeks support to delay the full implementation of the new Care Group model until 1st April 2027 with shadow arrangements in place from 1st January 2027. A roadmap has been developed (Appendix A) that sets out clear milestones and outputs for the programme with regular gateway reviews built in. The Executive Team have committed to supporting the achievement of these milestones to ensure confidence in the programme going forward. The care croup triumvirate job descriptions for a clinically led model are attached to the report for any final comments. |  |  |  |
| Key Issues |  |  |  |
| - Programme progress has been impacted by competing demands and leadership changes, which have required the programme to revisit previous decisions. - The successful establishment of a Delivery Unit will provide increased grip and coordination to support this programme. |  |  |  |
| Decision / Action required | No |  |  |
| Recommendations |  |  |  |
| Members are asked to consider the following items: - To support the proposed reset and sequencing of the organised for success programme - To support the development of one operating model, with MDT input, that meets the following targets: - Clinically led leadership model - Delayered management structure - More cost-effective than the current structure (after pay protection). - To acknowledge the risks and mitigation, including operational stability if further set backs are encountered. |  |  |  |

Organised for Success

- INTRODUCTION

The Organised for Success programme is a strategic transformation programme to redesign organisational structures, improve accountability and support the delivery of financial sustainability.

- Key Issues

The programme has progressed Phase 1 (Executive portfolios and Delivery Unit mobilisation) and is advancing Phase 2 (Care Group structure and leadership model).

2.1 Current Position

| Phase | Description | Status |
| --- | --- | --- |
| A | Executive Portfolios | Stage 1 completed |
| B | Deputy/ Tier 2 Management Structure | In progress |
| C | The Establishment of a Delivery Unit | In progress |
| D | Joint Posts across the Regional Partnership | Not started |
| E | The establishment of a new care group structure | In progress |
| F | A review of the care group leadership structure – confirming the Triumvirate Leadership model (e.g., operationally led or clinically led) | In progress |
| G | A review of the number of divisions or directorates within each new care group to ensure spans of control are reasonable and equitable. This will include a review of the specialities and services managed under each of the care groups to ensure they are organised in the best way for our patients | In progress |
| H | A review of the number of management layers within the new care groups with the aim to have a maximum of 6 layers, where appropriate, from Board to front line staff with a focus for this programme on the top 4 layers (Tri, Division, Directorate, speciality/ service) | In progress |
| I | A review of the wraparound support for each new care group (e.g., HRBP, Finance BP) to ensure this is reasonable and equitable | In planning |
| J | A review of corporate functions sitting in/ out of care groups to ascertain the most appropriate design of the function (e.g., hub and spoke, centralised) | Not Started |

2.2 Proposed Delivery Approach

The proposed outputs and key milestones are set out in the road map in Appendix A.

The roadmap sets out clear milestones and outputs with regular gateway reviews built in. The Executive Team has committed to supporting the achievement of these milestones to ensure confidence in the programme going forward.

2.3 Clinically Led Triumvirate Job Descriptions

The care croup triumvirate job descriptions for a clinically led model are attached to the report for any final comments.

- GOVERNANCE AND RISK ISSUES

| Key Risks | Current risk rating | Mitigating Actions | Risk Owner |
| --- | --- | --- | --- |
| There is a risk that the implementation of the programme will be delayed due to lack of programme management capacity | 6 (reduced) | Programme Lead appointed and commenced full-time on 2nd January 2026 Delivery Unit mobilisation increasing PMO, transformation and improvement capacity. Further resource requirements to be reviewed as part of next phase planning. | Director of Workforce & OD |
| There is a risk that the challenging timelines of the programme will not be met due to senior colleagues not seeing this programme as a priority/ not releasing the required resource | 12 | The resourcing of the programme will be overseen by the Steering Group. The establishment of a central delivery unit has been incorporated in phase 1 of the programme. This will be responsible for ensuring that all key HB programmes are adequately resourced. | Director of Workforce & OD |
| There is a risk that the operational performance of the Health Board is negatively impacted as colleagues become distracted with the programme/ associated organisational change processes | 12 | Operational performance will be overseen by the central delivery unit. The establishment of a delivery unit has been incorporated in phase 1 of the programme. Gateways are being developed for each phase of the programme so that a decision can be made on whether we can “go” safely. The criteria for each gateway will be shared with the Board for approval. | Chief Operating Officer |
| The programme will require a restructure of our budgets and corporate systems (e.g., the Electronic Staff Record System). There is a risk that this may limit the capacity of the corporate teams to work on other priorities. | 12 | Three ready groups have been set up with one focused on the restructure of our budgets and corporate systems. Regular updates on progress will be provided to the Steering Group. The impact on other priorities will be managed through the delivery unit. | Director of Workforce & OD |
| Delay to programme delivery due to a lack of clarity on final organisation design and sequencing | 16 New | Executive steer on direction and sequencing scheduled for 10th June 2026. Structured gateways in place to ensure decision are made at defined points prior to progression and then progressed. | Chief Operating Officer |
| Financial uncertainty due to incomplete validation of current model and therefore an inability to cost future model benefits. | 16 New | Validation exercise (O4S, finance, HR) to confirm the baseline structure and cost. Delivery of fully costed current structure and future structure v3 as a key June milestone and gateway. | Director or Workforce & OD |
| Organisational resistance or loss of staff confidence due to prolonged uncertainty delays and lack of communication | 12 New | Clear communication of agreed roadmap and timelines. Early clarity on leadership structure and OCP process to provide certainty. Engagement through Ready Groups and leadership forums. | Director of Workforce & OD |
| Risk of misaligned sequencing (e.g., recruitment before design confirmation) leading to challenge or rework | 12 New | Reset programme sequencing: - Design - Cost - OCP - Recruitment - mobilisation. Executive overview required before progression to each stage. | Director of Workforce & OD |

- OPEN AUDIT RECOMMENDATIONS

None

- FINANCIAL IMPLICATIONS

Emerging modelling indicates potential savings of between £2m–£5.m from revised management structure (subject to assumptions and final validation).

Transitional costs (e.g., pay protection) are expected but time limited.

Final position dependent on:

  - Confirmation of organisational design

  - Workforce assumptions (e.g., Spans of control / WTE numbers).

- RECOMMENDATION

The Committee is asked to:

- Support the strategic direction and sequencing of the programme as set out in appendix A

- Support progression to a fully costed proposed organisational model that will be used for the organisational change process

- Note the risks and endorse the mitigations

- Agree that at this point a focused communications piece is required, and that a dedicated “Ask Abi” would support this and the wider ongoing communications work around Organised for Success.

| Governance and Assurance |  |  |
| --- | --- | --- |
| Strategic Objectives |  |  |
| Strategic Objectives (please choose which is impacted) | People of Swansea Bay live healthier, fairer and more prosperous lives | ☐ |
|  | Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | ☒ |
|  | Care is delivered in partnership with our communities in safe and appropriate setting, supported by innovation | ☒ |
|  | The health board is a great place to work where staff feel valued and work together towards a common goal | ☐ |
|  | The health board is a resilient, sustainable and responsible organisation | ☒ |
| Health and Care Standards |  |  |
| Standards (please choose which applies) | Safe Care | ☐ |
|  | Timely Care | ☐ |
|  | Effective Care | ☐ |
|  | Efficient Care | ☐ |
|  | Equitable care | ☐ |
|  | Person-centred Care | ☐ |
|  | Staff and Resources | ☒ |
| Enablers (please choose which applies) | Whole Systems Approach | ☒ |
|  | Leadership | ☐ |
|  | Workforce | ☐ |
|  | Culture | ☐ |
|  | Information | ☐ |
|  | Learning, Improvement and Research | ☐ |
| Quality, Safety and Patient Experience |  |  |
| None identified |  |  |
| Financial Implications |  |  |
| Emerging modelling indicates potential savings of between £2m–£5.m from revised management structure (subject to assumptions and final validation). Transitional costs (e.g., pay protection) are expected but time limited. Final position dependent on: - Confirmation of organisational design - Workforce assumptions (e.g., Spans of control / WTE numbers). |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |
| None identified |  |  |
| Staffing Implications |  |  |
| As set out in the report. |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |
| Not applicable |  |  |
| Report History |  |  |
| Executive Board 10th June 2026 |  |  |
| Appendices |  |  |
| - Programme Road Map; Dated 3rd June 2026 - Care Group Triumvirate Clinically Led Job Descriptions |  |  |