## Mental Health & Learning Disabilities Service Group Staff Wellbeing Plan 2026

# Executive Summary

The Mental Health & Learning Disabilities Service Group continues to face workforce challenges associated with sickness absence, staff wellbeing, retention, recruitment pressures and increasing demand for services.

Previous Service Group wellbeing and resilience work has highlighted the importance of attendance management, staff support, wellbeing promotion and the development of resilient teams. The purpose of this paper is to provide a focused wellbeing plan that supports improved staff experience, reduced absence and enhanced workforce sustainability.

The proposed plan aligns with existing Health Board wellbeing priorities, including Occupational Health and Staff Wellbeing services, wellbeing champions, health passports, staff health checks and leadership development initiatives.

# Background

A number of Health Board initiatives are already in place to support staff wellbeing, including:

- Staff Health Checks and wellbeing programmes.

- Health and Wellbeing Passport arrangements supporting staff with health conditions and disabilities.

- Occupational Health and Staff Wellbeing mental health support pathways.

- Wellbeing Champion networks across the organisation.

- Trim / React

- Bespoke groups including GTEP, carers group, bereavement group

- Staff networks including the Disability staff network

- Learning, leadership and workforce development opportunities linked to the People Strategy.

In addition the service group employs a staff counsellor to provide individual support and group interventions to support staff wellbeing this is also supplemented by support from Psychologists who work closely with teams around psychological safety and reflective practice. The service group due to geographically challenges also utilise wellbeing champions and utilise their own flu champions. Sickness Absence Summits are held on a monthly basis to capture and share wellbeing initiatives for staff.

The Service Group wishes to strengthen local arrangements and confirm governance and performance monitoring through current Quality & Governance structure which each division reports on staff wellbeing monthly. With concerns being escalated from this group to SMT. Staff wellbeing will also continue to be reviewed in monthly Divisional Meetings and through quarterly Divisional Performance Reviews undertaken by the SMT.

# MH&LD Staff Wellbeing Action Plan 2026/27

| Priority | Action | Lead | Milestone | Measure | RAG |
| --- | --- | --- | --- | --- | --- |
| Psychological Wellbeing | Introduce quarterly wellbeing conversations within all teams | Directorate Leads | Dec 2026 | 100% teams participating | 🟠 |
| Wellbeing Champions | Expand MH&LD Wellbeing Champion network | Directorate Leads | Dec 2026 | Champion identified in all Directorates | 🟢 |
| Attendance & Resilience | Review sickness hotspots monthly and implement targeted interventions | Workforce Team | Monthly | Reduction in sickness absence rates | 🟠 |
| Mental Health Support | Improve awareness of Occupational Health and psychological support services | Managers / Workforce OH&WB | Jan 2027 | Increased support uptake | 🟢 |
| Health Promotion | Increase uptake of staff health checks and wellbeing events including flu vaccinations | Managers, / Workforce OH&WB Team | Mar 2027 | 15% increase in participation | 🟠 |
| Health Passport | Promote Health and Wellbeing Passport across MH&LD services | Directorate Leads | Mar 2027 | Increased utilisation | 🟢 |
| Leadership Support | Deliver wellbeing and compassionate leadership development, links established with USW | Learning & OD | Mar 2027 | Manager attendance and completion rates | 🟠 |
| Retention & Development | Expand mentoring, coaching and career pathways together with clinical / operational supervision | SMT Leads | Mar 2027 | Improved retention indicators | 🟠 |
| Staff Voice | Quarterly listening events and "You Said, We Did" feedback in line with feedback from staff survey, and other mechanisms in place for staff to speak up safely | SMT | Quarterly | Improvement in engagement measures | 🟢 |
| Recognition | Continue with monthly recognition videos and consider ntroducing quarterly staff recognition programme | Directorate Teams | Jan 2027 | Positive staff feedback | 🟢 |

# Key Performance Indicators

# The following indicators will be monitored quarterly:

| Indicator | Target |
| --- | --- |
| Sickness Absence Rate | Year-on-year reduction |
| Stress Related Absence | Year-on-year reduction |
| Staff Turnover | Reduction |
| Vacancy Rate | Reduction |
| Staff Survey Measures | Improvement |
| Health Check Participation | Increase |
| Wellbeing Champion Coverage | 100% |
| Health Passport Utilisation | Increase |
| Staff Engagement Measures | Improvement |

# Risks

| Risk | Mitigation |
| --- | --- |
| Limited staff engagement | Strong communication (social media, service group email, communication strategy and leadership support |
| Operational pressures affecting attendance at wellbeing activities | Flexible delivery methods and protected time where possible |
| Variable implementation across Directorates | Quarterly SMT monitoring and accountability |
| Sustained workforce pressures affecting wellbeing | Early intervention and targeted support arrangements |

# Financial and Workforce Implications

The majority of actions will be delivered through existing Occupational Health, Staff Wellbeing, Workforce and Learning & OD resources. Existing Health Board wellbeing programmes and support services will be utilised wherever possible. In addition the Service Group has established support from USW to deliver leadership modules for leaders supporting transformation work. The Service Group employs a permanent Counsellor and staff are trained and provided with release to support TRIM incidents. In addition staff reflect and support each other through MDT's which include psychological support.

# Conclusion

The proposed Wellbeing Improvement Plan provides a structured framework for improving staff wellbeing, attendance, engagement and retention across the Mental Health & Learning Disabilities Service Group. The plan builds upon existing Health Board wellbeing initiatives and introduces local governance arrangements to ensure delivery and measurable improvement.