Strategic Risk Register

September 2026 Detail

Risks assigned to the

Workforce & OD Committee

| Risk ID Number SRR-4.1 | Risk Label – Staff Health & Wellbeing and Organisational Performance Risk Description – If the Health Board does not improve workforce wellbeing, attendance and resilience during a period of sustained operational pressure and significant organisational change, then sickness absence, reduced engagement and diminished workforce capacity may persist or worsen, resulting in reduced productivity and service-delivery capacity, increased temporary staffing costs, poorer patient and staff experience, adverse quality outcomes and reduced ability to deliver transformation and strategic objectives. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | The health board is a great place to work where all staff feel valued and work together towards a common goal |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 4 | 4 | 16 |  | Lead Director / Risk Owner | Director of Workforce & OD |
| Current Score | 4 | 4 | 16 |  | Monitoring Committee | Workforce & OD Committee |
| Target Score | 2 | 4 | 8 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 25 | Dec 25 | Feb 26 | Apr 26 | Jun 26 | July 26 | Aug 26 | Sept |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - | - | - | - | - | 12 | 12 | 16 |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Title | Score |
| 64 | Health & Safety Infrastructure | 16 |
| 109 | Access to Planned Care | 12 |
| 110 | Access to Cancer Care | 20 |
| 114 | Mental Health & Learning Disabilities Staffing | 20 |
| 117 | Access to Timely Urgent & Emergency Care | 20 |
| 120 | Restrictions on Admin & Clerical Recruitment | 12 |
| 121 | Health & Safety of Staff | 16 |
| 123 | Nursing Staffing Levels / Templates | 12 |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | People Strategy aligned to organisational priorities |
| 2 | Staff Health & Wellbeing Plan |
| 3 | Managing attendance at work national policy and escalation processes |
| 4 | Monthly workforce performance dashboard, including sickness heatmaps, return-to-work compliance, wellbeing outcomes, turnover, vacancies, temporary staffing use, staff survey trends and stress risk-assessment completion. |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | People Strategy progress reports coordinated by corporate Workforce and monitored through Executive Board. |  |  | Reasonable |
| 2 | Health & Wellbeing Plan developed and delivered through Workforce Transformation Group. |  |  | Limited |
| 3 | Monthly reporting through Care Group and corporate performance reviews on sickness trends, policy triggers, formal case-management stages and return-to-work compliance, with targeted support and named management accountability in hotspot areas. | Corporate Workforce compliance review reported to Executive Board and Workforce and OD Committee. The September Board discussion identified return-to-work completion of approximately 36% against an expectation close to 100%, indicating that this control is not being applied consistently. |  | Limited |
| 4 | Trend data included in Integrated Performance Report for review by Executive Board. |  |  | Reasonable |
|  | Current Overall Assurance Rating |  |  | Moderate |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Incomplete assurance on policy application and workforce outcomes, including low return-to-work compliance, inconsistent reporting of formal attendance stages, and insufficient evidence that wellbeing interventions are improving absence, engagement and service capacity. | Explore marketplace for solution that enables the tracking of live sickness absence data. Implement a validated monthly sickness heatmap and live attendance dashboard by Care Group and corporate function; report return-to-work compliance, policy-stage data, wellbeing outcomes, staff survey trends and stress risk-assessment completion; provide targeted support to hotspot areas and escalate where absence rises, wellbeing deteriorates, service delivery is materially affected or controls do not improve the trajectory. | Director of Workforce & OD | 31/12/26 | Refreshed plan in development |
| 2 | Variation in management capability impacting staff experience | Targeted leadership development and assurance framework | Director of Workforce & OD | 31/12/26 | On track |

Additional Comments

24/09/2026: Updated following Board scrutiny of rising sickness absence, workforce resilience, return-to-work compliance and the need for clearer outcome-based assurance.

| Risk ID Number SRR-4.4 | Risk Label – Culture Risk Description – If the Health Board does not develop and sustain the leadership capability, behaviours and succession capacity required for a high performance culture, then leaders may be unable to create the values-based culture, engagement and accountability needed to manage performance and change effectively, resulting in inconsistent decision-making, reduced staff confidence, failure to improve organisational culture and delay or failure in delivery of strategic objectives. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | The health board is a great place to work where all staff feel valued and work together towards a common goal |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 4 | 4 | 16 |  | Lead Director / Risk Owner | Director of Workforce & OD |
| Current Score | 4 | 3 | 12 |  | Monitoring Committee | Workforce & OD Committee |
| Target Score | 3 | 3 | 9 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 25 | Dec 25 | Feb 26 | Apr 26 | Jun 26 | July 26 | Aug 26 | Sep 26 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - | - | - | - | - | 12 | 12 | 12 |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Title | Score |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | People Strategy |
| 2 | Intentional culture change programme (in development) |
| 3 | Organised for Success Programme |
| 4 | National leadership competency framework; values-based leadership standards; leadership development and Top 100 Leaders programmes; PADR quality arrangements; talent management and succession planning aligned to the future Care Group operating model. |
| 5 | Speak Up / Raising Concerns framework |
| 6 | Engagement through partnership forums and staff groups |
| 7 | Staff survey |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | Reporting on delivery against People strategy to Executive Board and WOD Committee. |  | Internal Audit Review: Staff Retention 2025/26 (Reasonable Assurance) | Reasonable |
| 2 | Reporting on Culture Change Programme to Executive Board, WOD Committee and Board. |  |  | Unsatisfactory (Not started) |
| 2 | Staff survey outputs reviewed and reported to Executive Board, WOD Committee and Board. |  |  | Reasonable |
| 3 | Organise for Success and leadership-capability reporting to Executive Board, Workforce and OD Committee and Board, including programme milestones, leadership readiness, staff engagement and wellbeing trends, benefits realisation and evidence that cultural and leadership outcomes accompany structural change. |  |  | Reasonable |
| 4 | Monitoring of concerns raised through the Speak up Safely route. |  | Internal Audit Review: Speaking Up Safely 2024/25 (Limited Assurance) | Reasonable |
| 5 | Partnership forum governance & oversight |  |  | Reasonable |
|  | Current Overall Assurance Rating |  |  | Moderate |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Lack of consistent culture metrics | Develop culture dashboard & KPIs | Director of Workforce & OD | 31/03/27 | On track |
| 2 | Variation in leadership capability and succession readiness, with limited evidence that leadership interventions, behavioural frameworks and Organise for Success activity are delivering measurable cultural improvement or return on investment. | Implement competency assessments, PADR quality indicators, leadership-programme participation and outcome measures, succession-readiness reporting and formal evaluation of benefits and return on investment. Escalate where competency expectations are not met, PADR quality remains weak, critical succession gaps persist or development activity does not demonstrate measurable benefit. | Director of Workforce & OD | 31/12/26 | On track |
| 3 | Limited triangulation of intelligence | Integrate survey, ESR & Speak Up data | Director of Workforce & OD | 31/03/27 | On track |

Additional Comments

24/09/2026: Updated following Board scrutiny of leadership capability, values-based culture, succession readiness and the need to demonstrate the impact and return on investment of leadership interventions. Current and target scores retained pending formal reassessment.

| Risk ID Number SRR-5.2 | Risk Label – Workforce (Sustainability) Risk Description – If the Health Board does not secure a workforce of the right size, shape, skills and affordability, , then workforce gaps, unsustainable staffing models, prolonged absence and reliance on temporary staffing may persist, resulting in reduced service capacity, increased workforce cost, impaired quality and patient experience, and failure to deliver transformation, financial recovery and longer-term sustainability. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | The health board is a resilient, sustainable and responsible organisation |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 5 | 4 | 20 |  | Lead Director / Risk Owner | Director of Workforce & OD |
| Current Score | 5 | 4 | 20 |  | Monitoring Committee | Workforce & OD Committee |
| Target Score | 5 | 2 | 10 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 25 | Dec 25 | Feb 26 | Apr 26 | Jun 26 | July 26 | Aug 26 | Sep 26 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - | - | - | - | - | 20 | 20 | 20 |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Title | Score |
| 3 | Recruitment of Consultant Medical and Dental Staff | 12 |
| 64 | Health & Safety Infrastructure | 16 |
| 89 | Healthcare Nursing Staff Levels at HMP Swansea | 20 |
| 109 | Access to Planned Care | 12 |
| 110 | Access to Cancer Care | 20 |
| 114 | Mental Health & Learning Disabilities Staffing | 20 |
| 117 | Access to Timely Urgent & Emergency Care | 20 |
| 120 | Restrictions on Admin & Clerical Recruitment | 12 |
| 122 | Staffing Models | 12 |
| 123 | Nursing Staffing Levels / Templates | 12 |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Annual workforce planning process |
| 2 | Establishment control including approval processes for posts and recruitment panels through workforce boards |
| 3 | Use of variable pay monitored through workforce boards |
| 4 | Organise for Success programme governance, benefits framework, workforce and equality impact assessments, change-management arrangements, and staff engagement monitoring. |
| 5 | Service redesign and new care models supported by demand and capacity modelling, workforce impact assessment, financial appraisal and benefits-realisation measures linking staffing changes to quality, productivity and patient outcomes. |
| 6 | Annual skills gap analysis |
| 7 | Annual Training Plan |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | Care Group and corporate workforce plans consolidated by the Workforce function and reported to Executive Board, with assurance on demand, establishment, skills, affordability, succession, temporary staffing dependency |  |  | Reasonable |
| 2 | Corporate workforce reporting to Executive Board of recruitment activity and application of approval process |  |  | Reasonable |
| 3 | Corporate workforce reporting on bank and agency staffing to Executive Board |  |  | Reasonable |
| 5 | Oversight of service redesign and delivery of change through Delivery Unit |  |  | Limited |
| 6 | Completion of annual skills gap analysis |  |  | Unsatisfactory (not started) |
| 7 | Development of annual training plan |  |  | Limited |
|  | Current Overall Assurance Rating |  |  | Moderate |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Lack of long-term workforce modelling including skills gap analysis | Develop strategic workforce plan | Director of Workforce & OD | 31/10/26 | On track |
| 2 | Reliance on temporary staffing | Reduce agency dependence programme | Director of Workforce & OD, Director of Nursing, Medical Director | 31/03/27 | On track |
| 3 | Mismatch of workforce to demand | Align workforce planning with demand modelling | Director of Planning / Director of Workforce & OD | 31/12/26 | On track |
| 4 | Limited evidence that workforce plans, management capability and staffing interventions are producing measurable improvements in service capacity, quality outcomes, productivity, attendance, temporary staffing dependency and financial sustainability. | Establish a monthly workforce-sustainability dashboard linking staffing to quality, productivity and financial outcomes; strengthen workforce modelling and manager accountability; evaluate benefits and return on investment from workforce interventions; and escalate where workforce gaps, absence-related costs or temporary staffing dependency increase, programme benefits are not realised or service and financial recovery milestones are adversely affected. | Director of Workforce & OD | 31/03/27 | On track |

Additional Comments

24/09/2026: Updated following Board scrutiny of workforce sustainability, management capability, Organise for Success dependencies and links to service, quality and financial outcomes. Current and target scores retained pending formal reassessment.

Key / Convention / Glossary

| Strength of Control |  | Level of Overall Assurance |
| --- | --- | --- |
| Substantial – The identified control(s) provide a strong mechanism for controlling the risk. Few matters require attention, which are advisory or compliance in nature. |  | Significant – Key governance, risk management and control processes in place provide significant assurance that the risk(s) is/are being managed effectively. Evidence demonstrates that systems and processes are being consistently applied and implemented. Outcomes are consistently achieved across all relevant areas. |
| Reasonable – The identified control(s) provide a reasonable mechanism for controlling the risk, albeit there is scope to strengthen this further. Some matters require management attention in control design or compliance. |  | Good - Key governance, risk management and control processes in place provide a good level of assurance that the risk(s) is/are being managed effectively. Evidence is available to demonstrate that systems and processes are generally being applied and implemented, but no across all relevant areas. Outcomes are generally achieved, but with inconsistences in some areas. |
| Limited – The identified control(s) provide only limited/partial mechanisms for controlling the risk. There are notable weaknesses which require management attention. |  | Moderate – Key governance, risk management and control processes in place provide moderate assurance that the risk(s) is/are being managed effectively. Evidence is available to demonstrate that systems and processes are being applied, but is insufficient to demonstrate implementation across all relevant areas. There is some evidence that outcomes are being achieved, but this is inconsistent and/or there are risks to current performance. |
| Unsatisfactory – The identified control(s) is/are not effective in providing a mechanism for controlling the risk. Action is required to address the whole control framework in this area. |  | Weak – Key governance, risk management and control processes in place provide only weak assurance that the risk(s) is/are being managed effectively. There is only limited evidence available that systems and processes are being applied or implemented. |

Lines of Assurance

First - This is the internal control environment put in place by Managers. It will typically include reports which detail their plans, performance monitoring data, and the results of local checks and reviews of controls within departments performing relevant day-to-day operational activities. Examples would include: - Results of compliance reviews undertaken within Departments/Functions, and reported to senior management - Progress and/or performance reports received by SDG Boards / Committee Sub-Groups

Second – This level of assurance is often referred to as organisational oversight. It is typically provided by Health Board corporate departments and functions which do not directly manage or deliver specific services, but which oversee and report on how controls are operating, thus providing a greater separation from day-to-day management. Typically, this level of assurance is typically provided to the Board or one of its committees (which allows Independent Members to bring an additional level of challenge and scrutiny), as well as to senior management groups (e.g., Management Board). Examples would include: - Reports on the results of Infection Control Audits undertaken by the IP&C Team - Reports on Fire Safety Audits - Progress and/or performance reports received by the Board or one of its committees

Third – This is independent assurance, which typically comes from outside the organisation. Examples would include reports received from: - NWSSP Audit & Assurance - Audit Wales - Healthcare Inspectorate Wales - Llais - Royal colleges

| Glossary of Register Fields & Their Use |  |
| --- | --- |
| Table / Field | Considerations for completion |
| Key Controls | What key controls/systems/processes/governance mechanisms do we already have in place to manage this risk? |
| Assurance on Control | What information do we have about the adequacy, effectiveness and application of each of our controls, where is it coming from, and what is it telling us? |
| Current Overall Assurance Rating | The Lead Director and/or nominated representative should state the overall level of assurance that can be taken and given regarding the effective management of this risk, having considered all of the information available regarding the adequacy, effectiveness and application of each of the controls in place, and any gaps identified. A convention is provided. |
| Gaps in Control and/or Assurance | Do we require further assurance that the key controls / systems / processes / governance mechanisms we have in place are working effectively? What more do we need to do to control this risk, that we are not already doing? |
| Actions to Address Gaps in Control and/or Assurance | What are we going to do, by when, to further manage and mitigate this risk? |