Afan Health Cluster

Integrated Medium Term Plan

(IMTP)

Annual Plan 2022 – 2023

Contents

1. CLUSTER OVERVIEW – PLAN ON A PAGE	1

2. FORWARD LOOK	2

SWOT ANALYSIS	3

3. VISION/MISSION STATEMENT	4

4. STRATEGIC BACKGROUND & PRIORITY AREAS	5

STRATEGIC BACKGROUND	5

STRATEGIC PRIORITY AREAS	8

5. CLUSTER NEEDS HIGHLIGHTS	10

SUMMARY	10

LOCALITY KEY FACTS	11

6. ACTION PLAN	13

7. GOVERNANCE ARRANGEMENTS	19

MEMBERS	19

8. CLUSTER ASSETS PROFILE	20

9. CLUSTER WORKFORCE PROFILE	21

10. CLUSTER FINANCIAL PROFILE	23

# 1. CLUSTER OVERVIEW – PLAN ON A PAGE

The following provides an at a glance summary of key actions planned by the cluster:

| IMPROVING PLANNED CARE | IMPROVING CANCER & PALLIATIVE CARE | IMPROVING UNSCHEDULED CARE |
| --- | --- | --- |
| - Promote COVID-19 vaccination programme to patients, carers, etc - Continue to engage in prescribing management schemes & improve antimicrobial stewardship - Increase awareness of Carers rights and needs and engage with the Carers Service | - Promote Help me Quit Level 3 service - Promote screening uptake - Improve end of life care for patients and patients families - Improve outcomes for USC patients - Improve access to most appropriate care | - Maximise referrals/sign posting to Common Ailments Scheme at Community Pharmacies - Research involvement of Afan Cluster in Virtual Ward model - Increase the use of Consultant Connect to support improved referral to treatment times |
| IMPROVING MENTAL HEALTH & LEARNING DIFFICULTIES | CHILDREN, YOUNG PEOPLE & MATERNITY | PREVENTION & REDUCING HEALTH INEQUALITIES |
| - Further development of the Cluster Mental Health Practitioner and Social Prescriber posts | - Support and work with the Specialist Health Visitor provision within the cluster | - Maximise engagement in Flu vaccination programme - Maximise engagement in Childhood vaccinations - Engage with public health screening programmes - Participation in the IRIS project across cluster membership - Identification and management of patients with pre-diabetes |

# 2. FORWARD LOOK

Dr Mark Goodwin

Afan Cluster GP Lead

Welcome to the Afan Cluster Integrated Medium Term Annual Delivery Plan for 2022-23. It reviews progress made in the first year of the IMTP 2020-2023 and sets out the Cluster’s delivery plan for 2022-2023. This is an honest reflection of the good and the yet to be good aspects of what has been achieved so far in Afan and what we aspire to in 2022-23.

As mentioned last year the Afan Cluster will continue to invest time and limited resources to a small number of projects that are of major importance, which the Cluster feels it can manage effectively rather than take on a plethora of “wishes” that so often well intentioned are ignored or later abandoned. We prefer to do a few tasks really well, learn from experience and the positivity of success and move on to a new topic.

We have continued Social Prescribing, Advanced Nurse Mental Health Practitioner, pre-diabetes, and now support five Physician Associates employed by our eight GP practices.

We recruited a Cluster Pharmacist only to see him snapped up by a practice within months and thus recruitment needs to start over.  Despite this, several practices via the pharmacist and PA’s have seen improved NOAC, warfarin and AF performance.

COVID has brought the Cluster closer, offering support in times of fear and possible threat and a rapidly evolving situation late 2020 early 2021, and in adopting new electronic access models, however, this has seen some practices overwhelmed by patient demand and they have reverted to telephone based models of access.

Two senior GPs including myself have reached retirement age and are being lost to the Cluster skill mix, therefore, younger new faces are being encouraged to make their mark.

The main irritations as Cluster Lead is the inability to migrate proven projects such as prediabetes, social prescribing and mental health practitioners into mainstream HB funding and thus recycle the limited Cluster funds to allow new innovation and test out more projects.  A sense of fatigue and overwork is more prevalent than ever, even amongst the most positive Cluster members.

The widening of Cluster members has seen some challenges in gaining planning momentum and decision-making, and the inability to recruit a Cluster Business & Implementation Manager or retain professional staff on short-term contracts continue to pose major difficulties.  I think time to allow Primary care to stand still and re group is needed.

## SWOT ANALYSIS

| STRENGTHS - Good working relationship between practices, other clinical disciplines and third sector organisations - Committed and experienced GP leads - Engagement from other health professionals and partners - Support from the Health Board on Cluster projects - Substantial Cluster Budget | WEAKNESSES - Cluster geography makes close working difficult - Achieving consensus is not always possible - No legal structure results in lack of autonomy and reliance on Health Board to employ staff; manage and release finances; procure goods and services etc. - Lack of capacity within Cluster to deliver programmes |
| --- | --- |
| OPPORTUNITIES - Increase collaboration - Development of MDTs and shared services - Alignment of policies and procedures - Explore other funding sources - Development of business plans based on evaluation - Working with other Clusters, via Pan Cluster working in relation to Acceleration Cluster Development | THREATS - Projects are dependent on WG funding which is annual - Disengagement if successful projects are not absorbed into core business, funded or rolled out by the Health Board - Practices facing sustainability issues may find it difficult to engage on a regular basis - COVID-19 and subsequent/frequent changes to working practices continues to be challenging |

# 3. VISION/MISSION STATEMENT

Our Vision

To enable communication between the right people at the right time, leading to cohesive working for the betterment of the population with provision of equitable services across the Network that are safe, timely and accessible

Our aims

Through the delivery of our plans we will work to meet the Quadruple Aims set out for Health and Social Care Systems in Wales in ‘a Healthier Wales’ (2018):

      - improved population health and wellbeing

      - better quality and more accessible health and social care services

      - higher value health and social care

      - a motivated and sustainable health and social care workforce

The Cluster will work collaboratively with Public Health to achieve the outcomes noted in the ‘Burden of Disease’ Action Plan by adopting the five ways of working as outlined in the Wellbeing of Future Generations Act. (Long term, integrated, involving, collaborative, prevention).

# 4. STRATEGIC BACKGROUND & PRIORITY AREAS

## STRATEGIC BACKGROUND

The Primary Care Model for Wales sets out how primary care will work within the whole system to deliver a place based approach. Our Cluster working is at the core of this to ensure care is better co-ordinated to promote the wellbeing of individuals and communities and will continue to be taken forward through the multi-disciplinary, multi-agency cluster planning teams reflecting all partner contributions.

The Cluster continues to focus resources on delivering the aims and aspirations of the Primary Care Model for Wales and to accommodate the delivery of improvements, our plan is flexible and will be underpinned by ongoing work to develop implementation and performance plans against the stated Goals, Methods and Outcomes Action Plan.

The 2022/23 Cluster IMTP is developed in alignment with national, regional and local strategic context and to address:

- COVID 19 Resilience

- Ministerial Delivery Milestones

- Local Primary Care Cluster Priorities

- Local Priorities influenced by Health Board IMTP, Regional Partnership Board, National Strategic Programmes and the Primary Care Model for Wales

- NHS Wales Planning Framework

- Framed within the context of the Well-being of Future Generations Act

- Social Services and Wellbeing Act 2014

- NHS Wales Decarbonisation Strategic Delivery Plan 2021-2030

As part of the process to develop this IMTP we have worked closely with Health Board colleagues to integrate with the Health Board IMTPs and planning arrangements, such as delivery plans for Cancer and Mental Health services, and under the context of The Clinical Services Plan (CSP) . The CSP remains the primary roadmap for the long-term delivery of services for our communities and Cluster planning and delivery remains aligned to the four CSP principles:

In Swansea Bay, Primary Care Clusters aim to:

- Work towards the Primary Care Model for Wales

- Prevent ill health

- Develop a range and quality of services in the community

- Ensure services in the community are better co-ordinated

- Improve communication and information sharing between professionals

- Facilitate closer working between community based and hospital services

- Support sustainability of primary care

Additionally, Cluster work is structured to encompass the Health Board’s overall Organisational Strategy as set out below in summary

The organisational strategies and priorities of a number of key regional partnerships are also accounted in our planning including:

- Swansea & Neath Port Talbot Wellbeing Plans

- The West Glamorgan Regional Partnership

- The Adult’s Transformation Board

- The Children and Young Adults’ Transformation Board

- The Integrated Transformation Board

## STRATEGIC PRIORITY AREAS

During the planning process, SBUHB Cluster leads considered the range of Health Board strategic priority areas, and agreed to focus their Cluster planning on a key range of six priority areas from those:

Improving Unscheduled Care

Improving Planned Care

Improving Cancer and Palliative Care

Prevention and Reducing Health Inequalities

Children, Young People and Maternity

Improving Mental Health and Learning Disabilities and the 7 goals

In addition the Cluster has mapped throughout its GMO Action Plan where work is undertaken which overlaps with the remaining HB Strategic Priority Areas, Ministerial Priorities (July 2021) and addressing the Four Harms of Covid.

Other SBUHB Strategic Priority Areas

- Responding to Covid  (including addressing the four harms of Covid)

- Improving Patient Quality and the 5 Q&S goals

- Improving Planned Care

- Increasing Digital Capability

- Improving primary, community and therapy services

Ministerial priorities refreshed in July 2021:

- A Healthier Wales - as the overarching policy context

- Population health

- Covid - response

- NHS recovery

- Mental Health and emotional wellbeing

- Supporting the health and care workforce

- NHS Finance and managing within resources

- Working alongside Social Care

Clusters have also given consideration to the enablers and programmes in place which will support facilitation of the plan and wider priorities set out above and have set these out at the end of the GMO action plan in section 6 below.

Finally, Clusters have also taken account of the Four Strategic Programme priorities and will continue to address these throughout the year:

-  Accelerated Cluster Development;

-  Urgent Primary Care;

-  Community Infrastructure and

-  Mental Well-being

Taking account of these priority areas ensures a robust approach to delivering safe, quality services and improving health population whilst maintaining the lighter touch approach requested for the development of the IMTPs in the annual delivery period prior to the implementation of the national Accelerated Cluster Development Programme. The ACD outline specification discussed nationally is currently being considered by Cluster Leads to identify key requirements and constraints into 2022-23 as an ongoing process, alongside Health Board and Local Authority discussions in the region.

# 5. CLUSTER NEEDS HIGHLIGHTS

## SUMMARY

Health Profile

- Chronic health conditions prevalence

  - COPD - 2.8%

  - Diabetes - 7.5%

  - Cancer - 2.8%

  - CVD - 3.15%

- Flu Immunisation uptake

  - 70% in patients 65+

  - 51% in patients <65 at risk

  - 57.5% in 2-3 year olds

- Smoking - prevalence is 29.23%

- Alcohol - aged 16+ with a record of alcohol intake is 82.85%

- Cervical Screening - uptake is 26.03%

- Exercise - 28.2% aged 16+ reported undertaking at least 30 minutes moderate exercise on five or more days in the previous week

- Healthy Diet - 30.4% aged 16+ reported consuming five or more portions of fruit or vegetables on the previous day.  Obesity rates are 13.3%

Service Demands

- Complexity - increasing number of patients presenting with comorbidities requiring long term care

- Sustainability - aging workforce, with inadequate succession plans in place

- Recruitment - difficulties in employing GPs and other Health Care Professionals

- Economics - low social economic area with pockets of deprivation resulting in high demand on health professionals

Other Influencing Factors

- Transport - Public transport is poor at the top geographical area of the cluster

- Estates - Primary care infrastructure is of variable quality across the cluster

- Housing/Employment - High levels of social housing and unemployment across the cluster

- Environment - Local Industry impacts on air quality in the lower geographical area of the cluster

## LOCALITY KEY FACTS

- The Afan Cluster servers a (GP registered) population of 50,505 (as at 01.04.2021) and is the fourth Largest cluster by registered population in the Health Board Area. (Source – NHS Wales Shared Services Partnership)

- It is 1 of 3 clusters within the county of Neath Port Talbot.

- Of the 20% most deprived LSOAs in Wales, 14 are within Neath Port Talbot, with 12 found within the Afan Cluster. (Source - https://wimd.gov.wales/geography/la/W06000012?lang=en#&min=0&max=10&domain=overall)

- This area consists of 34 LSOAs. 5.8% live in a Lower Super Output Area (LSOA) that is classified as rural (Source – IMTP 2020-2023)

- The Cluster geographically covers the wards: Glyncorrwg, Cymmer, Gwynfi, Pelenna, Bryn, Cwmavon, Port Talbot, Taibach, Margam, Baglan, Briton Ferry West, Sandfields West, Sandfields East and Aberavon (Source – Afan IMTP)

- Based on the projected population growth in Neath Port Talbot, provided in section 2, there is a forecast of 5.91% increase in population between 2018 – 2043. Based on the population in the Afan cluster area of 49,536 (as at 2018) (Population projections by local authority and year (gov.wales)) this could increase to 52,463.

- The Afan Cluster has approximately 10,505 people over the age of 65 years and over (20.8%) which is lower than the Welsh average of 21%. (Primary Source – Mid 2018 Population estimates (Source: Small area population estimates (2018), ONS) Secondary Source - Cluster IMTP

- The Cluster area has 8 GP practices (1 of which operates a branch practice).

- The locality has 13 community pharmacies.

- There are 8 dental practices that offer NHS treatment and 3 optometric practices.

- There are 9 care homes (Source - Cluster IMPT 2020 – 2023)

- There are 4 pharmacies in the Afan Cluster where services are available in English and Welsh.

- There is 1 hospital within the Afan Cluster; Neath Port Talbot Hospital

- According to the 2011 Census 15.3% of people aged 3 years and above in Neath Port Talbot are able to speak Welsh (Source: https://statswales.gov.wales/Catalogue/Welsh-Language/Census-Welsh-Language/welshspeakers-by-localauthority-gender-detailedagegroups-2011census)

- According to Neath Council Local Development Plan (2010-2026) it is estimated that a minimum of 198 homes will be built in the Afan Cluster

# 6. ACTION PLAN

How we developed this plan

Our plan is a flexible plan, informed by the strategic background and range of priorities, together with consideration of local needs highlighted above. It will be underpinned by ongoing work to develop implementation and performance plans against the stated Goals, Methods and Outcomes Action Plan. Future programmes of work such as those around Obesity Prevention, Diabetes prevention and Cancer, among others will be considered as the programme details evolve

Addressing Ministerial Priorities

A Healthier Wales – as the overarching policy context

Population Health

Covid Response

NHS Recovery

Mental Health and Emotional Wellbeing

Supporting the Health and Care Workforce

NHS Finance and Managing within Resources

Working Alongside Social Care

Strategic Priority Areas

Responding to Covid

Improving Patient Quality and the 5 Q&S goals

Improving Staff Experience

Improving Unscheduled Care

Improving Planned Care

Increasing Digital Capability

Improving Cancer and Palliative Care

Prevention and Reducing Health Inequalities

Children, Young People and Maternity

Improving primary, community and therapy services and the 6 priorities Primary and Community

Improving Mental Health and Learning Disabilities and the 7 goals

Key:

| - IMPROVING PLANNED CARE |  |  |
| --- | --- | --- |
| GOALS | METHODS | OUTCOMES |

| 1.1 | Responding to COVID-19 | - Promote COVID-19 vaccination programme to patients, carers, etc - Maintain up to date Business Continuity Plans | - Reduction of infection and mortality due to Covid-19 - Escalation of risk managed effectively to maintain patient safety |
| --- | --- | --- | --- |
| 1.2 | Improving Patient Quality and Safety | - Continue to engage in prescribing management schemes & improve antimicrobial stewardship and build relationships with HB / Cluster pharmacy advisers | - Reduction in inappropriate antibiotic prescribing |
| 1.3 | Meeting Carers needs | - Increase awareness of Carers rights and needs across Cluster members by engaging with the Carers Service - Individual Cluster member areas to have carers champions where possible - Explore projects that will support carers | - Improved staff training / skills / knowledge - Increased identification and support of Carers |

| - IMPROVING CANCER & PALLIATIVE CARE |  |  |
| --- | --- | --- |
| GOALS | METHODS | OUTCOMES |

| 2.1 | Improve EOL for patients and patient’s family | - Engage with Compassionate Communities Programme - Support Dying Matters weeks | - Better partnership working - Better outcomes for patients and families |
| --- | --- | --- | --- |
| 2.2 | Improve outcomes for USC patients | - Engage in Health Board Pre-habilitation project by supporting patients with USC referrals to make lifestyle changes | - Optimise patient health prior to treatment |
| 2.3 | Provide support to patients to quit smoking | - Promote Help me Quit to patients - Liaise with Pharmacy colleagues to increase engagement in Level 3 service - Ensure records of smoking status are up to date on patient records | - Increased referrals to Level 3 service - Reduction in smoking rates in cluster |
| 2.4 | Increase early diagnosis and treatment of cancers | - Promote screening uptake - Support early diagnostic centre | - Increased uptake to at least pre-COVID levels |
| 2.5 | Improve access to most appropriate care | - Accessing Dentist through Consultant Connect for more rapid feedback regarding dental cancer / dental care uncertainty, and reduction in referrals where unnecessary | - Reduction in Dental referrals |

| - IMPROVING UNSCHEDULED CARE |  |  |
| --- | --- | --- |
| GOALS | METHODS | OUTCOMES |

| 3.1 | Reduce demand on outpatients and support improved referral to treatment times | - Increase the use of Consultant Connect | - Improved communication between primary and secondary care - Patients treated in primary and community settings when most appropriate |
| --- | --- | --- | --- |
| 3.2 | Virtual Ward Model | - Cluster to research involvement in Virtual Ward model at a later date | - Reduction in unnecessary admissions to hospital - Improved access to identified geriatrician - Improved flow through step down from hospital step-up to Virtual Ward - Improved Advanced Care Planning - Improved Mental Health Provision - Supports discharge from Hospital |
| 3.3 | Enable patients to access most appropriate care | - Maximise referrals/sign posting to Common Ailments Scheme - Understand level of involvement for individual pharmacies and work to maximise use of service and a consistent approach across Community Pharmacies | - Increased referrals/sign posting - Increased uptake of CAS in Community Pharmacy - Reduced inappropriate appointments |

| - IMPROVING MENTAL HEALTH & LEARNING DISABILITIES |  |  |
| --- | --- | --- |
| GOALS | METHODS | OUTCOMES |

| 4.1 | Develop services to improve mental health and wellbeing of patients | - Monitor and evaluate the Cluster Mental Health Practitioner and Social Prescriber roles to ensure that patient needs are being met - Explore additional projects to address mental health and wellbeing needs of cluster population - Co-produce services with HB partners | - Increase in MDT provision - Better partnership working - Better outcomes for patients |
| --- | --- | --- | --- |

| - CHILDREN, YOUNG PEOPLE & MATERNITY |  |  |
| --- | --- | --- |
| GOALS | METHODS | OUTCOMES |

| 5.1 | Improve outcomes for the most vulnerable families within the NPT clusters | - Support and work with the Specialist Health Visitor provision within the cluster to ensure integrated approach to assessments, thresholds and referrals | - Increase in appropriate referrals - Decrease in inappropriate GP appointments |
| --- | --- | --- | --- |

| - PREVENTION AND REDUCING HEALTH INEQUALITIES |  |  |
| --- | --- | --- |
| GOALS | METHODS | OUTCOMES |

| 6.1 | Identify and manage patients who have pre diabetes | - Cluster based pre-diabetes programme ending with view to engage in HB funded project at a later date. | - Reduction in / delayed risk of onset of Type 2 diabetes |
| --- | --- | --- | --- |
| 6.2 | Maximise engagement in Flu vaccination programme | - Review IVOR data for flu vaccination - Develop and implement seasonal flu plan aimed at early administration of flu vaccine to eligible patients | - Increase in uptake in target group |
| 6.3 | Maximise engagement in Childhood vaccinations | - Maintain performance in uptake of childhood immunisations where targets achieved | - Increase in uptake in target group |
| 6.4 | Patients are engaging in Public Health screening programmes | - Practices will continue to engage with various Public Health screening programmes, i.e. smears, bowel cancer. | - Increase in uptake in target group |
| 6.5 | Identify and support patients experiencing domestic violence | - Engage in the roll out of the primary care IRIS project - Extend the roll out of the project to wider cluster members. | - Increase in appropriate referrals - Reduction in inappropriate appointments with GPs - Improved staff skills / knowledge |

| - ACTION PLAN ENABLERS |  |  |  |
| --- | --- | --- | --- |
| Technological | Workforce | Communication & Engagement | Finance |
| Ask My GP | Cluster Pharmacist | Twitter, Facebook, Websites | WG Funding |
| Footfall | Mental Health Practitioner | Partnership Working | Health Board funding |
| Message My GP | Social Prescribers | Emergency Planning Response and Resilience |  |
| Vision 360 | Specialist IT Support | Induction Pack for New Cluster members |  |
| My Health Online | Business Implementation & Development Manager | Patient Engagement |  |
| My Surgery App | Specialist Health Visitor |  |  |
| Attend Anywhere | Audiology |  |  |
| Consultant Connect | Cluster Lead |  |  |
| Microsoft Teams | Cluster Members |  |  |
| QR Pods | Health Board Staff Support |  |  |
|  | Multi-Disciplinary Partnership Working |  |  |

# 7. GOVERNANCE ARRANGEMENTS

The Cluster members meet 5 times a year at formal Cluster Board meetings, to plan and review progress and strategic direction related to the Cluster IMTP and to routinely address: Cluster Plan and associated planning actions, Cluster Spending Plan, Risk Register Update, Sustainability and Finance. Declarations of interest are addressed as standing items.

Welsh Government and Health Board allocated Cluster Funds are spent and allocated in accordance with Swansea Bay University Health Board’s Standing Financial Instructions. Non-Welsh Government funds are administered on behalf of the Cluster in accordance with agreed Cluster and funding body policies and procedures.

## MEMBERS

The core membership of the Primary Care Cluster shall comprise of representation from all local services involved in health and social care within the cluster area and shall include:

- Cluster Lead (Chair)

- Representation for each GP Practice* In Afan Cluster there will be representation from 8 GP Practices. This will include as a minimum a GP* and will also extend to Practice Manager.

- One representative from Community Pharmacy - to represent all community pharmacies within the cluster

- One representative from Dental - to represent dental services within the cluster

- One representative from Optometry - to represent optometry services within the cluster

- Primary, Community & Therapies Service Senior Manager

- Cluster Development Manager

- Nominated representative for Adult Nursing and Children’s Nursing

- Medicines Management Representation

- Nominated representative for Therapies; two members to represent the breadth of therapies services

- Representation from Mental Health

- Third Sector / Community Voluntary Service

# 8. CLUSTER ASSETS PROFILE

Primary Care Estates are used to support the development and implementation of community based clinics, particularly at Port Talbot Resource Centre (PTRC).  The Dental Unit is located at PTRC where emergency out of hours dental care is provided.

Population and Community Assets

- Afan has 2 Swimming Pools

- There are several Community Centres serving the population of Afan Cluster

- An extensive range of Third Sector Organisations operate in and serve the Afan Cluster area providing services for example to Carers, those with mental health needs, citizens advice, care and repair, domestic abuse and a range of condition specific services e.g. Substance Misuse

# 9. CLUSTER WORKFORCE PROFILE

| Role | WTE | Outcomes / Impact |
| --- | --- | --- |
| Pharmacist | 1 | Provide dedicated Pharmacist time for all cluster Practices in order to ensure:- - Improved quality, safety and cost effective prescribing to patients of the cluster GP Practices - Support for Practices to implement patient focused prudent healthcare and evidence-based prescribing strategies - Provision of professional expertise of the locum pharmacist role in GP practices delivering services to patients - Effective working with other health and social care professionals |
| Mental Health Practitioner (Practice based) | 0.8 | Provide Mental Health and Wellbeing support for patients with low to moderate mental health issues in order to ensure:- - Timely access and robust referral pathways for patients - Direct intervention and onward referral where appropriate - Improved outcomes for patients including less medication intervention - Saving of GP time by patients receiving the right care at the right time from the right Health Care professional |
| Social Prescriber (Practice based) | 1.6 | Provide Mental Health and wellbeing support for patients with low to moderate mental health issues in order to ensure:- - Timely access and robust referral pathways for patient - Direct intervention and onward referral where appropriate - Improved outcomes for patients including less medication intervention - Saving of GP time by patients receiving the right care at the right time from the right Health Care professional |
| Social Prescriber (Third Sector based) | 0.6 | Provide Mental Health and wellbeing support for patients with low to moderate mental health issues in order to ensure:- - Timely access and robust referral pathways for patients - Direct intervention and onward referral where appropriate - Improved outcomes for patients including less medication intervention - Saving of GP time by patients receiving the right care at the right time from the right Health Care professional |
| Specialist Health Visitor | 0.6 | Provide Specialist Health Visiting advice and service to the Child and Family Team across the age span in order to ensure:- - An Integrated approach to assessments, thresholds and referrals. - Improved outcomes for the most vulnerable families - Improved communication between health, social services and third-party agencies - Improved education for health partners - Effective and efficient referral pathway for health partners - Effective evaluation will ensure longevity of the service (part funded by the cluster as a shared resource between Afan, Neath and Upper Valleys Clusters) |
| Business Implementation & Development Manager | 0.8 | To provide support to the cluster lead/members and leadership for implementation of cluster projects in order to ensure:- - Effective project implementation, monitoring, evaluation and reporting - Support for the planning process including robust needs assessments - Implementation of the cluster IMTP |
| Primary Care Audiology |  | Provide wax removal and first contact hearing and tinnitus services in order to ensure:- - Timely First Contact Assessment and advice in primary care - Reduced consultations required with GPs (increase in GP capacity) - Reduced pathway complexity and length - Patients receive specialist hearing and tinnitus assessment and advice closer to home - Patients receive specialist tinnitus advice at first contact - Quicker identification and time sensitive treatment of Sudden Sensorieneural hearing loss (Cluster contribution to the SBUHB roll out of audiology services in primary care) |

# 10. CLUSTER FINANCIAL PROFILE

Afan - 2022/23

| BUDGET 22/23 |  |
| --- | --- |
| WG allocation 22/23 | £ 358,598.00 |
| Brokerage from 21/22 | £ - |
| Total available for 22/23 | £ 358,598.00 |

|  | 2022 - 2023 |
| --- | --- |
| Project | Agreed Total Spend |
| Home Flu Vaccinations | £4,500.00 |
| Specialist IT Support | £15,000.00 |
| INPS - V360 annual support contract | £3,930.00 |
| Mental Health Practitioner (Practice based) | £52,680.00 |
| Social Prescriber (Practice based) x 2 | £42,310.00 |
| Social Prescriber (Third sector based) | £30,939.00 |
| Specialist Health Visitor (Cross clusters) | £10,458.00 |
| Cluster Pharmacist (Practice based) | £47,400.00 |
| Business Implementation and Development Manager | £37,896.00 |
| Audiology (Cross clusters) | £10,625.00 |
| Communications Support | £10,000.00 |
|  | £265,738.00 |

The Cluster will continue to develop initiatives designed to meet the health and wellbeing needs of the local population and is considering further spend in relation to Mental Health support roles and Cluster communications.

Back to top